EU Community Initiative

INTERREG III B CADSES NEIGHBOURHOOD PROGRAMME

4th Call for Project Proposals

Applicants’ Manual

Version 22 september 2005

Content

A	OVERVIEW Of the 4th call for projects	1

A.1	Aim of the Guidelines	1

A.2	Financial Overview	1

A.3	Guidelines relating to project size	2

A.4	Contracting procedures	2

B	Introductory Note	5

B.1	CADSES – a programme facing the complexity of spatial development	5

B.2	The Decision-making Process	5

B.3	Where to obtain relevant information on CADSES	6

B.4	Implementing the Neighbourhood Approach within CADSES for the first time	6

C	General information	8

C.1	General notes	8

C.2	Partnership and the Lead Partner Principle	9

C.3	Submission and deadlines	10

C.4	Project evaluation and selection process	12

C.5	Eligible activities	16

C.5.1	Eligible costs under the ERDF	17

C.5.2	Eligible costs under the external funding instruments	19

C.6	The territoriality principle	20

C.7	The ERDF Subsidy Contract	21

C.8	The external funding grant contract	23

C.9	Eligible organisations for external funding	23

C.10	Other general remarks	24

D	INDICATIONS FOR FILLING IN THE PROJECT APPLICATION FORM	25

D.1	Project principal data	26

D.1.1	Summarised description of the project	26

D.1.2	Project duration	26

D.1.3	Project cost	26

D.2	List of partners	26

D.3	Project content	28

D.3.1	Background and demand for the overall project	28

D.3.2	Justification of new institutional structures (if foreseen)	28

D.3.3	Objectives, results, general effects	28

D.3.4	Target Group, Beneficiaries	29

D.3.5	Overview on project activities	29

D.3.6	Outputs and deliverables	29

D.4	Work Packages, milestones and Action Plan	30

D.4.1	Work Packages	30

D.4.2	Action Plan	30

D.4.3	Milestones	32

D.5	Monitoring Indicators	32

D.5.1	Category(ies) of intervention	32

D.5.2	Types of actions	32

D.5.3	Territory concerned	33

D.5.4	Quantified expected outputs	33

D.5.5	Quantified expected results	33

D.5.6	Quantified expected impacts	34

D.6	Complementarities with other projects	34

D.6.1	Complementarities with INTERREG II C CADSES projects	34

D.6.2	Complementarities with other INTERREG III B CADSES projects	34

D.6.3	Complementarities with projects in other relevant Programmes	34

D.7	Consistency with INTERREG III B general strategies	35

D.7.1	Compliance with European and national spatial development policy	35

D.7.2	Contribution to spatial development	35

D.7.3	Transnational added value	36

D.7.4	Impacts on competitiveness and regional cohesion	36

D.7.5	Impacts on employment and social cohesion	36

D.7.6	Equal opportunities	36

D.7.7	Environmental impacts	36

D.7.8	Innovative elements and innovative methods	37

D.7.9	Improvement of the institutional setting	37

D.8	Management of the project	37

D.8.1	General co-ordination and overall responsibilities	37

D.8.2	Operational management, including administrative and financial aspects	37

D.8.3	ERDF Certifying bodies	38

D.8.4	Provision of guarantees (in case of a Lead Partner under private law)	38

D.9	Actions for publicity and dissemination	38

D.10	Transfer of the project results	38

D.11	Follow-up actions	39

D.11.1	Project follow up after finalisation	39

D.11.2	Preparation of large investment	39

D.12	Bank information	39

D.13	Other information	39

D.14	Project Partners – detailed information	39

D.14.1	Lead Partner	39

D.14.2	Project Partners 2 - 25	40

D.14.3	Partner Profile	40

D.15	Certification and submission	40

D.16	Project finance for ERDF	41

D.16.1	Financial contribution by Project Partner and sources	41

D.16.2	Expenditures by Project Partner and Work Package	42

D.16.3	Expenditure by Project Partner and Budget Line (only EU PPs)	42

D.16.4	Certified expenditures to be submitted within each year (only EU PPs)	42

D.16.5	Breakdown of BL 7 “Other costs” (only EU PPs)	42

D.16.6	Breakdown of BL 8 “Small scale investments” (only EU PPs)	42

D.16.7	Breakdown of expenditures per Action alongside Project Partners and Budget Lines	42

D.16.8	Budget for External Funding	42

D.16.9	Fee rates of Project Partner's own staff - BL 2 "Personnel”	42

D.17	Co-financing Statements & Letters of Intent	43

D.18	EXTERNAL FUNDING - Financial identification of non-eu Project partners	43

E	Detailed explanation of ERDF budget Lines	44

E.1	Project co-ordination	44

E.2	Personnel (including overhead costs)	44

E.3	Meetings, conferences, seminars	44

E.4	Travel and accommodation	44

E.5	Promotion and publications	45

E.6	External expertise and audit	45

E.7	Others	45

E.8	Small scale investment	45

F	Project finance for external funding	46

G	Instructions on how to generate the financial tables	48

G.1	Detailed instructions on how to complete the ERDF financial tables	48

G.2	How to complete the external funding financial tables	54

H	CADSES regions and their Maximum EU co-financing rate	55

H.1	EU-Member States	55

H.2	Non-EU-Member States	57

I	CHECKLIST	58

J	Additional ANNEXES RElated to EXTERNAL FUNDING	60

Tables

Table 1: INTERREG III B CADSES Neighbourhood Programme - Priorities and Measures	25

Table 2: Country codes	27

Table 3: Countries and regions covered by the CIP CADSES	31

# OVERVIEW Of the 4th call for projects

The 4th Call for Projects under the CADSES programme is unique.  For the first time, project applicants will be able to apply for funding via the call, regardless of which CADSES country they are located in.

This has been achieved by integrating PHARE, CARDS and Tacis CBC funding inside the CADSES programme, and allowing the project selection process under CADSES to be used as the selection process for these funds as well.

The various sources of funding must be contracted separately to comply with existing legislation.  Nevertheless, a fully integrated approach to project preparation, submission, approval and implementation is now possible.  This offers significant possibilities for transnational co-operation across the CADSES programme area.

## Aim of the Guidelines

The present guidelines are intended to assist potential applicants eligible under the CADSES programme in preparing, applying for and implementing transnational co-operation projects and are a constituent part of the application package.

## Financial Overview

The maximum available finances for the 4th call are set out below.

| ERDF (for the 9 Member States) | 34.620.000 € |
| --- | --- |
| PHARE for Romania | 600 000 € |
| PHARE for Bulgaria | 1.334.000 € |
| CARDS (for Croatia, Albania, State Union of Serbia and Montenegro, Bosnia Hercegovina, Former Yugoslav Republic of Macedonia) | 1.600.000 € |
| Tacis CBC (for Ukraine and Moldova) | 1.500.000 € |

In addition, depending on whether the necessary financing agreements are signed prior to projects being selected, the following funding may also be available.

| CARDS (for Albania, State Union of Serbia and Montenegro, Bosnia-Hercegovina, Former Yugoslav Republic of Macedonia) | 1.250.000 € |
| --- | --- |
| Tacis CBC (for Ukraine and Moldova) | 3.500.000 € |

The Contracting Authority in Serbia may decide to allocate additional resources from the national CARDS programme for Serbian partners involved in projects selected under the 4th call, if the CARDS resources outlined above are fully allocated and further projects involving Serbian partners are still selected. The allocation of additional resources will be subject to the availability of funds.

As for the ERDF, there is no pre-allocation of funding among the countries indicated for Tacis CBC and CARDS funds.

## Guidelines relating to project size

According to the Neighbourhood Programme the average budget size of the overall project ranges between 0.5 and 5.0 M€. There is no fixed limitation to the ERDF budget per project, but the following should be taken into account when setting up the ERDF financial plan:

- the amount still available in the chosen measure / priority should not be exceeded;

- a budget size allowing the approval of two or more projects per measure is preferable.

With regard to the PHARE, CARDS and Tacis CBC funding which forms part of this call, there is a need to set a minimum and maximum level of funding which can be requested from the programme.  A minimum level is required because transnational projects, as opposed to cross-border projects, need to be of a reasonable size to ensure impact and because the programme wishes to avoid spreading its resources too thinly.  At the same time, a maximum size is required in order to ensure that a reasonable number of projects can be funded from the relatively limited resources available.

With these elements in mind, the rules for the use of PHARE, CARDS or Tacis CBC funding is as follows:

PHARE: the maximum amount of funding in any particular project should be EUR 250,000 per non-Member State and should be not more than 75% of the total cost of the actions for that country.

CARDS: the total amount of funding in any particular project should be between EUR 50,000 and EUR 300,000 per non-Member State (not per partner) up to a maximum of 90% of the total cost of the actions for that country.

Tacis CBC: the total amount of funding in any particular project should be at least EUR 50,000 per non-Member State.  No formal upper limit is set.  Tacis CBC funding can contribute up to 90% of the total cost of the actions for that country, unless the total cost is above EUR 300,000 – in this case Tacis CBC can contribute a maximum of 75%.

## Contracting procedures

Due to the additional funding sources (Phare, CARDS and Tacis CBC) involved in this call for projects, the transnational projects selected for funding may be the subject of different contracts, namely an ERDF contract for the partners from the Member States and other contracts according to the requested funding sources. The table below sets out where different contracts are required and the responsible body for signing the contracts. Regardless of how many partners are involved in a area dealt with by a responsible body, only one contract will be issued (e.g. if there are 3 partners from Ukraine and 4 partners from Moldova in a selected project, then 1 contract will be issued by the European Commission Delegation in Kyiv to one of those 7 partners on behalf of all of them. In contrast, if a project contains one partner from Croatia, one from Albania and one from Moldova, that will constitute 3 separate contracts).

| Partners in project from: | Contract to be issued by: |
| --- | --- |
| EU Member States | Managing Authority |
| Bulgaria | Bulgarian Ministry of Regional Development and Public Works |
| Romania | Romanian Ministry for European Integration |
| Croatia | European Commission Delegation in Zagreb |
| State Union of Serbia and Montenegro | European Agency for Reconstruction in Podgorica (for partners located in Montenegro) European Agency for Reconstruction in Pristina (for partners located in Kosovo) European Agency for Reconstruction in Belgrade (for other partners) |
| Albania | European Commission Delegation in Tirana |
| Bosnia-Hercegovina | European Commission Delegation in Sarajevo |
| Former Yugoslav Republic of Macedonia | European Agency for Reconstruction in Skopje |
| Ukraine | European Commission Delegation in Kyiv |
| Moldova | European Commission Delegation in Kyiv |

# Introductory Note

Whoever starts developing an INTERREG III B CADSES Neighbourhood project and then goes on to fill out the respective Application Form has to face a manifold challenge:

- the challenge of a complex subject;

- the challenge of a complex actor constellation;

- the challenge to describe the project as a well composed set of Work Packages which stands on its own feet and which at the same time contributes to the complex setting and ambitious objectives of the programme.

## CADSES – a programme facing the complexity of spatial development

Applicants sometimes have difficulties in identifying the specific profile of INTERREG IIIB and its spatial approach. Indeed, the programme offers links to all sectoral policies and all disciplines which are in some way linked to territorial development. Apparently, sometimes applicants just choose one specific subject mentioned somewhere in the programme, write a possibly excellent application on this specific subject and later on are very much surprised if their proposal is not appreciated. What goes wrong in such a case? INTERREG III B CADSES NP allows and even asks for specific applications but the difference with most other programmes is the interest in a more integrated and co-ordinated development of the territory. There are other programmes, which might be better suited for projects with a pure economic, environmental or social orientation. The specific profile of INTERREG III B is to focus on the interrelations and interdependencies between the different sectors. This might include even very specific subjects but it always must be clear from the application what constitutes the strategic objectives of the programme.

## The Decision-making Process

Another possible mistake besides missing the objectives of the programme is addressing an application to the wrong audience. Who will read the application submitted in the framework of INTERREG III B CADSES NP?

Firstly, there is the Joint Technical Secretariat (JTS) in Dresden with its international staff and its responsibility for the technical assessment according to criteria described in the programme, its complement and the Assessment Manual. Secondly, CADSES Contact Points (CCP) in all partner states will have access to the applications and contribute to the JTS work. Another task of the CCPs is to support National Committees. National Committees make recommendations to approve or not- projects and these Committees are composed of representatives of the regional and national level and by representatives of social and economic actors. In addition, the European Commission Delegations in the participating non-Member States, as well as the European Agency for Reconstruction (EAR), will have the opportunity to read and provide comments on project applications, especially those involving partners from the countries that they deal with. Of key importance is the transnational Selection Committee composed of national delegations (plus the European Commission and the EAR as observers), which takes the final decision on the projects proposed. Finally, there is the Managing Authority (MA) in Rome in charge of signing and supervising ERDF Subsidy Contracts for each project, and the various contracting bodies for the external funding contracts (see Section A.3). This is the group of actors, which assesses, discusses and/or approves project proposals and this is done only on the basis of the submitted Application Form (for more detailed information see chapter 6 of the NP).

Because of the actor constellation described above, it is highly recommended to fill in the Application Form having in mind the different actors. Please be aware that experts from different countries and different disciplines will read the applications.

## Where to obtain relevant information on CADSES

The broad audience of actors offers to applicants several sources of information. For first information it is recommended to contact the common website of the programme (www.cadses.net) or directly the CCP in your country. Information and partner search forums are occasions where applicants have the chance to contact directly the JTS, CCPs, committee members and other applicants. With respect not only to information on the programme but also to possible co-financing, members of national committees constitute another important addressee for requests by applicants. Summing up, the applicants have a chance to directly communicate with almost all actors on the programme level. That way it is possible to verify carefully if the project proposal fits with the needs of the programme.

## Implementing the Neighbourhood Approach within CADSES for the first time

In July 2003, the European Commission proposed significant steps to improve the EU´s interventions at its external borders after enlargement. The Commission adopted the Communication “Paving the Way for a New Neighbourhood Instrument” (a follow-up to the “Wider Europe Communication”) as the basis on which “Neighbourhood Programmes” (NP) were to be developed. They should cover the transition period 2004-2006 and are supposed to build on the experience from current cross-border and transnational cooperation programmes. The 2004-2006 Neighbourhood Programmes are intended to foster cooperation with neighbouring non-candidate countries through better co-ordination of existing instruments.

The Implementing Guidelines for the Neighbourhood Programmes 2004 – 2006 (from June 11, 2004) stipulate that the joint structures are to be established and joint procedures to be implemented for support of joint projects, combining the internal and external elements.

This sets out a particular challenge to the CADSES programme, as it consists of 9 Member States (eligible for ERDF), 2 accession countries (eligible for PHARE), 1 candidate country (Croatia – eligible for CARDS in 2004 and PHARE from 2005), 4 Western Balkan countries (eligible for CARDS) and 2 Western NIS countries (eligible for Tacis).  Nevertheless, the co-ordination of this funding package offers significant opportunities for genuine transnational co-operation across the CADSES programme area.  See lists H1 and H2 for the eligible areas in the CADSES programme.

# General information

## General notes

Aim of this manual

This Applicants’ Manual aims to give a guideline to potential applicants in order to correctly fill in the Application Form. Applicants are also asked to take carefully into consideration the Community Initiative Programme and the Programme Complement of the INTERREG III B CADSES Neighbourhood Programme.

Role of the CADSES Contact Points

- The CCPs serve as a first contact point for project applicants. Their activities are among others helping project development and providing information about the programme within the Partner States.

- All Project Partners (not only the Lead Partner) are recommended to contact their relevant CCPs and to inform them already at the stage of project preparation about their intention to participate in or even lead a INTERREG III B CADSES Neighbourhood project.

- The respective CCP will consult all Lead Partners and Project Partners and help them in working out a good project application that meets the criteria mentioned below.

- A list of CCPs is available on the programme website: www.cadses.net.  Where no CCP yet exists, non-Member State partners can contact the transnational CCPs, whose contact details are also available on the website.

The Application Package

The Application Package for the 4th call for project proposals of the INTERREG III B CADSES Neighbourhood Programme will be published on the programme website (www.cadses.net) on 5 August 2005. The Application Package consists of the following documents:

- The Application Form of the 4th call for project proposals has to be completed electronically using the format provided by the JTS. It consists of two parts:

a) Application Form (Part 1): a Word document for mainly text-based information;

b) Application Form (Part 2): an Excel worksheet for the financial tables, the list of partners, the Action Plan and the templates of a Co-financing Statement and a Letter of Intent (LoI);

Please respect the predefined format and do not exceed the character limitations stated in the Application Form. The language to be used for the entire project application is English.

- The Applicants’ Manual (this document)

- The Assessment Manual, setting out the assessment process

- An example of subsidy/grant contract for non-Member State funding can be found at:

http://europa.eu.int/comm/europeaid/tender/gestion/cont_typ/st/index_en.htm

## Partnership and the Lead Partner Principle

Partnership is a key component of transnational co-operation, at both programme and project level.  Transnational co-operation allows organisations to work together to address common challenges and solve common problems that would otherwise be insurmountable.  This does mean that such co-operation is easy – working with organisations from different countries and from different sectors is a challenge in itself.  This is why a structured, co-ordinated approach to project partnerships is required.

In the context of the CADSES Programme, a transnation project partnership means having “at least two ERDF financed project partners from different Partner States, wherein investment measures could take place in one or more of the ERDF financing partner states”.

All projects must follow the so-called ‘Lead Partner Principle’ in the management of the project. The Lead Partner is responsible for ensuring proper communication with and among the partners, and also that the project is implemented according to the approved Application Form.

Each project has to appoint a Financial Lead Partner for ERDF, which is at the same time the Overall Lead Partner of the project. To be in accordance with the terminology of the previous calls, the Financial Lead Partner for ERDF / Overall Lead Partner is referred to as “Lead Partner” (LP) in all documents of the 4th Call. The Lead Partner submits the Application Form, is responsible for the division of tasks among the partners involved in the project (a Joint Convention is recommended to govern this) and for the co-ordination of activities among all the involved partners. Should the project be selected for funding, this partner will sign a subsidy contract with the MA, thus undertaking the full financial and legal responsibility for the ERDF part of the project. Only the Lead Partner may request ERDF payments on the basis of the ERDF Subsidy Contract, and is solely responsible to the MA for the implementation of the terms of the Subsidy Contract. It is also responsible for timely and correct reporting to the JTS, ensuring that proper financial management and control procedures are applied, that the EU and national legislation concerning financial management and controls (1st level control), public procurement, information and publicity and state aid is respected and observed.

If the project combines ERDF and external funding, the project has to appoint financial Lead Partner(s) for external funding (ext.LP) among the project partner(s) from the non-Member State(s) concerned. Should the project be selected for funding, this partner will sign a Grant Contract with the relevant Contracting Authority. A separate external Grant Contract will be required for each involved Contracting Authority (see Section A.4). Regardless of how many partners are involved in an area dealt with by a responsible body, only one contract will be issued (e.g. if there are 3 partners from Ukraine and 4 partners from Moldova in a selected project, then 1 contract will be issued by the European Commission Delegation in Kyiv to one of those 7 partners on behalf of all of them. In contrast, if a project contains one partner from Croatia, one from Albania and one from Moldova, that will constitute 3 separate contracts). Each Grant Contract will be managed directly by the relevant Contracting Authority.

Lead Partners should consider the territorial principle rules (see. Chapter C.6)

## Submission and deadlines

In order to be considered for further assessment, the applicant has to deliver the following documents to the CADSES JTS in Dresden (Germany) within the deadline listed below and has to respect the following rules:

a) Hardcopy version of the Application Form

Documents to be submitted within the deadline

- One original of the signed and stamped Application Form
(Part 1 and Part 2), including all requested annexes (hardcopy version).

- The annex comprises notably:

  - The original (or at least fax version of the) signed Co-financing Statements of each financing partner – both Member State and non-Member State – participating in the project in the standard form as provided in the applicants package.

  - The original (or at least fax version of the) signed Letters of Intent (LoI) of all non-financing partners – both Member State and non-Member State – participating in the project in the standard form as provided in the applicants package;

  - Two pieces of each statute or article of association (for non-Member State partners), supplied in the form of originals or photocopies certified as true by an authorised independent body.

  - Two certified copies of the latest set of accounts for each non-Member State partner applying for funding.

Labelling of the envelope

The original paper hardcopy version of the application must be delivered in a single sealed package or a single sealed envelope. Each sealed envelope (or package) may only contain one application. The labelling of the envelope has at least to give clear reference to:

- the reference of the Call for Proposals to which the applicant is responding (here: “INTERREG III B CADSES Neighbourhood Programme– 4th Call for project proposals”);

- the full name and address of the Lead Partner of the project proposal;

- the chosen Project Title and/or Acronym;

- the priority/measure referring to.

Non-indication of any of these four information on the envelope leads to an exclusion of the application. Therefore please use also the document attached as annex 1 to the Application Form.

b) Electronic version of the Application Form

Documents to be submitted:

Additionally, an equivalent electronic version has to be sent by e-mail to the CADSES JTS. Only the following documents have to be submitted to the JTS in electronic version:

- The MS-Word document   Application Form 4th call - Part 1.doc

- The MS-Excel document   Application Form 4th  call - Part 2 automated.xls

Please note: Submission of scans of Co-financing Statements and Letters of Intent is not necessary or should be done only if explicitly requested by the JTS.

Labelling of the e-mail

The entire e-mail submission shall be labelled in the following way:

- with the reference “INTERREG III B CADSES Neighbourhood Programme – Submission of a Project Proposal under the 4th Call”;

- with the acronym of the project;

- with the name of the Lead Partner;

- with the priority/measure referring to.

Deadline

To be recognised as an admissible submission, the proposal must have been received at the JTS in Dresden

- in case of a hardcopy version of an application no later than

07 November 2005. – 18.00 hours CET

- in case of an e-mail version of an application no later than

07 November 2005. - 24.00 hours CET

Submission

The hardcopy version of the application must be sent either by mail, courier service or can also be delivered by hand. It must contain the original Application Form (part 1 and part 2 in English language), originally signed and stamped by the legal representative of the Lead Partner and, where relevant, the Financial Lead Partner(s) for external funding.

The hardcopy version of the Application Form including all annexes must be sent or delivered to the following address:

Postal delivery

CADSES Joint Technical Secretariat

Rathaus (Town Hall)

Postfach (P.O. Box) 12 00 20

D – 01001 Dresden

Delivery by courier or hand delivery

CADSES Joint Technical Secretariat

An der Kreuzkirche 6

D-01067 Dresden

Phone +49 351 488 1021

Fax +49 351 488 1025

The digital copy of the Application Form (part 1 and part 2) has to be sent by e-mail to the following address:

cadses@jts.dresden.de

Transmit the entire submission in a single e-mail. The message size cannot exceed 5 MB. Please submit the documents only in the file formats indicated above (*.doc and/or *.xls).

c) Other information

A signed Joint Convention between the partners is not requested on submission of the application. In any case, a Joint Convention will be an integral part of the Subsidy Contract to be concluded between the MA and the Lead Partners of the approved projects. Therefore it is strongly recommended that the Lead Partner start to establish legal relations with his Project Partners in order to legally define their co-operation and to safeguard himself against his partners by contract already during the project application period.

It is the responsibility of the applicants to ensure that proposals are addressed correctly and arrive at the JTS before the deadline. The JTS cannot be held responsible for packages wrongly addressed nor for proposals that are split between packages with no adequate identification to allow the different parts to be reassembled. No evaluation or analysis of the proposal contents will take place before the call deadline has passed, nor will any contact with applicants on the contents be permitted.

## Project evaluation and selection process

The completeness check

All project applications will first be formally checked as regards the completeness of application. After registration and the completeness check the JTS will send a letter of acknowledgement of receipt to the Lead Partner as well as to the CCP of the Lead Partner, indicating the date of project registration, the project reference number and the result of the completeness check. If the project application is not complete, the JTS will inform the Lead Partner and – relating to which information is missing (see clarification below)  – will ask him by fax and e-mail for submission of further information.

These additional documents have to be received at the JTS within 10 working days after sending out the information to the LP by the JTS (date of arrival at JTS). If the required information is not transmitted within the fixed deadline, the proposal will not be further evaluated and regarded as not complete.

a) The JTS will ask for submission of missing information only in the following cases:

- Electronic version not in *.doc and *.xls – format.

In case that the applicant did not submit by e-mail in electronic version the Application Form in the requested formats *.doc (part 1) and *.xls – format (part 2) but e.g. only in another format (e.g. *.pdf) the JTS will inform the applicant to submit the documents in correct file-formats within the above-mentioned deadline.

- Damaged electronic files

In case that the applicant delivered damaged electronic files which are obviously the Application Form but which contain unreadable data due to technical problems the JTS will ask for the submission of a new file within the above mentioned deadline.

- Co-financing Statements and/or Letters of Intent in fax copy

In case that Co-financing Statements or Letters of Intent were delivered in fax copy only the JTS will ask the Lead Partner to submit the original documents within the above mentioned deadline.

b) Especially in the following cases the JTS will not ask for a submission of additional documents. All other mistakes not explicitly listed here will also lead to an exclusion from the ongoing assessment procedure:

- Application Form partly filled in / Missing part 1 or 2 of the Application Form

In case that the Application Form was only partly filled in (e.g. financial tables), parts are missing or left blank (except chapters which only had to be filled in if applicable) or paragraphs of the Application Form were not filled in correctly the JTS will not ask for a submission of additional (corrected) documents. Exchange pages will not be requested! In this case it is irrelevant whether the applicant delivered an incomplete Application Form by accident or on purpose.

- Application Form not delivered in English language

In case that the Application Form and/or its annexes were not delivered in English language the JTS will not ask for a submission of a new version.

- Missing Co-financing Statements and Letters of Intent

In case that the Lead Partner did not submit at least fax copies of original signed, stamped and dated Co-financing Statements for financing partners and Letters of Intent for non-financing partners in the given form as presented in the Application Package the JTS will not ask for an additional submission of these documents.

- The statutes or articles of associations (of non-Member State partners)

In case the Lead Partner did not submit two pieces of each original or certified photocopies of statutes or articles of associations of the non-Member State partners the JTS will not ask for an additional submission of these documents.

- Latest set of accounts (of each non-Member State partner applying for funding)

In case the Lead Partner did not submit two certified copies of the latest set of accounts for each non-Member State partner applying for funding the JTS will not ask for an additional submission of these documents.

- Original version of the Application Form not signed and stamped

In case that the original version of the Application Form submitted to the JTS was not signed and stamped by the legal representative of the Lead Partner and, where relevant, the Financial Lead Partner(s) for external funding, the JTS will not ask for additional submission of the Application Form but will consider this application as not admissible.

- Application sent after the deadline

If the application does not arrive at the JTS within the given deadline the whole application will be considered as not admissible.

Please note: Errata, amendments, exchange pages etc., which are sent after the deadline without being explicitly requested by the JTS will not be considered!

If the project application is complete, the JTS in collaboration with the CCPs and the National Committees will carry out an assessment of the project proposal. In particular, this assessment is based on: (a) a check of the minimum requirements as presented in the Programme Complement; (b) an evaluation of priority criteria for the ranking of projects.

- Projects have to fulfil all minimum requirements otherwise they are rejected. Minimum requirements are simply examined by attributing “fulfilled” or “not fulfilled”.

List of minimum requirements, as presented in the Programme Complement:

|  | Minimum requirements for project selection |
| --- | --- |
| 1 | Be in accordance with European and national spatial development policy issues: Spatial development aims and issues of the ESDP, CEMAT Guiding Principles and national/regional spatial development strategies. |
| 2 | Have effects to integrate development in CADSES, i.e. a project design that focused on generating development impulses towards a perspective of an economically and socially integrated space across EU borders. |
| 3 | Provide a transnational project partnership, i.e. have at least two ERDF financed project partners from different Partner States, wherein investment measures could take place in one or more of the ERDF financing partner states |
| 4 | Demonstrate the value added of a spatial development approach (spatially integrating different sectoral approaches). |
| 5 | Respect relevant national and EU policies regarding structural funds policies, environment legislation. |
| 6 | Have project partners with sufficient capacity for project implementation and especially a Lead Partner who safeguards a reliable project organisation and a competent project implementation. |
| 7 | Secure national co-financing (Co-financing Statements enclosed) |
| 8 | Include the description of quantified outputs and / or clear attainable target to allow for appraisal and ex-post evaluation |
| 9 | Be completed within the programme period (before 31 August 2008) |
| 10 | Appropriateness of project budget (cost/benefit ratio) and project within the frame of eligible size and duration which allows several projects per measure (exceptions to be decided by the SC) |
| 11 | Not be funded by other EU programmes (except PHARE, ISPA, CARDS, SAPARD, TACIS and other instruments providing assistance for Non Member States) - parts of the project can be co-financed by other EU-programmes (e.g. 6th RDT, e-europe) if these parts are not calculated within the eligible project costs under CADSES |
| 12 | Do not duplicate existing work (a review of existing actions, studies, database and/or networks has to be included in the project application) |

- Project ranking on the basis of priority criteria for project selection. As the Programme Complement states, priority criteria refer to:

- The project’s contribution to the objectives of the Programme;

- Partnership and project management;

- Results and output.

In this phase, the CCPs contribute to the evaluation process: in particular, they undertake an estimation of the Project Partners’ capacity, evaluate the appropriateness of the project costs, and assess the accordance of the Project with national and regional development strategies.

In addition, the EC Delegations and the European Agency for Reconstruction may provide comments relating to the capacity of partners from the countries they operate in, and on the legality and risk of double funding of actions to be undertaken by these partners.

Once the check of projects has been completed, the JTS submits its evaluation to the Steering Committee (Selection Committee). The Steering Committee (Selection Committee) decides on project approval on the basis of the eligibility assessment and the assessment of priority criteria performed by the JTS. If some minor amendments are required for a formal approval, the Steering Committee (Selection Committee) might decide primarily on an admissibility status of the project. The amended application must be submitted again to the JTS to enter the second eligibility check. These additional documents have to be received at the JTS within 10 working days after sending out the information to the LP by the JTS (date of arrival at JTS). The Steering Committee (Selection Committee) might decide on the project approval on the basis of a written procedure. This allows a faster start up of project implementation in the case of minor failure for selection. In the case of rejection of a project the JTS on behalf of the Steering Committee (Selection Committee) will inform the Lead Partner, the CCPs and the EC Delegations and the EAR.

A selected project will receive a letter of confirmation. Later on, the MA will offer the Lead Partner of an approved project a Subsidy Contract, which will set out the terms and conditions for the use of the grant. This will include providing regular reports about progress, monitoring results and keeping well-organised files and accurate accounts.  For selected projects, which requested Tacis, PHARE or CARDS funds, the relevant national authorities, EC Delegations or the EAR will offer grant contracts to the relevant partners.

## Eligible activities

ERDF, Tacis, PHARE and CARDS assistance will be granted with reference to the following categories of eligible activities:

- Transnational studies and planning activities like development concepts project, programme and policy assessments (such as Environmental Impact Assessments, Transport Impact Assessments, Strategic Environmental Assessments);

- Project management;

- Establishment of new and extension and intensification of co-operation in existing transnational networks and associations of actors of spatial development policy, and network related activities (Staff exchange – joint training facilities and programmes);

- Pilot actions, pilot and demonstration projects with transnational dimension (if they are based on transnational concepts or strategies);

- Exchange of know-how and experience between actors of spatial development policy (comparative analysis of instruments, methodologies, standards and concepts);

- Feasibility studies for investments;

- Financing of small scale complementary infrastructure investment (bottlenecks, interfaces), proposed by transnational strategic concepts;

- Financing of small scale investment (e.g. information and innovation centres of transnational importance, Information and Communication Technology networks, part of buildings), proposed by transnational strategic concepts;

- Financing of implementation structures proposed by transnational strategic concepts.

### Eligible costs under the ERDF

In order to implement the eligible activities, project costs, which qualify for a subsidy consist exclusively of project costs listed in the application approved by the Steering Committee (Selection Committee). The eligibility of project costs for Structural Funds’ co-financing is regulated in Council Regulation (EC) No. 448/2004 and other relevant national and EU-regulations.

Eligible are only costs that have arisen after the following eligibility dates and in any case incurred during the lifetime of the project:

For partners from AT, DE, GR and IT:		March 12th 2001.

For partners from HU, SI and SK:		January 1st 2004

For partners from PL:	January 1st 2004, except for costs subject to public procurement law, which must be in line with the law of 2 March 2004

For partners from CZ:				May 1st 2004

The ERDF eligibility rules should be considered carefully before setting up the project budget and compiling the financial plan (see http://europa.eu.int/comm/regional_policy/sources/docoffic/official/regulation/content/en/02_pdf/00_9_4_expend2_en.pdf).

The eligibility rules consist of twelve rules stipulating the following:

- Expenditure actually paid out (e.g. payments by final beneficiaries, proof of expenditure and subcontracting)

- Accounting treatment of receipts

- Financial and other charges and legal expenses (e.g. bank charges and accounts, legal fees for advise, notary fees, the costs of technical or financial expertise and accountancy or audit costs, fines and financial penalties)

- Purchase of second-hand equipment

- Purchase of land

- Purchase of real estate

- VAT and other taxes and charges

- Venture capital and loan funds

- Guarantee funds

- Leasing

- Costs incurred in managing and implementing the Structural Funds

- Eligibility of operations depending on the location

As stated above, the eligibility of costs is determined on the basis of Commission Regulation (EC) No 448/2004 and national laws. As an example, eligible can be costs such as:

- the cost of staff assigned to the operation, corresponding to real salaries plus social security charges and other remuneration-related costs;

- travel and subsistence costs for staff taking part in the operation;

- purchase costs for equipment (new or used), provided that these correspond to normal market costs and that the value of the items concerned is written off in accordance with the tax and accounting rules applicable to the beneficiary; only the proportion of depreciation of the item corresponding to the duration of the operation may be taken into account, except where the nature and/or use of the item justifies different treatment;

- costs of consumables and supplies;

- expenditure on subcontracting of external experts;

- costs deriving directly from the requirements of the contract (dissemination of information, specific evaluation of the operation, translation, reproduction, etc.) including, where appropriate, financial service costs (in particular the cost of financial guarantees), but not including exchange risks unless the agreement expressly provides for their inclusion;

- overheads, provided that they are based on real costs which relate to the implementation of the operation co-financed and are allocated pro rata to the operation, according to a duly justified fair and equitable method.

It has to be noticed that costs for auditing are eligible if inserted in the project’s financial plan.

### Eligible costs under the external funding instruments

For non-Member State partners only costs incurred after the date on which the grant contract is signed are eligible for co-financing from PHARE, CARDS, Tacis.

With these elements in mind, the rules for the use of PHARE, CARDS or Tacis CBC funding is as follows:

PHARE: the maximum amount of funding in any particular project should be EUR 250,000 per non-Member State and should be not more than 75% of the total cost of the actions for that country.

CARDS: the total amount of funding in any particular project should be between EUR 50,000 and EUR 300,000 per non-Member State (not per partner) up to a maximum of 90% of the total cost of the actions for that country.

Tacis CBC: the total amount of funding in any particular project should be at least EUR 50,000 per non-Member State.  No formal upper limit is set.  Tacis CBC funding can contribute up to 90% of the total cost of the actions for that country, unless the total cost is above EUR 300,000 – in this case Tacis CBC can contribute a maximum of 75%.

The eligibility of project costs for Tacis, PHARE and CARDS co-financing can consist of costs, which must:

- be necessary for carrying out the project, comply with the principles of sound financial management, in particular value for money and cost-effectiveness;

- have actually been incurred by the project partners during the project implementation period, whatever the time of actual disbursement by the project partner, this does not affect the eligibility of final audit costs;

- be recorded in the partner’s accounts or tax documents, be identifiable and verifiable, and be backed by originals of supporting documents.

Subject to those conditions and where relevant to the contract-award procedures being respected, eligible direct costs include:

- the costs of staff assigned to the project, corresponding to actual salaries plus social security charges and other remuneration-related costs; salaries and costs must not exceed those normally borne by the project partner;

- travel and subsistence costs for staff taking part in the project, provided they do not exceed those normally borne by the project partner, any flat-rate reimbursement must not exceed the scales approved annually by the European Commission;

- the cost of purchasing equipment (new or used) and services, provided they correspond to market rates;

- the cost of consumables and supplies;

- subcontracting expenditure;

- costs arising directly from the requirements of the contract (dissemination of information, evaluation specific to the project, audit, translation, printing, insurance, etc.) including financial service costs (in particular the costs of transfers and financial guarantees).

The co-financing of the project partner can consist of the following expenses:

- Fees: In the case of civil servants employed by the project partner, a percentage of the nominal time of the employee, which is spent for the project, is charged to the project. In short, the monthly salary is divided by 22 (number of working days/ month) to give the daily rate. The daily rate is then multiplied by the number of days spent for the project.

- Travel expenses: these travel expenses should be recorded and copies of justifying documents must be provided.

- Equipment: copies of invoices must be provided.

- Office rental: if the project partner is renting premises for the project, within a separate rental agreement, the rental expenses are eligible. If part of the administration’s building is allocated to the project, this can not be considered as a financial contribution.

- Administrative costs (up to a max. of 7% of the total budget): administrative costs usually cover all small office equipment, stationery, secretarial costs, photocopies, etc. This amount is a lump sum allocated to the project.

Based on EC regulations and the Programme provisions, the following expenditure is considered ineligible expenditure for Tacis, PHARE and CARDS co-financing:

- in-kind contributions (NOTE: salaries of project staff are not considered in-kind contributions and can be eligible for funding);

- debts and provisions for losses or debts;

- interest owed;

- items already financed in another framework;

- purchases of land or buildings, except where necessary for the direct implementation of the project, in which case ownership must be transferred to the project partner at the end of the project;

- currency exchange losses;

- taxes, including VAT, unless the project partner cannot reclaim them and the applicable regulations authorise coverage of taxes.

## The territoriality principle

In general, Structural Funds assistance is for use within the territory of the European Union. This means that a territoriality principle applies, which in general excludes — also within the INTERREG Initiative — the possibility that non-Member States have access to ERDF funds. Regulation (EC) 448/2004 (Rule No 12: eligibility of operations depending on the location) states that operations co-financed by the Structural Funds shall be located in the region to which the assistance relates.

This general rule has exceptions. The travel and subsistence expenses by partners and participants from EU Member States on parts of operations that take place in a Non-EU-Member State and are vital for the success of the project as a whole are also eligible for ERDF assistance.

To ease the co-operation as much as possible, travel and subsistence expenses of partners or participants from non-EU Member States of the CADSES space can be eligible costs for a project when the meeting or seminar takes place in the EU and is part of an approved project.

The territoriality principle does not exclude the possibility that, in accordance with EU, national and international public procurement law, services or equipment used for implementing a project within the EU can also come from the non-EU Member States of the CADSES space.

The territoriality principle includes that, as a general rule, projects co-financed by the ERDF resources for CADSES, shall be located in the area established for the Programme co-operation. That means that Lead Partners and Project Partners, who want to participate as official partner (listed under §2 “List of partners” of the Application Form) in an INTERREG III B CADSES Neighbourhood project, must have their seat inside the CADSES programme area! There may be an exemption for certain partners outside the area, provided that the results of a project are for the benefit of the eligible area. This applies, for instance, to public bodies who are based outside the eligible area, but whose competencies also relate to territories within the eligible area – e.g. ministries, federal agencies, government departments, statistical offices, national research bodies, etc.

In all other cases, expenditure incurred by parties, external to the CADSES programme area cannot be considered as eligible. External parties may however participate as sub-contractors to implement certain actions or activities within a project, under contract with a partner located in the CADSES co-operation space.

Private organisations or institutes located outside the CADSES space may only be eligible partners where they have branch offices located inside, which would act as partners.

It is recommended that, where a non-Member State partner is participating in a project and requires only travel and subsistence expenses for their involvement, then these costs should be co-financed by the ERDF as described above.  This allows the whole project to be co-financed only via the ERDF.

Where the involvement of a non-Member State partner in a project is more substantial, and involves costs beyond travel and subsistence expenses, then all the costs of the non-Member State partner should be co-financed by the relevant external funding instrument (Tacis, PHARE or CARDS).  This will then require an ERDF contract for the Member States’ part of the project, and an external funding contract for the non-Member State partner.

## The ERDF Subsidy Contract

The legal framework of the project implementation is based on a Subsidy Contract between the MA and the Lead Partner. The Lead Partner is the final beneficiary according to Council Regulation (EC) 1260/1999 and point 31 of the INTERREG III Guidelines. The Lead Partner takes the overall responsibility for the application and implementation of the entire financial ERDF part of the project.The Lead Partner is the sole responsible party to the MA concerning the due implementation of the whole CADSES project. The Lead Partner has to establish legal relations with the Project Partners in order to legally define their co-operation and to safeguard himself against his partners.

The Subsidy Contract refers to the most important aspects of the legal relation between the Lead Partner and the MA, such as the object of use, the request for payments, the eligible costs, the obligations of the Lead Partner, etc. The standard Subsidy Contract, as it was used for 3rd call projects, is published on the CADSES web site, so the applicants can examine it in detail. In this paragraph, it may be useful just to remind — inter alia — three important aspects:

- contracts are governed by Italian Law, because the MA is located in Italy. This means that controversies (if any) will be judged by an Italian court (the place of jurisdictions is Rome) on the basis of Italian law;

- if the Lead Partner is a private institution, it will have to present securities as customary for banking practice, such as a deficiency guarantee from a bank or a public body. The formal basis is the PC (1.2.1 Lead partner principle), which stipulates: "Lead partners under private law have to provide sufficient guarantees equal to the amount of ERDF funds they are claiming for the whole project." The subsidy contract to be signed will include a similar clause. There are the following options to provide the requested guarantees:

  - Bank Guarantee: The LP have to provide a bank guarantee, lasting until 31 December 2012 and covering the full amount of ERDF funding of the whole project (i.e. the amount stated in paragraph 1 of the Subsidy Contract towards the MA). It has to be presented, at latest, on the submission of the first payment claim. Costs for the bank guarantee are eligible, provided they are part of the financial plan of the project;

  - An Acceptance of liability by a public authority will supersede the bank guarantee. The LP presents a "Letter of Acceptance of Liability" made out by a public authority. The issuing public authority has to assume the liability of the LP for the ERDF subsidy contract between LP and MA.

  - Private entities, which can be classified, as public equivalent bodies, do not have to present the above-mentioned securities. The LP has to present a certificate, which declares him being a "public equivalent body" according to the "Council Directive 92/50/EEC of 18 June 1992 relating to the coordination of procedures for the award of public service contract" (amended by EUROPEAN PARLIAMENT AND COUNCIL DIRECTIVE 97/52/EC of 13 October 1997). The certificate shall be made out by one of the bodies governed by public law, which either finance or supervise the LP in the meaning of the quoted Council Directive.

- as a general principle, the Lead Partner — as final beneficiary — and its partners own the project outputs, which have to be made available to the public. Especially all financing bodies (European Commission and co-financing institutions) and all bodies participating in the decision making about grants (Monitoring Committee and Steering Committee (Selection Committee) members) need to have access to the results.

## The external funding grant contract

The relevant Contracting Authority will prepare and sign the Grant Contract for the relevant external element of each project with the financial Lead Partner for external funding for the country or region concerned. The relevant Contracting Authority will sign the contract within 3 months of the decision of the Steering Committee (Selection Committee).

Following the signature of the Grant Contract, the Contracting Authority reserves the right to terminate the Contract with two months written notice, in which case a grant payment will only be made for the period of the project carried out. The Contracting Authority may terminate the Contract without giving notice and with the possibility of demanding repayment of the financing already granted if any of the following cases has occurred:

- Failure to meet contractual conditions as set out in the Project Grant Contract;

- Financial Lead Partner for the external funding is declared bankrupt;

- Changes of legal personality, without prior approval;

- Grant has been obtained on false or incomplete statements or reports include untrue statements;

- Financial irregularities have been committed.

## Eligible organisations for external funding

This call for projects is open to applicants from the non-Member States complying with all the conditions stated below:

- Are non-profit legal persons established by public or private law for the purposes of public interest or specific purpose of meeting needs of general interest, belonging to one of the following groups:

- National authorities,

- Regional and local public authorities,

- Public funds, public institutes and public agencies, established by the state or a municipality,

- Non-governmental organisations,

- Legal entities established by private law (societies) with non-profit status and purpose of operating,

- Public institutions for economic development, public companies, as well as other legal entities with predominant impact of the state or municipalities on management;

- Educational and research institutions.

- Have their headquarters or an organisation unit in the respective eligible area of the CADSES Programme, except for Ukraine where the applicants and partners can come also from other parts of Ukraine as long as the actions are carried out in the eligible area;

- Are directly responsible for the preparation and implementation of the project, not acting as intermediaries;

- Are experienced and able to demonstrate their capacity to manage larger-scale activity corresponding to the size of the project for which a subsidy/grant is requested;

- Have valid registration to pursue activities;

- Have financial capacity – this means that the average annual turnover of the applicant must exceed 5 times the requested funding and the averages of cash and cash equivalents at the beginning and end of last financial year were positive;

- Within the last five years have not been issued an order for criminal offence connected with business operations or an order for prohibiting their activities;

- Are not subject to orderly settlement, bankruptcy or liquidation;

- Have not been granted funds from a national or a local budget or from any other EU programmes for the same activities.

## Other general remarks

In order to assess the quality and content of the project proposal, an examination of the logical consistency between the various project phases will be undertaken, starting from the analysis of the situation and demands prevailing in the area and/or sector of transnational co-operation identified by the project (the starting point);

- to the determination of objectives to be achieved;

- to the determination of the interventions to be carried out, coherently with the Neighbourhood Programme provisions;

- to the determination of the expected concrete results;

- to the consequent identification of indicators (output, result and impact indicators) and global effects of the projects;

- and to the formulation of an efficient partnership and of appropriate management procedures.

Moreover, it must be demonstrated that the project is coherent with the orientations, strategies and aims of European spatial development policies; with the objectives of the Community Initiative INTERREG; and with other interventions. It is also required that projects will be able to produce added value in the fields of transnational co-operation, institutional settings and “horizontal” priorities of structural fund interventions, such as environment, equal opportunities, employment, information society. In any case, it has also to be noted that to get a positive evaluation, the project has not necessarily to contribute to “horizontal” priorities, being sufficient that it does not produce negative effects on those issues.

The applicants should carry out a self-evaluation in order to test the coherence of the project content with strategies, objectives and activities relating to EC interventions, priorities and programmes in the fields of co-operation and spatial development. This can be carried out listing, for examples, relevant information for such interventions (objectives, strategies, interventions); and assigning scores to the links (in terms of complementarity, synergy, integration) between the project content and those information. Of course, this is not a mandatory rule but just a test to verify the consistency of the project.

# INDICATIONS FOR FILLING IN THE PROJECT APPLICATION FORM

Limitations apply to several paragraphs in the Application Form in terms of space available for filling in. These limitations are indicated with a figure giving the maximum number of characters allowed, which must not be exceeded.

On the cover page, the applicant will write the project short title and the acronym. Give the full project title.

Please choose an acronym related to the subject matter of the project that can be easily identified.

Due to several questions during the previous application rounds please find here an example for a project title and a project acronym (Project Title: Secretariats in Progress;  Project Acronym: SIP)

Moreover, the institution that will act as Lead Partner has to be indicated, together with the country where it is located. Use the English name of the institution.

The project must clearly refer to one of the Measures of the Programme within the Priority of reference. Priorities and Measures of the INTERREG III B CADSES Neighbourhood Programme are listed in the Programme Complement, paragraph 2.1, and are reported below.

Table 1: INTERREG III B CADSES Neighbourhood Programme - Priorities and Measures

| Priority 1 Promoting spatial development approaches and actions for social and economic cohesion | Priority 2 Efficient and sustainable transport systems and access to the information society | Priority 3 Promotion and management of landscape, natural and cultural heritage | Priority 4 Environment protection, resource management and risk prevention |
| --- | --- | --- | --- |
| Measure 1.1 Supporting joint strategies for spatial development and actions for implementation | Measure 2.1 Developing efficient transport systems with regard to sustainable development | Measure 3.1 Protecting and developing cultural heritage | Measure 4.1 Promoting environmental protection and resource management |
| Measure 1.2 Shaping urban development, promoting urban networks and co-operation | Measure 2.2 Improving access to knowledge and the information society | Measure 3.2 Protecting and developing natural heritage | Measure 4.2 Promoting risk management and prevention of disasters |
| Measure 1.3 Shaping rural development |  | Measure 3.3 Protecting and developing landscape | Measure 4.3 Promoting integrated water management and prevention of floods |
| Measure 1.4 Spatial impact of immigration |  |  |  |

For further information about the content of each Priority and Measure, see Chapter 4 of the Community Initiative Programme and Chapter 2 of the Programme Complement.

In general, the project content will have to be defined according to the content and the specific requirements defined by the Programme Complement for the measure concerned.

## Project principal data

### Summarised description of the project

Please give a short description of the contents of the project, with reference to the main objectives and activities. Note that applicants will be asked for more detailed information on the contents of their project in section 3 (Project Content).

### Project duration

In this paragraph, the applicant has to specify: (a) the expected date of project start or the actual date if it has already started; (b) the date when the project is expected to be concluded. Dates will be specified in a DD/MM/YYYY format. Please note that the Programme Complement foresees an average duration of project implementation between two and three years and the project must be completed before 31 August 2008. State also the number of months the project is running. The date of project start also defines the starting date for eligibility of project expenditures.

### Project cost

This table will be calculated automatically within the preparation of the project’s budget in the Excel part “Application Form 4th Call – part2”. Please insert in the part the table printed from the Excel file. For detailed instructions refer to the chapter G of this manual.

All values shall be expressed in Euro with two decimal places. Please make sure that these amounts are consistent with the financial tables.

## List of partners

Please fill in this table in the Excel file “Application Form 4th Call – part2”, worksheet “Insert-Partners”. Once printed, insert the table into this part of the Application Form. For detailed instructions refer to the Chapter G.

Please, note that project partnership must have at least two ERDF financed project partners from at least two different Partner States, wherein investment measures can take place in one or more of the financing partner states. Detailed information on Lead and Project Partners will be supplied in Chapter 14 of the Application Form. Lead Partners and Project Partners who want to participate as official partner (listed under §2 “List of partners” of the Application Form) in an INTERREG III B CADSES Neighbourhood project must have their seat inside the CADSES programme area! Those interested in cooperation but coming from outside the CADSES programme area should not be listed here!

The table below shows the abbreviations of partner states used in the CADSES Programme.

Table 2: Country codes

| Austria | AT | Bulgaria | BG | Poland | PL |
| --- | --- | --- | --- | --- | --- |
| Germany | DE | Croatia | HR | Republic of Moldova | MD |
| Greece | GR | Czech Republic | CZ | Romania | RO |
| Italy | IT | State Union of Serbia and Montenegro | SCG | Slovakia | SK |
| Albania | AL | Former Yugoslav Republic of Macedonia | MK | Slovenia | SI |
| Bosnia Herzegovina | BA | Hungary | HU | Ukraine | UA |

Indicate the amount, which will be provided as in-kind contribution.

Please note: ERDF co-financing per partner cannot exceed the partner’s total expenditure minus his contribution in kind (Reg. (CE) No 448/2004, Rule No 1, point 1.4).

Rule 1 point 1.6 of the above regulation stipulates the following:

“In kind, contributions are eligible expenditure provided that:

(a) they consist in the provision of land or real estate, equipment or materials, research or professional activity, or unpaid voluntary work;

(b) they are not made in respect of financial engineering measures referred to in Rules 8, 9 and 10;

(c) their value can be independently assessed and audited;

(d) in the case of the provision of land or real estate, the value is certified by an independent qualified valuer or duly authorised official body;

(e) in the case of unpaid voluntary work, the value of that work is determined taking into account the amount of time spent and the normal hourly and daily rate for the work carried out;

(f) the provisions of Rules 4, 5 and 6 are complied with where applicable.”

Internal hours (staff costs) of Project Partners (public or private) are not considered as contribution in kind. The related expenditure must be supported by specific documents – refer to point 1.1 of the eligibility regulation 448/2004. In contrast, unpaid voluntary work is regarded as contribution in kind.

## Project content

### Background and demand for the overall project

Explain the circumstances under which your project originated, by whom it has been proposed and designed. Please justify how your project will meet the needs, strengths, weaknesses and constraints of the project’s target group(s) and target region(s). Details should be given on the local situation and on the Project Partners. Please indicate whether any special preparatory work (i.e. a survey, a feasibility study) has been carried out prior to designing the project. For projects targeting an improvement of the institutional setting also describe the existing institutional framework in the sector concerned. In order to demonstrate that the project does not duplicate already existing work, a review of existing actions in the realm of the project should be added.

### Justification of new institutional structures (if foreseen)

There might be some elements in your project, which require further justification.

If your project foresees the creation of new institutional structures (e.g. service centres, resource centres, focal points, associations, observatories etc.), describe the existing institutional framework in the sector(s) and region(s) concerned. Thoroughly justify the need and the added value of the planned structure and line out how co-ordination with already existing organisations will be safeguarded. Demonstrate clearly that duplication of work can be excluded. It is highly recommended to present a business plan for the new entity, covering both the funding period and the period after completion of the CADSES project. Contrast the solution you propose with alternatives. Prove the viability of the entity and its sustainability in a mid to long-term perspective.

In this paragraph, give a summarised justification and annex supporting documentation (e.g. feasibility study, business plan, etc.) to the Application Form.

### Objectives, results, general effects

#### Overall, long-term objectives

In this paragraph, the applicants explain the wider strategic objectives they intend to achieve. A limited set of objectives is defined. Please take into consideration especially those objectives, which give an idea of an added value at European level and contribute to spatial development in the CADSES area. A maximum of 3 objectives is recommended.

#### Concrete results

Describe concrete results to be achieved by the end of the project. Wherever possible quantify the results. Concrete results to be achieved within non-Member States as a result of co-financing from Tacis, PHARE or CARDS, should be set out clearly and separately, detailed by country.

#### Expected impacts

Describe the long-term impacts of your project beyond the funding period with regard to the set strategic objectives. Impacts expected within non-Member States as a result of co-financing from Tacis, PHARE or CARDS, should be set out clearly and separately, detailed by country.

### Target Group, Beneficiaries

#### Target Group

Please describe the nature and characteristics of the population and /or organisations your project is targeted at and who will benefit from it in the long term. If possible indicate the approximate number of people / organisations in the target group.

#### Direct Beneficiaries

Please explain who will directly benefit from the project within the project duration. If possible indicate their approximate number.

### Overview on project activities

Give an overview of the foreseen activities within your project. Describe the different activities, components and means to be developed within the project duration. Explain to what extent they will contribute in reaching the set objectives. Emphasis should be on a clear and comprehensible presentation of the planned actions in the context of the entire project rather than a complete and fully detailed listing of the individual activities. (The latter shall be given by means of the Action Plan.)

Project activities to be carried out within non-Member States as a result of co-financing from Tacis, PHARE or CARDS should be set out clearly and separately, detailed by country.

If your project foresees pilot projects, please consider the following:

A pilot project is a project which breaks new ground and provides new ideas, new ways of doing things, carried out on a trial basis. Pilot projects are normally small and are designed so that lessons can be drawn from them and, if successful, replicated.

Describe pilot projects in the light of the above. Make clear which problem they tackle, which findings you expect from them, how they can (and eventually will) be replicated. Define criteria that allow for a check of whether the pilot project was successful. Highlight the particular added value that emanates from the transnational approach.

### Outputs and deliverables

Please describe the main outputs and deliverables of your project. Indicate at which stage of the implementation they will be completed. Whenever possible specify and quantify them. Focus on a clear and comprehensible presentation, which allows understanding easily how your project evolves and how its progress can be checked over the implementation period. A formalized listing of outputs and deliverables will be requested in the Action Plan (see 4.2).

Outputs and deliverables expected within non-Member States as a result of co-financing from Tacis, PHARE or CARDS, should be set out clearly and separately, detailed by country.

## Work Packages, milestones and Action Plan

### Work Packages

In order to facilitate the management and the co-ordination of the project, applicants are asked to divide the project into thematically diversified Work Packages (WP). The number of WP shall range between a minimum of three and a maximum of six. In this paragraph, applicants will assign a title to each WP. The title should reflect the focus of the Work Package (e.g. sustainable development strategy, transport networking, development of territorial partnership, dissemination of results, etc.). Moreover, responsibility for each package will be identified, showing the Project Partner and the number of the responsible partner. Please note that this responsibility must be clearly assigned to only one partner per WP, i.e. a sharing of the responsibility among two or more partners is not allowed. The division of Work Packages should not reflect organisational aspects or geographical aspects, nor be defined according to a time-schedule.

### Action Plan

Please fill in this table in the Excel file “Application Form 4th Call – part2”, worksheet “Insert-Actions”. Once printed, insert the table 4.2 into this part of the Application Form. For detailed technical instructions how to fill in the specific table, please see Chapter G.

The Action Plan shall provide a formalized description of all actions to be carried out within the project. Action means a group of activities, components and means forming a functional unit (e.g. organisation and delivery of a workshop; setting up a project office, etc.). The typical budget per Action should be around EUR 100,000. Actions that exceed this limit significantly must be split up into accordingly sized Actions.

This holds also true for pilot projects. They have to be depicted the very same manner like all other Actions.

Please note: By reserving Budget Lines for Actions that are not duly specified (“black boxes” without verifiable outputs, deliverables,) the application runs the risk of being rejected.

Before filling in the Action Plan please read also carefully the “Detailed explanation of ERDF budget lines” (Chapter E of this manual).

For each Action describe its cornerstones in a way that allows to estimate roughly the dimension of its costs. You may use up to 5 lines in the data field “description of the Action” to give details.

Indicate the expected outputs and deliverables. Whenever possible give quantifications.

All Actions should be labelled with a code consisting of the consecutive number of the WP and the consecutive number of the Action (starting for each WP from 1). The two numbers shall be separated by a dot (e.g. Code for Action 1 of WP5 = 5.1). Please note that the detailed breakdown of the budget relates to the Action Plan by this code.

Project activities should be described on overall project level (line “Overall”), but also detailed separately for EU Member State partners and for non-Member State partners. For partners co-financed from TACIS, PHARE or CARDS description of activities should be detailed by country (see “Table 2. - Country codes” in the chapter D.2)

For each Action a single responsible partner shall be indicated.

Location of activities

In this column, state the NUTS II code(s) of the region(s) where the project activities will take place. A table comprising the regions covered by the CADSES NP is in Chapter H.1.

Table 3: Countries and regions covered by the CADSES NP

| Albania | NM | The whole country |
| --- | --- | --- |
| Austria | MS | The whole country |
| Bosnia Herzegovina | NM | The whole country |
| Bulgaria | AC | The whole country |
| Croatia | AC | The whole country |
| Czech Republic | MS | The whole country |
| State Union of Serbia and Montenegro | NM | The whole country |
| Former Yugoslav Republic of Macedonia | NM | The whole country |
| Germany | MS | Baden-Württemberg , Bayern, Mecklenburg-Vorpommern, Sachsen, Sachsen-Anhalt, Berlin, Brandenburg, Thüringen |
| Greece | MS | The whole country |
| Hungary | MS | The whole country |
| Italy | MS | Puglia, Molise, Abruzzi, Marche, Friuli-Venezia Giulia, Veneto, Emilia-Romagna, Lombardia, Trentino-Alto Adige, Umbria, Basilicata |
| Poland | MS | The whole country |
| Republic of Moldova | NM | The whole country |
| Romania | AC | The whole country |
| Slovakia | MS | The whole country |
| Slovenia | MS | The whole country |
| Ukraine | NM | Odesska oblast, Zakarpatska oblast, Lvivska oblast, Volynska oblast, Ivano-Frankivska oblast, Chernivetska oblast |

### Milestones

Please indicate at least one milestone for each semester of the implementation period.

A milestone is a significant scheduled event that acts as a progress marker in the life of a project. A milestone is either passed or not, its achievement or non-achievement is monitored and reported. Milestones are a way of identifying or labelling significant events which can then be used to report progress. A milestone is often used to identify the completion of a series of tasks, or readiness to begin a new stage (i.e. when all the dependencies or prerequisites have been satisfied). It is an important project event that often marks the end of a major project phase. It is an important step reached in the project by the completion of several activities with achieved deliverables, outputs and results. A milestone has been always reached at a certain and single date and usually not within a time period.

Milestone could be also defined as “a point in time representing a key or important intermediate event in the life of a project. A milestone should be capable of validation by meeting all of the items prescribed in a defining checklist”. To allow its validation, specify appropriate items by which the completion of a milestone can be checked.

## Monitoring Indicators

This section serves monitoring purposes beyond the immediate project level. Indicators given here should not duplicate the information provided in section 3, but present them on an aggregated level.

### Category(ies) of intervention

Please specify the categories/subcategories of intervention according to list annexed to the Programme Complement. If your project covers more than one area of intervention, give percentages indicating the relevant share of the project.

### Types of actions

The Programme Complement lists four types of actions:

- planning activities, such as transnational studies and strategies, land use plans, etc.

- Networking;

- Pilot actions;

- Information, training and awareness raising. Please describe in the second column of the table the relevant activities carried out by the project, in correspondence with the relevant type of action. For example: within the type of action n. 2 - Networking, the project will carry out activities directed to develop a network between cities along major rivers in a Central Europe area.

### Territory concerned

In this paragraph, state the location where the project activities will take place. The applicant may annex a map showing the location of the project activities. A table containing the countries and regions covered by the CADSES NP is shown in part H of this document.

The countries and regions where the participating partners in the project implementation are located have to be listed in this paragraph. In the case of Member States, EUROSTAT codes at a NUTS II level will be used (further information may be downloaded from the EUROSTAT web site at:

http://europa.eu.int/comm/eurostat/ramon/nuts/home_regions_en.html

### Quantified expected outputs

Output indicators show the immediate product of a project’s activity. They can be measured in physical or monetary units. Examples of output indicators are: number of local authorities involved in planning activities, number of studies and researches carried out, number of networks created among cities, etc. Please see the Measure description in the Programme Complement for reference. Applicants can consider the Programme Complement indicators as a general reference. If necessary, other indicators might be chosen which best fit to the project. In any case, applicants are recommended to provide for the quantification of the selected indicators, when possible. Also indicate the timeframe within which the expected outputs are produced (e.g. 8 months after project start).

Output indicators for non-Member State partners should be set out clearly and separately, detailed by country.

For further detail on indicators within the monitoring and evaluation of structural policies, please see the European Commission Working Papers no. 3 (Indicators for monitoring and evaluation) and no. 7 (Ex ante evaluation and indicators). Even if these documents are mainly referred to a programme and not to a project level, they give clear definitions of output, result and impact indicators. These definitions apply also for project promoters.

### Quantified expected results

Result indicators show the immediate effect of the project on the direct beneficiaries, such as changes of behaviour, increase of services supplied, etc. Results can be measured in physical (e.g. number of trainees, number of target groups reached, increase in know-how exchange among actors, etc.) or financial (e.g. leverage of private resources) units. Examples of result indicators from the Programme Complement are: number of organisations representing migrants participating in a project, number of actions and planning documents promoting use of ICT in transport development, number of trainees in courses concerning ICT use.

Result indicators for non-Member State partners should be set out clearly and separately, detailed by country.

### Quantified expected impacts

Impact indicators show the mid- to long-term consequences of the project beyond the immediate effects on its direct beneficiaries. Impacts can be specific when they occur after a certain lapse of time but are, nonetheless, directly linked to the action taken or global when they consist of longer-term effects affecting a wider population (e.g. creation of new jobs, decrease in natural disasters, increase in tourist flows, increase in investment opportunities, improvement of public or private services, etc). Examples of impact indicators from the Programme Complement are: number of project results used by partners, increase in tourist activity focusing on cultural heritage, new opportunities for investment attraction.

Please indicate also the timeframe within which the expected impacts shall become effective (e.g. 6 months after project completion).

Impact indicators for non-Member State partners should be set out clearly and separately, detailed by country.

## Complementarities with other projects

Restrain to links that are really relevant to your application. Please describe in detail how the projects are linked. Which provisions have been made to safeguard co-ordination and exchange of information with related projects? In case of a follow-up of an INTERREG II C or even IIIB CADSES NP project: What is the added value of continuing and what is the main progress in comparison with the former project?

### Complementarities with INTERREG II C CADSES projects

In this paragraph, applicants indicate if the project and/or the partnership has its origin in any of the INTERREG II C CADSES projects and in particular if the submitted proposal builds on the results of a previous project. If this applies, a short description is given of the objectives, activities, costs, results, and follow-ups of previous projects or partnerships.

### Complementarities with other INTERREG III B CADSES projects

If your project would be complementary or exploit synergies with proposed,  approved or finished projects in the same or other INTERREG III B measures, indicate the project(s) and the programme(s) here and describe the link. Demonstrate briefly how the projects would benefit from each other. Information given here should allow the CADSES JTS to contact the responsible programme management units for co-ordination.

### Complementarities with projects in other relevant Programmes

In this paragraph, applicants explain if and how their project is linked — in terms of synergy, complementarity and integration — with other EU co-financed Programmes:

- other INTERREG Programmes, within Strands A, B and C;

- other Community Initiatives (URBAN, LEADER+, EQUAL);

- Programmes co-financed by Structural funds under Objective 1, Objective 2 or Objective 3. For instance, links may be defined in terms of:

    - territorial integration;

    - preparation of conditions for larger structural actions, as infrastructure construction, support to private investments, etc;

    - transfer of innovative methods and know how

    - exchange of experience, etc.

- Other projects financed by PHARE, Tacis or CARDS funds.  In such cases, you shoud indicate the project(s) and the programme(s) here and describe how the CADSES project would be complementary or exploit synergies with the previous project. Information should also be provided to allow contact to be made with the responsible programme management units for co-ordination.

Moreover applicants have to state whether they or any other partners have ever submitted this or a similar project proposal to any other Community Programme. If yes, they have to state under which other programmes they have applied for funding. They will declare whether the proposed project or parts of it have already been funded by other EU sources. If yes, applicants will disclose the name of the programme, the amount of the grant obtained, and the date of approval. The project cannot be considered eligible in case of double EU funding.

## Consistency with INTERREG III B general strategies

### Compliance with European and national spatial development policy

How does your project fit into European and national spatial development policy issues?

In this paragraph, the project’s contribution to the implementation of strategies and objectives of spatial policies has to be described, with reference to their wide range of intervention in economic, social, environmental, urban and other structural fields.

In particular, applicants first explain how their project is consistent with relevant European policies/activities and how it contributes to their implementation. A special reference shall be made to: (a) European Spatial Development Perspective and related documents; (b) CEMAT Guidelines; (c) Trans-European Transport Networks; (d) Natura 2000 – “Habitat” – Directive 6th Environmental Action Plan.

Secondly, applicants discuss how their project is consistent with relevant national policies at a Project Partner level (e.g. environmental legislation, transports, sustainable development, natural risk prevention, etc.) and how it contributes to their implementation.

### Contribution to spatial development

How does your project contribute to the spatial development of a wider CADSES area?

Describe if and how your project generates spatial development impulses for a wider CADSES area. Focus on effects that are not purely local or regional but help improving economic, ecologic and social integration in a broader geographical context.

### Transnational added value

What is the particular value added to your project through its transnational approach compared to a purely national implementation?

Outline the specific advantages of your project’s transnational approach to achieve the set objectives and results. In particular, contrast it with what might be achieved by a mere national approach.

### Impacts on competitiveness and regional cohesion

Does your project generate positive impacts in terms of competitiveness and regional cohesion? If yes, please specify:

Discuss the capacity of your project to generate and spread positive effects in terms of increasing competitiveness and enhancing regional cohesion. Highlight if and how the proposed project is able to generate effects to increase efficiency, quality and productive capacity of economic sectors in the target region(s).

### Impacts on employment and social cohesion

Does your project generate positive impacts in terms of employment and social cohesion? If yes, please specify:

Discuss your project’s ability to generate positive effects on the employment situation, with particular reference to additional employment provided, creation of permanent jobs (beyond project conclusion), indirect effects on employment, job creation and income opportunities, job opportunities for young people, contribution to the economic and social welfare on the regional scale, increase of quality and mobility of labour force, social cohesion and conditions of immigrated labour force.

### Equal opportunities

Does your project generate positive impacts in terms of equal opportunities? If yes, please specify:

Describe here how the project contributes to an improvement of equal opportunities (with reference to age, race, gender, handicap and nationality). A particular concern shall be paid to the creation of equal opportunities for men and women. The demonstration of positive effect on equal opportunities mainly relates to the project capacity to contribute to the inclusion in labour force, opportunities of professional training and education, establishment of partnership among countries of different cultural background and/or languages, creation or preparation of social infrastructure and services, avoiding social segregation, promotion of an adequate variety of jobs, etc. Applicants shall indicate here

- if the project has equal opportunities as its main focus;

- if it is positive in terms of equal opportunities; or

- if it is neutral in terms of them.

### Environmental impacts

What impacts on the environment can be expected from your project? Please specify:

Describe your project’s impact on the environment. For example, applicants shall describe the project’s capacity

- to promote strategies and actions to eliminate negative environmental impacts of economic activities;

- to promote and enhance natural resources; to improve co-operation in the field of natural resources and environmental (or land use) regulations;

- to promote the creation and use of alternative energy resources;

- to raise the degree of public awareness on environmental issues, etc.

Please indicate if the project has environmental issues as its main focus; or it is environment friendly; or it is neutral in terms of environment.

### Innovative elements and innovative methods

Does your project develop innovative elements or apply innovative methods that have never been used before in a comparable environment? If yes, please specify:

Specify and describe innovative element(s) to be developed by your project.  Demonstrate if your project will apply innovative methods, strategies and techniques that have never been used before in a comparable environment. Give particular reference to their degree of originality, their innovation potential and their capability to determine transferable experiences.

### Improvement of the institutional setting

Does your project contribute to an improvement of the institutional settings? If yes, please specify:

Demonstrate the capacity of your project to contribute to an improvement in the institutional settings, with reference — for instance — to the adoption of plans, procedures and strategies by national or local governments; to the setting of innovative partnership or networks; to the transfer of new methods, procedures and tools to public administration, etc.

## Management of the project

### General co-ordination and overall responsibilities

Describe: (a) how the project (and its work-packages) will be co-ordinated and managed among the partners; (b) how the co-ordination responsibilities - if the case - will be shared by different partners; (c) how the different competencies and know-how will be used; (d) and how the decision making process will be handled (e.g. decisions on the responsibility for and execution of the Work Packages, partnership contracts, administrative procedures, etc.). It is strongly advisable to use a flow diagram in order to depict clearly the management structure of the project at all levels.

### Operational management, including administrative and financial aspects

In this paragraph, applicants specify how operational management tasks and responsibilities will be distributed among the various partners. They shall outline their provisions made for monitoring, auditing, reporting, financial management and evaluation on project level. It should be indicated how many persons from which partners will be employed in transnational management activities.

The Lead Partner is asked to describe in which way it will establish contractual relationships with its Project Partners. Please pay particular attention to provisions for crisis management and the settling of disputes among the partners.

### ERDF Certifying bodies

In this paragraph, applicants are required to indicate, for each partner, the body / institution which will certify expenditures related to ERDF co-financing. Depending on the source of the national co-funding of a project, certifications of expenditure will be generally given by a public or private accountant, independent of the project implementation. If the co-funding stems from public funds, the declaration will be generally made by the responsible public co-funding authority, if the co-funding comes from private funds, the declaration of expenditure will be given by an external accountant.  The certification of expenditure shall confirm the delivery of the products and services co-financed, the reality and eligibility of expenditure claimed and that national and community rules, especially Commission Regulation (EC) 448/2004, have been respected.

Before entering data here, please contact the relevant CCP in the CADSES programme area to receive more information about specific national conditions and obligations concerning certification of expenditures and certifying bodies.

### Provision of guarantees (in case of a Lead Partner under private law)

In case of a Lead Partner under private law, please describe which provisions will (or have already been made) to present the securities as requested by the PC (1.2.1 Lead Partner Principle). For further information on this issue see also Chapter C.7

## Actions for publicity and dissemination

This section of the Applicant Form regards the project’s communication plan. Applicants have to describe clearly the actions foreseen for project’s publicity and for dissemination of final results, both to the relevant target groups and to the wider audience. Applicants should indicate which target groups the project’s publicity will aim at and what tools and material will be produced (electronic, printed or audio-visual) in order to communicate the project and its results to the various target groups and to the public.

Specific and separate actions for publicity and dissemination within non-Member States as a result of co-financing from Tacis, PHARE or CARDS should be set out clearly and separately.

## Transfer of the project results

It is necessary to describe here firstly the degree of transferability of the project results, i.e. in which way they can be transferred to and used in other parts of the CADSES area or in other INTERREG III B co-operation areas. Moreover, concrete actions foreseen to put in practice the transfer of the project results are described.

## Follow-up actions

### Project follow up after finalisation

In this paragraph, applicants indicate: (a) if the project will lay the ground for further investigation or political declarations or strategies once the project has been finalised; (b) if and in which way the partnership set up by the project will continue to co-operate once the project has been finalised or if partnership is expected to be closed after project realisation. Applicants will also indicate here if and how potential investors and other respective groups have been contacted or will be contacted to implement the project results. Furthermore it should be outlined how the project results will be used beyond the project period.

### Preparation of large investment

In this paragraph, applicants show whether the project will lead to large investment once the project has been finalised. Such investments are described and the institutions that will be responsible for their realisation and management are identified. Potential investors should be listed here.

## Bank information

Please provide here the details on the requested bank accounts of the Lead Partner, and the financial Lead Partner for external funding where appropriate. For financial Lead Partners for external funding, please complete Chapter 18 as well.

## Other information

Add here any further key points that you consider relevant to support your application.

## Project Partners – detailed information

### Lead Partner

Please provide the requested contact information and further technical details for the Lead Partner.

The Lead Partner’s legal representative is the person authorised to act as signatory of the Subsidy Contract.

All official correspondence relating to the project will be sent to the official contact person indicated in the information sheet on the Lead Partner. In some cases the legal representative will also act as official contact person. However, the Lead Partners may instead designate an authorised person different from the legal representative, but from the same institutional body, as official contact person. By indicating such a contact person in the information sheet on the Lead Partner he/she will become the sole recipient of all formal communication.

In the field “legal status” please specify whether public or private law governs the partner. Private partners who meet the requirements of a “public equivalent body” according to the Council Directive 92/50/EEC of 18 June 1992 relating to the coordination of procedures for the award of public service contracts” (Official Journal L 209, 24/07/1992 P.0001 – 00024) shall choose this option.

Indicate the amount, which will be provided as in-kind contribution.

Please note: ERDF co-financing per partner cannot exceed the partner’s total expenditure minus his contribution in kind (Reg. (CE) No 448/2004, Rule No 1, point 1.4).

Rule 1 point 1.6 of the above regulation stipulates the following:

“In kind, contributions are eligible expenditure provided that:

(a) they consist in the provision of land or real estate, equipment or materials, research or professional activity, or unpaid voluntary work;

(b) they are not made in respect of financial engineering measures referred to in Rules 8, 9 and 10;

(c) their value can be independently assessed and audited;

(d) in the case of the provision of land or real estate, the value is certified by an independent qualified valuer or duly authorised official body;

(e) in the case of unpaid voluntary work, the value of that work is determined taking into account the amount of time spent and the normal hourly and daily rate for the work carried out;

(f) the provisions of Rules 4, 5 and 6 are complied with where applicable.”

Internal hours (staff costs) of Project Partners (public or private) are not considered as contribution in kind. The related expenditure must be supported by specific documents – refer to point 1.1 of the eligibility regulation 448/2004. In contrast, unpaid voluntary work is regarded as contribution in kind.

### Project Partners 2 - 25

Please provide the requested contact information and further technical details for each Project Partner. For further information see above (chapter 14.1).

### Partner Profile

In this section each partner shall describe his specific role in the implementation and management of the project. What is the partner responsible for? How does he contribute to which actions? Make sure that each partner has a clearly defined role in the project and renders clearly defined services. Pay particular attention to allow for each partner a check whether his participation in the project was successful. Further each partner shall indicate the source(s) and the respective legal basis of his contribution to the project.

## Certification and submission

The Lead Partner’s legal representative (or a person authorised to do so on his behalf) shall certify the correctness of the information stated in the Application Form.

## Project finance for ERDF

The application package includes an Excel file named “Application Form 4th Call – part2” that shall be used to generate the financial tables of the project proposal. This file features three groups of worksheets:

- 4 worksheets whose names contain “insert” provide entry masks allowing you to insert data requested to complete the financial tables. These worksheets serve for data entry ONLY; no printout of them is needed.

- 4 worksheets whose names contain “print” include automatically generated tables and/or supporting documents (like Co-fin. Statements), which must be printed once all data have been inserted. The printouts must be integrated into the hardcopy version of the Application Form.

- Worksheets for financial tables 16.1 – 16.9, which must be filled in and printed. All of them must be submitted with the hardcopy version of the Application Form.

Section E of this manual provides detailed instructions on how to generate the financial tables.

The above-mentioned Excel file is and integral part of the Application Form and must be submitted in both the hard copy and the electronic version.

### Financial contribution by Project Partner and sources

In this table, applicants will indicate which kind of funds will be used by the partners, distinguishing between partners coming from Member States and from Non-Member States.

EU partners from Objective 1 areas, with the exception of Austria and Italy, are eligible for maximum 75% ERDF co-financing. All other EU partners are eligible up to 50% ERDF co-financing of their total budget.

Partners from non-EU-Member States are eligible for co-financing from Tacis, PHARE or CARDS as set out in part H.

For detailed information on EU co-financing rate of the CADSES NP regions, see part H at the end of this manual.

Please note that the Lead Partner has to safeguard the duly implementation of the entire project. The budget presented here forms a contractual basis, i.e. its non-fulfilment might lead the MA to withdraw from the Subsidy Contract. Therefore it is advisable to consider only reliable Co-financing Statements and secured promises of grants.

If funded by INTERREG III B CADSES NP, the project cannot receive additional funding from other EU programmes except financial instruments providing assistance to non-Member States (PHARE, CARDS, Tacis etc.). Irrespective of this restriction, clearly separated parts of the project may be supported by other EU programmes (e.g. Sixth RDT, E-Europe) provided these parts are not calculated within the eligible project costs under CADSES.  Other EU funds cannot be used to co-finance the funding provided via the CADSES programme.

### Expenditures by Project Partner and Work Package

This table shows the total eligible expenditures by partners and Work Packages.

### Expenditure by Project Partner and Budget Line (only EU PPs)

This table shows the total eligible expenditures by partners and Budget Lines, for EU Project Partners.

### Certified expenditures to be submitted within each year (only EU PPs)

This table shows the foreseen payment claims per year that will be submitted to the Paying Authority. The amounts reflect the fact that the Project Partners have to have certified their expenditures before they can submit them to the Paying Authority, which takes some time. Moreover, the latest payment claim of each year can be submitted no later than 1 December.

The totals per years of the table 16.4 will be part of the Subsidy Contract and therefore binding for the project. If necessary, the project can shift up to 20% of the amounts stated per year to the following year. Subsequently, if the project requests less than 80% of stated totals within the respective year, it will loose the corresponding ERDF subsidy for these not submitted expenditures. This table concerns only EU Project Partners.

### Breakdown of BL 7 “Other costs” (only EU PPs)

This table itemizes the planned expenditures for other costs. This table concerns only EU Project Partners.

### Breakdown of BL 8 “Small scale investments” (only EU PPs)

This table itemizes the planned expenditures for small-scale investments. This table concerns only EU Project Partners.

### Breakdown of expenditures per Action alongside Project Partners and Budget Lines

This table gives a complete overview of costs of each single action, contribution of each Project Partner to this action and splited into Budget Lines. This table concerns only EU Project Partners.

### Budget for External Funding

Tables 16.8 concern only non-EU Project Partners. Each financial Lead Partner for external funding (ext.LP) will fill in the for his country corresponding table, giving details on finances of all Project Partners from the same country. Common table will be filled in for partners from Ukraine and Moldova.

### Fee rates of Project Partner's own staff - BL 2 "Personnel”

Each Project Partner fills in the details on expert categories and costs of own staff involved in the project.

## Co-financing Statements & Letters of Intent

For each partner contributing financially to the project, a signed and stamped original Co-financing Statement has to be included into the Application Form. Use the standard format, filled in automatically in the Excel file - Application Form Part 2. No changes or amendments to the text of the standard Co-financing Statement are allowed.

For each partner who participates without financial contribution to the project, a signed and stamped original Letter of Intent has to be included into the Application Form. Use the standard format, filled in automatically in the Excel file - Application Form Part 2. No changes or amendments to the text of the standard Letter of Intent are allowed.

## EXTERNAL FUNDING - Financial identification of non-eu Project partners

Provide for each financial Lead Partner for external funds a financial identification sheet, which shall be completed handwritten.

# Detailed explanation of ERDF budget Lines

## Project co-ordination

Costs for project co-ordination comprise administrative costs that accrue in relation to the overall management of the project and are not calculated under overhead costs. They cover for instance legal fees (e.g. for partnership contracts), fees for bank guarantees, notarisations, insurance fees, courier services, etc.

Project preparatory costs (i.e. costs for the preparation of the project, which were incurred before the official project start) up to a maximum of 2% of the overall budget, but not exceeding 20.000€ can be calculated under this cost category as eligible expenditure in relation to ERDF funding. Anyway the eligibility dates of the programme (see B.4) have to be respected.

For the participation in transnational working groups and other programme events of the CADSES programme a lump sum of 3000 € per year and project shall be calculated under this Budget Line.

## Personnel (including overhead costs)

This section includes all fees of the Project Partners’ staff to be paid in the context of the project. External staff must be budgeted under “External expertise and audit”. Fee rates must reflect the actual cost of employing a person within the context of the project including social contributions/payroll taxes, national insurance contributions etc. and may not include a profit margin. Depending on the level of detail of the accounting system general overhead costs may be included. The overhead costs must be based on real costs, which directly relate to the implementation of the operation. The overhead costs should in this case be allocated pro rata to the operation according to a duly justified fair and equitable method.

## Meetings, conferences, seminars

For each event provide a total budget which includes: the rental of the venue, rental of equipment, documents, translators and interpreters and meals if not covered by daily allowances. The fees of trainers, speakers, and facilitators should be mentioned under the “external expertise” header.

## Travel and accommodation

This Budget Line comprises project expenditures that are related to international or national travel.

Allowances are paid to project staff or beneficiaries (e.g. trainees, participants in a study tour, etc.) who have to travel abroad or stay away from their usual place of work for more than one day for the purpose of the project. Allowances are intended to cover accommodation, meals and sundry expenses (such as tips, laundry, toiletries, buses and taxis).

Per diem rates shall not exceed those paid to experts on missions undertaken in the course of an EC-funded external aid contract. For the effective rate please refer to:

http://europa.eu.int/comm/europeaid/perdiem/liste1_en.htm

Please note that flight tickets should be economy class.

## Promotion and publications

Specify the nature of promotion activities or publications and justify in relation to project activities.

For each important promotion activity provide information on the target group, expected outcome, deliverables, total budget etc.

For each important publication specify the purpose, target group, number of copies, number of pages, language(s) used. Give the total budget per document including costs for editing, translation, printing, mailing, etc.

## External expertise and audit

Specify the nature of external expertise (e.g. subcontracting of external staff, speakers for workshops, trainers, web designer, studies, services, etc.). Describe, in principle, for each assignment or contract its content, total budget, expected deliverables, and envisaged procedure for selection of contractor.

Expenditures for auditing, if any, shall be budgeted in an amount of approx. 3 to 5 % of the total costs.

## Others

Any other costs, which do not fit under any of the other headings, should be fully detailed (description, number of units, unit rate).

## Small scale investment

This category comprises small-scale physical infrastructure investments proposed by transnational strategic concepts. Thoroughly justify the need for the investment. Only equipment or works that is strictly necessary for the implementation of the project can be included in the project budget. Only infrastructure with a transnational impact in compliance with the INTERREG III guidelines (Art. III 14) can be taken into consideration).

Split the budget by item. Please note that you will be required to organise procurement using competitive methods. Please state clearly who will retain the ownership of the investments at the end of the project.

# Project finance for external funding

Eligible direct costs: These are costs directly generated by the project and essential for its implementation. They would not have been incurred if the project had not been carried out.

The following direct costs are eligible:

# Staff costs:

- Internal staff costs (unit cost per day for work on the project). These may not exceed the salaries and other charges paid by the partner for the person employed. In the case of civil servants employed by the Project, a percentage of the normal time of the employee, which is spent for the project, is charged to the project. In short, the monthly salary is divided by 22 (number of working days per month) to give the daily rate. The daily rate is then multiplied by the number of days spent on the project.

- Staff costs can only be included for staff employed by the Lead Partner or Financial Lead Partner for external funding or one of the Project Partners. Documentation must be provided through the duly filled time sheets, for each person, nominated as staff under the project.

# Living costs (per diems):

- Per diems (covering accommodation, subsistence and local travel) applied for international travel can not exceed those laid down by the Commission. The per diem is due when the expert is staying overnight in the country visited. The per diem is a lump sum, which should be paid to all staff listed in the project under Staff Costs. A summary of the per diems for the staff is to be annexed to the financial report.

# Operational costs:

- Travel at rates and in terms set according to the market conditions but not exceeding those laid down by the Commission. The most economical mode of travel should be chosen taking time into consideration; flights should be economy class, train can be first class and costs for the use of car equivalent to a first class train ticket for the same distance. National travel expenses are covered by the project budget on the bases of actual incurred costs for travel and subsistence. No per diems apply for the national travel. Original invoices/ tickets and boarding passes must be kept, and a copy must be attached to the Reports.

- Experts/consultants: please note that where activities are paid for by PHARE, Tacis or CARDS funds experts/consultants for services (such as studies, audits and evaluations) need to be procured on the basis of the standard procurement rules for grant beneficiaries as outlined in annex IV of the standard grant contract.  Only experts introduced as project staff and budgeted under human resources costs can be hired on a personal basis.  Note also that key persons in the project such as Project Coordinator and experts can be exchanged only under special circumstances, with the prior approval of the Project Manager of the European Commission or the European Agency for Reconstruction (as appropriate).

- Costs of equipment (new or second-hand) must not exceed normal market prices. This budget item should not exceed 20-25% of the total project costs. The rules concerning origin of goods must be respected; only goods from the EC, PHARE, CARDS or Tacis beneficiary countries can be purchased. At the closure of the project equipment purchased for the purpose of the project must ultimately become the property of the partner, the project partners must sign a declaration for transfer of the ownership. Purchase rules for equipment in accordance with EU legislation apply; up to EUR 5,000 the contract may be awarded on the basis of a “single offer”.  For supply contracts in the range of EUR 5,000 to EUR 30,000, a contract may be awarded on the basis of a competitive negotiated procedure, where at least three suppliers are consulted.  Between 30,000 and 150,000 Euro an open local tender has to be arranged.  The beneficiary is advised always to consult the European Commission or the European Agency for Reconstruction (as appropriate) for issues concerning larger scale tenders.

- Small-scale infrastructure can be supported provided it is an integral part of the project and can only be included if it forms an integral part of a larger co-operation. Please specify the type of expense and partner carrying the cost. Acquisition of land or vehicles cannot be funded.

- Conferences/ workshops, costs in relation to organizing events can be included. Examples are: rent of venue and equipment, interpretation. Internal staff costs cannot be included.

- Translation, information and dissemination costs

- Audit

# Eligible indirect costs/ Administrative costs

Eligible indirect costs include a maximum of 7% of the total amount of eligible direct costs. The indirect costs are eligible provided that they do not include costs assigned for another heading in the project budget included in the Grant Contract.

# Instructions on how to generate the financial tables

## Detailed instructions on how to complete the ERDF financial tables

The creation of a proper project budget is not easy, and the task can be also more complicated by the fact that the financial information is scattered in different parts of the Application Form. In order to help the applicants to achieve the consistency of all figures, the financial information related to the project has been gathered into the excel file “Application Form 4th Call part 2”.

So you will find here not only the financial tables 16.1, 16.2, …16.9, but also other parts, which combine finances and text. These are thematically rather part of the “Application Form 4th Call part 1” and should be integrated to the word part after beeing printed  - §1.3 Project Costs and their financial sources, §2 List of Partners with their financial contribution, §4.2 Action Plan with complete description of each Action and related costs.

Also Co-financing Statements and Letters of Intent are an integral part of the Excel file. They are created automatically and need only to be printed out. This way assures the consistency of the Co-financing Statements with the partners’ contribution, which is a crucial point of the assessment of the project.

In order to safeguard the consistency of all finance-related parts of the Application Form, the single worksheets are linked with each other. Each figure is inserted only one time and is automatically summed or repeated in other worksheets. Moreover, a series of checks is built-in into the worksheets. This will warn you in case of a mistake, usually by wording or graphic announcement (the cell will become red).

Please follow the 13 steps bellow to fill in succesfully the financial tables of the “Application Form 4th Call part 2”.

Step 1. Fill in worksheet “Insert-Partners”

- Fill in the Acronym of the project (cell B2), which will be used for generating Co-financing Statements and Letters of Intent

- Fill in the institution of the Lead Partner in English (cell B5) and select his country (cell C5). Do not fill in his address; the length is limited to 80 characters.

- Fill in the institution of all other EU Project Partners (cells B8 to B31) and select their country (cells C8 to C31).

Use one line per project partner, e.g. if you have five EU partners of which one is the Lead Partner, you will use only cells B8, B9, B10 and B11 and for their country the cells C8, C9, C10 and C11.

- Fill in the institution of all non-EU Project Partners (cells B34 to B123) according to their country. For each non-EU country there are 10 cells available. For each non-EU country, the first Project Partner has also the role of Financial Lead Partner for external funds. (extLP; dark yellow cells).

Use only as many lines for each country as many PPs from this country you have. If you have two Albanian PPs and two Bulgarian, you will fill in the cells B34, B35 and B54, B55.

For Ukraine and Moldova you cannot distinguish the common Financial Lead Partner for external funds in this phase. The first PP in the list from both countries will be marked as extLP. The common ext LP will become clear from the §15 - Certification and submission, which the extLP must sign.

- Check in the table in the upper right side of the worksheet (Cells U3 to X30) if the order of Project Partners is correct. Stick to the shown numbering of the partners. Try to avoid later changes of order in the List of Partners.

Remark:

The inserted information will be used in the table §2 List of Partner, which you will print, in a later stage, from the worksheet “Print §2”. Do not print the worksheet “Insert-Partners”, unless for internal use. The worksheet is linked to all other worksheets except of “Insert-Actions”, “Print §4.2 ActionPlan” and all worksheets “16.8”. Total contribution of each PP will be inserted in the worksheet “Insert-sources”.

Step 2. Fill in worksheet “Insert-sources”

Following the List of Partners inserted in step 1, you must now fill in only the cells in yellow. The following cells are compulsory:

For EU PPs: rows 16 and 22

For non-EU PPs: rows 25 and respectively one of the rows 31, 33 or 35.

Other yellow-marked cells should be filled in only if suitable. Be careful not to assign amounts to a different Project Partner.

- Fill in the Co-financing EU PPs for respective partners  (yellow-marked cells in row 16).

The Co-financing, also called National Co-financing, is the amount each Project Partner guarantees from its own resources and which constitutes the 50% or 25% counterpart to the ERDF funding. This is also the amount, which will be stated in the Co-financing Statement. Example: Total partner’s contribution is 100.000, 50% will be funded from ERDF, i.e. insert 50.000 into the row 16.

- Specify what part of your co-financing is made of IN-KIND contribution (no matter the financing source; row 17).

- Fill in the sources of the co-financing for EU PPs, if suitable (yellow-marked cells in rows 18, 19, 20 and 21)

Sum of rows 18 to 21 cannot be greater than the co-financing in row 16.

- Fill in the ERDF funding rate for EU PPs (yellow-marked cells in row 22). Usually 50% shall be inserted, 75% for partners from Objective 1 areas.

Based on this information, the ERDF subsidy (row 22) and the partner’s total contribution (row 14) will be calculated for each EU PP.

- Fill in the Co-financing (non-EU PPs) for respective partners  (yellow-marked cells in row 25).

- Fill in the sources of co-financing for non-EU PPs (yellow-marked cells in rows 27, 28, 29 and 30, if suitable.

- Fill in the PHARE funding rate for partners from Bulgaria, Croatia and Romania (yellow-marked cells in row 31). Usually 75% shall be inserted.

- Fill in the TACIS funding rate for partners from Republic Moldova and Ukraine (yellow-marked cells in row 33). Usually 90% shall be inserted.

- Fill in the CARDS funding rate for partners from Albania, Bosnia Hercegovina, Croatia, FYROM (MK) and State Union of Serbia and Montenegro (yellow-marked cells in row 35). Usually 90% shall be inserted.

Based on this information, the PHARE, TACIS and CARDS subsidy (rows 31, 33 and 35) and the partner’s total contribution (row 14) will be calculated for each non-EU PP.

Remark:

The figures inserted here will be printed from the worksheet “16.1” in a later phase. Do not print this worksheet, unless for internal use. The information from this worksheet are reported and linked with worksheets “Print Co-fin St+LoI”, “Insert-Expenditures”, “Print §1.3”, “Print §2” and “16.1”.

Step 3. Print out or export the worksheet “Print Co-fin St+LoI”

At this stage you have compiled all information needed for automatic generation of Co-financing Statements and/or Letters of Intent. In this worksheet you will find a Co-fin. Statement for each partner with financial contribution and a Letter of Intent for partners without financial contribution.

- Print the Co-financing Statements and/or Letters of Intent and let them sign by each Project Partner’s legal representative.

You can also print selected pages with acrobat distiller as .pdf and send them to your PPs per e-mail. You can also send the whole excel file to your PPs, which will print out the needed Co-fin. St. or Letter of Intent.

Remark:

Print only as many pages as many Project Partners you have. Once you printed this worksheet, you cannot change the worksheets “Insert-Partners”and “Insert-Sources”, because it would influence the information in the Co-fin. St. and LoI.

Step 4. Fill in worksheet “Insert-Actions”

- For each Action in your project, select first the number of Action (column A), selects months of start and end of the Action.

- Fill in the columns Description, Responsible PPs, Location and Expected Outputs/Deliverables for the groups of partners involved in this very Action. For EU partners use the line “EU PPs” (line 5 in Action 1.1), for non-EU PPs the respective line of their country.

Use the line “Overall” if an action involves (i) both EU and non-EU partners or if (ii) more non-EU countries are involved. The line overall summarizes the whole Action for all involved groups.

You can leave the line “Overall” empty if an Action involves exclusively one group of partners (either only EU PPs or partners from only one non-EU country)

Order the Actions carefully in increasing order – first all Actions of the Work Package 1: 1.1, 1.2 …, only then Actions of the Work Package 2: 2.1, 2.2, etc.

Remark:

Do not print this worksheet, unless for internal use. The figures inserted here will be printed from the worksheet “Print §4.2 ActionPlan” in a later phase. Costs of each Action and of each group of partners within the Action will be added automatically once the worksheet “Insert-Expenditures” is filled in.

Information from this worksheet are reported or linked with worksheets “Insert-Expenditures”, “Print §4.2 ActionPlan”, “16.2”, “16.3” and “16.9”.

Step 5. Fill in worksheet “Insert-expenditures”

- You will find this table already tailored according to the actions that you inserted in Step 4. Now you must allocate the budget available for each Project Partner to the appropriate Actions, splitting the costs in each Action along the Budget Lines.

IMPORTANT: Non EU partners are not required to split their expenditures according to these budget lines. In this table they are requested to insert only the total amount per action in the yellow cells placed in the first line in each table called “BL 1 Co-ordination / non EU PPs total”.

Since the non EU PPs use different budget lines, they will provide a breakdown of their expenditures in the step 12. Nonetheless, for the correctness of the tables 16.2 and §4.2 Action Plan, the total expenditures per action of non-EU PPs must be inserted into this worksheet.

- Check the correctness of the figures in the row 25 – the table is completed correctly when all cells in this row are marked blue. Check also row 1005, where all cells must indicate “OK”. Then you are sure that you allocated the whole available budget for each Project Partner.

Remark:

Do not print this worksheet, unless for internal use. The figures inserted here will be printed from the worksheet “16.7” in a later phase.

It is recommendable to fill in first the table 16.9 (step 13) and only then to insert costs of BL 2 Personnel into this worksheet.

Information from this worksheet are reported or linked with worksheets “Insert-Actions”, “Print §4.2 ActionPlan”, “16.2”, “16.3”, “16.4”, “16.5”, “16.6”, and “16.9”.

Step 6. Print worksheets “Print §1.3”, “Print §2” and “Print §4.2 ActionPlan”

- Save the changes, close the Excel file and re-open it. Only in this way the links between the tables will be updated.

- Print the worksheets “Print §1.3”, “Print §2”, each of them is only 1 page. Integrate them into the appropriate part of the hard copy of the Application Form. In the §2 List of Partner, ExtLP will be marked with a star.

- Visualize print pre-view of the worksheet “Print §4.2 ActionPlan”, browse the pre-view in order to count pages containing your description. Print only as many pages as many are required to show all inserted Actions. Do not print empty pages containing only the header.

Unlike the worksheet “Insert-Actions”, the worksheet “Print §4.2 ActionPlan” contains not empty lines from of the Action Plan. This significantly reduces the number of pages necessary for printout of the Action Plan.

- Make a quick check whether the printout of the Action Plan contains all descriptions from the worksheet “Insert-Actions”. Integrate the Action Plan between chapters 4.1 and 4.3 of the Application Form. Do not submit empty pages.

Step 7. Print the worksheets “16.1”, “16.2”, “16.3”

- Print worksheets “16.1”, “16.2”, “16.3” (each only 1 page). These tables sum up information inserted in steps 1, 2, 4 and 5 and are therefore already filled in completely.

Step 8. Fill in worksheet “16.4”; print it

- Fill in only yellow-marked cells in the table 16.4 (only EU PPs). In the column K you can check the consistency with the total contribution of EU partners. The table is consistent if all cells in column K indicate “OK”.

- Print the table 16.4

Provide a breakdown of certified expenditures to be submitted in Payment Claims annually, for each Project Partner. Insert the appropriate amount of total certified expenditures (sum of ERDF and co-financing), which will be submitted to the Paying Authority within the last deadline of each year. Only the costs of partners requesting ERDF subsidy can be inserted (yellow fields).

Please take into account that the Project Partners have to have certified their expenditures, which takes some time. Moreover, the latest payment claim of each year can be submitted no later than 1 December. The yearly payment claims handed in at the Paying Authority do not fully match the yearly expenditures, which is also due to the different timing of expenditures and real payments. As a rough rule of thumb the payment claims of a certain year cover the months of October through December of the previous year plus the January through September months of the current year.

Step 9. Fill in worksheet “16.5”; print the table 16.5 (only for EU PPs)

- Fill in the table 16.5. Describe shortly the expenditures in the BL 7 “Others” item-by-item. State the used unit or its abbreviation in the column “Unit” (e.g. pcs., kg). State the costs per unit (in €) and the number of units to be purchased. The total costs of each item will be calculated automatically.

If you need more lines, copy the last line (cells A57 to E57) and past them to as many following lines as you need. Leave the table empty if your

- Check the consistency with other tables in the cell F3. This must indicate “OK”.

- Print the table 16.5. Print and add to the hard copy only not empty pages containing some description.

Step 10. Fill in worksheet “16.6”; print the table 16.6 (only for EU PPs)

- Fill in the table 16.6 in the same way as 16.5 (see above).

- Check the consistency with other tables in the cell F3. This must indicate “OK”.

- Print the table 16.6 in the same way as 16.5 (see above).

Step 11. Print the worksheet “16.7”

- Print the table 16.7 in the worksheet “16.7” This table contains information from the worksheet “Insert-Expenditures” and is therefore already filled in completely.

Visualize the print pre-view, find out how many pages contain inserted information and print only those pages. Do not print pages where the Action no indicates “Action 0”.

Step 12. Fill in relevant tables worksheets “16.8”; print tables 16.8 (only non-EU PPs)

- According to countries of in your project involved non-EU Project Partners, fill in the relevant worksheets “16.8”. Insert lines if necessary and copy also the corresponding summing formulas. Each of these worksheets groups the PPs coming from the same country: therefore, for instance two Romanian partners will aggregate their data in the table “16.8 RO”. All the PPs receiving TACIS co-financing are grouped under the same table “16.8 UA+MD”.

- Print only the filled in tables 16.8.

Step 13. Fill in table 16.9 in worksheet “16.9”; print the table 16.9 (only EU PPs)

- Group the own staff of each EU Project Partner (persons working fully or partly for the project) into categories according to their expert level and costs per day. Each Project Partner has usually several categories. Insert the name of each category in the column “Expert Category” and assign to it a fee of a man-day in EUR. Moreover specify the number of man-days of deployment of each category in the project activities.

Total costs of personnel per EU Project Partner and for the whole table must be consistent with the table 16.3, BL 2 Personnel.

- Check the consistency with other tables in the cell G4. This must indicate “OK”.

- Print the table 16.9. Print and add to the hard copy only not empty pages containing some description.

Recapitulation: What to do with each single worksheet

| ONLY filled in | (No printout) | “Insert-Partners” “Insert-Sources” | “Insert-Actions” “Insert-Expenditures” |
| --- | --- | --- | --- |
| ONLY printed | Print completely | “Print §1.3” “Print §2” “16.1” | “16.2” “16.3” |
|  | Print only relvant pages | “Print Co-fin St+LoI” “Print §4.2 ActionPlan” | “16.7” |
| Filled in AND printed | Print completely | “16.8” (for each involved country) |  |
|  | Print only relevant pages | “16.5” “16.6” | “16.9” |

## How to complete the external funding financial tables

For the external funding, one table 16.8 must be filled in for each contract required.  This table will form the financial basis for a resultant contract if the project is selected for funding. Refer to the Step 12 of the previous subchapter.

# CADSES regions and their Maximum EU co-financing rate

## EU-Member States

| Country | Region | NUTS II code | Objective | Maximum eligible ERDF funding rate (%) |
| --- | --- | --- | --- | --- |
| Austria | Burgenland | AT 11 | 1 | 50 |
|  | Niederösterreich | AT 12 | 2 | 50 |
|  | Wien | AT 13 | 2 | 50 |
|  | Kärnten | AT 21 | 2 | 50 |
|  | Steiermark | AT 22 | 2 | 50 |
|  | Oberösterreich | AT 31 | 2 | 50 |
|  | Salzburg | AT 32 | 2 | 50 |
|  | Tirol | AT 33 | 2 | 50 |
|  | Vorarlberg | AT 34 | 2 | 50 |
| Czech Republic | Praha | Cz 01 | 2 | 50 |
|  | Stredni Cechy | CZ 02 | 1 | 75 |
|  | Jihozapad | CZ 03 | 1 | 75 |
|  | Severozapad | CZ 04 | 1 | 75 |
|  | Severovychod | CZ 05 | 1 | 75 |
|  | Jihovychod | CZ 06 | 1 | 75 |
|  | Stredni Morava | CZ 07 | 1 | 75 |
|  | Moravskoslezsko | CZ 08 | 1 | 75 |
| Germany | Baden-Württemberg | DE 11-14 | 2 | 50 |
|  | Bayern | DE 21-27 | 2 | 50 |
|  | Berlin | DE 30 | 2 | 50 |
|  | Brandenburg | DE 41-42 | 1 | 75 |
|  | Mecklenburg-Vorpommern | DE 80 | 1 | 75 |
|  | Sachsen | DED 1-3 | 1 | 75 |
|  | Sachsen-Anhalt | DEE 1-3 | 1 | 75 |
|  | Thüringen | DEG 0 | 1 | 75 |
| Greece | Anatoliki Makedonia, Thraki | GR 11 | 1 | 75 |
|  | Kentriki Makedonia | GR 12 | 1 | 75 |
|  | Dytiki Makedonia | GR 13 | 1 | 75 |
|  | Thessalia | GR 14 | 1 | 75 |
|  | Ipeiros | GR 21 | 1 | 75 |
|  | Ionia Nisia | GR 22 | 1 | 75 |
|  | Dytiki Ellada | GR 23 | 1 | 75 |
|  | Sterea Ellada | GR 24 | 1 | 75 |
|  | Peloponnisos | GR 25 | 1 | 75 |
|  | Attiki | GR 30 | 1 | 75 |
|  | Voreio Aigaio | GR 41 | 1 | 75 |
|  | Notio Aigaio | GR 42 | 1 | 75 |
|  | Kriti | GR 43 | 1 | 75 |
| Hungary | Közép-Magyarország | HU 10 | 1 | 75 |
|  | Közép-Dunántúl | HU 21 | 1 | 75 |
|  | Nyugat-Dunántúl | HU 22 | 1 | 75 |
|  | Del-Dunántúl | HU 23 | 1 | 75 |
|  | Észak-Magyarország | HU 31 | 1 | 75 |
|  | Észak-Alföld | HU 32 | 1 | 75 |
|  | Dél-Alföld | HU 33 | 1 | 75 |
| Italy | Lombardia | ITC 4 | 2 | 50 |
|  | Trentino-Alto Adige | ITD 2 | 2 | 50 |
|  | Veneto | ITD 3 | 2 | 50 |
|  | Friuli-Venezia Giulia | ITD 4 | 2 | 50 |
|  | Emilia-Romagna | ITD 5 | 2 | 50 |
|  | Umbria | ITE 2 | 2 | 50 |
|  | Marche | ITE 3 | 2 | 50 |
|  | Abruzzo | ITF 1 | 2 | 50 |
|  | Molise | ITF 2 | 1 | 50 |
|  | Puglia | ITF 4 | 1 | 50 |
|  | Basilicata | ITF 5 | 1 | 50 |
| Poland | Lodzkie | PL 11 | 1 | 75 |
|  | Mazowieckie | PL 12 | 1 | 75 |
|  | Malopolskie | PL 21 | 1 | 75 |
|  | Slaskie | PL 22 | 1 | 75 |
|  | Lubelskie | PL 31 | 1 | 75 |
|  | Podkarpackie | PL 32 | 1 | 75 |
|  | Swietokrzyskie | PL 33 | 1 | 75 |
|  | Podlaskie | PL 34 | 1 | 75 |
|  | Wielkopolskie | PL 41 | 1 | 75 |
|  | Zachodniopomorskie | PL 42 | 1 | 75 |
|  | Lubuskie | PL 43 | 1 | 75 |
|  | Dolnoslaskie | PL 51 | 1 | 75 |
|  | Opolskie | PL 52 | 1 | 75 |
|  | Kujawsko-Pomorskie | PL 61 | 1 | 75 |
|  | Warminsko-Mazurskie | PL 62 | 1 | 75 |
|  | Pomorskie | PL 63 | 1 | 75 |
| Slovakia | Bratislavsky | Sk 01 | 2 | 50 |
|  | Zapadne Slovensko | SK 02 | 1 | 75 |
|  | Stredne Slovensko | SK 03 | 1 | 75 |
|  | Vychodne Slovensko | SK 04 | 1 | 75 |
| Slovenia | Slovenija | SI 00 | 1 | 75 |

## Non-EU-Member States

| Country | Regions | EU funding source | Maximum eligible EU funding rate (%) |
| --- | --- | --- | --- |
| Albania | The whole country | CARDS | 90 |
| Bosnia Herzegovina | The whole country | CARDS | 90 |
| Bulgaria | The whole country | PHARE | 75 |
| Croatia | The whole country | CARDS/ PHARE** | 90 |
| Former Yugoslav Republic of Macedonia | The whole country | CARDS | 90 |
| Republic of Moldova | The whole country | TACIS | 50000 -300000 90% < 300000 75% |
| Romania | The whole country | PHARE | 75 |
| State Union of Serbia and Montenegro | The whole country | CARDS | 90 |
| Ukraine | Chernivetska oblast | TACIS | 50000 -300000 90% < 300000 75% |
|  | Ivano-Frankivska oblast |  |  |
|  | Lvivska oblast |  |  |
|  | Odesska oblast |  |  |
|  | Volynska oblast |  |  |
|  | Zakarpatska oblast |  |  |

** Croatia is eligible for EU co-financing from CARDS for budget year 2004 and from PHARE for budget year 2005 on.

# CHECKLIST

- The Lead Partner has ensured that the complete hardcopy version of the application to be submitted arrives at the premises of the JTS in Dresden no later than 07 November 2005 18:00 hours CET.

- The Lead Partner has ensured that an electronic version of the filled in Application Form (Word and Excel part) arrives by e-mail at cadses@jts.dresden.de no later than 07 November 2005. 24:00 hours CET.

- The hardcopy version is submitted in one single sealed package / envelope that contains only one application.

- The package/envelope is labelled with the reference “INTERREG III B CADSES Neighbourhood Programme – Submission of a Project Proposal under the 4th Call”, the acronym of the project, the Lead Partner and the priority/measure referring to.

- The e-mail submission is labelled with the reference “INTERREG III B CADSES Neighbourhood Programme – Submission of a Project Proposal under the 4th Call”; the acronym of the project; with the name of the Lead Partner; and with the priority/measure referring to.

- The package/envelope contains the entire application (filled in Application Form, all annexes) in original.

- All financing partners (also for those from non-Member States) have submitted Co-financing Statements as provided in the Application Package.

- All non-financing partners (also for those from non-Member States) have submitted the relevant “Letter of Intent” as provided in the Application Package.

- The figures stated in the submitted Co-financing Statements correspond with each partner’s national co-financing (i.e. total contribution minus requested ERDF), as stated in the financial tables.

- The standard form of the Co-financing Statement for the 4th Call as presented on http://www.cadses.net as part of the Application Package has been used and no amendments or changes to the text have been made.

- All non-Member State partners have submitted two pieces of each of their statutes or articles of associations in the form of originals or photocopies certified as true by an authorised independent body.

- Each non-Member State partner applying for funding have submitted two certified copies of their latest set of accounts

- All partners participating in the project are listed in chapter 2 of the Application Form.

- All partners are listed in chapter 2 of the Application Form with their institutions’ name in English language.

- The Lead Partner and, where relevant, the Financial Lead Partner(s) for external funding have stamped, signed and dated the application.

- Each Financial Lead Partner for external funding has submitted their originally signed and stamped financial identification sheet

- The Application Form is filled in completely in English language.

# Additional ANNEXES RElated to EXTERNAL FUNDING

For the external funding the relevant contracting authority will prepare a contract to be signed with the financial lead partner for external funding on the basis of a standard contract model as outlined in the annexes to the Practical Guide.  It is advised that applicants for whom this is relevant carefully read this documentation.  These standard annexes can be found at the following website: http://europa.eu.int/comm/europeaid/tender/gestion/cont_typ/st/index_en.htm

- the draft grant contract, including the Special Conditions: to be completed for each contract, they comprise the amount of the contract, the duration of the action, the payment plan, the addresses of the parties, etc....

The annexes:

- Description of the action (annex I) to be drawn from this Application Form

- General Conditions (annex II)

- Budget for the Action (annex III) – see table 16.7 of the CADSES Application Form

- Contract-award procedures (annex IV)

- Standard request for payment

- Financial identification form (annex V) – see table 17 of the CADSES Application Form

- Specimen audit certificate (annex VI)

- Specimen financial guarantee (annex VII)

# Footnotes

Known as "Steering Committee" under INTERREG programmes, the name has been changed to "Selection Committee" to underline the change to the Neighbourhood Programme approach.

It is recommended that projects be completed before the deadline above, leaving reasonable time for the submission of the final payment claim and the final report. These documents must be delivered within this deadline.

Please contact the relevant national CADSES Contact Point to receive further information concerning these eligibility dates.

according to the Council Directive 92/50/EEC of 18 June 1992 relating to the coordination of procedures for the award of public service contracts” (Official Journal L 209, 24/07/1992 P.0001 – 00024)

Please see chapter B4 for the eligibility dates for Project Partners from EU member states.

Due to the different contracting authorities which will be used for the external funding, information on Ukraine and Moldova should be given jointly, while information for Serbia, Kosovo and Montenegro should be given separately.  This applies each time the phrase “detailed by country” is indicated.

Wideman Comparative Glossary of Common Project Management Terms v2.1 is copyright by R. Max Wideman, May, 2001

NUTS means “Nomenclature of territorial units for statistics”. It is the classification by codes of EU territories.

Non-EU Project Partners use different budget lines specified in tables 16.8; breakdown alongside CADSES Budget Lines is therefore relevant only for EU Project Partners.

Also expeditures of non-EU Project Partners are included in this table, nonetheless, due to different budget lines for external funds the breakdown alongside Budget Lines is relevant only for EU PPs. For non-EU Project Partners the totals per Partner and Action are inserted in the Budget Line 1 “Coordination”.