Report on implementation

Integrated Operational Programme

for the period

1 Oct 2011 – 31 Mar 2012

Intended for the 9th meeting of the IOP Monitoring Committee

held on 31 May 2012

CONTENTS

INTRODUCTION	7

1 PROGRAMME IDENTIFICATION	8

2 OVERVIEW OF PROGRAMME IMPLEMENTATION	10

2.1 Summary Tables on Progress Achieved in IOP Implementation	10

2.2 Progress in the Fulfilment of Indicators at the Programme Level	17

2.3 Core Activities in the Period from 1 Oct 2011 to 31 Mar 2012	17

2.3.1 IOP milestones in the period from 1 Oct 2011 to 31 Mar 2012	17

2.3.2 Overview of ongoing and newly announced calls in the period from 1 Oct 2011 to 31 Mar 2012	18

2.3.3 Changes in the IOP underlying documents and amendments thereto	19

2.4 Main Problems Encountered in Programme Implementation and Measures Taken to Overcome Them	22

2.5 Measures Adopted in Response to the Conclusions of the Previous Monitoring Committee Meeting	25

2.6 Analysis of Risks in Relation to the Fulfilment of n+3/n+2 Rule	27

2.6.1  Analysis of risks in relation to the fulfilment of n+3 rule by the Managing Authority and Intermediate Bodies	31

2.6.2 Forecast of the progress in IOP absorption (in EUR)	43

2.7 Analysis of Risks in Relation to Future Progress in Programme Implementation	50

2.8 Foreseen Timetable of the Announcement of Calls	53

2.9 Overview of approved projects	55

2.10 Implementation of the Major Project	58

3 PROGRESS AT THE LEVEL OF PRIORITY AXIS	59

3.1 Priority axis 1a, 1b – Modernisation of public administration	59

3.1.1 Focus of priority axes/intervention areas	59

3.1.2 Progress achieved in the implementation of priority axes/intervention areas	60

3.1.3 Fulfilment of indicators	62

3.1.4 Problems and measures taken	63

3.1.5 Example of a project	65

3.2 Priority axis 2 – Introducing ICT in territorial public administration	66

3.2.1 Focus of priority axes/intervention areas	66

3.2.2 Progress achieved in implementation of priority axes/intervention areas	67

Overview of ongoing calls	69

3.2.3 Fulfilment of indicators	69

3.2.4 Problems and measures taken	71

3.2.5 Example of a project	71

3.3 Priority axis 3 – Improving public services quality and accessibility	72

3.3.1 Focus of priority axes/intervention areas	72

3.3.2 Progress achieved in implementation of priority axes/intervention areas	73

3.3.3 Fulfilment of indicators	78

3.3.4 Problems and measures taken	83

3.3.5 Example of project	87

3.4 Priority axis 4a, 4b – National support of tourism	91

3.4.1 Focus of priority axes/intervention areas	91

3.4.2 Progress achieved in implementation of priority axes/intervention areas	93

3.4.3 Fulfilment of indicators	94

3.4.4 Problems and measures taken	97

3.4.5 Example of a project	97

3.5 Priority axis 5 – National support of territorial development	99

3.5.1 Focus of priority axes/intervention areas	99

3.5.2 Progress achieved in implementation of priority axes/intervention areas	100

3.5.3 Fulfilment of indicators	106

3.5.4 Problems and measures taken	110

3.5.5 Example of a project	112

3.6 Priority axis 6a, 6b – Technical assistance	116

3.6.1 Focus of priority axes/intervention areas	116

3.6.2 Progress achieved in implementation of priority axes/intervention areas	117

3.6.3 Fulfilment of indicators	120

3.6.4 Problems and measures taken	122

4 ADMINISTRATION OF THE PROGRAMME	122

4.1 Information on the Conduct and Results of Audits and Financial Controls	122

4.2 Implementation of the Communication Plan and Activities in the Field of Publicity	133

4.3 Conducted Evaluations and Studies	135

4.3.1 Evaluation carried out by the Managing Authority	135

4.3.2 Evaluation and studies carried out by the Intermediate Bodies	136

4.4 Other Activities of the Managing Authority and the Monitoring Committee	136

4.4.1 Activities of the Managing Authority	136

4.4.2 Activities of the Monitoring Committee	139

4.4.3 Activities of Working Groups	139

4.5 Administrative Capacity of Implementation Structure Entities of the Programme	142

5 MAIN CONCLUSIONS	147

LIST OF ABBREVIATIONS	149

ANNEXES	150

Annex No 1 – Publicity Activities in the period from 1 Oct 2011 to 31 Mar 2012	151

Annex No 2 – Action Plans	160

# INTRODUCTION

The Integrated Operational Programme is implemented in the 2007-2013 programming period. The programme focuses on addressing common regional issues in the field of infrastructure for public administration, public services and territorial development: development of information technologies in public administration, improving the infrastructure for social services, public health, employment services and services in the field of security, risk prevention and management, support of tourism, cultural heritage, improving the environment in housing estates and development of systems for creation of territorial policies.

The total IOP allocation amounts to  EUR 1 861.6 million, major part of which in the amount of EUR 1 827.0 million is channelled to the Convergence objective, while EUR 34.5 million goes to the Regional Competitiveness and Employment objective.

Details concerning the progress and implementation of the IOP in the period from 1 Oct 2011 to 31 Mar 2012 are presented in this Report on Implementation intended for the 9th meeting of the IOP Monitoring Committee, compiled by the IOP Managing Authority in cooperation with other actors involved in the programme.

# 1 PROGRAMME IDENTIFICATION

The Integrated Operational Programme is implemented in the Czech Republic based on the National Strategic Reference Framework 2007-2013 programming period.

The IOP opted for the strategy of assistance at national level with all-national impact on improving the quality of life of inhabitants and enhancing attractiveness of the CR for investors as a result of better effectiveness and accessibility of public administration and public services. Due to the systemic concept of the assistance, it is necessary for the selected areas to be targeted at the whole territory of the CR, the City of Prague inclusive. Therefore, the IOP is designed as a multi-objective programme – in line with Article 32 para 1 of the General Regulation and on the basis of discussions with the EC,  apart from the main focus of assistance on the support to regions under the Convergence objective, it also facilitates the support granted under the Regional competitiveness and employment objective (RCE).

Table No 1 – Allocation by year and objective (in EUR)

| Year | ERDF Convergence objective | ERDF RCE objective | Total |
| --- | --- | --- | --- |
| 2007 | 192 686 939 | 3 951 894 | 196 638 833 |
| 2008 | 202 164 946 | 4 030 931 | 206 195 877 |
| 2009 | 211 684 389 | 4 111 551 | 215 795 940 |
| 2010 | 221 648 970 | 4 193 781 | 225 842 751 |
| 2011 | 237 465 225 | 4 277 657 | 241 742 882 |
| 2012 | 247 398 119 | 4 363 210 | 251 761 329 |
| 2013 | 278 308 099 | 4 450 474 | 282 758 573 |
| Total for 2007 - 2013 | 1 591 359 687 | 29 379 498 | 1 620 736 185 |

Source: Programming Document, December 2011

In accordance with Government Resolution No 175/2006 the Ministry for Regional Development was designated to act as the IOP Managing Authority. The MA fulfils its tasks in line with Article 60 of Council Regulation (EC) No 1083/2006. Pursuant to Article 59 para 2, or Article 42 para 1 of Council Regulation (EC) No 1083/2006 the MA delegates some of the tasks to the Intermediate Bodies.

Due to insufficient administrative capacity, i.e. understaffing of the MoLSA and MoI, the MRD in 2009 concluded with the MoLSA and MoI the Addendum No 1 to the Agreement on delegating the tasks of the IOP Managing Authority. The Addenda concerned the involvement of CRD in the administration of projects under Intervention areas 2.1, 3.1, 3.3 and 3.4.

Powers with respect to the individual IOP intervention areas are given in the table below.

Table No 2 - IOP Intermediate Bodies broken down by intervention area

| Intervention area | Intermediate Body |
| --- | --- |
| 1.1 a, b Developing information society in public administration | Ministry of Interior CR (SF Department) |
| 2.1 Introducing ICT in territorial public administration | Ministry of Interior CR (SF Department), Centre for Regional Development CR |
| 3.1 Social integration services | Ministry of Labour and Social Affairs CR (EU Funds Implementation Department and Programme Financing Department), Centre for Regional Development CR |
| 3.2 Public health services | Ministry of Health CR (EU Funds Department) |
| 3.3 Employment services | Ministry of Labour and Social Affairs CR (EU Funds Implementation Department and Programme Financing Department), Centre for Regional Development CR |
| 3.4 Services in security, risk prevention and management | Ministry of Interior CR (SF Department), Centre for Regional Development CR |
| 4.1 a, b National support of tourism | Centre for Regional Development CR |
| 5.1 National support for utilising the cultural heritage potential | Ministry of Culture (Strategy and Aid Policy Department) |
| 5.2 Improving the environment in problematic housing estates | Centre for Regional Development CR |
| 5.3 Modernisation and development of systems for creating territorial policies | Centre for Regional Development CR |
| 6.1 a, b Activities connected with the IOP management and 6.2 a, b Other costs of the IOP technical assistance | Centre for Regional Development CR |

# 2 OVERVIEW OF PROGRAMME IMPLEMENTATION

## 2.1 Summary Tables on Progress Achieved in IOP Implementation

In line with the NCA guidelines for the elaboration of the Report on implementation the Submitted project applications column includes all the applications registered in IS Monit7+ as of 31 Mar 2012, namely also those that were rejected and will not be implemented. Projects with issued Decision/signed Contract column represents the amount of all the projects for which the Decision on providing a grant or the Statement of expenditure were issued and it also covers the projects prematurely terminated following the issuance of the Decision, Statement of expenditure or the Letter of the Minister (upon request of the beneficiary or upon the decision of the MA/IB).

Approved projects in this report shall mean the projects with the issued Decision/Statement of expenditure/Letter of the Minister (stated in the relevant tables). Monitored period shall mean the period from 1 Oct 2011 to 31 Mar 2012, i.e. the period covered by this report.

Table No 3- Status of IOP absorption cumulatively as of 31 Mar 2012 (in million CZK/EUR)

| PA/IA | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified funds submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| 1 | 9 737,87 | 393,52 | 79 | 11 570,01 | 119% | 466,95 | 60 | 9 163,36 | 94% | 369,82 | 1 998,60 | 21% | 80,66 | 1 522,02 | 16% | 62,14 | 942,19 | 10% | 38,54 |
| 1.1a | 9 042,31 | 365,41 | 79 | 10 743,58 | 119% | 433,59 | 60 | 8 508,84 | 94% | 343,40 | 1 855,84 | 21% | 74,90 | 1 413,30 | 16% | 57,70 | 874,89 | 10% | 35,79 |
| 1.1b | 695,56 | 28,11 | 0 | 826,43 | 119% | 33,35 | 0 | 654,53 | 94% | 26,42 | 142,75 | 21% | 5,76 | 108,72 | 16% | 4,44 | 67,30 | 10% | 2,75 |
| 2 | 4 981,58 | 200,98 | 5 839 | 5 465,67 | 110% | 220,59 | 5 540 | 4 643,35 | 93% | 187,40 | 554,05 | 11% | 22,36 | 386,53 | 8% | 15,46 | 265,54 | 5% | 10,65 |
| 2.1 | 4 981,58 | 200,98 | 5 839 | 5 465,67 | 110% | 220,59 | 5 540 | 4 643,35 | 93% | 187,40 | 554,05 | 11% | 22,36 | 386,53 | 8% | 15,46 | 265,54 | 5% | 10,65 |
| 3 | 15 943,68 | 641,30 | 548 | 17 023,96 | 107% | 687,06 | 255 | 10 839,45 | 68% | 437,46 | 3 892,91 | 24% | 157,11 | 3 711,49 | 23% | 146,90 | 2 779,64 | 17% | 110,02 |
| 3.1 | 2 308,32 | 93,18 | 257 | 1 945,62 | 84% | 78,52 | 31 | 329,98 | 14% | 13,32 | 38,88 | 2% | 1,57 | 41,30 | 2% | 1,67 | 30,85 | 1% | 1,27 |
| 3.2 | 7 291,42 | 292,33 | 164 | 7 886,40 | 108% | 318,28 | 139 | 6 563,70 | 90% | 264,90 | 3 232,34 | 44% | 130,45 | 3 048,49 | 42% | 120,51 | 2 573,23 | 35% | 101,91 |
| 3.3 | 1 357,87 | 54,81 | 19 | 1 444,76 | 106% | 58,31 | 8 | 611,46 | 45% | 24,68 | 9,53 | 1% | 0,38 | 9,53 | 1% | 0,40 | 9,53 | 1% | 0,40 |
| 3.4 | 4 986,07 | 200,98 | 108 | 5 747,18 | 115% | 231,95 | 77 | 3 334,31 | 67% | 134,57 | 612,16 | 12% | 24,71 | 612,16 | 12% | 24,32 | 166,03 | 3% | 6,45 |
| 4 | 1 900,28 | 76,74 | 148 | 3 478,73 | 183% | 140,40 | 46 | 808,32 | 43% | 32,62 | 205,79 | 11% | 8,31 | 201,87 | 11% | 8,20 | 177,38 | 9% | 7,20 |
| 4.1a | 1 764,55 | 71,26 | 74 | 3 230,27 | 183% | 130,37 | 23 | 750,58 | 43% | 30,29 | 191,09 | 11% | 7,71 | 187,44 | 11% | 7,61 | 164,70 | 9% | 6,69 |
| 4.1b | 135,73 | 5,48 | 74 | 248,45 | 183% | 10,03 | 23 | 57,74 | 43% | 2,33 | 14,70 | 11% | 0,59 | 14,43 | 11% | 0,59 | 12,68 | 9% | 0,51 |
| 5 | 13 381,18 | 540,25 | 1 525 | 20 260,13 | 151% | 817,67 | 1 339 | 9 451,35 | 71% | 381,44 | 3 325,38 | 25% | 134,21 | 2 928,78 | 22% | 117,73 | 1 991,20 | 15% | 80,57 |
| 5.1 | 6 707,95 | 270,95 | 51 | 15 815,05 | 236% | 638,27 | 18 | 5 842,81 | 87% | 235,81 | 1 013,28 | 15% | 40,89 | 894,06 | 13% | 36,01 | 510,78 | 8% | 20,84 |
| 5.2 | 6 207,49 | 251,03 | 895 | 3 943,46 | 64% | 159,15 | 803 | 3 169,46 | 51% | 127,91 | 1 931,36 | 31% | 77,95 | 1 669,98 | 27% | 67,54 | 1 152,69 | 19% | 47,03 |
| 5.3 | 465,75 | 18,27 | 579 | 501,63 | 108% | 20,24 | 518 | 439,08 | 94% | 17,72 | 380,75 | 82% | 15,37 | 364,74 | 78% | 14,18 | 327,73 | 70% | 12,70 |
| 6 | 1 339,43 | 53,96 | 82 | 1 393,25 | 104% | 56,23 | 79 | 1 319,79 | 99% | 53,26 | 388,27 | 29% | 15,67 | 367,47 | 27% | 14,72 | 348,96 | 26% | 13,99 |
| 6.1a | 793,88 | 31,97 | 31 | 998,79 | 126% | 40,31 | 31 | 966,49 | 122% | 39,01 | 308,61 | 39% | 12,45 | 292,28 | 37% | 11,71 | 274,96 | 35% | 11,03 |
| 6.2a | 521,37 | 21,01 | 51 | 369,31 | 71% | 14,90 | 48 | 329,47 | 63% | 13,30 | 72,65 | 14% | 2,93 | 68,55 | 13% | 2,74 | 67,69 | 13% | 2,70 |
| 6a | 1 315,25 | 52,98 | 82 | 1 368,09 | 104% | 55,21 | 79 | 1 295,96 | 99% | 52,30 | 381,26 | 29% | 15,39 | 360,83 | 27% | 14,45 | 342,65 | 26% | 13,73 |
| 6.1b | 14,59 | 0,59 | 0 | 18,36 | 126% | 0,74 | 0 | 17,77 | 122% | 0,72 | 5,68 | 39% | 0,23 | 5,38 | 37% | 0,22 | 5,06 | 35% | 0,20 |
| 6.2b | 9,59 | 0,39 | 0 | 6,79 | 71% | 0,27 | 0 | 6,06 | 63% | 0,24 | 1,34 | 14% | 0,05 | 1,26 | 13% | 0,05 | 1,25 | 13% | 0,05 |
| 6b | 24,18 | 0,97 | 0 | 25,15 | 104% | 1,02 | 0 | 23,83 | 99% | 0,96 | 7,01 | 29% | 0,28 | 6,64 | 27% | 0,27 | 6,30 | 26% | 0,25 |
| Total | 47 284,03 | 1 906,75 | 8 221 | 59 191,75 | 125% | 2 388,88 | 7 319 | 36 225,62 | 77% | 1 462,01 | 10 365,00 | 22% | 418,31 | 9 118,16 | 19% | 365,14 | 6 504,89 | 14% | 260,97 |

Source: MSC2007 as of 4 Apr 2012; CZK/EUR exchange rate (for conversion of columns a) – d): 24.778; for conversion of columns e) – f) the exchange rate valid at the time of entry into IS VIOLA is used

Source of funding – public funds total

Cumulatively as of 31 Mar 2012, a total of 8 221 project applications were submitted in IOP in the amount of EUR 2 388.88 million, which represents 125 % of the total allocation for the programme. The volume of allocation to the given intervention areas was highly exceeded by project applications submitted under Intervention area 5.1 (236 % of the allocation), 4.1a and 4.1b (183 %), 6.1a and 6.1b (126 %), 1.1a and 1.1b (119 %), 2.1 (110 %), 3.4 (115 %), 5.3 and 3.2 (108 %) and 3.3 
(106 %). The lowest share of funds required by the submitted project applications in the total allocation is, on the contrary, shown by Intervention areas 5.2 (64 % of the allocation), 6.2a and 6.2b (71 % of the allocation) and 3.1 (84 %).

Of all the submitted project applications a total of 7 319 project applications in the amount of EUR 1 462.01 million were approved, which represents 77 % of the total allocation. The highest share of approved projects, equalling 122 % of the allocation (EUR 39.73 million) is reported by Intervention areas 6.1a and 6.1b, where the share of approved projects in the allocation minus the projects withdrawn from implementation is 91 % (EUR 29.82 million). A high share of approved projects as against the allocation (90 – 94 %) is also exhibited by Intervention areas 1.1a and 1.1b (94 % equalling EUR 369.82 million), 2.1 (93 % equalling EUR 187.40 million), 3.2 (90 % of the allocation equalling EUR 264.90 million) and 5.3 (94 % of the allocation totalling EUR 17.72 million). The lowest share of approved funds is registered in Intervention area 3.1 (14 % of the allocation representing EUR13.32 million).

The beneficiaries were paid funds amounting to EUR 418.31 million, representing 22 % of the total allocation. The largest share of funds paid to beneficiaries is in Intervention area 5.3, where the beneficiaries were reimbursed 82 % of the allocation for this Intervention area (EUR 15.37 million), while the largest volume of funds was reimbursed  in Intervention area 3.2 (EUR 130.45 million accounting for 44 % of the allocation). Only 1 % of the allocation was paid out in Intervention area 3.3 (EUR 0.38 million) and 2 % of the allocation were paid out in Intervention area 3.1 (EUR 1.57 million).

The aggregate payment claims (applications for payment) accounted for by the PCA totalled EUR 365.14 million, which represents 19 % of the total allocation. The same trend as in the reimbursed funds is seen also in funds included in aggregate payment claims accounted for by the PCA, with the largest share reported in Intervention area 5.3 (78 % of the allocation, i.e. EUR 14.18 million) and the largest volume of funds reported by Intervention area 3.2 (EUR 120.51 million, which accounts for 42 % of the allocation for this intervention area). The aggregate payment claims covered funds of all intervention areas, with the lowest volume of funds (1 % of the allocation) in Intervention area 3.3 (EUR 0.40 million) and 2 % in Intervention area 3.1 (EUR 1.67 million).

The certified expenditure reached the total amount of EUR 260.97 million (14 % of the allocation), it covers funds from all the intervention areas. The largest share of certified funds submitted to the EC was reached by Intervention area 5.3 (EUR 12.70 million representing 70 % of the allocation), 3.2 (EUR 101.91 million and 35 % of the allocation) and 6.1a and 6.1b (35 % of the allocation representing EUR 11.23 million).

Table No 4 - Progress achieved in IOP absorption in the period from 1 Oct 2011 to 31 Mar 2012 (in million CZK/EUR)

| PA/IA | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| 1 | 9 737,87 | 393,52 | 0 | 0,00 | 0% | 0,00 | 0 | -16,14 | 0% | -0,65 | 568,60 | 6% | 22,95 | 579,83 | 6% | 23,78 | 536,99 | 6% | 22,26 |
| 1.1a | 9 042,31 | 365,41 | 0 | 0,00 | 0% | 0,00 | 0 | -14,98 | 0% | -0,60 | 527,99 | 6% | 21,31 | 538,42 | 6% | 22,08 | 498,63 | 6% | 20,67 |
| 1.1b | 695,56 | 28,11 | 0 | 0,00 | 0% | 0,00 | 0 | -1,15 | 0% | -0,05 | 40,61 | 6% | 1,64 | 41,42 | 6% | 1,70 | 38,36 | 6% | 1,59 |
| 2 | 4 981,58 | 200,98 | 0 | 0,00 | 0% | 0,00 | 1 | 21,31 | 0% | 0,86 | 139,19 | 3% | 5,62 | 120,99 | 2% | 4,65 | 98,95 | 2% | 4,09 |
| 2.1 | 4 981,58 | 200,98 | 0 | 0,00 | 0% | 0,00 | 1 | 21,31 | 0% | 0,86 | 139,19 | 3% | 5,62 | 120,99 | 2% | 4,65 | 98,95 | 2% | 4,09 |
| 3 | 15 943,68 | 641,30 | 103 | 1 985,09 | 12% | 80,12 | 82 | 2 798,67 | 18% | 112,95 | 607,59 | 4% | 24,52 | 505,23 | 3% | 16,37 | 330,80 | 2% | 13,66 |
| 3.1 | 2 308,32 | 93,18 | 71 | 661,51 | 29% | 26,70 | 12 | 247,74 | 11% | 10,00 | 9,35 | 0% | 0,38 | 10,59 | 0% | 0,42 | 24,22 | 1% | 1,00 |
| 3.2 | 7 291,42 | 292,33 | 0 | 0,00 | 0% | 0,00 | 31 | 1 022,51 | 14% | 41,27 | 502,83 | 7% | 20,29 | 399,23 | 5% | 12,65 | 255,27 | 4% | 10,54 |
| 3.3 | 1 357,87 | 54,81 | 4 | 323,58 | 24% | 13,06 | 6 | 525,72 | 39% | 21,22 | 0,00 | 0% | 0,00 | 0,00 | 0% | 0,01 | 9,53 | 1% | 0,40 |
| 3.4 | 4 986,07 | 200,98 | 28 | 1 000,00 | 20% | 40,36 | 33 | 1 002,70 | 20% | 40,47 | 95,41 | 2% | 3,85 | 95,41 | 2% | 3,29 | 41,78 | 1% | 1,73 |
| 4 | 1 900,28 | 76,74 | 16 | 778,93 | 41% | 31,44 | 2 | -4,96 | 0% | -0,20 | 8,00 | 0% | 0,32 | 24,50 | 1% | 0,98 | 66,57 | 4% | 2,74 |
| 4.1a | 1 764,55 | 71,26 | 8 | 723,29 | 41% | 29,19 | 1 | -4,61 | 0% | -0,19 | 7,43 | 0% | 0,30 | 22,75 | 1% | 0,91 | 61,81 | 4% | 2,54 |
| 4.1b | 135,73 | 5,48 | 8 | 55,64 | 41% | 2,25 | 1 | -0,35 | 0% | -0,01 | 0,57 | 0% | 0,02 | 1,75 | 1% | 0,07 | 4,76 | 4% | 0,20 |
| 5 | 13 381,18 | 540,25 | 94 | 2 316,38 | 17% | 93,49 | 148 | 492,17 | 4% | 19,86 | 1 311,74 | 10% | 52,94 | 935,68 | 7% | 36,58 | 593,52 | 4% | 24,50 |
| 5.1 | 6 707,95 | 270,95 | 9 | 1 789,26 | 27% | 72,21 | 0 | -1,95 | 0% | -0,08 | 505,26 | 8% | 20,39 | 381,38 | 6% | 15,14 | 241,45 | 4% | 9,97 |
| 5.2 | 6 207,49 | 251,03 | 85 | 527,12 | 8% | 21,27 | 145 | 486,30 | 8% | 19,63 | 759,39 | 12% | 30,65 | 517,30 | 8% | 20,61 | 311,39 | 5% | 12,86 |
| 5.3 | 465,75 | 18,27 | 0 | 0,00 | 0% | 0,00 | 3 | 7,82 | 2% | 0,32 | 47,09 | 10% | 1,90 | 37,01 | 8% | 0,83 | 40,68 | 9% | 1,67 |
| 6 | 1 339,43 | 53,96 | 6 | 109,27 | 8% | 4,41 | 16 | 221,55 | 17% | 8,94 | 38,41 | 3% | 1,55 | 18,51 | 1% | 0,51 | 86,03 | 6% | 3,56 |
| 6.1a | 793,88 | 31,97 | 3 | 102,29 | 13% | 4,13 | 8 | 189,26 | 24% | 7,64 | 33,61 | 4% | 1,36 | 17,32 | 2% | 0,52 | 77,41 | 10% | 3,20 |
| 6.2a | 521,37 | 21,01 | 3 | 5,01 | 1% | 0,20 | 8 | 28,29 | 5% | 1,14 | 4,10 | 1% | 0,17 | 0,86 | 0% | -0,02 | 7,07 | 1% | 0,29 |
| 6a | 1 315,25 | 52,98 | 6 | 107,30 | 8% | 4,33 | 16 | 217,55 | 17% | 8,78 | 37,71 | 3% | 1,52 | 18,18 | 1% | 0,50 | 84,47 | 6% | 3,49 |
| 6.1b | 14,59 | 0,59 | 0 | 1,88 | 13% | 0,08 | 0 | 3,48 | 24% | 0,14 | 0,62 | 4% | 0,02 | 0,32 | 2% | 0,01 | 1,42 | 10% | 0,06 |
| 6.2b | 9,59 | 0,39 | 0 | 0,09 | 1% | 0,00 | 0 | 0,52 | 5% | 0,02 | 0,08 | 1% | 0,00 | 0,02 | 0% | 0,00 | 0,13 | 1% | 0,01 |
| 6b | 24,18 | 0,97 | 0 | 1,97 | 8% | 0,08 | 0 | 4,00 | 17% | 0,16 | 0,69 | 3% | 0,03 | 0,33 | 1% | 0,01 | 1,55 | 6% | 0,06 |
| Total | 47 284,03 | 1 906,75 | 219 | 5 189,66 | 11% | 209,45 | 249 | 3 512,60 | 7% | 141,76 | 2 673,53 | 6% | 107,90 | 2 184,75 | 5% | 82,87 | 1 712,86 | 4% | 70,80 |

Source: MSC2007 as of 4 Apr 2012; CZK/EUR exchange rate (for conversion of columns a) – d): 24.778;,for conversion of columns e) – f) the exchange rate valid at the time of entry into IS VIOLA is used

Source of funding – public funds total

In the period from 1 Oct 2011 to 31 Mar 2012, a total of 219 applications in the amount of EUR 209.45 million were submitted, the most notable progress in the volume of submitted project applications was seen in Intervention areas 5.1 (EUR 72.21 million representing 27 % of the allocation), 3.4 (EUR 40.36 million representing 20 % of the allocation), 4.1a and 4.1b (EUR 31.44 million representing 41 % of the allocation), 3.1 (EUR 26.70 million representing 29 % of the allocation), 5.2 (EUR 21.27 million representing 8 % of the allocation) and 3.3 (EUR 13.06 million representing 24 % of the allocation). In this period, no project applications were submitted under Intervention areas 1.1a and 1.1b, 2.1, 3.2 and 5.3.

In the monitored period, 249 projects in the amount of EUR 141.76 million were approved, with the largest volume of funds  approved in Intervention areas 3.2 (EUR 41.27 million representing 14 %), 3.4 (EUR 40.47 million representing 20 %) and 5.2 (EUR 19.63 million representing 8 % of the allocation). The most remarkable progress in terms of the share of approved funds in the total allocation for the intervention area was reported by Intervention area 3.3 (39 % accounting for EUR 21.22 million), 6.1a and 6.1b (24 % accounting for EUR 7.64 million) and 3.4. In the monitored period no projects were approved in Intervention areas 1.1a and 1.1b (where the changes in projects resulted in a drop of the total amount of funds covered by the issued Decisions by EUR 0.65 million) and 5.1 (also in this intervention area the changes in projects led to the decline in the total amount of funds covered by the issued Decisions by EUR 0.08 million). The amount required by the approved projects also decreased in Intervention areas 4.1a and 4.1b, despite the approval of one project in the monitored period.

Beneficiaries were reimbursed funds totalling EUR 107.90 million, which accounts for 6 % of the total allocation. The largest volume of funds was paid out in Intervention areas 5.2 (EUR 30.65 million representing 12 % of the allocation), 1.1a and 1.1b (EUR 22.95 million representing 6 % of the allocation), 5.1 (EUR 20.39 million equalling 8 % of the allocation) and 3.2 (EUR 20.29 million equalling 7 % of the allocation). Apart from Intervention area 5.2, the most remarkable progress achieved as against the allocation was seen in Intervention area 5.3, with 10 % of the allocation representing EUR 1.90 million reimbursed). In the monitored period, no funds were reimbursed in Intervention area 3.3.

In the period from October 2011 to March 2012, the aggregate payment claims covered the amount of EUR 82.87 million representing 5 % of the total allocation. The largest share of funds included in aggregate payment claims is in Intervention areas 5.2 and 5.3 (8 % of the allocation each), 1.1a and 1.1b and 5.1 (6 % each) and 3.2 (5 % of the allocation).

In the monitored period, expenditure amounting to EUR 70.80 million was certified, which accounts for 4 % of the total allocation. The expenditure was certified under all the intervention areas. The largest share of certified expenditure in the allocation was reported by Intervention areas 6.1a and 6.1b (10 % representing EUR 3.26 million), 5.3 (9 % representing EUR 1.67 million), 1.1a and 1.1b (6 % representing 22.26 million).

The progress in IOP absorption in the period from 1 Oct 2011 to 31 Mar 2012 is illustrated by the Chart No 1, with the blue parts of bars indicating the status of absorption as of 30 Sep 2011, the green parts of bars showing the progress in the period from 1 Oct 2011 to 31 Mar 2012 and the total heights of bars representing the cumulative status of absorption as of 31 Mar 2012.

Chart No 1 – Progress in IOP absorption as of 31 Mar 2012

Source: MSC2007 as of 4 Apr 2012;  CZK/EUR exchange rate (for conversion of columns up to the funds paid to beneficiaries): 24.778;  starting from the funds included in aggregate payment claims the exchange rate valid at the time of entry into IS VIOLA was used

Source of funding – public funds total

## 2.2 Progress in the Fulfilment of Indicators at the Programme Level

In line with the NCA guidelines for the elaboration of report on implementation, the chapter shall give only the indicators monitored by the Managing Authority, i.e. not the indicators monitored by external sources such as CSO, Eurostat, etc.

In the IOP at the level of the programme, 3 impact indicators are monitored, the achieved values of which are not generated at the project level and are monitored by the external source.

Due to the referred to facts no indicator is given in this chapter.

## 2.3 Core Activities in the Period from 1 Oct 2011 to 31 Mar 2012

### 2.3.1 IOP milestones in the period from 1 Oct 2011 to 31 Mar 2012

| Date | Name of activity |
| --- | --- |
| 7 Oct 2011 | Submission of the 16th aggregate application for payment (payment claim) to the MoF |
| 9 Oct 2011 | Commencement of the audit of the system of AAE No 28/11 at IOP IB and IOP MA |
| 13 Oct 2011 – 14 Oct 2011 | Annual Conference of IOP in Písek – Integrated Urban Development Plans |
| 21 Oct 2011 | Submission of the 17th aggregate application for payment to the MoF |
| 21 Oct 2011 | Submission of the 18th aggregate application for payment to the MoF |
| 21 Oct 2011 | Submission of the 19th aggregate application for payment to the MoF |
| 24 Oct 2011 | Announcement of the 3rd call of MoC for Intervention area 5.1, activity b) |
| 31 Oct 2011 | Bilateral meeting between IOP MA and Intermediate Bodies of MoC and MoLSA on the current situation in their intervention areas |
| 4 Nov 2011 | Submission of the 20th aggregate application for payment to the MoF |
| 7 Nov 2011 | 7th interim application for payment was sent to the EC |
| 22 Nov 2011 | 1st Final conference and opening of the National Museum of Photography and Tapestry Workshop – Centre of Indigenous Crafts and Unique Technologies” in Jindřichův Hradec |
| 1 Dec 2011 | Submission of the 21st aggregate application for payment to the MoF |
| 14 Dec 2011 | Announcement of the 13th call of MRD for Intervention area 4.1, activity b) |
| 15 Dec 2011 | Submission of the 22nd aggregate application for payment to the MoF |
| 16 Dec 2011 | Submission of the 23rd aggregate application for payment to the MoF |
| 19 Dec 2011 | The annual opinion of AA was sent to the EC, including the Annual Control Report of IOP for the period from 1 Jul 2010 to 30 Jun 2011 |
| 20 Dec 2011 | 8th interim application for payment was sent to the EC |
| 21 Dec 2011 | Approval of revision of the IOP Programming Document - by Commission Decision C(2011)9790 |
| 30 Dec 2011 | Closing of the call No 03 of the MoC for Intervention area 5.1, activity b) |
| 30 Dec 2011 | Closing of the call No 05 of MoLSA for Intervention area 3.3, activity c) |
| 17 Jan 2012 | Commencement of the control of the Supreme Audit Office at the IOP MA No 12/02 Monetary resources of EU and SB earmarked for the implementation of IOP |
| 20 Jan 2012 | Submission of the 1st aggregate application for payment to the MoF |
| 26 Jan 2012 | Completion of the system audit of AAE No 28/11 |
| 31 Jan 2012 | Change in the 12th continuous call of MRD for Priority axes 4a and 4b National support of tourism – restriction of supported activities and transfer of allocated funds from the cancelled activity b) Introduction and information support of national and international standards in tourism services (including especially certification, manuals, methodologies, systems, controls) to activity e) Support for the promotion of the CR as a tourism destination |
| 31 Jan 2012 | Closing of the call No 13 of MRD for Intervention area 4.1, activity b) |
| 2 Feb 2012 | Announcement of the 13th call of MoI for Intervention area 3.4, activity d) |
| 17 Feb 2012 | EC recommended to the IOP MA to withdraw the 8th interim application for payment submitted on 20 Dec 2012 |
| 20 Feb 2012 | IOP MA applied for the withdrawal of the 8th interim application for payment |
| 27 Feb 2012 | AA received a draft report of DG REGIO audit |
| 28 Feb 2012 | Information of PCA concerning the suspension of the 9th certification of IOP expenditure |
| 1 Mar 2012 | Submission of the 2nd aggregate application for payment to the MoF |
| 7 Mar 2012 | Announcement of the 9th and 10th call of MoH for Intervention area 3.2, activity c) and b) |
| 29 Mar 2012 | Launch of www.kvalitazivota.eu website which provides information on successful projects of IOP |
| 30 Mar 2012 | Meeting with the European Commission concerning the state of play of Smart Administration and of the implementation of intervention areas under the responsibility of MoI CR and MoLSA |

### 2.3.2 Overview of ongoing and newly announced calls in the period from 1 Oct 2011 to 31 Mar 2012

In the period from 1 Oct 2011 to 31 Mar 2012, the project applications were submitted under 14 calls for Intervention areas 3.1, 3.2, 3.3, 3.4, 4.1a and 4.1b, 5.1, 5.2, 6.1a and 6.1b, 6.2a and 6.2b a, of which 5 calls were announced in the monitored period. As at 31 Mar 2012, a total of 1 111 project applications in the amount of EUR 552.0 million were submitted under these calls. Altogether 867 projects in the amount of EUR 286.75 million were approved under these calls.

Detailed information on calls is given under individual priority axes in Chapter 3.

Table No 5 - Overview of ongoing and newly announced calls in the period from 1 Oct 2011 to 31 Mar 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Interven-tion area/activi-ty | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 2. | 01 | 5.6.2008 | 30.9.2015 | continuous | 6.1 a)-e) | 32 337 528 | 31 | 40 309 348 | 31 | 39 005 808 |
|  |  |  |  |  |  | 594 585 |  | 741 162 |  | 717 194 |
|  |  |  |  | Call total | 32 932 113 | 31 | 41 050 510 | 31 | 39 723 002 |
| 14. | 07 | 22.5.2009 |  | continuous | 5.2 a),b),c) | 165 946 629 | 894 | 258 306 814 | 803 | 217 888 947 |
| 23. | 04 | 11.11.2009 | 30.6.2013 | continuous | 3.3 a), b) | 38 794 604 | 11 | 49 584 381 | 7 | 23 624 998 |
| 24. | 05 | 11.11.2009 | 30.12.2011 | continuous | 3.3 c) | 6 780 201 | 8 | 8 723 993 | 1 | 1 052 626 |
| 35. | 10 | 27.9.2010 |  | continuous | 6.2 a)-g) | 12 681 510 | 27 | 4 984 571 | 25 | 4 378 886 |
|  |  |  |  |  |  | 233 173 |  | 91 651 |  | 80 514 |
|  |  |  |  | Call total | 12 914 682 | 27 | 5 076 222 | 25 | 4 459 400 |
| 39. | 06 | 31.5.2011 | 30.6.2013 | continuous | 3.1 b) | 10 510 666 | 13 | 6 426 094 | 0 | 0 |
| 40. | 07 | 7.7.2011 | 30.6.2013 | continuous | 3.1 a) | 32 408 951 | 19 | 16 404 993 | 0 | 0 |
| 41. | 08 | 29.7.2011 | 29.6.2012 | continuous | 3.1 c) | 8 890 292 | 51 | 6 935 668 | 0 | 0 |
| 42. | 12 | 7.9.2011 |  | continuous | 4.1 a),b),c,e) | 36 977 372 | 9 | 39 998 691 | 0 | 0 |
|  |  |  |  |  |  | 2 844 413 | 9 | 3 076 822 | 0 | 0 |
|  |  |  |  | Call total | 39 821 785 | 18 | 43 075 513 | 0 | 0 |
| 43. | 03 | 24.10.2011 | 30.11.2011 | time-limited | 5.1 b) | 26 914 198 | 9 | 72 211 610 |  | 0 |
| 44. | 13 | 14.12.2011 | 31.1.2012 | time-limited | 4.1 b) | 3 592 340 | 1 | 3 587 879 |  | 0 |
|  |  |  |  |  |  | 276 334 | 1 | 275 991 |  | 0 |
|  |  |  |  |  |  | 3 868 674 | 2 | 3 863 870 | 0 | 0 |
| 45. | 13 | 2.2.2012 | 30.4.2012 | continuous | 3.4 d) | 40 358 382 | 28 | 40 358 382 | 0 | 0 |
| 46. | 09 | 7.3.2012 | 17.5.2012 | time-limited | 3.2 c) | 8 677 052 | 0 | 0 | 0 | 0 |
| 47. | 10 | 7.3.2012 | 10.5.2012 | time-limited | 3.2 b) | 8 273 468 | 0 | 0 | 0 | 0 |
| CONV total |  |  |  |  | 416 192 673 | 1 101 | 547 832 426 | 867 | 285 951 265 |
| RCE total |  |  |  |  | 3 948 505 | 10 | 4 185 625 | 0 | 797 707 |
| IOP total |  |  |  |  | 420 141 178 | 1 111 | 552 018 051 | 867 | 286 748 973 |

Source: IS Monit7+ as of 3 Apr 2012

CZK/EUR exchange rate: 24.778

Source of funding – public funds total

### 2.3.3 Changes in the IOP underlying documents and amendments thereto

Changes in the Programming Document

With respect to changes in the Programming Document of IOP, approved at the 7th meeting of IOP MC and submitted to the European Commission through SFC2007 on 28 July 2011, in September 2011 the IOP MA received the following requirements from the European Commission.

- To explain why the funds from the cancelled major project were allocated to Intervention area 3.4, when one of the two conducted evaluations of proposed changes in the IOP PD suggested also other possibilities of reallocations.

- To explain the proposed change in the originally planned project “Introduction of the national information and reservation system“, particularly to explain the added value of the new project called “Introduction of the national information portal and Call centre“ and to justify the unchanged amount of costs of the new project.

- To align the additional allocation to Jessica financial instrument for individual years with the OPTA, from which the additional allocation is transferred, the EC also recommended adequate rounding off of the planned target values of indicators with respect to the concerned changes of IOP PD.

The EC made no comments on the proposed changes of the Programming Document concerning the Intervention areas 5.1, 5.2 and 3.3.

In the course of October the IOP MA compiled the required additional information, modified the IOP Programming Document and sent both the documents to the EC on 25 Oct 2011. On 21 December 2011, the European Commission adopted the Decision C(2011)9790 concerning the approval of these changes in the IOP.

- Reallocation between activities in Intervention area 3.3,

- Cancellation of the major project in 3.4c) and reallocation of funds to 3.4d),

- Modification of the activity in Priority axis 4,

- Increase in the allocation for activity 5.1b) by additional funds granted pursuant to Article 17 of Interinstitutional Agreement,

- Increase in the allocation for Intervention area 5.2 through the reallocation from the Operational Programme Technical Assistance to the implementation of Jessica financial instrument,

- Modification of names, codes and definitions of monitoring indicators in order to ensure their consistency with the National Code list of Indicators.

Methodological Guidelines of IOP MA

Methodological Guideline No 23 Setting the exchange rate reserve in IOP, in force from 14 October 2011.

This methodological guideline was issued as a revision of the Methodological Guideline No 18 of 1 February 2011 in which the MA announced the update of exchange rate reserves based on the programme implementation. The IOP MA determines the exchange rate reserve in dependence on the actual development in individual intervention areas. The basis for the calculation of the exchange rate reserve is the allocation for intervention area, not included in the aggregate applications for payment.

Methodological Guideline No 24 Cancellation of the Implementing Document of the Integrated Operational Programme for 2007-2013, in force from 21 October 2011.

The reason for the cancelation of the Implementing Document was the endeavour to simplify the procedures and to reduce the administrative burden since sufficient and necessary for the certification of expenditure is the compliance with the Programming Document of IOP.

Methodological Guideline No 25 List of substitute projects, in force from 10 November 2011.

The guideline allowed for the use of the institute of substitutes also in the continuous call and laid down the procedure for offering the available funds to applicants included in the list of substitute projects.

Methodological Guideline No 26 Suspension of administration, in force from 16 January 2012.

The guideline was issued in order to lay down a uniform procedure in case of  suspension of project administration, to inform beneficiaries and to enter data into IS MONIT.

Methodological Guideline No 27 Submission of guidance documents in case of SB contribution of more than CZK 200 million to the Ministry of Finance of the CR, with effect from 27 January 2012.

The issuance of this guideline was necessitated by the amendment to Act No 218/2000 Coll., on budgetary rules and on amendments to some related laws (budgetary rules), which changed the amount in Section 13 para 3 letter a) and c) from CZK 100 000 000 to CZK 200 000 000.

Methodological Guideline No 28 Change in criteria for the evaluation of Integrated Urban Development Plans (IUDP), in force from 27 January 2012.

The Monitoring Committee at its 8th meeting approved the change in criteria for final evaluation of IUDP with the view to cut the process shorter and to make it more effective in order to allow for the distribution of additional allocation from OPTA earmarked to the pilot testing of Jessica financial instrument in the form of loans no later than by the end of 2015.

Methodological Guideline No 29 Cancellation of ex-ante risk analysis following the ex-ante check, under preparation, it is expected to come into force in April 2012.

The reason of the cancelation of ex-ante risk analysis following the ex-ante check is the duplicity of activities in case the project is recommended for financing following this check and the 1st interim risk analysis follows during the project implementation. Another reason is to increase the effectiveness of activities in case of a check with negative findings, which is always followed by the public administration check.

Methodological Guideline No 30 Procedure for the payment of bonuses for absorption of allocation by individual Intermediate Bodies, under preparation, it is expected to come into force in 2012.

The reason behind the issuance of the binding procedure is to lay down the procedure for paying bonuses following the absorption of allocation in line with Government Resolution No 818/2007,  Recommended procedures of NCA for reimbursement of bonuses following the absorption of allocation and upon accomplishment of another task of special importance in the system of absorption of EU funds and in line with Procedures providing for the payment of bonuses following the absorption of allocation in line with Government Resolution No 1332/2009.

Methodological Guideline No 31  Monthly report on activities of IB in IOP, under preparation, it is expected to come into force in April 2012.

The guideline will help streamline and update the structure of the monthly monitoring reports of individual IBs in IOP concerning the progress in programme implementation.

Methodological Guideline No 32 for the reduction of thresholds for individual categories of small-scale public contracts, in force from 1 Apr 2012.

The reason of the issuance of this guideline is the coming into effect of Act No 55/2012 Coll., amending Act No 137/2006 Coll., on public contracts, as amended (hereinafter referred to as the “APC“). In accordance with Act No 55/2012 Coll., the threshold will be decreased to below CZK 1.000.000,-  net of VAT in case of small-scale public contracts on supplies and services and to below CZK 3.000.000,- net of VAT in case of small-scale contracts for construction works.

Binding Opinion No 1 concerning the use of terms and conditions of a contract as a partial evaluation criterion, in force from 14 Dec 2011.

The reason for the issuance of this binding opinion was the information of the PCA that the use of the partial evaluation criterion of the amount of contractual penalties is non-compliant with Directive No 18/2004/EC of the European Parliament and of the Council on the coordination of procedures for the award of public works contracts, public supply contracts and public service contracts (hereinafter referred to as the “Directive”), its Article 53 in particular.

## 2.4 Main Problems Encountered in Programme Implementation and Measures Taken to Overcome Them

2.4.1 Reinforced risk management of IOP MA

Change in the administration of Intervention area 2.1

One of the measures adopted by IOP MA with the view to improve and speed up the absorption in intervention areas under the responsibility of MoI CR is a change in delegating the activities under Intervention area 2.1. It consists in a transfer of the remaining administrative activities to IOP MA and CRD.

The purpose of this system change is to improve the quality and to accelerate the administration in Intervention area 2.1 of IOP. By reducing the agenda, the SFD will have capacities available to strengthen the administration and control in Intervention area 1.1 of IOP. This change will also help save expenditure on SFD outsourced activities as well as expenditure incurred in relation to the performance of delegated activities.

The SFD will continue to conduct physical evaluation of projects, approval of projects and substantial changes in projects by Selection Committee, or it shall also cooperate in the announcement of new calls. Agendas related to the Smart Administration Strategy and to the role of aid provider will stay at the MOI CR.

According to the timetable, the transfer of activities under Intervention area 2.1 will take place in the course of April 2012 and at present negotiations are held concerning the transfer of remaining administrative activities under Intervention area 3.4.

Unless improvements are made and absorption is accelerated in Intervention area 1.1 following these measures, it will be necessary to also transfer the administrative activities under this intervention area to IOP MA and CRD.

Information on the status of intervention areas administered by MoLSA

In the monitored period, the number of submitted projects (especially in Intervention area 3.1) increased, but due to a complicated and lengthy process of administration the approval of projects, issuance of decisions and absorption of allocation are not accelerated to a satisfactory degree.

The partial measures adopted by MoLSA are not sufficient yet. The Managing Authority commenced an internal evaluation called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“. The main aim is to identify and evaluate the procedural and systemic barriers to absorption and to propose measures for their removal or the reduction of their impacts. At present, comments are raised on this document and the document should be finalised in the course of April. After that, an action plan for the implementation of short-term and mid-term measures should be drawn up, in which the MoLSA will participate together with the MA and CRD.

Since December 2011, the MoLSA has been providing monthly information to IOP MA on the issuance of legal acts and administration of applications for payment at the level of individual project and has sent a summary forecast absorption by individual intervention area. This reporting serves mainly as a tool to supervise this intermediate body in the course of administration of project applications and applications for payment. The data is also sent to the European Commission.

Opinion of the IOP MA concerning the error rate quantified in the Annual Control Report of IOP for 2011

In the context of the error rate quantified in the Annual Control Report of IOP for 2011 (“ACR“), the MA requested the PCA to suspend/remove the applications for payment affected by suspected irregularities from certification until they are finally settled. The PCA deducted the amount from the statement of expenditure.

The IOP MA disagrees with multiple findings based on which the financial correction was quantified in the ACR and articulates its arguments in its opinion on the ACR. Majority of the findings relate to projects implemented under the first calls of the programme and at the beginning of its implementation. In the following calls the work procedures of IOP MA and IOP IB were gradually modified and specified and measures were taken that are not reflected in the ACR. Despite the error rate quantified in the ACR is stated as anticipated, i.e. it can decrease once the investigation of irregularities is concluded, the IOP MA has adopted multiple other measures, such as:

- In the light of amendment to Act No 137/2006 Coll., on public contracts, the IOP MA and IB amend, supplement and modify the checklists for control of public contracts so that they reflect the valid legislation governing the award of public contracts;

- In the revision of the IOP Operational Manual (IOP OM), the IOP MA shall modify, supplement and specify the checklists for on-the-spot checks, especially  in the field of state aid, it shall also revise other parts of checklists and specify the individual control questions;

- In the revision of IOP OM, it shall modify the procedures and obligations of the IOP IB during the controls of public contracts, and the focal point of control activities in the field of public contracts will be shifted to the stage prior to the conclusion of the contract with supplier;

- IOP MA conducts checks on a sample of contract documents prior to the publication of a contract notice, despite this check is conducted at the first stage by IOP IB;

- IOP MA delegated the conduct of on-the-spot checks pursuant to Article 13 of the Implementing Regulation to IOP IB, nonetheless it also conducts control of physical implementation (or administrative checks) on a sample of projects in risky intervention areas;

- IOP MA increased the number of controls of activities delegated to IOP IB in order to make sure about the legality and correctness of IOP IB procedures, to that end it also implements public procurement procedures to support the performance of controls, by which the control teams of IOP MA will be expanded with no delegation of responsibilities for these controls;

- IOP MA commenced the transfer of administration of Intervention area 2.1 from the Ministry of Interior to the Centre for Regional Development and the IOP MA on the account of problems in the implementation of intervention areas of MoI CR, high error rate in control and administrative activities of this IB, high turnover of staff and a large volume of outsourced activities; IOP MA will monitor the progress in other intervention areas of MoI CR and in case the problems continue to prevail it shall negotiate the transfer of other intervention areas;

- IOP MA in cooperation with an external expert conducts the Analysis of evaluation and control of 3E (economy, effectiveness and efficiency) principles;

- In May 2011, IOP MA set up the Working Group Public Contracts for the transfer of experience and sharing best practice across the implementation structure;

- IOP MA has held training courses for IOP MA and IB staff on problematic or currently addressed areas.

2.4.2. Information on risks identified in IOP implementation for the members of the Government

Based on the Decision of the Minister for Regional Development, on 29 Feb 2012 the Ministry for Regional Development of the CR submitted the  information on risks faced in the implementation of the Integrated Operational Programme to the members of the Government. The aim of this measure was to inform the Government on a long-lasting unsatisfactory situation and risks in intervention areas of IOP under the responsibility of MoI CR, in Intervention area 1.1 in particular.

The information described the current situation and risks faced provided the current status of implementation of IOP intervention areas under the responsibility of MoI CR remains unchanged. Drastic measures are necessary due to the long-lasting extremely unsatisfactory status of implementation. In case radical measures are not taken, the accomplishment of objectives of the whole Integrated Operational Programme is at risk.

Government Resolution No 133/2012 tasks the Minister for Regional Development and the Minister of Interior to promptly start addressing the current situation in IOP.

2.4.5 Problems addressed at the national level

The EC did not reimburse the 8th application for payment under extraordinary interim certification of expenditure for the period from 16 Sep 2011 to 31 Oct 2011 because of investigation of the foreseen high error rate stated in the Annual Control Report of AA for 2010. Therefore, the MA asked the PCA on 20 Feb 2012 to withdraw the application for payment. For this reason, the amount of certified expenditure submitted to the EC was cut by EUR 28 120 764.12 under the Convergence objective and by EUR 1 442 828.55 under the RCE objective.

For the same reason, the MA upon the agreement with the PCA did not submit the supporting documents for the regular 9th certification of expenditure for the period from 1 Nov 2011 to 31 Jan 2012. Once the situation was clarified, the MA would apply for a new extraordinary certification of expenditure which would cover the expenditure ever since 16 Sep 2011.

The EC informed the CR by letter of 20 Mar 2012 that it would not reimburse the interim applications for payment of OPs financed from ERDF and CF due to deficiencies identified in the following five areas:

- Insufficient independence of AAE,

- Insufficient methodological guidance of AAE activities by the Audit Authority,

- Shortcomings in the system of addressing irregularities and funds recovery,

- Insufficient management control of MA and IB especially with respect to public contracts,

- Problems with administrative capacity.

Attached to the letter is the Action Plan for the improvement of management and control system of the Structural Funds in the CR, the EC set the deadline for the implementation of corrective measures at 1 Jul 2012.

The IOP MA will cooperate in the implementation of corrective measures pursuant to the NCA, PCA, and AA instructions. The MA is directly responsible for matters related to management controls, while  corrective measures in other areas are the responsibility of the national authorities.

The implementation of IOP continues, the funds are paid to beneficiaries from national sources, the MA prepares aggregate applications for payment and submits them to the PCA. As of 30 Mar 2012, the  expenditure prepared for certification by the IOP MA equals EUR 305 622 390.38 under the Convergence objective and EUR 4 477 864.26 under the RCE objective.

## 2.5 Measures Adopted in Response to the Conclusions of the Previous Monitoring Committee Meeting

The previous 8th meeting of the IOP Monitoring Committee was held on 24 November 2011. The meeting arrived at a number of conclusions and tasks for the MA and individual IBs.

The IOP Monitoring Committee imposed upon:

IOP Managing Authority

- To incorporate in the wording of the Report on Implementation of IOP as of 30 Sep 2011the comments made during the discussion and sent by the IOP Monitoring Committee members;

Accomplishment: incorporated in the Report on Implementation of IOP as of 30 Sep 2011;

- To inform about the evaluation of activities of working groups set up by the IOP MC at the next meeting of IOP MC and to propose effective solutions;

Accomplishment: MA will inform the IOP MC members at the 9th meeting of IOP MC.

- To include in supporting documents for the next IOP MC meeting detailed tables presenting the progress achieved in the implementation of projects under Priority axis 1;

Accomplishment: MA will include the tables in the supporting documents for the 9th meeting of IOP MC;

- To send the information on the status of preparation of Jessica FI and the updated timetable of its implementation to IOP MC members at a two-months interval; to send the first information as of 16 Jan 2012;

Accomplishment: sent on 16 Jan 2012, 16 Mar 2012;

- To include the information on the accomplishment of tasks from Action Plans from individual evaluations in the future Reports on Implementation of IOP and Annual Reports of IOP;

Accomplishment: included in the Report on Implementation as of 31 Mar 2012 and the Annual Report of IOP for 2011;

- To invite the project holders under Intervention area 4.1, in activities a), b), c) and e) to ensure the involvement of regions and MoC CR in the implementation of projects and preparation of the Tourism Development Policy; to inform the MC members at the next meeting;

Accomplishment: MA will inform the IOP MC members at the 9th meeting of IOP MC;

- To send the final reports from conducted evaluations to MC members;

Accomplishment: in the monitored period no report was compiled, they will be sent to IOP MC members once they are drafted;

- To hand over proposals for the extension of the focus of Strategic Evaluation 2012 to the NCA;

Accomplishment: sent to the NCA on 7 Dec 2011;

- To verify the structure of expenditure spent on outsourced activities at IOP MA and IOP IB and to present this information to the MC at the next meeting;

Accomplishment: MA will inform the IOP MC members at the 9th meeting of IOP MC;

- To inform the MC members on measures taken in order to improve the absorption and management of projects under intervention areas falling under the competence of MoI;

Accomplishment: MA will inform the IOP MC members at the 9th meeting of IOP MC.

Ministry of Interior of the CR

- To submit to IOP MA by 6 Jan 2012 a proposal for addressing the situation in staffing of the MoI CR Intermediate Body with respect to the optimisation of outsourced activities and employment based on agreement on work activities;

Accomplishment: submitted to IOP MA on 6 Jan 2012;

- Through IOP MA to submit to the EC by 6 Jan 2012 an update on institutional structure of the implementation of Smart Administration Strategy and the timetable of measures necessary for full functioning of involved structures;

Accomplishment: the update was sent to the EC (Mr Kuchtík, Mr Pravda) on 6 Jan 2012;

- Through IOP MA to submit to the EC by 15 Dec 2011 summary information on progress achieved in the implementation of projects of basic registers and follow-up IOP and OP HRE projects and risks threatening the launch of basic registers by the deadline set out by the relevant law;

Accomplishment: information was sent to the EC (Mr Kuchtík, Mr Pravda) on 15 Dec 2011;

- To inform the IOP MC members through IOP MA by 6 Jan 2012 on measures taken to address the risks jeopardising the launch of basic registers;

Accomplishment: information was sent to IOP MC members on 10 Jan 2012.

The Managing Authority in cooperation with the Ministry of Labour and Social Affairs in the CR and the Centre for Regional Development of the CR

- To conduct an analysis of delegated activities with the aim to identify redundant and duplicate processes and to propose their changes by 31 Mar 2012;

Accomplishment: information on the accomplishment was sent to the EC (Mr Kuchtík) on 26 Mar 2012. Comments were invited on this report on 30 Mar 2012, the final version will be sent to the EC in mid May 2012, once all the comments are incorporated.

Ministry of Labour and Social Affairs of the CR

- To submit to the IOP MA by 6 Jan 2012 a proposal for addressing the situation in staffing of the MoLSA Intermediate Body with respect to a high number of part-time employment contracts;

Accomplishment: sent to the EC (Mr Kuchtík) on 28 Mar 2012

- To send to the EC the monthly reports on progress in the implementation of individual projects, forecasts and measures taken to improve the situation. The first report was forwarded on 15 Dec 2011;

Accomplishment: reports have been sent to the EC ever since December 2011 always as of the 15th day of the given month.

Ministry of Health of the CR

- To submit to the IOP MA by 5 Dec 2011 an analysis of the medical technology market and to make it available to the public. The MA will hand over the analysis to the EC;

Accomplishment: the analysis was sent to the EC electronically on 31 Jan 2012. It was published on the Ministry of Health CR website on 9 Jan 2012.

Tourism Department of MRD

- Through IOP MA to provide the EC with the information on the state of play of preparations of the Tourism Development Policy after 2014 by 15 Dec 2011;

Accomplishment: information on the state of play of preparations of the policy was sent to the EC (Mr Kuchtík, Mr Pravda) electronically on 15 Dec 2011.

IOP Managing Authority in Cooperation with IOP Intermediate Bodies

- To make a list of tools and processes applied in IOP in relation to 3E rules and an overview of possible ways of their optimisation in the future, to inform the IOP MC members at the next meeting;

Accomplishment: IOP MA in cooperation with the IOP IB will inform the IOP MC members at the 9th meeting of IOP MC.

## 2.6 Analysis of Risks in Relation to the Fulfilment of n+3/n+2 Rule

In order to fulfil the n+3 rule by the end of 2011 – 2013 period, the allocation for 2008 – 2010 shall be certified, while for the fulfilment of n+2 rule by the end of 2013-2015 period the allocation for 2011-2013 period shall be certified, in 2013 both the targets for n+3 and n+2 rule shall be achieved, i.e. the allocation for 2010 and 2011 shall be absorbed. The specific amounts of allocations (“Total EU allocation for 2007-2013 – annual“ column) and targets (“a” column – “n+3/n+2 targets - aggregate“) are given in the two tables below in a breakdown by objective. For meeting the n+3/n+2 targets, the advance payments can be considered (column ”b” in the tables – “Advance payments from EC – annual“), which will reduce the target for the given year.

The target for 2011, that had to be absorbed in order to fulfil the n+3 rule under the Convergence objective by the end of 2011, equals EUR 234.28 million. By the end of 2011, expenditure totalling EUR 247.0 million  was submitted for certification, thus the target was met. Following the withdrawal of the 8th interim application for payment  (see Chapter 2.4.5 Problems addressed at the national level), this amount equals EUR 218.82 million. As of 31 Mar the expenditure prepared by the MA for certification accounts for EUR 51.28 million, if this amount is included the certified expenditure would total EUR 270.10 million.

The fulfilment of n+3/n+2 rule under the Convergence objective is illustrated in detail in the following table, where the first target for the fulfilment of n+3 rule (column ”a” in the table) is binding in 2011. In order to meet the target for 2012, the MA shall submit for certification the expenditure of at least EUR 119.49 million by the end of the year.

Table No 6 – Fulfilment of n+3/n+2 rule (in EUR) under CONV objective

| Financing plan – year | Total EU allocation for 2007-2013 – annual | n+3/n+2 targets - aggregate | EC advance payments – annual | Interim /final applications for payment submitted to the EC – annual | Advance payments from EC + payment claims from the CR – annual | Advance payments from EC + payment claims - aggregate | Difference between the thresholds and payments – aggregate |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | a | B | c | d=b+c | E | f=e-a |
| 2007 | 192 686 939 |  |  |  | 0 | 0 |  |
| 2008 | 202 164 946 |  | 77 650 533 |  | 77 650 533 | 77 650 533 |  |
| 2009 | 211 684 389 |  | 62 120 427 | 5 008 671 | 67 129 098 | 144 779 631 |  |
| 2010 | 221 648 970 | - |  | 80 625 348 | 80 625 348 | 225 404 979 |  |
| 2011 | 237 465 225 | 234 279 436 |  | 133 186 699 | 133 186 699 | 358 591 678 | 124 312 242 |
| As of 31 Mar 2012 | 247 398 119 | 478 078 315 |  |  | 0 | 358 591 678 | -119 486 637 |
| 2013 | 278 308 099 | 1 001 421 489 |  |  |  |  |  |
| 2014 |  | 1 280 934 098 |  |  |  |  |  |
| 2015 |  | 1 591 356 687 |  |  |  |  |  |
| Total | 1 591 356 687 | 1 591 356 687 | 139 770 960 | 218 820 718 | 358 591 678 | 358 591 678 |  |

Note: The n+3 rule is applicable to 2007-2010 period, the n+2 rule is applicable to 2011-2013 period, the n+3/n+2 rules coincide in 2013

Source: IOP MA, MSC2007 as of 31 Mar 2012

For Regional competitiveness and employment objective, the target for the fulfilment of n+3 rule in 2011 amounts to EUR 4.7 million. By the end of 2011, expenditure in the total amount of EUR 4.4 million was submitted for certification. In order to meet the target, the advance payments in the amount of EUR 0.3 million were used. Following the withdrawal of the 8th interim application for payment, the amount of certified expenditure under the RCE objective equals EUR 2.6 million. As of 31 Mar, the expenditure prepared for certification by the MA total EUR 1.46 million, if this amount is included the certified expenditure would total EUR 4.45 million.

The fulfilment of n+3/n+2 rule for the Regional competitiveness and employment objective is illustrated in detail in the following table, where the first target for the fulfilment of n+3 rule (column ”a” in the table) is binding in 2011. In order to meet the target for 2012, the MA shall submit for certification the expenditure of at least EUR 3.82 million by the end of the year.

Table No 7 – Fulfilment of n+3/n+2 rule (in EUR) under RCE objective

| Financing plan – year | Total EU allocation for 2007-2013 – annual | n+3/n+2 targets - aggregate * | EC advance payments – annual | Interim /final applications for payment submitted to the EC – annual | Advance payments from EC + payment claims from the CR – annual | Advance payments from EC + payment claims - aggregate | Difference between the thresholds and payments – aggregate |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | A | b | c | d=b+c | E | f=e-a |
| 2007 | 3 951 894 |  |  |  | 0 | 0 |  |
| 2008 | 4 030 931 |  | 1 468 975 |  | 1 468 975 | 1 468 975 |  |
| 2009 | 4 111 551 |  | 1 175 180 | 3 569 | 1 178 749 | 2 647 724 |  |
| 2010 | 4 193 781 | - |  | 850 986 | 850 986 | 3 498 710 |  |
| 2011 | 4 277 657 | 4 689 580 |  | 2 137 974 | 2 137 974 | 5 636 684 | 947 104 |
| As of 31 Mar 2012 | 4 363 210 | 9 459 780 |  |  | 0 | 5 636 684 | -3 823 096 |
| 2013 | 4 450 474 | 19 248 516 |  |  |  |  |  |
| 2014 |  | 24 270 375 |  |  |  |  |  |
| 2015 |  | 29 379 498 |  |  |  |  |  |
| Total | 29 379 498 | 29 379 498 | 2 644 155 | 2 992 530 | 5 636 684 | 5 636 684 |  |

Note: The n+3 rule is applicable to 2007-2010 period, the n+2 rule is applicable to 2011-2013 period, the n+3/n+2 rules coincide  in 2013

Source: IOP MA, MSC2007 as of 31 Mar 2012

The Managing Authority monitors and as at the end of each month evaluates the fulfilment of n+3 rule in 2012 by individual intervention area, objective and aid provider. The progress and the volume of absorbed funds in the monitored stages of administration are compared against the total allocation and the allocation for the given year, or against the allocation reduced by the advance payments provided by the EC, see the following charts for individual objectives and charts for individual intermediate bodies and intervention areas in Chapter 2.6.1 The Analysis of risks in relation to the fulfilment of n+3/n+2 rule by the Managing Authority and Intermediate Bodies.

All the charts of the fulfilment of n+3 rule show the committed allocation as the announced allocation for the ongoing calls and financial requirements of projects submitted in the closed calls. The submitted projects comprise only the funds of projects in a positive status, the recommended for financing  covers the funds of projects recommended for financing by the Selection Committee. The implementation of a project stage completed bar gives cumulative sums total of all the amounts under the completed project stages.

The “certified” bar shows the current amount of certified expenditure. The “implementation completed by 05/2012” bar covers the forecast expenditure that should be certified by the end of 2012. It concerns the expenditure of project stages that according to the timetable should have been completed by the end of May 2012.

The following chart No 2 depicts the forecast fulfilment of n+3 rule in 2012 under the Convergence objective. The status of absorption by individual stage of project administration is compared against the n+3 target for 2012 (EUR 478.08 million – green line), or reduced by the first advance payment received from the EC (EUR 447.02 million – red line) and reduced by all the advance payments received from the EC (EUR 338.31 million – black line). The blue line expresses the n+3 target for 2011 (EUR 234.28 million).

The certified expenditure (EUR 218.57 million) fails to reach the allocation for 2008 (EUR 234.28 million) due to the withdrawal of the 8th interim applications for payment. If the submitted projects meet the timetable, the achievement of n+3 target for 2012 can be anticipated, provided the first advance payment is used (EUR 447.02 million), the volume of estimated certified expenditure by the end of 2012 amounts to EUR 449.11 million.

Chart No 2 – Fulfilment of n+3 rule under CONV objective in 2011 and forecast for 2012

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

The Chart No 3 below illustrates the forecast of fulfilment of n+3 rule in 2012 under the Regional competitiveness and employment objective. The status of absorption by individual stage of project administration is compared against the n+3 target for 2012 (EUR 9.46 million – green line), or reduced by the first advance payment received from the EC (EUR 8.87 million – red line) and reduced by all the advance payments received from the EC (EUR 6.82 million – black line). The blue line expresses the  n+3 target for 2011 (EUR 4.69 million).

The certified expenditure following the withdrawal of the 8th interim applications for payment amounted to EUR 2.97 million, with the target for 2011 being EUR 4.69 million. If the submitted projects meet the timetable, the achievement of n+3 target for 2012 (EUR 9.46 million) can be anticipated, provided a part of the received advance payments is used (EUR 6.82 million). The volume of certified expenditure by the end of 2012 is EUR 7.42 million.

Chart No 3 – Fulfilment of n+3 rule under RCE objective in 2011 and forecast for 2012

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

Chart No 4 illustrates funds in aggregate payment claims and certified expenditure over time. The monthly progress in the amount of funds covered by the aggregate payment claims is expressed by the green part of bars. The chart clearly shows that the volume of funds covered by aggregate payment claims as of 31 Mar 2012 does not reach the n+3 target for 2012, reduced by the EC advance payments.

Chart No 4 – Overview of certified expenditure and funds included in aggregate payment claims

Source: Internal sources of IOP MA and PCA as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

As of 31 Mar 2012, the aggregate payment claims included EUR 310.10 million and EUR 221.81 million was certified. Altogether seven certifications of expenditure were conducted in the amounts of EUR 5.01 million, EUR 18.44 million, EUR 21.97 million, EUR 41.07 million, EUR 33.91 million, in August 2011 certification of expenditure in the amount of EUR 41.23 million was conducted and in November  in the amount of EUR 60.18 million. The eights certification of expenditure in the amount of EUR 29.58 million was withdrawn in February 2012 upon request of the IOP MA.

### 2.6.1  Analysis of risks in relation to the fulfilment of n+3 rule by the Managing Authority and Intermediate Bodies

The n+3 rule shall be fulfilled at the level of programme and objectives. For the purpose of programme monitoring and management, the MA monitors the fulfilment of n+3 rule also by individual ministry and intervention area, although their fulfilment is not mandatory.

Ministry for Regional Development

The projects in Intervention areas 4.1, 5.2, 5.3 and Priority axis 6 fall under the responsibility of the Ministry for Regional Development. Projects in the total amount of EUR 223.45 million were submitted and projects in the amount of EUR 180.95 million were recommended for financing. The funds paid to beneficiaries amounted to EUR 99.19 million. The certified expenditure totalled EUR 68.76 million and exceeds the n+3 target for 2011 by EUR 20.56 million. The target is met to the highest degree by Intervention areas 6.1a and 6.1b, 5.3 and 5.2.

According to the data from IS Monit7+ IOP, the certification of expenditure in the amount of EUR 123.61 million is foreseen by the end of 2012 and the allocation for 2009 for the intervention areas within the responsibility of the Ministry for Regional Development equals EUR 98.34 million. The amount of forecast certified expenditure exceeds the allocation earmarked for 2009 in all the intervention areas of the Ministry for Regional Development, except for 4.1 and 6.2a and 6.2b.

The following Charts No 5 - 10 give a clear overview of the overall status as of 31 Mar 2012 in all the intervention areas under the responsibility of the MRD and the status of individual intervention areas.

Chart No 5 – Fulfilment of n+3 rule by the Ministry for Regional Development

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

Note.: green/orange part of the bar – increase/decrease of the volume of funds in the period from 1 Oct 2011 to 31 Mar 2012

In Intervention areas 4.1a and 4.1b, the n+3 rule in 2011 was not fulfilled and according to the current forecasts the fulfilment of n+3 rule cannot be expected in 2012 either. A total of 16 projects in the total amount of EUR 40.36 million were submitted under the 12th continuous call and the 13th time-limited call. According to the referred to timetables these projects will be submitted for certification only in the years to come.

Chart No 6 – Fulfilment of n+3 rule in Intervention area 4.1

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

In Intervention area 5.2, expenditure in the amount of EUR 39.96 million was certified. Since the target for 2008 was EUR 23.58 million, the n+3 rule was fulfilled. Since the allocation for this intervention area continues to be absorbed fairly smoothly, the non-fulfilment of n+3 rule in 2012 is not anticipated. The target for the fulfilment of the rule in 2012 equals EUR 52.64 million and according to the project timetables the certification of expenditure in the amount of EUR 79.83 million can be expected by the end of 2012.

Chart No 7 – Fulfilment of n+3 rule in Intervention area 5.2

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

In Intervention area 5.3, the n+3 rule was fulfilled in 2011, the amount of certified expenditure as of 31 Dec 2011 reached EUR 10.80 million, the target for 2011 totalled EUR 7.82 million. With regard to the exchange rate reserve, announcement of additional calls for this intervention area is not foreseen, the submitted projects in the amount of EUR 14.86 million are under implementation. Their expenditure will be certified in dependence on the timetable of individual projects. The target for the fulfilment of n+3 rule in 2012 is EUR 11.42 million, the amount of certified expenditure by the end of 2012 should according to the current data of projects reach EUR 13.50 million.

Chart No 8 – Fulfilment of n+3 rule in Intervention area 5.3

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

In Intervention are 6.1a a 6.1b, the n+3 rule for 2011 was fulfilled. The certified expenditure reached EUR 9.55 million, the target for 2011 equalled EUR 7.82 million. As of 30 Mar 2012, projects in the volume of EUR 25.35 million were submitted under these intervention areas, all the projects are under implementation. Funds in the amount of EUR 10.63 million were reimbursed to beneficiaries and the target for the fulfilment of n+3 rule in 2012 equals EUR 8.53 million. According to the timetables of submitted projects, it can be expected that by the end of 2012 the certified expenditure shall have totalled EUR 14.26 million. The n+3 rule should thus be fulfilled also in 2012 without any difficulty.

Chart No 9 – Fulfilment of n+3 rule in Intervention area 6.1

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

In Intervention areas 6.2a and 6.2b, the certified expenditure in the amount of EUR 2.34 million has been certified, the target for the fulfilment of n+3 rule in 2011 is EUR 4.18 million, therefore the n+3 rule was not fulfilled in 2011. As of 31 Mar 2012, a total of EUR 7.20 million is under implementation, according to the set out timetables the certified expenditure by the end of 2012 should have equalled EUR 3.14 million. The target for the fulfilment of n+3 rule in 2012 is EUR 5.60 million, when using all the advance payments EUR 3.97 million, the fulfilment of n+3 rule in 2012 is not envisaged, not even with the use of all the advance payments.

Chart No 10 – Fulfilment of n+3 rule in Intervention area 6.2

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

Ministry of Interior

AS of 31 Mar 2012, under the announced calls of the Ministry of Interior  applications in the amount of EUR 619.27 million were submitted, of which applications in the amount of EUR 581.07 million were recommended for financing, all these projects are under implementation. The reimbursed funds exceed the target for 2011 by EUR 2.24 million. In total, the expenditure (without the 8th interim application for payment) in the amount of EUR 47.03 million were certified, the target equalled EUR 102.21 million (with the inclusion of the 8th interim application for payment in intervention areas under the responsibility of the Ministry of Interior expenditure in the amount of EUR 69.83 million was certified). The n+3 rule for the Ministry of Interior has been fulfilled, when considering the advance payments.

According to the timetables of projects, it can be anticipated that expenditure in the amount of EUR 156.41 million will have been certified by the end of 2012, whereas at the last IOP Monitoring Committee meeting the value of EUR 287.50 million was stated, which means that the forecast amount of certified expenditure by the end of 2012 dropped by EUR 131.10 million. The current data suggests that the n+3 rule will be fulfilled in 2012, when considering the advance payments (target of EUR 147.63 million).

The Structural Funds Department (SFD) of the Ministry of Interior is fully aware of the risk of non-fulfilment of n+3 rule in 2012. The slow progress in administration is caused both by the Ministry of Interior as the Intermediate Body and the beneficiaries.

One of the causes on the part of the MoI CR IB is the high turnover of staff of the Structural Funds Department. The new employees are continuously trained, but they lack the knowledge of procedures, practical experience with the management of projects and addressing problems of beneficiaries as well as experience from the past. One of the measures taken was personal changes among senior staff of the IOP implementation unit.

The reasons on the part of beneficiaries are mainly the distorted forecasts of absorption. Primarily due to the delays in implementation, postponements in the conduct of tenders and changes in projects. These complications are the consequence of inexperience with project management and the nature of beneficiaries as such, i.e. government agencies under Priority axis 1. These reasons were established as fundamental when identifying the so called “sleeping projects”. This term refers to projects for which the Decision on providing a grant has been issued (e.g. already in 2010), but no tender, or only its unimportant part, has been completed so far. The SFD staff call upon the beneficiaries to immediately modify the financing plans of stages, or the postponements in the planned publication of tenders once a change occurs, but during the controls of data topicality in IS Monit conducted during the controls of delegated activities the IOP MA still discovers discrepancies between the reality and the data stated in IS Monit.

Based on the IOP MA recommendation, the MoI CR is drawing up a document for the Government Council for Information Society with a list of sleeping projects and a proposal for their withdrawal from implementation. This document should be elaborated during the month of May and should contain also the OP HRE projects so that it reflects the reality across the topic of Smart Administration. Due to requirements set out in the budgetary rules of the state budget, the fastest way to cancel these projects is the withdrawal from implementation by beneficiaries themselves, i.e. by individual ministries.

For the sake of improving the quality and accelerating the administration of projects under the responsibility of the Ministry of Interior, the IOP MA proposed a change in the administration of activities under Intervention area 2.1 and a transfer of the remaining activities in this intervention area to the IOP MA and CRD. In order to prepare this change, the WG for mitigation of risks in Smart Administration was set up, on the occasion of which the IOP MA, MoI CR and CRD every week discuss the tasks and their attainment. The purpose is to reduce the agenda under this intervention area and to make available the MoI CR capacity for strengthening the administration and control under Intervention area 1.1. In case even these measures fail to improve the absorption under Intervention area 1.1, the IOP MA considers necessary to transfer also administrative activities under Intervention area 3.4., or perhaps also 1.1., to the IOP MA and CRD.

In the light of unsatisfactory state of play and risks faced in intervention areas under the responsibility of the Ministry of Interior (IA 1.1 in particular), based on the decision of the Minister for Regional Development on 29 Feb 2012 the information on risks in the implementation of IOP was presented to the Government members. The Government Resolution No 133/2012 tasks the Minister for Regional Development and the Minister of Interior to promptly address the current situation in the Integrated Operational Programme.

Chart No 11 – Fulfilment of n+3 rule by the Ministry of Interior

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of finding: Community contribution

Note: green/orange part of the bar – increase/decrease of the volume of funds in the period from 1 Oct 2011 to 31 Mar 2012

Chart No 12 – Fulfilment of n+3 rule in Intervention area 1.1

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of finding: Community contribution

The funds committed to Intervention area 1.1 amount to EUR 303.27 million. The submitted projects amount to EUR 307.60 million, all the projects are under implementation. The beneficiaries have been paid out EUR 62.26 million and the expenditure in the amount of EUR 32.50 million has been certified. In 2012, the certification of funds in the amount of EUR 86.68 million is anticipated, with the target for 2012 being EUR 103.31 million, which when considering the advance payments is reduced to EUR 73.20 million. The current data indicates that the n+3 rule for 2012 can be fulfilled when using the advance payments.

However, bearing in mind the major problem of meeting the forecasts that have been for a long time already fulfilled to the degree of less than 50 %, there is a significant risk of the non-fulfilment of n+3  rule even when the advance payments are included. The reason behind the failure to fulfil the forecast absorptions is especially the failure to meet the timetable of project implementation, postponement of deadlines of tenders and frequent changes in projects of government agencies.

Chart No 13 – Fulfilment of n+3 rule in Intervention area 2.1

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of finding: Community contribution

In Intervention area 2.1, the submitted projects equal EUR 161.66 million, of which projects in the amount of EUR 157.77 million are under implementation. The funds reimbursed to beneficiaries amount to EUR 21.19 million and the certified expenditure equals EUR 9.05 million. By the end of 2012 the certification of expenditure in the amount of EUR 47.52 million can be foreseen, the n+3 rule would thus be fulfilled if the advance payments are included (the target for 2012 is EUR 52.59 million, when considering the advance payments it is EUR 37.22 million). Also in this intervention area the fulfilment of n+ 3 rule is put at risk if the forecast absorptions are not fulfilled.

Chart No 14 – Fulfilment of n+3 rule in Intervention area 3.4

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of finding: Community contribution

In Intervention area 3.4, the funds under the submitted projects amount to EUR 209.44 million, all the projects are under implementation. Funds totalling  EUR 110.88 million were reimbursed and the expenditure in the amount of  EUR 5.48 million was certified. It can be foreseen that by the end of 2012 the expenditure in the amount of EUR 22.21 million shall have been certified, with the target for the fulfilment of n+3 rule in 2012 being EUR 52.59 million, or EUR 37.21 million when the advance payments are included. Judging from the timetables of the so far submitted projects, the fulfilment of n+3 rule in this intervention area cannot be anticipated.

The highest absorption in this intervention area is foreseen to take place in 2013 and at the beginning of 2014 in line with the timetables of projects under the calls No 11, 12 and 13.

Ministry of Labour and Social Affairs

In continuous calls of the Ministry of Labour and Social Affairs projects in the volume of EUR 67.58 million were submitted and projects in the volume of EUR 43.27 million were recommended for financing. During 2011, the first volume of expenditure in the amount of EUR 1.4 million was certified, which does not reach the target for this year (EUR 18.98 million). According to the data from the timetables of submitted projects, the fulfilment of n+3 rule cannot be expected in 2012 either (the forecast certification of expenditure in the amount of EUR 7.29 million will not reach the target in the amount of EUR 38.72 million).

Chart No 15 – Fulfilment of n+3 rule by the Ministry of Labour and Social Affairs

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

Note.: green/orange part of the bar – increase/decrease of the volume of funds in the period from 1 Oct 2011 to 31 Mar 2012

Judging from the development of absorption in 2011, in Intervention area 3.1 the fulfilment of n+3 rule and the absorption of allocation for 2009 (EUR 24.38 million) by the end of 2012 cannot be expected. The forecast certified expenditure by the end of 2012 equals EUR 4.65 million. Since the previous meeting of IOP Monitoring Committee the certified expenditure has grown by EUR 0.23 million to EUR 1.08 million. One of the reasons of slow absorption is  the  frequent extension of stages and thus of the whole implementation of projects.

The delays are caused mainly by excessive administrative burden of beneficiaries resulting in postponements in the implementation of the whole project. One of the examples is the obligation of beneficiaries to submit the project documentation for evaluation and approval prior to the publication of a contract notice for the construction part of the project. In the course of implementation, some changes resulting in a fairly complicated administrative process usually occur in all the projects. These factors are accompanied by other externalities that slow down the absorption. In activity a), it concerns especially the tactical behaviour of regions that do not have this area among their priorities and postpone the submission of projects, while in activity c) it concerns matters related to understanding and interpretation of social enterprise and a large number of projects rejected during evaluation.

In mid-2011, new calls were announced for all activities of this intervention area, the number of submitted projects was low at the beginning. The projects were submitted mostly for activity 3.1 c). Since the beginning of 2012 the number of submitted projects has been increasing. The priority of MoLSA is not only to maintain the faster pace of project submission, but primarily to increase the volume of supported projects, namely both in terms of the number and amount of required funds.

Chart No 16 – Fulfilment of n+3 rule in Intervention area 3.1

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of finding: Community contribution

In Intervention area 3.3, the certified expenditure has reached EUR 0.34 million and it is the first volume of expenditure certified under this intervention area. Since the allocation for this area amounts to EUR 7.03 million, the n+3 rule for this intervention area was not fulfilled in 2011.

Judging from the so far development of absorption, problems with the fulfilment of n+3 rule and failure to absorb the allocated funds in 2012 can be envisaged. In line with the timetables of submitted projects, the volume of certified expenditure can be foreseen to equal EUR 2.63 million, while the target is EUR 14.34 million. The main reason is primarily the late announcement of calls for activity c) and low interest of regions, which led to the closure of the call No 05 as of 30 Dec 2011. Another  factor conducive to the failure to fulfil the n+3 rule is the postponement in timetables of project implementation. The MoLSA will monitor the fulfilment of internal timetables of projects.

Chart No 17 – Fulfilment of n+3 rule in Intervention area 3.3

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of finding: Community contribution

Despite the increased number of submitted project applications in intervention areas under the responsibility of the Ministry of Labour and Social Affairs (Intervention area 3.1 in particular), the approval of projects and absorption of allocation have not been accelerated.

Since the partial measures taken by MoLSA are insufficient, the MA commenced the conduct of internal evaluation “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“. Its main aim is to identify and evaluate the procedural and systemic barriers to absorption and to propose measures for their removal or reduction of their impacts. The MoLSA in cooperation with CRD CR and IOP MA will draw up an action plan from the evaluation and will send it to the European Commission through the IOP MA.

Ministry of Health

The Intervention area 3.2 of the Ministry of Health shows an obvious progress in the administration of newly received projects from previous calls, reimbursement of funds to beneficiaries and certification of expenditure. In total, applications in the volume of EUR 209.44 million were submitted, all these projects are recommended for financing and are currently under implementation. The total volume of projects with completed implementation of stages is EUR 125.94 million, of which EUR 110.88 million was reimbursed to beneficiaries and expenditure in the amount of EUR 86.61 million was certified. By this volume of certified expenditure the n+3 rule for 2011, with the target of EUR 37.48 million, was fulfilled. Since the limit for 2012 is EUR 76.49 million, the n+3 rule in this intervention area will be fulfilled also in 2012. The volume of certified expenditure can be anticipated at EUR 129.77 million.

Chart No 18 – Fulfilment of n+3 rule by the Ministry of Health

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

Note.: green/orange part of the bar – increase/decrease of the volume of funds in the period from 1 Oct 2011 to 31 Mar 2012

Ministry of Culture

In Intervention area 5.1 the submitted project applications amounted to EUR 253.95 million. In October and November, the third call of the Ministry of Culture  was under way, in which projects totalling EUR 61.38 million were submitted. Since the allocation for this call was EUR 22.88 million, the amount of submitted projects thus currently exceeds the allocation committed to this intervention area. All the projects received in this call are now at the stage of evaluation.

As against the data presented at the previous MC meeting, the beneficiaries were paid by EUR 17.56 million more and the volume of certified expenditure increased to EUR 8.58 million. Based on the data from timetables of projects, the n+3 rule in 2012 would not be fulfilled, not even with the inclusion of all the advance payments (the target for 2012 is EUR 65.50 million, decreased by all the advance payments it equals EUR 46.34 million). The forecasts cover the stages of projects that shall be completed by 31 May 2012 – according to this forecast the expenditure in the amount of EUR 39.46 million would be certified. The projects in this intervention area are divided into three months or six months stages, in case the forecast covers the expenditure of stages completed by 30 Jun 2012 the certified expenditure would grow by EUR 8.5 million , which would mean that the n+3 rule for 2012 would be fulfilled, once the advance payments received from the EC are considered.

Chart No 19 – Fulfilment of n+3 rule by the Ministry of Culture

Source: IS Monit7+ as of 31 Mar 2012; CZK/EUR exchange rate: 24.778

Source of funding: Community contribution

Note.: green/orange part of the bar – increase/decrease of the volume of funds in the period from 1 Oct 2011 to 31 Mar 2012

### 2.6.2 Forecast of the progress in IOP absorption (in EUR)

2.6.2.1 Submitted applications for payment (payment claims) – forecast (in EUR)

The following table gives the forecast of submitted applications for payment for the period from April 2012 to December 2012. It is an estimate of individual financial amounts in a breakdown by month based on the data in IS Monit7+ as of 31 Mar 2012.

The amounts in individual months correspond with the amounts for the planned stages as given in the timetable of individual projects. In the calculation of forecasts the MA took into account the fact that the beneficiary submits the application for payment within 20 working days following the completion of the project stage.

Table No 8 – Forecast of submitted payment claims

| Priority axis / | Submitted payment claims – forecast |
| --- | --- |
| Intervention area | April 12 | May 12 | June 12 | July 12 | August 12 | September 12 | October 12 | November 12 | December 12 |
| 1a | 89 530 | 1 232 186 | 6 241 718 | 50 109 780 | 13 027 607 | 0 | 8 993 020 | 5 013 104 | 0 |
| 1b | 6 887 | 94 784 | 480 132 | 3 854 599 | 1 002 124 | 0 | 691 771 | 385 623 | 0 |
| 1 | 96 417 | 1 326 970 | 6 721 850 | 53 964 379 | 14 029 731 | 0 | 9 684 791 | 5 398 728 | 0 |
| 2.1 | 5 215 632 | 1 246 995 | 5 819 693 | 4 728 698 | 3 345 831 | 0 | 23 991 690 | 4 088 439 | 0 |
| 2 | 5 215 632 | 1 246 995 | 5 819 693 | 4 728 698 | 3 345 831 | 0 | 23 991 690 | 4 088 439 | 0 |
| 3.1 | 600 434 | 1 419 138 | 361 090 | 473 292 | 189 451 | 0 | 4 444 877 | 2 544 288 | 0 |
| 3.2 | 3 780 075 | 1 326 587 | 973 648 | 22 210 858 | 1 038 744 | 0 | 6 228 955 | 2 241 091 | 0 |
| 3.3 | 407 024 | 1 701 710 | 0 | 0 | 298 353 | 0 | 0 | 593 799 | 0 |
| 3.4 | 473 227 | 0 | 51 738 | 16 513 807 | 4 848 650 | 61 692 | 1 992 721 | 332 378 | 0 |
| 3 | 5 260 761 | 4 447 435 | 1 386 476 | 39 197 957 | 6 375 198 | 61 692 | 12 666 553 | 5 711 555 | 0 |
| 4.1a | 450 275 | 81 619 | 290 305 | 1 679 627 | 72 280 | 0 | 2 358 197 | 0 | 0 |
| 4a | 450 275 | 81 619 | 290 305 | 1 679 627 | 72 280 | 0 | 2 358 197 | 0 | 0 |
| 4.1b | 34 637 | 6 278 | 22 331 | 129 210 | 5 560 | 0 | 181 400 | 0 | 0 |
| 4b | 34 637 | 6 278 | 22 331 | 129 210 | 5 560 | 0 | 181 400 | 0 | 0 |
| 5.1 | 11 863 598 | 0 | 0 | 14 616 102 | 0 | 0 | 20 373 684 | 0 | 0 |
| 5.2 | 1 244 503 | 1 337 235 | 4 472 411 | 1 709 577 | 399 192 | 280 701 | 12 500 865 | 1 315 609 | 0 |
| 5.3 | 59 937 | 271 624 | 53 317 | 1 205 066 | 0 | 0 | 0 | 0 | 0 |
| 5 | 13 168 038 | 1 608 859 | 4 525 729 | 17 530 745 | 399 192 | 280 701 | 32 874 549 | 1 315 609 | 0 |
| 6.1a | 1 536 267 | 633 211 | 61 981 | 1 344 842 | 0 | 0 | 635 995 | 85 224 | 0 |
| 6.2a | 142 792 | 187 964 | 0 | 632 455 | 0 | 0 | 50 528 | 0 | 0 |
| 6a | 1 679 059 | 821 175 | 61 981 | 1 977 297 | 0 | 0 | 686 522 | 85 224 | 0 |
| 6.1b | 28 247 | 11 643 | 1 140 | 24 727 | 0 | 0 | 11 694 | 1 567 | 0 |
| 6.2b | 2 625 | 3 456 | 0 | 11 629 | 0 | 0 | 929 | 0 | 0 |
| 6b | 30 873 | 15 099 | 1 140 | 36 356 | 0 | 0 | 12 623 | 1 567 | 0 |
| Convergence | 25 863 295 | 9 438 269 | 18 325 902 | 115 224 104 | 23 220 109 | 342 393 | 81 570 531 | 16 213 932 | 0 |
| RCE | 72 396 | 116 161 | 503 603 | 4 020 165 | 1 007 684 | 0 | 885 793 | 387 190 | 0 |
| IOP | 25 935 691 | 9 554 430 | 18 829 505 | 119 244 269 | 24 227 793 | 342 393 | 82 456 324 | 16 601 122 | 0 |

Source: IS Monit7+ as of 31 Mar 2012

Source of funding: Community contribution

2.6.2.2 Submitted applications for payment (payment claims) – forecast and actual (in EUR)

The Tables No 9 and 10 give the actually submitted payment claims and the forecast volume of funds of the submitted payment claims in a breakdown by individual month. These are the forecasts as of 30 Sep 2011 presented at the 8th meeting of IOP Monitoring Committee in the Report on Implementation of IOP as of 30 Sep 2011.

When calculating the forecasts, the IOP Managing Authority proceeds from the data in IS Monit7+. For monitoring and calculation of forecasts the projects in a positive status are selected. The “actual” line includes the submitted payment claims for the month in question, in case of ex-ante financing it concerns the statement of the reimbursed funds.

In the period from 1 Oct 2011 to 31 Mar 2012, the payment claims in the total amount of EUR 96.32 million were submitted. The forecast for the monitored period amounts to EUR 286.93 million, the difference thus equals EUR 190.61 million. The forecast has been fulfilled to the degree of 33.6 %.

The major difference between the forecast and the actually submitted applications for payment is reported in Intervention area 1.1a and 1.1b (EUR 75.64 million). In cooperation with the IOP MA, a system of monitoring and management of projects in this intervention area was set up in the past in the form of regular status reports, in which the beneficiaries present also the state of play of the absorption and the SFD thus every month avails of data that is evaluated and facilitates faster initiation of changes and adoption of necessary measures to eliminate potential risks. Not all the beneficiaries, however, respond immediately to these requests of timely change in stages, in majority of cases the change is made only at the end of the stage due to lengthy tenders, appeals lodged by unsuccessful applicants, examinations by OPC and frequent changes in staffing and thus also in priorities of beneficiaries. Although this tool made it possible for project and financial managers to monitor the progress achieved in projects, it falls under the category of passive tools which have no influence on projects and their timely and due implementation. The MoI CR only scarcely uses the proactive tools which can also be the outcome of the lack of in-depth knowledge of the essence of individual projects that could help propose recommendations for the improvement of project implementation. The IOP MA has for a long time already drawn the attention of the MoI CR to the most effective tool for the management of problematic projects, i.e. the public administration checks with the imposition of corrective measures. Nonetheless, the IOP MA recommendations are faced with the limited control capacity of MoI CR.

Smooth fulfilment of forecasts has been consistently reported in Intervention areas 5.2 and 5.3.

Table No 9 – Submitted payment claims - forecast and actual (in EUR)

| Priority axis / | Submitted payment claims – forecast and actual (in EUR) | SUM TOTAL | Difference between the actual and the forecast | Rate of fulfilment of the forecast |
| --- | --- | --- | --- | --- |
| Intervention area | October 11 | November 11 | December 11 | January 12 | February 12 | March 12 |  |  |  |
| 1.1a | 5 941 541 | 5 426 169 | 362 436 | 83 053 892 | 0 | 2 417 042 | 97 201 080 | -70 241 693 | 27,7% |
| Actual | 3 831 207 | 0 | 359 184 | 21 377 900 | 951 432 | 439 664 | 26 959 387 |  |  |
| 1.1b | 457 042 | 417 398 | 27 880 | 6 388 761 | 0 | 185 926 | 7 477 007 | -5 403 208 | 27,7% |
| Actual | 294 708 | 0 | 27 630 | 1 644 454 | 73 187 | 33 820 | 2 073 799 |  |  |
| 2.1 | 10 812 813 | 1 204 434 | 2 659 102 | 21 487 174 | 4 317 257 | 6 469 324 | 46 950 104 | -36 191 360 | 22,9% |
| Actual | 2 926 758 | 685 502 | 518 075 | 5 577 791 | 457 915 | 592 703 | 10 758 744 |  |  |
| 3.1 | 302 501 | 872 241 | 46 390 | 2 062 413 | 1 273 010 | 588 755 | 5 145 310 | -4 521 895 | 12,1% |
| Actual | 0 | 38 094 | 105 288 | 458 530 | 21 503 | 0 | 623 415 |  |  |
| 3.2 | 7 543 569 | 0 | 3 576 110 | 15 404 899 | 4 479 828 | 0 | 31 004 406 | -22 230 228 | 28,3% |
| Actual | 4 387 980 | 0 | 842 991 | 2 198 974 | 1 018 221 | 326 012 | 8 774 178 |  |  |
| 3.3 | 1 002 612 | 0 | 43 118 | 909 460 | 0 | 691 489 | 2 646 679 | -2 230 793 | 15,7% |
| Actual | 0 | 0 | 3 429 | 0 | 0 | 412 457 | 415 886 |  |  |
| 3.4 | 1 195 599 | 376 432 | 53 015 | 12 605 544 | 564 786 | 4 874 134 | 19 669 510 | -18 569 644 | 5,6% |
| Actual | 477 181 | 0 | 0 | 622 685 | 0 | 0 | 1 099 866 |  |  |
| 3 | 10 044 281 | 1 248 673 | 3 718 633 | 30 982 316 | 6 317 624 | 6 154 378 | 58 465 905 | -47 552 559 | 18,7% |
| Actual | 4 865 161 | 38 094 | 951 709 | 3 280 189 | 1 039 723 | 738 469 | 10 913 346 |  |  |
| 4.1a | 318 470 | 14 973 | 592 132 | 4 030 442 | 643 415 | 0 | 5 599 432 | -4 208 708 | 24,8% |
| Actual | 29 651 | 0 | 189 277 | 1 171 796 | 0 | 0 | 1 390 724 |  |  |
| 4.1b | 26 418 | 0 | 45 472 | 310 026 | 49 493 | 0 | 431 409 | -324 323 | 24,8% |
| Actual | 2 283 | 0 | 14 574 | 90 229 | 0 | 0 | 107 086 |  |  |
| 5.1 | 16 042 917 | 0 | 0 | 17 301 028 | 0 | 755 615 | 34 099 560 | -17 854 742 | 47,6% |
| Actual | 7 609 674 | 0 | 0 | 8 635 143 | 0 | 0 | 16 244 818 |  |  |
| 5.2 | 14 927 958 | 1 485 827 | 7 635 853 | 5 449 572 | 555 843 | 998 843 | 31 053 896 | -6 511 135 | 79,0% |
| Actual | 11 284 350 | 1 172 038 | 6 101 399 | 3 781 505 | 907 535 | 1 295 934 | 24 542 761 |  |  |
| 5.3 | 408 476 | 282 590 | 170 824 | 545 708 | 152 317 | 71 009 | 1 630 924 | -309 082 | 81,0% |
| Actual | 299 630 | 365 495 | 182 748 | 174 161 | 41 907 | 257 902 | 1 321 842 |  |  |
| 5 | 31 379 351 | 1 768 417 | 7 806 677 | 23 296 308 | 708 160 | 1 825 467 | 66 784 380 | -24 674 959 | 63,1% |
| Actual | 19 193 655 | 1 537 533 | 6 284 146 | 12 590 810 | 949 441 | 1 553 836 | 42 109 421 |  |  |
| 6.1a | 188 159 | 0 | 0 | 1 928 173 | 246 356 | 309 559 | 2 672 247 | -1 090 441 | 59,2% |
| Actual | 154 187 | 0 | 0 | 1 018 242 | 168 376 | 241 001 | 1 581 806 |  |  |
| 6.2a | 0 | 0 | 0 | 996 734 | 82 232 | 200 483 | 1 279 449 | -892 061 | 30,3% |
| Actual | 0 | 0 | 0 | 244 822 | 56 565 | 86 000 | 387 388 |  |  |
| 6a | 188 159 | 0 | 0 | 2 924 907 | 328 588 | 510 042 | 3 951 696 | -1 982 502 | 49,8% |
| Actual | 154 187 | 0 | 0 | 1 263 065 | 224 941 | 327 001 | 1 969 194 |  |  |
| 6.1b | 3 460 | 0 | 0 | 35 453 | 4 530 | 5 692 | 49 135 | -20 051 | 59,2% |
| Actual | 2 835 | 0 | 0 | 18 722 | 3 096 | 4 431 | 29 084 |  |  |
| 6.2b | 0 | 0 | 0 | 18 327 | 1 512 | 3 686 | 23 525 | -16 402 | 30,3% |
| Actual | 0 | 0 | 0 | 4 502 | 1 040 | 1 581 | 7 123 |  |  |
| 6b | 3 460 | 0 | 0 | 53 780 | 6 042 | 9 378 | 72 660 | -36 453 | 49,8% |
| Actual | 2 835 | 0 | 0 | 23 224 | 4 136 | 6 013 | 36 207 |  |  |
| Forecast TOTAL | 59 171 535 | 10 080 064 | 15 212 332 | 172 527 606 | 12 370 579 | 17 571 557 | 286 933 673 | -190 615 765 | 33,6% |
| Actual TOTAL | 31 300 446 | 2 261 129 | 8 344 594 | 47 019 457 | 3 700 776 | 3 691 507 | 96 317 908 |  |  |

Source: IS Monit7+ as of 31 Mar 2012

Source of funding: Community contribution

Yellow cells = forecast

Table No 10 - Submitted payment claims by individual ministry – forecast and actual (in EUR)

| IOP | Submitted payment claims – forecast and actual (in EUR) | SUM TOTAL | Difference between the actual and the forecast | Rate of fulfilment of the forecast | Ministry |
| --- | --- | --- | --- | --- | --- |
|  | October 11 | November 11 | December 11 | January 12 | February 12 | March 12 |  |  |  |  |
| Forecast | 18 406 995 | 7 424 433 | 3 102 433 | 123 535 371 | 4 882 043 | 13 946 426 | 171 297 701 | -130 405 905 | 23,9% | MoI |
| Actual | 7 529 855 | 685 502 | 904 888 | 29 222 830 | 1 482 534 | 1 066 188 | 40 891 796 |  |  |  |
| Forecast | 1 305 113 | 872 241 | 89 508 | 2 971 873 | 1 273 010 | 1 280 244 | 7 791 989 | -6 752 688 | 13,3% | MoLSA |
| Actual | 0 | 38 094 | 108 718 | 458 530 | 21 503 | 412 457 | 1 039 301 |  |  |  |
| Forecast | 7 543 569 | 0 | 3 576 110 | 15 404 899 | 4 479 828 | 0 | 31 004 406 | -22 230 228 | 28,3% | MoH |
| Actual | 4 387 980 | 0 | 842 991 | 2 198 974 | 1 018 221 | 326 012 | 8 774 178 |  |  |  |
| Forecast | 16 042 917 | 0 | 0 | 17 301 028 | 0 | 755 615 | 34 099 560 | -17 854 742 | 47,6% | MoC |
| Actual | 7 609 674 | 0 | 0 | 8 635 143 | 0 | 0 | 16 244 818 |  |  |  |
| Forecast | 15 872 941 | 1 783 390 | 8 444 281 | 13 314 435 | 1 735 698 | 1 589 272 | 42 740 017 | -13 370 810 | 68,7% | MRD |
| Actual | 11 772 967 | 1 537 533 | 6 488 186 | 6 505 153 | 1 178 518 | 1 886 850 | 29 369 207 |  |  |  |

Source: IS Monit7+ as of 31 Mar 2012

Source of funding: Community contribution

In 2011 already, the IOP MA started to intensively monitor the absorption of the total allocation by individual intervention area, with account taken of the planned development in the submission of payment claims and funds in the intervention areas with completed tenders. The IOP MA builds on the idea that the forecast volumes of anticipated applications for payment could be considered unreliable  if the tenders are not completed at this stage. Then it would be impossible to calculate the incurred and invoiced expenditure. Whereas the preliminary summaries revealed major differences between the forecast values of applications for payment  and the volume of conducted tenders in billions of CZK, now, in the month of April, the difference between these two values equals CZK 297.64  million (EUR 12.01 million). This difference is caused predominantly by the fact that in Priority axis 6 (Technical assistance) a substantial volume of expenditure e.g. on labour costs is incurred without tenders that are subject to registration in IS Monit. The original vast difference was caused by the non-topicality of data on completed tenders entered in IS Monit IOP by IOP IB. This shortcoming was eliminated in cooperation with the IOP IB.

Table No 11 – Absorption of the total allocation as against the funds committed to completed tenders

| IA/PA | Allocation for 2007-2013 (a) | 2/6 2007 + 2008 + 2009 allocation | Approved projects* | Value of awarded contracts** | Approved payment claims*** | Reimbursed | Forecast submitted payment claims in April 2012 | Submitted, but not approved payment claims as of 31 Mar 2012 | Approved+forecast+ submitted, but not yet approved | Difference between the value of awarded contracts and submitted and forecast payment claims |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | Amount in CZK (b) | % (b/a) | Amount in CZK (c) | % (c/a) | Amount in CZK (d) | % (d/a) | Amount in CZK (e) | % (e/a) | (f) | (g) | (h= d+f+g) | % (h/a) | Amount in CZK (i=c-h) |
| 1 | 9 737 870 930 | 3 011 509 299 | 8 999 324 145 | 92% | 3 350 310 009 | 34% | 1 998 595 949 | 20,5% | 1 998 595 949 | 20,5% | 2 389 027 | 515 315 993 | 2 516 300 969 | 25,8% | 834 009 040 |
| 1.1a | 9 042 308 706 | 2 787 252 814 | 8 356 515 271 | 92% | 3 111 002 149 | 34% | 1 855 841 836 | 20,5% | 1 855 841 836 | 20,5% | 2 218 382 | 478 507 707 | 2 336 567 925 | 25,8% | 774 434 224 |
| 1.1b | 695 562 224 | 224 256 485 | 642 808 873 | 92% | 239 307 860 | 34% | 142 754 113 | 20,5% | 142 754 113 | 20,5% | 170 645 | 36 808 286 | 179 733 043 | 25,8% | 59 574 817 |
| 2 | 4 981 583 358 | 1 303 040 702 | 4 604 408 786 | 92% | 983 608 266 | 20% | 574 401 903 | 11,5% | 554 052 259 | 11,1% | 129 232 920 | 190 684 880 | 894 319 703 | 18,0% | 89 288 563 |
| 2.1 | 4 981 583 358 | 1 303 040 702 | 4 604 408 786 | 92% | 983 608 266 | 20% | 574 401 903 | 11,5% | 554 052 259 | 11,1% | 129 232 920 | 190 684 880 | 894 319 703 | 18,0% | 89 288 563 |
| 3 | 15 943 684 511 | 4 883 475 975 | 10 416 263 162 | 65% | 5 827 070 695 | 37% | 3 892 911 787 | 24,4% | 3 892 911 787 | 24,4% | 130 351 129 | 309 393 927 | 4 332 656 843 | 27,2% | 1 494 413 852 |
| 3.1 | 2 308 323 285 | 710 749 472 | 329 979 792 | 14% | 99 440 076 | 4% | 38 879 864 | 1,7% | 38 879 864 | 1,7% | 14 877 563 | 13 992 977 | 67 750 404 | 2,9% | 31 689 672 |
| 3.2 | 7 291 422 389 | 2 229 802 251 | 6 140 511 392 | 84% | 4 868 790 627 | 67% | 3 232 343 236 | 44,3% | 3 232 343 236 | 44,3% | 93 662 688 | 261 326 968 | 3 587 332 892 | 49,2% | 1 281 457 735 |
| 3.3 | 1 357 866 400 | 409 935 186 | 611 462 164 | 45% | 106 596 914 | 8% | 9 526 865 | 0,7% | 9 526 865 | 0,7% | 10 085 250 | 12 108 330 | 31 720 445 | 2,3% | 74 876 469 |
| 3.4 | 4 986 072 437 | 1 532 989 066 | 3 334 309 814 | 67% | 752 243 077 | 15% | 612 161 822 | 12,3% | 612 161 822 | 12,3% | 11 725 628 | 21 965 652 | 645 853 102 | 13,0% | 106 389 975 |
| 4 | 1 900 281 658 | 587 244 299 | 657 323 810 | 35% | 543 245 610 | 29% | 205 789 065 | 10,8% | 205 789 065 | 10,8% | 12 015 145 | 43 730 707 | 261 534 916 | 13,8% | 281 710 694 |
| 4.1a | 1 764 547 338 | 543 514 301 | 610 371 547 | 35% | 504 442 352 | 29% | 191 090 059 | 10,8% | 191 090 059 | 10,8% | 11 156 920 | 40 607 063 | 242 854 042 | 13,8% | 261 588 310 |
| 4.1b | 135 734 320 | 43 729 998 | 46 952 264 | 35% | 38 803 258 | 29% | 14 699 006 | 10,8% | 14 699 006 | 10,8% | 858 225 | 3 123 644 | 18 680 875 | 13,8% | 20 122 384 |
| 5 | 13 381 182 261 | 3 638 621 078 | 9 139 595 833 | 68% | 6 213 277 041 | 46% | 3 587 279 874 | 26,8% | 3 325 383 859 | 24,9% | 326 277 657 | 183 698 866 | 4 097 256 397 | 30,6% | 2 116 020 644 |
| 5.1 | 6 707 946 201 | 1 909 268 195 | 5 614 767 186 | 84% | 1 887 626 220 | 28% | 1 193 108 208 | 17,8% | 1 013 276 261 | 15,1% | 293 956 240 | 6 149 039 | 1 493 213 487 | 22,3% | 394 412 733 |
| 5.2 | 6 207 488 021 | 1 396 409 980 | 3 091 523 201 | 50% | 3 911 643 925 | 63% | 2 012 301 354 | 32,4% | 1 931 357 286 | 31,1% | 30 836 297 | 168 213 227 | 2 211 350 878 | 35,6% | 1 700 293 047 |
| 5.3 | 465 748 040 | 332 942 903 | 433 305 446 | 93% | 414 006 896 | 89% | 381 870 312 | 82,0% | 380 750 312 | 81,8% | 1 485 120 | 9 336 600 | 392 692 032 | 84,3% | 21 314 864 |
| 6 | 1 339 428 800 | 411 923 298 | 943 523 352 | 70% | 120 540 934 | 9% | 388 269 486 | 29% | 388 269 486 | 29,0% | 42 368 675 | 54 515 406 | 418 182 909 | 31,2% | -297 641 975 |
| 6.1a | 793 882 818 | 243 884 626 | 725 511 292 | 91% | 45 942 374 | 6% | 308 608 406 | 38,9% | 308 608 558 | 38,9% | 38 065 619 | 45 010 409 | 391 684 434 | 49,3% | -345 742 061 |
| 6.2a | 521 365 422 | 160 267 028 | 200 978 887 | 39% | 72 422 210 | 14% | 72 647 555 | 13,9% | 72 647 654 | 13,9% | 3 538 096 | 8 520 728 | 17 735 721 | 3,4% | 54 686 490 |
| 6a | 1 315 248 240 | 404 151 654 | 926 490 179 | 70% | 118 364 584 | 9% | 381 255 961 | 29,0% | 381 256 212 | 29,0% | 41 603 714 | 53 531 138 | 409 420 155 | 31,1% | -291 055 571 |
| 6.1b | 14 594 261 | 4 689 410 | 13 338 252 | 91% | 844 735 | 6% | 5 676 897 | 38,9% | 5 676 745 | 38,9% | 699 906 | 827 599 | 7 204 402 | 49,4% | -6 359 667 |
| 6.2b | 9 586 299 | 3 082 235 | 3 694 921 | 39% | 1 331 616 | 14% | 1 336 628 | 13,9% | 1 336 529 | 13,9% | 65 054 | 156 669 | 1 558 352 | 16,3% | -226 736 |
| 6b | 24 180 559 | 7 771 644 | 17 033 174 | 70% | 2 176 351 | 9% | 7 013 525 | 29,0% | 7 013 274 | 29,0% | 764 961 | 984 268 | 8 762 754 | 36,2% | -6 586 403 |
| Total | 47 284 031 518 | 13 835 814 651 | 34 760 439 087 | 74% | 17 038 052 555 | 36% | 10 647 248 064 | 22,5% | 10 365 002 405 | 21,9% | 642 634 553 | 1 297 339 778 | 12 520 251 737 | 26,5% | 4 517 800 818 |
| Source: IS Monit7+ IOP as of 3 Apr 2012 (for columns c, f, g) MSC2007 of 4 Mar 2012 for columns a, b, d, e | Volume of funds in submitted and forecast payment claims not covered by the value of awarded contracts (sum total of negative amounts in column “I”) | 297 641 975 |

CZK/EUR exchange rate: 24.778

Source of funding: public funds total

* the value is the sum total of amounts from the Decision/Statement of expenditure of projects that passed the P4.1status  - Decision on providing a grant/Statement of expenditure was issued and the following statuses, since 31 Jan 2012 this column has not included projects that had  not been completed

** the value is the sum total of the contractual amounts of eligible expenditure on tenders that were completed and are relevant or approved – namely only in projects in positive status.

*** for ex-ante payments the value covers the advance payments or  the so called limit

Note: If the value stated in the “Reimbursed “ column is higher than the value  in the “Value of awarded contracts” column, it can concern the small-scale contracts which are not subject to tenders  (these are contracts the forecast value of which in case of supplies and services is below CZK 2 000  000,- net of VAT and in case of construction works below CZK 6 000 000 net of VAT)

## 2.7 Analysis of Risks in Relation to Future Progress in Programme Implementation

The IOP MA coordinates the management of risks faced by the IB and MA in IOP implementation. It regularly shares information with the NCA in the form of a summary report on IOP risk management, namely always following the approval of the Catalogue of IOP Risks. It continuously monitors the measures adopted to eliminate the risks and their effectiveness.

The most significant risks related to programme implementation and the implemented and proposed measures to eliminate them are summarised in the table below.

| Name of the risk | Description of the risk | Measures implemented to eliminate the risk and the risk development | Proposed measures to eliminate the risk in the future |
| --- | --- | --- | --- |
| 1. Political influences or risk of corruption behaviour | Promoting the interests of certain groups and entities, especially through non-transparent procedures: pressure on granting derogations and allowing for changes in parameters of a call advantageous for certain groups, activities or eligible expenditure. Efforts to intervene in the selection of projects. Risk of corruption behaviour and influencing the evaluation, results of controls, permitting changes, sanctions or amount of support in projects. | The risk had to be accepted to some extent. Processes and responsibilities are set in administration procedures so as to eliminate the likelihood of risk. In Intervention area 1.1 the IOP MA in cooperation with MoI CR introduced a system of shared approval of changes in projects, which lead to the postponement of timetable by more than 3 months. | To continue to set out processes and responsibilities in order to eliminate the likelihood of the occurrence of risk. To continuously monitor the changes in priorities based on political changes and to evaluate their influence on absorption under IOP. To consider the application of joint approval of changes in timetables of projects also in other intervention areas. To inform the direct superiors in case similar phenomena occur. |
| 2. Failure to fulfil the n+3/n+2 rule and to absorb the allocation | Failure to absorb is one of the main risks of the programme that may be the consequence of a number of other risks – too complicated conditions for applicants and beneficiaries, delays in the announcement of calls and insufficient volume of funds allocated to the call, delays in administration, delays in project implementation, unpreparedness of projects, inadequate absorption capacity, administrative capacity (staff) lacking experience and competences, errors in project implementation, irregularities. | Though the MA and IBs monitor the absorption capacity, they fail to adequately evaluate it and particularly to adopt measures where the absorption capacity tends to be low on a long-term basis. A number of measures have been adopted to improve the administrative capacity and it was increased at some IBs. Measures supporting the publicity of the programme are implemented on a continuous basis. The allocation of funds to the announced calls has improved as well as the monitoring and management of calls by the MA. The ministers of individual IBs and their deputy ministers took part in the discussion on measures leading to the fulfilment of N+3 rule. The risk of failure to fulfil the n+3 rule was eliminated in 2011, but continues to be significant for the following years. | To timely prepare the calls and monitor and manage the volume of funds announced in individual calls at the level of MA. To support the absorption capacity. To ensure the administrative capacity and to simplify the implementation. To continuously monitor and evaluate the absorption capacity and forecast absorption. To ensure adequate publicity. To set priorities for administration. |
| 3. Non-compliance with or violation of binding procedures | Non-compliance with the mandatory procedures and processes set out in the binding IOP documentation and violation of Agreements on delegating the tasks to IBs or the Decision of the Minister for Regional Development on delegating the tasks to the CRD. It can result in wrong decisions, disputes and complaints. The level of likelihood of this risk varies in individual IBs. Low frequency of checks on delegated activities. | The MA conducts the controls of tasks delegated by the MA to IBs. The controls confirmed the non-compliance or violation of the binding procedures in certain activities. Adequate measures to ensure effective internal control system in certain IBs have so far not been adopted. Conducted controls of outsourced activities are insufficient. The MA will conduct a tender for external experts who will perform the controls of delegated activities at IB and it will also use the NCA databasis of experts. | To control the compliance with the agreements and the execution of delegated activities at IB, to impose corrective measures and to monitor their accomplishment. To inform the management, or the government, on risks ensuing from inadequate tools for management of IB. To complete a contract award procedure for external assistance (outsourcing) in the field of controls of delegated activities. To settle disputable matters at the meeting of deputy ministers of ministries acting as the intermediate bodies. To address risky areas at bilateral meetings of MA/IB. To timely incorporate the changes in procedures into MA/IB documentation. To control the compliance with archiving procedures. To set uniform reporting of administration of payments with the IB. To introduce additional reporting to monitor the projects, in which the submission of the application of payment is anticipated in individual months. To identify the causes leading to delays and suspension of administration. |
| 4. Errors in public procurement procedures and wrongly assessed correctness of public procurement procedures in procurement checks | Lack of experience of applicants and beneficiaries with the award of contracts. Inadequate observance of the principles of economy, effectiveness and efficiency in the award of contracts. Lack of experience of staff conducting the checks of public procurement procedures. Non-existence of a consultative body in case of uncertainty whether the rules for the award of small-scale contracts were/ were not violated. | The MA and IB provide consultations to applicants and beneficiaries. Recommendations were made as to the procedures that would guarantee the effectiveness, economy and efficiency in the award of contracts. All completed and commenced tenders/public procurement procedures shall be subject to checks prior to the approval of the application for support. For all major contracts an obligation is set in the IOP OM to check the tender/public procurement procedure already prior to its commencement and in the course of its conduct in order to facilitate timely correction of potential errors in the award of a public contract. The IBs and MA conduct checks in line with the detailed checklists. Training courses were held. The assistance of experts in this field is exploited. The MA conducts checks verifying the correctness of public procurement procedures in the award of problematic contracts. The MA provides consultations for IBs. During the MA checks and AAE audits on a sample of projects and contracts, errors were detected in public procurement procedures that confirmed also deficiencies in the control of contracts. The Working Group for public contracts was set up under the leadership of the MA. | To provide for seminars and consultations for applicants and beneficiaries in the field of award of public contracts. To continuously update the checklists for verifications of contracts. To train and share experience in this field. To conduct checks of delegated activities focused on the conduct of checks of contracts of IBs. More intensively exploit the assistance of experts in this field. To ensure more effective checks of the correctness of procurement procedures by Intermediate Bodies. |
| 5.Failure to fulfil the objectives and monitoring indicators of the programme | Failure to fulfil the global and specific objectives of the programme. Failure to fulfil the target monitoring indicators at programme level. | The target values of monitoring indicators were changed in the revised version of the operational programme in consequence of reallocations. The MA updated the methodological sheets for monitoring indicators with the view to finalise the description of calculations of the target and actual values of the monitoring indicators. | To modify the monitoring indicators. To target the announcement of calls for activities leading to the fulfilment of MIs. To monitor the achieved target values of MIs at programme level. To report the achieved target values in Reports on Implementation and Annual Reports of IOP and to explain the differences. |
| 6. Inadequate risk management and record keeping by MA/IB | Failure to present partial analyses of risks by the MA/IB in a timely manner and in line with the requirements and methodology. Inadequate work with risks, underestimation of the significance of risk management. Poor awareness and knowledge of reported risks on the part of IB risk management coordinators. Inadequate measures adopted to eliminate the risks at the level of both MA and IB. The IOP MA has no feedback from the integrated risk management system from the NCA. | The MA drafted a new version of the Catalogue of Risks and monitoring of the implementation of corrective measures with respect to major risks in monthly monitoring reports submitted by the IBs. Changes in risk management and monitoring of corrective measures will be approved at the WG for risk management in April 2012. Simultaneously, the Catalogue of IOP Risks will be approved. | Request addressed to the NCA concerning the feedback on risk analysis. To link the information from the Catalogue of IOP Risks with data included in the monitoring reports of the programme. To train the implementation structure staff in the field of risk identification and management. To regularly evaluate the implementation and effectiveness of corrective measures. |

## 2.8 Foreseen Timetable of the Announcement of Calls

The MA intends to announce the calls gradually throughout the programming period. One of the reasons is the evenly distributed release of funds which will safeguard necessary response to the needs of applicants and beneficiaries. The other reason is the effort to modify the calls based on the experience gained in the previous calls.

The planned timetable of calls and the actual opening dates of the calls (in green) in the period from 1 Oct 2011 to 31 Mar 2012 are given in the table below.

Table No 10 – Timetable of planned calls

| Plan/ actual | Intervention area, activity | Type of the call | Planned /actual opening date of the call | Allocation for the call in CZK (ERDF+SB) | Note |
| --- | --- | --- | --- | --- | --- |
| Plan | 5.1b) Implementation of model projects of renovation and use of the most significant components of immovable heritage fund | time-limited | 24.10.2011 | To be specified based on the current rate of exchange (approx. CZK 650-700 million) |  |
| Actual | 5.1 b) | time-limited | 24.10.2011 | 666 880 000 |  |
| Plan | 4.1 |  |  |  | The call was not planned, it was announced due to availability of remaining funds |
| Actual | 4.1 b) | time-limited | 14.12.2011 | 95 858 000 | Allocation for the call consists of funds saved in the implemented projects and savings derived from the exchange rate differences |
| Plan | 3.4 d) Better quality in the field of risk prevention and management through modernisation of infrastructure | time-limited | January 2012 | 1 000 000 000 |  |
| Actual | 3.4 d) | continu-ous | 2.2.2012 | 1 000 000 000 |  |
| Plan | 3.2 c) Management of quality and cost-effectiveness of public healthcare system | time-limited | 1st quarter of 2012 | 150 000 000 |  |
| Actual | 3.2 c) | time-limited | 7.3.2012 | 215 000 000 | Due to the failure to absorb the funds allocated to the 8th call and decrease of the exchange rate reserve, in accordance with the conclusions of the Evaluation of possibilities and feasibility of the transfer of funds within the Integrated Operational Programme a call was announced for the activity with low fulfilment of monitoring indicators as against their target values set out in the IOP Programming Document. |
| Actual | 3.2 b | time-limited | 7.3.2012 | 205 000 000 |  |

- the volume of scheduled calls can changer taking into account the exchange rate fluctuations and savings achieved in the previous calls

White cell = calls planned

Green cell = calls actually opened

An overview of ongoing calls of IOP is available on: http://www.strukturalni-fondy.cz/Narodni-organ-pro-koordinaci/Dokumenty/Publikace (overview of open calls).

## 2.9 Overview of approved projects

An essential parameter in the development of the programme cycle is the volume of projects approved for implementation.

A list of assisted projects and aid beneficiaries is updated by the MA at a monthly interval and published on the website: http://www.strukturalni-fondy.cz/Programy-2007-2013/Tematicke-operacni-programy/Integrovany-operacni-program/Projekty/Podporene-projekty.

More detailed information on approved projects is derived from IS Monit7+ and made available on www.risy.cz portal run by the Centre for Regional Development, which also facilitates the search for projects based on various parameters.

Information on rejected projects

The IOP MA monitors the statistics of rejected projects in the period prior to the issuance of the legal act (status N1.1, N1.2, N2.1, N2.2, N2.3, N4.1 and N5) and at the time of project implementation following the issuance of the legal act (status N7, N8). Projects can be rejected based on a decision of the applicant, who will no more seek aid, which corresponds to status N5 Project application withdrawn by the applicant and N7 Project not completed/withdrawn in IS Monit7+ IOP, or based on a decision of the MA/IB (hereinafter referred to as denied projects).

As of 31 Mar 2012, of the total of 8 220 submitted project applications 778 applications were rejected (of which 343 project applications in Intervention area 2.1 in call No 02 of the Ministry of Interior  for eGovernment in municipalities – CzechPoint – contact points), which represents 9.5 % of all the submitted project applications ..  The project applications were most frequently withdrawn by the applicant, namely in 258 cases, i.e. in 33 % of all the rejected projects (see Chart No 20).

Of 778 rejected projects, a total of 429 projects were denied. The projects are most often denied on the grounds of non-compliance with evaluation requirements, namely in 174 cases, which represents 40.6 % of all the denied projects. The eligibility criteria were not met in 127 cases (29.6% of all the denied projects).

The following chart gives the number and share of rejected projects by individual stage of administration.

Chart No 20 – Rejected projects by status

Source: IS Monit7+ as of 31 Mar 2012

N1.1 Project application failed to meet at least one of the eligibility criteria

N1.2 Project application failed to meet formal requisites

N2.1 Project failed to meet evaluation requirements

N2.2 Letter on rejection of project application based on ex-ante check was sent

N2.3 Project was not recommended for financing by the Selection Committee

N4.1 Issuance of Decision on providing a grant/Statement of expenditure was denied

N5 Project application was withdrawn by the applicant

N7 Project was not completed/project was withdrawn

N8 Contract was terminated by the MA/IB

Chart No 21 – Share of rejected projects by intervention area

Source: IS Monit7+ as of 31 Mar 2012

Chart No 20 illustrates the share of rejected projects by individual intervention area. The highest number of projects is rejected in Intervention areas 3.1 (58.9 %), 4.1a and 4.1b (59.5 %) and 5.1 (48.0 %). The lowest share of rejected projects is on the very contrary reported by Intervention areas 3.4 (2.8 %), 6.1a and 6.1b (3.2 %) and 5.2 (4.1 %).

In Intervention area 3.1, of the total number of 257 submitted project applications 58.9 % was rejected, which equals 152 projects. Of these 152 rejected projects, 135 project applications (89 %) were rejected under activity c) investment support to social economy. In this activity the main reason for rejection is non-compliance with the evaluation requirements (95 project applications, 70 % of projects rejected in activity c).

Based on the consultations with applicants in activity c) and the results of project quality evaluation, identified as the most frequent reasons of not meeting the quality evaluation requirements were the following:

- insufficient documenting of project sustainability (through the analysis of market, competition and potential/future demand, closing futures contracts, etc.),

- insufficient description and documenting of the necessity of project implementation from the perspective of the target group and market (i.e. regional contribution of the project).

The attention of  applicants is brought to these parts of project applications, or business plans, in the course of consultations and seminars for applicants (their content is modified with respect to the problematic parts of project applications). For the sake of applicants, the annex to the Handbook for Applicants and Beneficiaries No 5 Manual for evaluation of projects is published on the MoLSA website, because (apart from the Handbook for Applicants and Beneficiaries) it can become a valuable source of information during the elaboration of project application and the follow-up evaluation of sustainability.

Of 152 rejected projects in this intervention area, 101 projects were rejected on the grounds of non-compliance with evaluation requirements, which accounts for 66 % of all the denied projects. The second most significant reason is the withdrawal of the project application by the applicant, which happened in 26 cases, which constitutes 17 % of projects of all the 152 rejected projects.

The highest number of rejected projects was reported in Intervention areas 4.1a and 4.1b, but no project was rejected in the monitored period.

The high share of rejected projects in Intervention area 5.1 is caused by rejection or withdrawal of projects prior to the monitored period.

The Intervention area 5.2 exhibits the lowest share of rejected projects thanks to the information campaign of MA and CRD. The most frequent reason of rejection is currently the withdrawal of the application by the applicant.

The intervention areas under the responsibility of the Ministry of Interior show a fairly low percentage of rejected projects. It is the case especially of Intervention area 3.4, where evaluation of projects was under way in the monitored period. Due to high score the projects were not rejected. Projects under implementation are only exceptionally withdrawn by the beneficiary.

## 2.10 Implementation of the Major Project

The major project as defined in Article 39 of Council Regulation (EC) No 1083/2006 was planned in Intervention area 3.4 Services in security, risk prevention and management under the title National Centre for Emergency Preparedness and Training of IRS Units in Hradec Králové.

By decision of the top officials of the Ministry of Interior of November 2010 the preparation of the project was terminated. This fact was announced by the MoI representative at the 6th meeting of IOP Monitoring Committee in November 2010. The Monitoring Committee tasked the MoI CR with the conduct of evaluation of impact of the major project cancellation on the implementation and accomplishment of objectives of Intervention area 3.4 and the possible use of funds in other intervention areas. The conclusions of evaluations were presented at the Technical meeting of the IOP MC and the reallocation from activity c) to activity d) was approved at the 7th meeting of IOP Monitoring Committee in May 2011. This change was incorporated in the revision of the Programming Document, approved by the European Commission on 21 Dec 2011.

# 3 PROGRESS AT THE LEVEL OF PRIORITY AXIS

The financial tables and the tables of indicators are in line with the NCA Guideline for the elaboration of the report on implementation of the programme.

In indicators both the commitments of approved projects and the values achieved as of 31 Mar 2012 were monitored. The commitments are calculated from the target values of projects starting with status P4 in IS Monit7+ (project with issued Decision/Statement of expenditure). The achieved values are calculated based on projects starting with status P45 in IS Monit7+ (project under implementation), with the exception of the “Number of projects” type of indicators,  in which the values are aggregated starting with status P5 (Project implementation was completed). The baseline values from 2005 are taken over from the Programming Document.

The charts “Comparison of physical and financial progress by individual intervention area” represent the comparison of physical progress (the violet bar expresses the commitment to approved projects, i.e. the total target value of the indicator, which is stated by beneficiaries in their applications and which the beneficiaries undertake to fulfil by project implementation, it is expressed in % of the total value set in the IOP Programming Document, the same value is given in the tables of indicators) and the financial progress (the blue bar covers the funds of projects, for which the Decision is issued, expressed as a percentage of the allocation for activity(ies), under which the relevant indicator falls).

## 3.1 Priority axis 1a, 1b – Modernisation of public administration

### 3.1.1 Focus of priority axes/intervention areas

Priority axes 1a and 1b aim to achieve faster and more reliable provision of state administration services to the public, and, by implementing electronic administration, to enable citizens and business entities to communicate simply and quickly with state administration authorities.

Specific goals:

- To improve the level of services of electronic public administration (eGovernment)

- To increase the use of the Internet by citizens for communication with public administration

- To reduce the administrative burden of citizens, entrepreneurs and public sector

Supported activities:

- Creation, development and maintenance of national basic and other relevant registers of the public administration, including safe and protected access system,

- Construction of the public administration communication infrastructure,

- Creation of access points for communication with the public administration information systems,

- Digitisation of public administration services.

Beneficiaries:

  - government agencies and semi-budgetary organisations established by them.

### 3.1.2 Progress achieved in the implementation of priority axes/intervention areas

Since in the monitored period no new call was opened or announced in Intervention areas 1.1a and 1.1b, no change occurred in the submitted applications or projects with issued Decision. Due to the issuance of the changed Decisions, the amount covered by the issued Decisions dropped from EUR 373.71 million to EUR 369.82  million. Announcement of new calls is envisaged in the first half of 2012, namely for funds saved thanks to the planned cancelation of sleeping projects (see the description of sleeping projects in Chapter 2.6.1). the focus of the call is currently being discussed at the MoI CR in cooperation with the IOP MA.

The progress was made in the volume of funds reimbursed to beneficiaries, which increased from EUR 58.22 million to EUR 80.66 million. The submitted aggregate payment claims increased from EUR 38.36 million to EUR 62.14 million, the certified expenditure grew from EUR 16.28 million to EUR 38.54 million. This progress cannot be considered satisfactory with regard to the share in the total IOP allocation. The reasons of this situation as well as some measures taken by the MoI CR IB and IOP MA are given in Chapter 2.6.1. in the description of the state of play in intervention areas under the responsibility of the Ministry of Interior.

Table No 13 - Cumulative progress at the level of Intervention areas 1.1a and 1.1b (in mil. CZK/EUR)

| 1.1a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 9 042,31 | 365,41 | 79 | 10 743,58 | 118,8% | 433,59 | 60 | 8 508,84 | 94,1% | 343,40 | 1 855,84 | 20,5% | 74,90 | 1 413,30 | 15,6% | 57,70 | 874,89 | 9,7% | 35,79 |
| Previous MC | 8 975,67 | 365,41 | 79 | 10 743,58 | 119,7% | 437,39 | 60 | 8 523,82 | 95,0% | 347,02 | 1 327,85 | 14,8% | 54,06 | 874,89 | 9,7% | 35,62 | 376,25 | 4,2% | 15,12 |
| 1.1b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 695,56 | 28,11 | 0 | 826,43 | 118,8% | 33,35 | 0 | 654,53 | 94,1% | 26,42 | 142,75 | 20,5% | 5,76 | 108,72 | 15,6% | 4,44 | 67,30 | 9,7% | 2,75 |
| Previous MC | 690,44 | 28,11 | 0 | 826,43 | 119,7% | 33,65 | 0 | 655,68 | 95,0% | 26,69 | 102,14 | 14,8% | 4,16 | 67,30 | 9,7% | 2,74 | 28,94 | 4,2% | 1,16 |

Source: Current MC – MSC2007 as of 4 Apr 2012; Previous MC – MSC2007+ as of 4 Oct 2011

CZK/EUR exchange rate: Current MC – 24.778;Previous MC (“a” column) – 24.563

Source of funding – public funds total

Overview of ongoing calls

In the period from 1 Oct 2011 to 31 Mar 2012, no calls for submission of projects applications were under way and no calls were newly announced.

### 3.1.3 Fulfilment of indicators

Table No 14 – Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects CONV | Commitment of approved projects RCE | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 150106 | Number of created basic registers of public administration | Number | 0 | 4 | 5,57 | 0,43 | 0 |
| 150108* | Increase in the new fully digitised agendas of public administration, EU methodology | Number | 6 | 15 | N/A | N/A | N/A |
| 150109 | Share of registers connected to central registers | % | 0 | 75 | 22,08 | 22,08 | 0 |
| 150110 | Share of authorities using the shared CIPA | % | 0 | 80 | 28,00 | 28,00 | 28 |
| 150111 | Share of ministerial and agenda portals interconnected to the Public Administration Portal | % | 19 | 75 | 49,17 | 49,17 | 34,5 |
| 150112 | Share of digitized documents | % | 0 | 20 | 20,34 | 20,34 | 1,57 |
| 150113 | Share of authorities with electronic records management system and electronic document circulation | % | 20 | 100 | 8,73 | 8,73 | 6,70 |

Source: MSC2007 as of  31 Mar 2012

*  Indicator No 150108 is not monitored

Table No 15 – Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects CONV | Commitment of approved projects RCE | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 152105 | Reduction of administrative burden of citizens, entrepreneurs and public sector | % | 100 | 75 | 95,65 | 95,65 | 95,65 |

Source: MSC2007 as of  31 Mar 2012

Chart No 22 –Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

The chart indicates that activities in Intervention area 1.1 fulfilling indicators No 150106, 150109, 150110, 150111 and 152105 are fulfilled in terms of the financial volume, whereas the commitments of approved projects are supported only by indicators No 150106, 150112 and 152105.

In calls of the MoI CR, the data of the fulfilment of indicators is quantified as at the date of project completion. Some beneficiaries under Intervention area 1.1 considered the definition of indicators unclear and had problems with the wrongly set target values. The SFD in cooperation with the MA is drafting a revision of the Handbooks for Applicants and Beneficiaries, which will detail procedures for the calculation of the achieved values of indicators at project level.

### 3.1.4 Problems and measures taken

Risk of the failure to fulfil n+3 rule and to fulfil the forecast absorption

Measures taken: use of information from status reports, frequent communication with aid beneficiaries through consultations, holding of thematic seminars (e.g. on public contracts), despite these measures the forecast absorption is not being fulfilled (see Chapter 2.6.2 Forecast of the progress in IOP absorption).

Administrative capacity: a few officers left, the restricted recruitment of new staff at MoI CR leads to the filling up of the vacant positions mainly by junior candidates, shortage of experienced employees and experts in the field of Structural Funds. Frequent changes among the top officials of the department, problems related to cooperation between various MoI departments.

Measures taken: Stress on quality recruitment of new staff, provision of vocational training to the existing staff, negotiating of incentive bonuses

Insufficient activity of the control unit – underqualification and lack of experience of controllers, insufficient audit trail.

Measures taken: use of an external law firm, hiring of 3 new controllers for the control unit, cooperation between the Control Unit and PM/FM, archiving procedures are presented to the employees during the initial training course at MoI, further familiarisation with GINIS records management is done internally within the department.

Keeping the documentation in IS is the responsibility of project managers and the control unit employees. The control of entered data is a component part of their job description and shall correspond to the project file kept by the project manager in the paper form.

Within the control unit, tasks related to the provision of missing documents were reassigned, employees were trained to use the records management system.

Unclearly defined monitoring indicators – inappropriately set values of indicators or the indicator itself by beneficiaries.

Measures taken: communication with beneficiaries, revision of Handbooks for Applicants and Beneficiaries.

Delays in the implementation of tenders/public procurement procedures, poor quality of documentation submitted for tenders/public procurement procedures

Measures taken: communication with beneficiaries is gradually intensified and preliminary checks of documentation are intensified so that these supporting documents are submitted continuously by beneficiaries, holding of thematic seminars on public contracts.

Non-compliance with the timetables of projects by beneficiaries

Measures taken: monitoring in the form of regular status reports, based on which the beneficiaries are requested to update the data, bilateral meetings are held, a letter was sent to the directors of problematic projects with an appeal to improve the status of absorption.

High turnover of staff in project implementation teams: lack of experience with administration of projects, conduct of tenders, failure to share all the information with newly recruited staff.

Measures taken: intensive communication with beneficiaries, bilateral meetings, one-to-one, e-mail and telephone business communication, holding thematic seminars (a seminar for IOP beneficiaries from among public administration – most frequent mistakes in projects; a seminar for beneficiaries under Intervention area 1.1 of IOP – copyright, IT licences with respect to the Act on public contracts; a seminar for IOP beneficiaries from among public administration – public contracts).

Delays in the implementation of projects of Basic registers and the risk of failure to launch the portfolio of Basic registers by the deadline laid down by the law, i.e. on 1 Jul 2012

Measures taken:

The IOP MA held a series of meetings with the directors of projects of Basic registers and the director of the National Registers Authority: establishment of the Interministerial Working Group for basic registers at the level of Deputy Ministers with adequate decision-making powers, chaired by the Deputy Minister of Interior for information technologies and eGovernment. The IOP MA and SFD participate in the meetings of this working group.

Problem of the so called “sleeping projects”, which for a long time have failed to report any progress in implementation

Measures taken: a letter of the SFD Director – informing beneficiaries about the alarming status, more stringent assessment of changes, bilateral meetings with beneficiaries, setting out deadlines for complementing the required documents. The SFD elaborates information for the Government Council for Information Society on sleeping projects, the information was compiled due to the withdrawal of projects from implementation by beneficiaries (addressed together with OP HRE).

Unclear use of savings in projects

Measures taken: creation of the Methodological Guideline of the SFD No 16 of 14 Feb 2012, which lays down the rules for the use of savings.

### 3.1.5 Example of a project

Intervention area: 1.1 Modernisation of public administration

Name of the project, registration number: Introducing the Electronic Licensing Administration,

CZ.1.06/1.1.00/07.06384

Beneficiary: Ministry of Industry and Trade of the CR

Project funding: SF contribution: CZK 67 808 664 (CZK 57 637 364.40, SB contribution: CZK 10 171 299.60)

The main aim of the project is the establishment of an electronic information system which will facilitate the keeping of an administrative file and record keeping and settlement of applications for licences in the electronic form. The project responds to the current development of society determined by the potential development of state-of-the-art technologies in information processing. The electronic licensing administration will be linked to other agenda information systems enabling automatic sharing of data for the sake of more effective communication with public administration entities and the ministry.

## 3.2 Priority axis 2 – Introducing ICT in territorial public administration

### 3.2.1 Focus of priority axes/intervention areas

Priority axis 2 is focused on modernisation of the territorial public administration, mainly on creating the conditions for application of e-Government at the local level, on optimisation of processes in the local self-governing bodies, mainstreaming electronic communication between the individual levels of public administration by ensuring mutual compatibility of information systems and data consistency, by providing as much information as possible free of charge via the Internet.

Specific goals:

- To increase the level of services of electronic public administration at regional and local level,

- To decrease the administrative burden of citizens, entrepreneurs and public sector.

Supported activities:

- Data sharing with central registers in public administration and creation of other relevant registers for needs of territorial public administration,

- Construction of the territorial public administration communication infrastructure:

- Creation of access points for communication with the public administration information systems

- Digitisation of the public administration services, particularly by means of digitalisation of procedures of individual agendas performed by the territorial public administration bodies.

Beneficiaries:

- Regions and municipalities and organisations established and founded by them, unions of municipalities

### 3.2.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention area 2.1, no call was announced or opened, which is why no progress was achieved in the number of submitted applications in the period from 1 Oct 2011 to 31 Mar 2012. One project was approved in this period, the amount of approved projects thus equals EUR 187.05 million (93 %). No announcement of calls is anticipated, bearing in mind the setting aside of the necessary minimum exchange rate reserve.

A slight progress was made in the volume of reimbursed funds (from EUR 16.89 million representing  8.4 % of the allocation to EUR 22.36 million representing 11.1 %) and in the amount of funds of submitted aggregate payment claims (from EUR 10.81 million representing 5.4 % of the allocation to EUR 15.46 million representing 7.8 %). In the monitored period, expenditure in the amount of EUR 4.09 million was certified and the volume of certified expenditure thus increased to EUR 10.65 million, equalling 5.3 % of the allocation.

Table No 16 - Cumulative progress at the level of Intervention area 2.1 (in mil. CZK/EUR)

| 2.1 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 4 981,58 | 200,98 | 5 839 | 5 465,67 | 109,7% | 220,59 | 5 540 | 4 643,35 | 93,2% | 187,40 | 554,05 | 11,1% | 22,36 | 386,53 | 7,8% | 15,46 | 265,54 | 5,3% | 10,65 |
| Previous MC | 4 936,62 | 200,98 | 5 839 | 5 465,67 | 110,7% | 222,52 | 5 539 | 4 622,05 | 93,6% | 188,17 | 414,86 | 8,4% | 16,89 | 265,54 | 5,4% | 10,81 | 166,58 | 3,4% | 6,56 |

Source: Current MC – MSC2007 as of 4 Apr 2012

Previous MC – MSC2007+ as of 4 Oct 2011

CZK/EUR exchange rate: Current MC – 24.778

Previous MC (“a” column) – 24.563

Source of funding – public funds total

### Overview of ongoing calls

In the monitored period no calls for submission of project applications were under way and no calls were newly announced for Intervention area 2.1.

### 3.2.3 Fulfilment of indicators

Table No 17 – Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 150105 | Number of contact points of public administration (Czech Point) | Number | 1300 | 6244 | 6572 | 6557 |
| 150117 | Share of local public administration registers connected to central registers | % | 0 | 75 | 16 | 0 |
| 150115 | Share of local networks connected to CIPA | % | 10 | 85 | 85 | 10 |
| 150116 | Share of regional portals integrated into the Public Administration Portal | % | 0 | 75 | 65,6 | 0 |
| 150114 | Number of new fully digitised agendas of local public administration | Number | 0 | 10 | 106 | 1 |
| 150112 | Share of digitised documents | % | 0 | 20 | 20,47 | 2,13 |
| 150113 | Share of authorities with electronic records management system and electronic document circulation | % | 20 | 100 | 0 | 0 |

Source: MSC2007 as of 31 Mar 2012

Table No 18 – Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 152105 | Reduction of administrative burden of citizens, entrepreneurs and public sector | % | 100 | 75 | 88,58 | 95,65 |

Source: MSC2007 as of 31 Mar 2012

Chart No 23 – Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

The chart reveals that the activities in Intervention area 2.1 fulfilling the indicators 150114 and 150112 are fulfilled in terms of the financial volume, whereas the commitments of approved projects are supported only by indicators No 150105, 150115, 150116, 150114, 150112 and 152105. The excess in indicator No 150114 is caused by irrelevant value of 10 that was set out in the Programming Document, while the beneficiaries in projects have undertaken to achieve the value of 106. The indicator No 150114  - Number of new fully digitised agendas of local public administration - has been exceeded because the records management systems were established under calls No 8 and 9 by municipalities and regions also for other municipalities in the region or municipalities with extended powers. A total of 39 submitted projects comprised this indicator and the commitment was on average 3.92 electronic agenda per project. The total number of 10 would make sense in case the applicants were exclusively the regions and established only a single records management system per project. When taking into account the fact that the indicator can be fulfilled also by regions and municipalities, the target value of 10 is strongly understated. Indicator No 150113 is not fulfilled in Intervention area 2.1, the beneficiaries have been recommended to use indicator No 150118 instead, with the number being the unit of measure. The methodology for calculating the indicator No 150113 is currently being prepared.

### 3.2.4 Problems and measures taken

Administrative capacity of staff of IOP unit: a few officers left, the restricted recruitment of new staff at MoI CR leads to the filling up of the vacant positions mainly by junior candidates, shortage of experienced employees and experts in the field of Structural Funds.

Measures taken: stress on quality recruitment of new staff, provision of vocational training to existing staff, negotiating of incentive bonuses

Failure to meet the timetables of project implementation

Measures taken: support to beneficiaries by CRD and SFD staff, consultation activities, holding of thematically focused seminars for beneficiaries.

Frequent changes in projects

Measures taken: intensive support to beneficiaries, holding thematic seminars, efforts to accelerate the administration of these changes.

Lengthy approval process of contract documents at the MoF (it concerns public contracts worth more than CZK 30 million in projects worth more than CZK 100 million)

Measures taken: acceleration of the process thanks to the SFD submission of additional information on projects together with the contract documents to the MoF.

Need for strengthening the administrative capacity for verifying and assessing the physical compliance of technical and technological solution of individual projects. Since these are technologically challenging projects, consultations on technical changes in projects and checks on monitoring reports are necessary. Their control requires an advanced knowledge of ICT and technical solutions.

Measures taken: hiring of another employee (technical consultant) in January 2012, who provides technical consultations and conducts checks of monitoring reports and payment claims in terms of technical and technological solution and fulfilment of indicators, establishment of effective communication between the SFD and CRD.

### 3.2.5 Example of a project

Intervention area: 2.1 Introducing ICT in territorial public administration

Name of the project, registration number: Development of eGovernment services in the municipality with extended powers Klatovy I - III,   CZ.1.06/2.1.00/06.06766

Beneficiary: Town of Klatovy

Project funding: total budget CZK 6 323 130,-, of which SF contribution CZK 5 374 660.50 and municipal budget CZK 948 469.5

The Town of Klatovy implemented the project under all the three parts of the call. The Technology centre is equipped with state-of-the-art technology, it is fitted with a modern records management system and assists in the internal integration of the authority. It helped radically speed up the flow of documents between municipalities, regions and central information systems and registers.

## 3.3 Priority axis 3 – Improving public services quality and accessibility

### 3.3.1 Focus of priority axes/intervention areas

Activities of Priority Axis 3 follow from the interventions into the quality and effectiveness of the public administration functioning. The common goal is to improve the organisation, financing and the evaluation process of public services. The priority axis is focused on four intervention areas:

- 3.1 – Social integration services

- 3.2 – Public health services

- 3.3 – Employment services

- 3.4 – Services in security, risk prevention and management

Specific goals:

- reinforcing social integration by transforming residential social welfare facilities into other types of social services, while improving the quality and accessibility of social services to allow the clients return to the labour market and to the society in general

- innovation and modernisation of the infrastructure for care for the population’s health, with an emphasis put on the extension of national networks of specialised facilities, prevention of health risks and higher effectiveness, quality and availability in the system of providing public health services,

- enhancement of quality of employment services and support of development of new tools and  institutions of employment services, including education of employees and clients of the employment services,

- better quality  in the field of prevention and risk management through modernisation of infrastructure.

Beneficiaries:

- government agencies and semi-budgetary organisations established by them,

- regions and municipalities and organisations established by them,

- non-governmental non-profit organisations,

- entrepreneurs (persons registered in the Commercial Register, persons doing business based on a trade licence or based on special regulations)

### 3.3.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention area 3.1 , a total of 257 project applications were submitted in the amount of EUR 78.52 million, which represents 84.3 % of allocation for this intervention area. A significant increase in the number of received project applications was brought about by projects submitted under the new calls announced in mid-2011.

In the monitored period, major progress was reported also in the amount of issued Decisions on providing a grant. The volume of approved projects equals EUR 13.32 million, i.e. 14.3 % of the total allocation for this intervention area, which means an increase by EUR 9.97 million. In the monitored period, 12 Decisions on providing a grant were issued.

A slight increase of EUR 0.37 million was seen in the volume of funds reimbursed to beneficiaries and subsequently also in the volume of certified expenditure, namely by EUR 1 million (1 % of the allocation). Minor increase in the volume of reimbursed funds and certified expenditure is caused by a low number of projects approved in the previous period.

Table No 19 – Cumulative progress at the level of Intervention area 3.1 (in mil. CZK/EUR)

| 3.1 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 2 308,32 | 93,18 | 257 | 1 945,62 | 84,3% | 78,52 | 31 | 329,98 | 14,3% | 13,32 | 38,88 | 1,7% | 1,57 | 41,30 | 1,8% | 1,67 | 30,85 | 1,3% | 1,27 |
| Previous MC | 2 288,80 | 93,18 | 186 | 1 284,11 | 56,1% | 52,28 | 19 | 82,24 | 3,6% | 3,35 | 29,53 | 1,3% | 1,20 | 30,71 | 1,3% | 1,25 | 6,63 | 0,3% | 0,27 |

In Intervention area 3.2, no new project applications were submitted in the monitored period. Two new calls were announced, progress in the number of received project applications will be reported only when the calls are closed in mid-May.

In the period from 1 Oct 2011 to 31 Mar 2012, a total of 31 projects from the 8th call of the Ministry of Health were approved, the amount of approved projects thus increased by EUR 39.31 million to EUR 364.90 million.

More consistent controls of observance of the efficiency, economy and effectiveness rules to the slowdown of absorption of funds, or the approval of final monitoring reports.  It was also necessary to set clear rules for the cooperation with external experts (e.g. cases when the opinions of two experts were contradictory). More consistent control of the 3E rules has already been introduced, thus no slowdown should occur in the next calls.

As of 31 Mar 2012, the funds in the amount of EUR 130.45 million were reimbursed to beneficiaries, the aggregate payment claims totalled EUR 120.51 million, representing  41.8 % of the allocation. The amount of certified expenditure grew from  EUR 91.38 million to EUR 101.91 million. The certified expenditure reached 35.3 % of the total allocation for this intervention area.

Table No 20 – Cumulative progress at the level of Intervention area 3.2 (in mil. CZK/EUR)

| 3.2 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 7 291,42 | 292,33 | 164 | 7 886,40 | 108,2% | 318,28 | 139 | 6 563,70 | 90,0% | 264,90 | 3 232,34 | 44,3% | 130,45 | 3 048,49 | 41,8% | 120,51 | 2 573,23 | 35,3% | 101,91 |
| Previous MC | 7 180,54 | 292,33 | 164 | 7 886,40 | 109,8% | 321,07 | 108 | 5 541,19 | 77,2% | 225,59 | 2 729,51 | 38,0% | 111,12 | 2 649,26 | 36,9% | 107,86 | 2 317,96 | 32,3% | 91,38 |

In Intervention area 3.3, a total of 19 project applications in the amount of EUR 58.91 million were submitted, of which 4  applications were submitted in the period from October 2011 to March 2012. The amount of submitted applications thus increased by EUR 12.66 million. One application was submitted for each activity under this intervention area. In the monitored period, 6 projects were approved. The amount of issued Decisions thus grew from EUR 3.49 million to EUR 24.68 million, which represents an increase by 38.6 %.

In the monitored period, no funds were reimbursed to beneficiaries or included in aggregate payment claims accounted for by the PCA. Certified expenditure in the amount of EUR 0.40 million was submitted to the EC.

Table No 21 – Cumulative progress at the level of Intervention area 3.3 (in mil. CZK/EUR)

| 3.3 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 1 357,87 | 54,81 | 19 | 1 444,76 | 106,4% | 58,31 | 8 | 611,46 | 45,0% | 24,68 | 9,53 | 0,7% | 0,38 | 9,53 | 0,7% | 0,40 | 9,53 | 0,7% | 0,40 |
| Previous MC | 1 346,35 | 54,81 | 15 | 1 121,18 | 83,3% | 45,65 | 2 | 85,74 | 6,4% | 3,49 | 9,53 | 0,7% | 0,39 | 9,53 | 0,7% | 0,39 | 0,00 | 0,0% | 0,00 |

In Intervention area 3.4, one call was announced, under which 28 project applications were submitted. The amount of submitted applications thus increased by EUR 38.68 million. Progress was also achieved in projects with issued Decision, the volume of which increased from EUR 94.92 million to EUR 134.57 million.

Funds in the amount of EUR 3.67 million were reimbursed to beneficiaries and funds in the amount of EUR 3.28 million were included in the aggregate payment claims accounted for by the PCA. In the monitored period, expenditure in the total of EUR 1.74 million was certified, thus the volume of certified expenditure reached EUR 6.45 million. Changes in staffing at the Ministry of Interior resulted in a slight increase at these stages. Currently the situation has become stable. Another issue is the failure to comply with the financing plans of individual stages by beneficiaries. It is caused by often complicated tenders or changes in staffing in project teams.

Table No 22 – Cumulative progress at the level of Intervention area 3.4 (in mil. CZK/EUR)

| 3.4 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 4 986,07 | 200,98 | 108 | 5 747,18 | 115,3% | 231,95 | 77 | 3 334,31 | 66,9% | 134,57 | 612,16 | 12,3% | 24,71 | 612,16 | 12,3% | 24,32 | 166,03 | 3,3% | 6,45 |
| Previous MC | 4 936,62 | 200,98 | 80 | 4 747,18 | 96,2% | 193,27 | 44 | 2 331,61 | 47,2% | 94,92 | 516,75 | 10,5% | 21,04 | 516,75 | 10,5% | 21,04 | 124,25 | 2,5% | 4,71 |

The following is applicable to all the tables above:

Source: Current MC – MSC2007 as of 4 Apr 2012

Previous MC – MSC2007+ as of 4 Oct 2011

CZK/EUR exchange rate: Current MC – 24.778

Previous MC (“a” column) – 24.563

Source of funding – public funds total

Overview of ongoing calls

In the period from 1 Oct 2011 to 31 Mar 2012, a total of 8 calls for submission of project applications were under way for Priority axis 3, of which 3 calls were announced in the monitored period. In total, 130 project applications in the amount of EUR 128.43 million were submitted and 8 projects in the amount of EUR 24.68 million were approved.

In Intervention area 3.2, two time-limited calls with the closing date in May 2012 were announced, the project applications submitted under these calls will influence the results only once the calls are closed.

In Intervention area 3.3, two continuous calls were under way, call No 05 for activity c) was closed due to low interest in this activity and the funds will be used in favour of activity a). As of 31 Mar 2012, under these two calls a total of 19 project applications were submitted – 11 under call No 04 and 8 under call No 05. One project was approved (EUR 1.05 million) under the closed call No 05 and 7 projects in the amount of EUR 23.62 million were approved under call No 04.

In Intervention area 3.4, the 13th continuous call was announced, under which 28 project applications in the amount of EUR 40.36 million were submitted. By the end of March 2012, no projects were approved.

Table No 23 – Overview of ongoing and announced calls in the period from 1 Oct 2011 to 31 Mar 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Priority axis / interven-tion area | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 23. | 04 | 11.11.2009 | 30.6.2013 | continuous | 3.3 a), b) | 38 794 604 | 11 | 49 584 381 | 7 | 23 624 998 |
| 24. | 05 | 11.11.2009 | 30.12.2011 | continuous | 3.3 c) | 6 780 201 | 8 | 8 723 993 | 1 | 1 052 626 |
| 39. | 06 | 31.5.2011 | 30.6.2013 | continuous | 3.1 b) | 10 510 666 | 13 | 6 426 094 | 0 | 0 |
| 40. | 07 | 7.7.2011 | 30.6.2013 | continuous | 3.1 a) | 32 408 951 | 19 | 16 404 993 | 0 | 0 |
| 41. | 08 | 29.7.2011 | 29.6.2012 | continuous | 3.1 c) | 8 890 292 | 51 | 6 935 668 | 0 | 0 |
| 45. | 13 | 2.2.2012 | 30.4.2012 | continuous | 3.4 d) | 40 358 382 | 28 | 40 358 382 | 0 | 0 |
| 46. | 09 | 7.3.2012 | 17.5.2012 | time-limited | 3.2 c) | 8 677 052 |  | 0 |  | 0 |
| 47. | 10 | 7.3.2012 | 10.5.2012 | time-limited | 3.2 b) | 8 273 468 |  | 0 |  | 0 |
| IA 3.1 Total |  |  |  |  |  | 51 809 910 | 83 | 29 766 755 | 0 | 0 |
| IA 3.2 Total |  |  |  |  |  | 16 950 521 | 0 | 0 | 0 | 0 |
| IA 3.3 Total |  |  |  |  |  | 45 574 805 | 19 | 58 308 374 | 8 | 24 677 624 |
| IA 3.4 Total |  |  |  |  |  | 40 358 382 | 28 | 40 358 382 | 0 | 0 |
| PA 3 Total |  |  |  |  |  | 154 693 618 | 130 | 128 433 512 | 8 | 24 677 624 |

Source: IS Monit7+ as of 3 Apr 2012

CZK/EUR exchange rate: 24.778

Source of funding – public funds total

### 3.3.3 Fulfilment of indicators

Table No 24 – Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 330300 | Number of projects focused on social inclusion | Number | 0 | 294 | 31 | 15 |
| 075713 | Facilities with transformation in progress | Number | 0 | 30 | 5 | 0 |
| 075714 | Number of supported organisations | Number | 0 | 30 | 7 | 2 |
| 075802 | Number of supported entities | Number | 0 | 250 | 19 | 13 |
| 080100 Core 38 | Projects on the support of health – total | Number | 0 | 110 | 133 | 72 |
| 080102 | Projects on the support of health – modernising medical equipment | Number | 0 | 50 | 84 | 43 |
| 080101 | Project on the support of health – health risk prevention | Number | 0 | 45 | 38 | 20 |
| 080702 | Number of projects focused on the introduction of standards and standard procedures of quality and cost management | Number | 0 | 15 | 11 | 9 |
| 074521 | Number of supported employment services institutions | Number | 0 | 8 | 5 | 0 |
| 074532 | Number of newly built and supported existing training centres of employment services | Number | 0 | 4 | 3 | 0 |
| 074533 | Number of newly built and supported existing information and education centres of employment services | Number | 0 | 2 | 1 | 0 |
| 260407 | Number of IRS operation centres with integrated ICT | Number | 0 | 14 | 41 | 0 |
| 260408 | Number of newly built logistics bases | Number | 0 | 1 | 1 | 1 |
| 260410 | Number of modernised or newly built contact points of Front office type connected to IRS network | Number | 0 | 369 | 370 | 275 |
| 260412 | Number of technological equipment for elimination of safety risks or their implications | Number | 0 | 2 180 | 1 950 | 0 |

Source: MSC2007 as of 31 Mar 2012

Table No 25 – Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 075711 | Alternative social services | Number | 0 | 60 | 28 | 2 |
| 075712 | Number of newly established social services and activities | Number | 0 | 50 | 20 | 6 |
| 075603 | Efficiency of support | % | 0 | 60 | 65,5 | 61,11 |
| 080721 | Increase in the standard (fit-out) of specialised workplaces in national networks | % | 0 | 60 | 72,08 | 70,98 |
| 080712 | Number of prevention programmes available to citizens | Number | 0 | 45 | 52 | 26 |
| 080704 | Number of programmes introducing the standards and standard procedures for quality and cost management | Number | 0 | 40 | 13 | 10 |
| 074514 | Quality increase in working and client environment of the employment services institutions | % | 0 | 15 | 8,4 | 0 |
| 074512 | Increase in the capacity of training centres of employment services | % | 0 | 20 | 0 | 0 |
| 074513 | Increase in the capacity of consultancy-training centres | % | 0 | 25 | 0 | 0 |
| 260401 | Number of supported IRS units | Number | 0 | 3 | 3 | 0 |
| 260406 | Decrease in average response time to imminent or existing safety risks | % | 0 | 75 | 0 | 0 |
| 260404 | Creation of new capacities for effective provision of humanitarian aid to other countries | m2 | 0 | 2 500 | 2 500 | 2500 |

Source: MSC2007 as of 31 Mar 2012

Chart No 24 – Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

Indicators in Intervention area 3.1 reflect the positive progress in absorption of funds under IA 3.1, their fulfilment depends on successful completion of the implementation of projects focused on social integration that can be reported only in the period of sustainability.

In activity 3.1 a), as of 31 Mar 2012 the Selection Committee approved 7 project applications, of which for 5 projects the Decision on providing a grant was issued. Indicator No 075713 is reported at the time of registration or a change in the registration of a social service, i.e. mostly after the project completion. Under no submitted project  a change in the registration of service has so far been made, with the commitment of 5 approved projects the achieved value as of 31 Mar 2012 is therefore zero.

In activity 3.1 b), as of 31 Mar 2012 a total of 12 project applications were approved, for all of them the Registration of an action was issued, for 7 of them the Decision on providing a grant was issued. 2 projects were completed, the achieved value of indicator No 075712 is 6 new social services.

In activity 3.1c), as of 31 Mar 2012 a total of 35 project applications were approved, in five cases the beneficiary withdrew from implementation following the approval of the project. Even though the number of entities implementing the project on social economy does not reach the planned target value, the efficiency of support (indicator No 075603) expressing the usefulness for the supported target groups of inhabitants was fulfilled due to the achieved value of 61.11% as of 31 Mar 2012. The original predictions for the setting out of the target value of indicator No 075802 will thus have to be reassessed.

Low number of completed projects is obvious from the chart of the Physical and financial progress in Intervention area 3.1 above. The chart gives the comparison of values of the monitored monitoring indicators.

The lowest value of physical progress is reported by indicator No 75802, reflecting the low number of supported entities in the field of social economy. Related to activity 3.1 c) is also the indicator No 75603, which expresses the share of successfully supported persons in the total number of supported persons. This indicator, on the contrary, shows above the standard fulfilment. The supported projects exploit to the maximum degree the assistance in order to support the socially excluded person or persons at risk of social exclusion. The positive impact of measures on increasing the absorption capacity and the drawdown expressed in the number of received projects and issued Decisions on providing a grant will be reflected in the values of monitored indicators only in the following periods.

Chart No 25 – Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

The values of indicators in Intervention area 3.2 are being fulfilled on a continuous basis. In the monitored period, the output indicator No 80102 “Number of projects on the support of health – modernising medical equipment (3.2 a)” increased, namely by the approval of 31 projects under the 8th call (i.e. the value “Commitment of approved projects”). The “achieved values” are being fulfilled continuously in line with the approval of monitoring reports.

The risk of non-fulfilment of MI is especially faced by Intervention areas 3.2b and 3.2c (i.e. in the indicators: Number of prevention programmes available to inhabitants (3.2 b), Number of programmes focused on the introduction of standards and standard procedures of quality and cost management (3.2 c), Number of projects on the support of health – health risk prevention (3.2 b) and Number of projects focused on the introduction of standards and standard procedures of quality and cost management  (3.2 c). For this reason on 7 Mar 2012 new calls were announced for Intervention areas 3.2b and 3.2c so that the MI target values are achieved.

The failure to fulfil the indicators is addressed through the announcement of new calls.

The summary indicator for Intervention area 3.2 - 080100 – Projects on the support of health total – has already been fulfilled to the degree of 120%, whereas the allocation was distributed only to slightly more than 80%.

The indicators in activity 3.2a) are also fairly well covered – indicator No 80102 – “Projects on the support of health – modernising medical equipment” has been fulfilled to more than 160% and the indicator No 080721 – “Increase in the standard (fit-out) of specialised workplaces of national networks“ has been fulfilled to approximately 120%. The allocation was distributed to the degree of 100%. The reason behind the excessive fulfilment of the indicators against the original plan is the fact that at the time the indicators were set out, the particular number of beneficiaries under Intervention area 3.2a was unknown. Only based on the conducted audits the number of hospitals in individual networks of specialised workplaces was determined.

The values of indicators in activities 3.2b) presented by indicators No 80101 “Project on the support of health – health risk prevention” and No 80712 – “Number of prevention programmes available for citizens” have approached or achieved the target value. The values will be fulfilled thanks to the announced 10th call.

The values of indicators in activity 3.2c) presented by indicators No 80702 – “Number of projects introducing the standards and standard procedures for quality and cost management” and No 80704 – “Number of programmes introducing the standards and standard procedures for quality and cost management” have not been fulfilled as yet. For this reason the 9th call focused on this intervention area was announced. The allocation for activity was exceeded thanks to the financially demanding project “Provision of IS/ICT for the Ministry of Health” amounting to CZK 450 million, which however fulfils the indicators only marginally and not adequately with respect to its value. The project requires a lot of funds since it should provide IS/ICT for the whole Ministry of Health, but it is a single project, which means that the indicator  No 80704 will be increased by the value of “1”.

Chart No 26 – Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

In Intervention area 3.3, no project has so far been completed, which is obvious from the chart. Zero values are now reported in the commitments of approved projects in indicators No 74512 and 74513, which express the increase in the capacity of set up training centres  in activities b) and c). In these projects the legal acts have already been issued, the indicators will be gradually fulfilled during the following periods. A positive effect on increasing the absorption capacity in activity a) is obvious in indicators No 74521 and 74514.

For better monitoring of result indicators No 74514, 74512 and 74513, in cooperation with IOP MA the Methodology for reporting indicators at the level of projects in Intervention area 3.3 was drafted.

Chart No 27 – Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

The Intervention area 3.4 reports gradual fulfilment of indicators. Indicator No 260412 is related to call No 12 and the ongoing call No 13, under which no legal acts have so far been issued.

No commitment of approved projects is reported in indicator No 260406, its value will be derived at the global level from data provided by the Police CR and GD FRS.  In indicator No 260407 the physical commitment highly exceeds the financial progress. It is caused by the fact that in the call the regional standardised projects were divided into those for the units of the Police CR, units of FRS CR and regions (Emergency Medical Services), while the Programming Document reckons only with the number of regions.

### 3.3.4 Problems and measures taken

Intervention area 3.1

Failure to achieve the targets of n+3 rule for 2011 and 2012 in this intervention area: The main problem faced during the implementation of projects in Intervention area 3.1 is the slow rate of absorption accompanied with a high risk of failure to achieve the n+3 targets. This risk has been addressed by MoLSA ever since the launch of IOP implementation. The delay that occurred at the beginning of programme implementation, follow-up problems related to the establishment of cooperation between MoLSA and CRD, frequent modifications of calls for Intervention area 3.1 complicating its administration, and other issues that have an impact on absorption could not be fully eliminated. The MoLSA, however, strives to at least strongly influence the risk. The risk of failure to achieve the n+3 targets in this intervention area in 2011 was affected primarily by slow preparation of projects in activity b), postponement of implementation of projects in activity a). The low number of approved projects in activity c) did not help increase the absorption either. The MoLSA also failed to implement the project in support of consultancy during development and implementation of business plans.

Measures taken:

Following from the 8th meeting of IOP MC, in December 2011 a regular reporting to the EC was introduced, providing information on the issuance of guidance documents, overview of absorption of funds and forecast absorption.

An important measure in support of absorption under activity 3.1a) is the division of projects with high financial and time requirements into smaller projects.

Concurrently, the timetable for preparation and submission of projects under IA 3.1 a) is continuously worked with. This timetable is monthly submitted to the IOP Managing Authority and it is continuously updated and supplemented with newly acquired information. This tool was introduced by MoLSA in 2010 and is still actively exploited. It enables an individual approach to each project and it gives an opportunity to timely respond to potential postponements of project preparation.

Apart from activities supporting the absorption, focused on beneficiaries, also changes in the implementation system are under preparation, particularly a change in work procedures with the view to cut short the periods necessary for the issuance of the Decision on providing a grant. One of such changes is e.g. the joint issuance of the Registration of an action and the Decision on providing a grant.

In December 2011, the MA commenced an analysis of work procedures in order to identify redundant and duplicate processes so as to accelerate the administration of projects and to support the absorption. This analysis is conducted under the title “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“. It is expected to be completed in April 2012.

Risk of the shortage of prepared and submitted projects that are suitable and of good quality

Measures taken:

In October 2011, the MoLSA identified a high risk of the shortage of projects under activity 3.1b). Although the call for submission of projects was announced in May 2011, in November only one project was submitted under this call. Based on this fact the communication plan was modified, the planned support for activity 3.1c) was suspended and all attention was paid to the support of publicity for activity 3.1b). In December 2011, the call was publicised in the Moderní obec periodical. The article highlighted the extension of its geographical scope to all socially excluded Roma locations in the CR (except for the City of Prague). By this measure, the MoLSA responded to the finding that some municipalities in the CR did not notice the modification of the new call, thanks to which they could become eligible applicants for support.

In support of absorption capacity of IA 3.1b), the MoLSA in cooperation with regional Roma coordinators held 6 seminars for applicants across the Czech Republic. The aim was to introduce the call and the possibilities of absorption of IOP assistance to new potential beneficiaries with excluded Roma locations at their territory.

In the period from 1 Oct 2011 to 31 Mar 2012, a total of 7 seminars were held, attended by 176 potential beneficiaries, of whom 82 % were potential beneficiaries under Activity 3.1b).

Based on the consultations, a pipeline of prepared projects was newly created for activity 3.1b), which is a significant tool for monitoring and fulfilment of the forecast submission of projects.

One of the most effective measures with a direct effect on successful submission of projects continues to be consultations on the prepared projects. In case of consultations of projects developed for activity 3.1 b, the participation of the Agency for Social Inclusion of Roma Locations at the Office of the Government has proven useful . Additional consultations in support of absorption are offered by the National Centre for Support of the Transformation for activity 3.1 a) and by the Centre for Regional Development during the award of public contracts.

The absorption in activity a) was supported by the introduction of regular provision of information to potential applicants on the status of allocation in the monthly newsletter of the National Centre for Support of the Transformation. It seeks to put pressure on potential beneficiaries under activity a) to observe the timetable of absorption and to promptly complete the preparations of projects that have not been submitted as yet.

Interest of  applicants in activity a) is adversely impacted by political factors, this risk has been taken into account by MoLSA since the announcement of the first call and efforts have been executed to eliminate it. The key measure taken is the waging of an intensive “pro-transformation” campaign  (through the implementation of an individual project of MoLSA called “Support to transformation of social services“) and holding of individual meetings with regions (applicants) in case the transformation process and submission of a specific project application is put at risk. In 2011, the MoLSA staff also participated as lecturers in several panel discussions, conferences and seminars held by the cooperating organisations or beneficiaries. It was e.g. the seminar called “Transformation of social services” held in the Chamber of Deputies of the Parliament of the CR on 6 Oct 2011, the “Introductory conference to the project called “Support to the process of transformation of residential social services”  held under the responsibility of aid beneficiary under IA 3.1 in the Moravian-Silesian region on 12 Oct 2011, a public hearing in the Senate on the topic of “Transformation of social services: exercise of rights of disabled persons“ on 22 Nov 2011, a conference “Life in community“ held on 1 – 2 Nov 2011 with the participation of approximately 250 participants from among professional and general public, and a conference called “Architecture of social services in common environment“ held on 13 Dec 2011.

Most effective measure in support of the submission of quality projects under 3.1c) continues to be the consultations of project outlines and support of publicity in the form of seminars for applicants.

Intervention area 3.2

Inadequate system of control of the observance of the rule of economy

Measures taken: elaboration of a standardised, transparent and uniform procedure for the control of observance of the rule of economy by aid beneficiaries and cooperation with the MA on the approval of this procedure.

Understaffing

Measures taken: In the framework of the Technical assistance project, the number of employees was increased by two posts – a lawyer and an expert in the field of medical devices and equipment. Following the update of the rules of organisation, in line with the NCA rules a selection procedure will be published for these posts.

Error rate in the implementation of public contracts in aid beneficiaries

Measures taken: holding of a seminar that will be focused on the amendment to Act on public contracts. Moreover, regular dissemination of information to beneficiaries via e-mail and website.

Problems in evidencing the eligibility of expenditure on project management and monitoring (documenting the factual and  time connection of activities declared by the supplier)

Measures taken: consistent control of documents during the control of the application for payment, preparation of a seminar for applicants concentrated on evidencing the eligible expenditure with stress on the observance of 3E rule (scheduled for April 2012).

Intervention area 3.3

Failure to absorb the allocation to call No 5 for activity c): in activity c) following the reallocation, approved by the 7th meeting of IOP Monitoring Committee, the funds were earmarked for 4 planned projects. As of 20 Mar 2012, 1 project was granted support, 2 additional projects are under administration. There is an imminent risk of failure to absorb the allocation.

Measures taken: The MoLSA now considers all possible scenarios. In case the remaining allocation is not absorbed, it seems most likely that a new call will be announced.

Time consuming preparation of projects: In call No 4, the MoLSA has registered extension of deadlines for submission of  projects. It concerns construction investment actions, the preparation of which is extremely time-consuming (acquisition of a building permit, planning permission procedure, acquisition of the building by the applicant, etc.). Minor risk is faced by projects incorporated in the List of Projects of the Labour Office CR only in 2011, for the preparation of which there is not much time.

Measures taken: Intensive methodological support by MoLSA, increased monitoring of preparation of these projects.

Complicated system of issuance of the Statement of expenditure for financing GA actions and the Decision on providing a grant: the different system of gradual issuance of legal acts had to be simplified so that the data is comparable with the data of other IBs

Measures taken:

In cooperation with the General Directorate of the Labour Office of the Czech Republic, at the end of March 2012 the invitations were published to centralised tenders for an administrator of public contracts, technical supervision of the investor and occupational health and safety coordinator and project documentation supplier (including engineering activities and author's supervision) for those projects under which these activities have not been tendered as yet (approximately 10 projects are foreseen) – time savings equalling 6 months in the administration of each project.

Shorter periods of time necessary for issuing and signing the Statement of expenditure/Decision, closer cooperation with involved MoLSA units – time savings equalling 5-10 working days.

Increase of the limit for approval of projects by the Ministry of Finance from CZK100 million to CZK 200 million (EU + SB) – time savings equalling 1-5 months each project.

Preparation of the issuance of the Registration and Statement/Decision in the form of a single (joint) document – time savings of at least 4 months.

Intervention area 3.4

Delays in the implementation of the umbrella project called the Information System of the Integrated Rescue System and of the follow-up regional standardised projects on the account of selection of the general supplier of the system.

Measures taken: top level intensive discussions in order to select the general supplier. They resulted in Government Resolution No 224 of 4 Apr 2012 extending the scope of activity of Česká pošta, s.p., by the performance of selected services, particularly the information and communication technology services used by state administration, including the way of implementation of the programme called Uniform standard of information systems of operational management and upgrading of technologies for the receipt of emergency calls of basic units of the Integrated Rescue System. More intensive negotiations are held concerning the actual involvement of Česká pošta, s.p. in individual projects and necessary documents are being drafted.

Inexperience of beneficiaries with the administration of projects under IOP

Measures taken: organisation of seminars for beneficiaries; bringing attention of beneficiaries to the possibility of continuous communication with CRD concerning the requisites of documents submitted within the application for payment and the monitoring report in order to achieve maximum effectiveness and speed of the process; provision of consultation activities for beneficiaries (elaboration of monitoring reports, applications for payment, public contracts, administration of changes, sustainability); appointment of a contact person responding to enquiries of beneficiaries.

### 3.3.5 Example of project

Intervention area: 3.1 Social integration services

Name of the project, registration number: Woodworking plant Tomíkovice – Social enterprise in Roma location Kobylá nad Vidnavkou, Velká Kraš, CZ.1.06/3.1.02/01.6232

Beneficiary: A & D KLÁSEK spol. s r.o.

Project funding:  total budget CZK 2 004 435,-, of which CZK 1 703 770,-  SF contribution and CZK 300 665,- SB contribution)

Firma A & D KLÁSEK spol. s r.o. used the assistance to purchase the machinery and equipment for the implementation of the project. The beneficiary purchased the machinery and equipment necessary for the operation of the social enterprise, primarily a fork lift truck, winch for dragging logs, chain saw for round timber, bell conveyors, a log feeder, edger etc. Since it is a social enterprise, 51 % of the profit generated by the project has to be reinvested in the firm.

Local raw materials are used in the activities performed by the enterprise, namely the saw timber is purchased from local municipal or private forest owner. Since the project is implemented in Rychleby mountains, there is a high likelihood of project sustainability and use of local sources.

The implementation of this project implementation resulted in the creation of five new jobs, of which 3 were filled with persons recruited from the target group. The employment of these persons helps them apart from other things also to acquire work habits, to safeguard permanent income. It may also help improve the image of Roma in the eyes of the general public.

Intervention area: 3.2 Public health services

Name of the project, registration number: Upgrade and renewal of medical devices and equipment of the Comprehensive Cardiovascular Centre of the University Hospital in Motol (children's section), CZ.1.06/3.2.01/05.06558

Beneficiary: University Hospital in Motol

Project funding: total budget CZK 79 671 000, of which CZK 56 885 094 SF contribution and CZK 22 785 906 SB contribution

The purpose of the project called “Upgrade and renewal of the medical devices and equipment of the Comprehensive Cardiovascular Centre of the University Hospital in Motol – children's section“ was the purchase of state-of-the-art diagnostic and therapeutic medical devices and equipment for the Comprehensive children's cardio centre of the UH in Motol, which is the only centre in the Czech Republic specialising in complex congenital heart defects surgeries in children from birth to 18 years.

The University Hospital in Motol has acquired two angiography suites and an echocardiograph. Monoplanar angiography is used to treat particularly vascular diseases of children aged 1 day to 18 years of age. It concerns the treatment of brain and other malformations, embolism and thrombosis complications, interventions in oncologic patients and interventions in transplanted organs. Biplane angiocardiographic equipment serves for detail diagnostic and treatment catheter-based interventions in new born babies, infants and children with congenital heart defect. The diagnostic heart catheterization is performed especially in patients with the most complicated congenital heart defects. Echocardiography is an ultrasound examination method which facilitates to assess a heart anatomy and function without surgery and thus to determine the type and details of the heart defect. This method thus makes it possible in approximately 80 percent of children who have to undergo a heart surgery to replace the more risky heart catheterization and angiocardiography, which used to be necessary and during which the children are also exposed to ionising radiation. The method is used also for the diagnostics of heart defects in the prenatal period. Early recognition of the defect in pregnancy facilitates to concentrate the deliveries of children with a severe heart defect from the whole CR in the University Hospital in Motol and thus to increase their chances for a successful surgery.

The aim of the project was to upgrade the technical equipment and devices of the Children's cardiocentre, to increase the quality of medical care and to achieve the European standards at the Children's cardiocentre of the UH in Motol.

Intervention area: 3.3 Employment services

Name of the project: Labour Office of the CR – Klatovy – purchase and reconstruction of a new building, CZ.1.06/3.3.00/04.07995

Beneficiary: Labour Office of the CR

Project funding:  total budget CZK  42 661 327, of which CZK 36 262 127.95 SF contribution and CZK 6 399 199.05 SB contribution

This project satisfies the need of higher quality and availability of employment services in the district of Klatovy. The new building will be purchased and then reconstructed, which will allow for centralising all the agendas into a single building and providing services at a single place. This will meet spatial requirements of the contact point in Klatovy and create adequate conditions for clients and office employees.

The office in Klatovy seeks to establish a close cooperation with employers, mayors of municipal authorities and elementary and secondary schools in the region. Spaces for meetings and discussions with these groups are currently also unsuitable and lacking the required capacity.

The purchase and reconstruction of the building will broaden and improve the quality of services provided to job seekers and job applicants. All the agendas of the labour office shall be brought to a single building. Another benefit will be the new, more spacious office of the Information and Advisory Centre for Career Choice that is now located in one room which cannot accommodate more than 15 persons. Worth mentioning is also the suitable location of the new building, within the reach of public transport, bus and railway stations. Contrary to the current situation, the new building will also avail of sufficient parking places and will be equipped with a wheelchair access.

Intervention area: 3.4 Services in security, risk prevention and management

Name of the project: Integrated Operation Centre – Regional Directorate of the Police of Olomouc region, CZ.1.06/3.4.00/11.07555

Beneficiary: Regional Directorate of the Police of Olomouc region

Project funding: total budget CZK 49 363 000,-, of which CZK 37 723 000,- SF contribution and CZK 6 657 000,- SB contribution

The project focuses on the purchase of new technology for the operative management and is linked to the umbrella project called “National Information System of the IRS”, which facilitates the provision of better quality information for the sake of exploiting information from emergency calls, achievement of higher effectiveness of operative management and deployment of forces and equipment, improvement of the knowledge of the emergency situation, reducing the transportation time, forces and equipment, and also enhancing the interoperability at the level of individual regions and among the other IRS basic units.

## 3.4 Priority axis 4a, 4b – National support of tourism

### 3.4.1 Focus of priority axes/intervention areas

The aim of Priority axes 4a, 4b is to support the formation of basic environment and conditions necessary for tourism development at the national level. To achieve its effective development it is necessary to manage and coordinate some tourism activities from the national level, which helps create suitable conditions for the development of business, increased competitiveness and employment in the this area.

The priority axis covers the Convergence objective (4a) and the Regional Competitiveness and Employment objective (4b).

Specific goals:

- Increase of the number of entities connected to the reservation (booking) system in tourism sector,

- To improve the quality of services provided in tourism, their uniform certification and standardisation,

- To improve the tourism statistics and information,

- To increase the number of publicity and marketing products of tourism.

Supported activities:

  - establishment of a national information and reservation (booking) system,

  - introduction and information support of national and international standards in tourism services,

  - support of nationwide marketing and creation of source databases,

  - presentation and promotion of cultural and natural wealth, culture industry and services used for tourism on the national level,

  - support of the promotion of the CR as a tourism destination.

Beneficiaries:

- government agencies and semi-budgetary organisations established by them (activities a, b, c, e),

- non-governmental non-profit organisations and interest associations of legal persons with national scope of activities in tourism (activity d).

### 3.4.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention areas 4.1a and 4.1b project applications were submitted under the 12th and 13th call, a total of 16 applications were submitted in the monitored period, the amount of submitted applications increased from EUR 2 699.80 million to EUR 3 478.72 million. Majority of projects met the quality evaluation requirements and are under ex-ante checks. Two projects were approved. The total amount of approved projects decreased from EUR 33.10 million to EUR 32.62 million due to changes in projects.

Progress in the amount of reimbursed funds is minimum since the largest volume of funds included in payment claims were requested towards the end of the year and these payment claims have not been administered or reimbursed as yet. Major problem in the control of payment claims is the evidencing of eligible expenditure by beneficiaries with respect to a lot of non-investment, labour  and overhead expenditure. The aggregate payment claims accounted for by the PCA equal EUR 8.20 million, which represents 10.6 % of the allocation. The certified expenditure amounts to EUR 2.73 million. In total, the certified expenditure has reached EUR 7.20 million, which totals 9.3 % of the allocation for this intervention area.

Table No. 26 – Cumulative progress at the level of Intervention area 4.1a and 4.1b (in mil. CZK/EUR)

| 4.1a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 1 764,55 | 71,26 | 74 | 3 230,27 | 183,1% | 130,37 | 23 | 750,58 | 42,5% | 30,29 | 191,09 | 10,8% | 7,71 | 187,44 | 10,6% | 7,61 | 164,70 | 9,3% | 6,69 |
| Previous MC | 1 750,26 | 71,26 | 66 | 2 506,99 | 143,2% | 102,06 | 22 | 755,19 | 43,1% | 30,74 | 183,66 | 10,5% | 7,48 | 164,70 | 9,4% | 6,71 | 102,89 | 5,9% | 4,15 |
| 4.1b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 135,73 | 5,48 | 74 | 248,45 | 183,0% | 10,03 | 23 | 57,74 | 42,5% | 2,33 | 14,70 | 10,8% | 0,59 | 14,43 | 10,6% | 0,59 | 12,68 | 9,3% | 0,51 |
| Previous MC | 134,64 | 5,48 | 66 | 192,81 | 143,2% | 7,85 | 22 | 58,09 | 43,1% | 2,36 | 14,13 | 10,5% | 0,58 | 12,68 | 9,4% | 0,52 | 7,91 | 5,9% | 0,32 |

Source: Current MC – MSC2007 as of 4 Apr 2012

Previous MC – MSC2007+ as of 4 Oct 2011

CZK/EUR exchange rate: Current MC – 24.778

Previous MC (“a” column) – 24.563

Source of funding – public funds total

Overview of ongoing calls

In the period from 1 Oct 2011 to 31 Mar 2012, two calls were under way  for Intervention areas 4.1a and 4.1b, in which  a total of 20 project applications in the amount of EUR 46.94 million were submitted.  Right now, the projects are under quality evaluations and ex-ante checks. No projects were approved in the monitored period.

Table No 27 – Overview of ongoing and announced calls in the period from 1 Oct 2011 to 31 Mar 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Interven-tion area/activi-ty | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 42. | 12 | 7.9.2011 |  | continuous | 4.1 a),b),c,e) | 36 977 372 | 9 | 39 998 691 | 0 | 0 |
|  |  |  |  |  |  | 2 844 413 | 9 | 3 076 822 | 0 | 0 |
|  |  |  |  | Call total | 39 821 785 | 18 | 43 075 513 | 0 | 0 |
| 44. | 13 | 14.12.2011 | 31.1.2012 | time-limited | 4.1 b) | 3 592 340 | 1 | 3 587 879 |  | 0 |
|  |  |  |  |  |  | 276 334 | 1 | 275 991 |  | 0 |
|  |  |  |  |  |  | 3 868 674 | 2 | 3 863 870 | 0 | 0 |
| CONV total |  |  |  | 40 569 712 | 10 | 43 586 570 | 0 | 0 |
| RCE total |  |  |  |  | 3 120 747 | 10 | 3 352 813 | 0 | 0 |
| PA 4 total |  |  |  |  | 43 690 459 | 20 | 46 939 383 | 0 | 0 |

Source: IS Monit7+ as of 3 Apr 2012

CZK/EUR exchange rate: 24.778

Source of funding – public funds total

### 3.4.3 Fulfilment of indicators

Table No 28 – Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value CONV | Target value RCE | Commit-ment of approved projects CONV | Commit-ment of approved projects RCE | Achieved value as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 410100 Core 34 | Number of projects focused on tourism development | Number | 0 | 44 | 23 | 19 | 19 | 8 |
| 413305 | Number of information portals | Number | 0 | 1 | 1 | 0 | 0 | 0 |
| 413315 | Number of introduced standards in tourism services | Number | 0 | 5 | 5 | 0 | 0 | 0 |
| 410304 | Number of marketing and statistical surveys | Number | 0 | 6 | 6 | 9,29 | 0,71 | 0 |
| 410303 | Number of publicity campaigns promoting tourism products | Number | 0 | 32 | 11 | 18,58 | 1,42 | 6 |

Source: MSC2007 as of 31 Mar 2012

Table No 29 – Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value CONV | Target value RCE | Commit-ment of approved projects CONV | Commit-ment of approved projects RCE | Achieved value as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 413311 | Share of entities operating in tourism in the CR, which will be connected to the information portal | % | 0 | 50 | 50 | 0 | 0 | 0 |
| 413320 | Number of newly classified and certified entities operating in tourism | Number | 0 | 1720 | 280 | 0 | 0 | 0 |
| 413321 | Number of created source databases | Number | 0 | 6 | 6 | 3,72 | 0,28 | 0 |
| 410302 | Number of created publicity or marketing products for tourism | Number | 0 | 10 | 10 | 17,65 | 1,35 | 9 |

Source: MSC2007 as of 31 Mar 2012

Chart No 28 -  Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

Progress in the fulfilment of monitoring indicators in Intervention area 4.1 is very low because the prevailing majority of them will be fulfilled only after the completion of project implementation, as of  31 Mar implementation of four projects was completed. For the fulfilment of MI in activity a) Establishment of the national information system, and b) Introduction and information support of national and international standards in tourism services (including especially certification, manuals, methodologies, systems, controls) – indicators No 413315, 413305, 413311 and 413320 – the projects were submitted at the beginning of 2012. Projects in activities c) and e) are at the stage of approval.

When the programme was prepared and the indicative targets for both the objectives were set out, it was not assumed that the indicator No 410302 would be fulfilled by all the projects focused on promoting tourism. Since this indicator has been opted for by majority of applicants for support, the target value of monitoring indicators has been exceeded. The exceeded value of indicator No 410304 is brought about by the necessity to conduct a higher number of separate statistical surveys than originally planned.

### 3.4.4 Problems and measures taken

Difficult control of economy, efficiency and effectiveness of spent funds

Measures taken:

- during the controls of contract documents the envisaged value of the public contract shall be presented,

- preparation of a selection procedure for experts in the field of tourism who shall cooperate during controls especially of contract documents and applications for payment,

- preparation of cooperation with experts in the field of tourism under the NCA projects.

Frequent changes in projects (postponements of deadlines and transfers of funds, failure to  implement activities), poorly developed supporting documents for changes

Measures taken:

- consultations at CRD branches prior to the submission of project applications and during project implementation,

- development of a procedure for applicants for the elaboration of supporting documents concerning the changes in projects,

- publishing of the most frequently asked questions (FAQ).

Tenders – errors in tenders (failure to produce the expected contract value, addenda to concluded contracts that have an effect on the selection of a supplier, etc.) and related ineligible project expenditure; lengthy approval of tenders at beneficiaries of the GA type.

Measures taken:

- Consultations concerning the contract documents prior to the publication of an invitation to tender,

- IOP MA informed the aid beneficiary about the possibility to attend seminars held by the NCA and focused on tenders,

- Publishing of the most frequently asked questions (FAQ),

- Provision of information on lengthy approval of tenders to the top officials of the ministry.

Risk of unauthorised state aid in projects

Measures taken:

- Consultations of problematic projects with an expert in the field of state aid.

### 3.4.5 Example of a project

Intervention area: 4.1 National support of tourism

Name of the project, registration number: Increasing the quality of information on selected sectors of tourism, CZ.1.06/4.1.00/04.05942

Beneficiary: Ministry for Regional Development of the CR

Project funding: total budget CZK 83 386 000,-, of which CZK 70 878 100,- SF contribution and CZK 12 507 900,- SB contribution

The aim of the project is to provide comprehensive statistical information on the sector of domestic collective and individual accommodation establishments for tourism (number, structure, regional distribution, offered services, etc.) and on the number of tour operators and travel agencies in the territory of the CR and their further characteristics (e.g. offered services). The project comprises also the creation of relevant databases, which will become an important source of information on tourism.

Analysis evaluating the quality and structure of data sets

Source: Analysis of needs of the users of statistical data on selected sectors of tourism in the territory of the CR (http://www.mmr.cz/CMSPages/GetFile.aspx?guid=b3afbc12-43ff-4469-b1b1-601546a0d7c4)

## 3.5 Priority axis 5 – National support of territorial development

### 3.5.1 Focus of priority axes/intervention areas

The interventions aim to create the basic environment that will be complemented by interventions from Regional Operational Programmes. The intervention areas are:

- 5.1 – National support for utilising the cultural heritage potential

- 5.2 – Improving the environment in problematic housing estates

- 5.3    Modernisation and development of systems for creating territorial policies

Specific goals:

- Improvement of services for owners of the monuments in the field of care of the  cultural heritage, more intensive use of cultural heritage in the CR and presentation of culture to the public

- Enhancing the quality of life and environment for inhabitants of problematic housing estates in large towns over 20 000 inhabitants by means of revitalisation of the environment of these estates and regeneration of residential buildings in the housing estates, including energy savings.

- Enforcing the management of sustainable development of the territory with the use of territorial plans of municipalities and better analytical planning materials to reduce regional disparities.

Beneficiaries:

- Government agencies and semi-budgetary organisations established by them,

- Municipalities and organisations established by them, unions of municipalities,

- Non-governmental non-profit organisations and interest associations of legal persons

- Owners of residential, or non-residential premises,

- Regions.

### 3.5.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention area 5.1, thanks to the funds additionally allocated based on the Interinstitutional Agreement and approval of the MC and EC the total allocation has been increased. The increased allocation and funds made available due to the withdrawal of one project facilitated the announcement of the 3rd

time-limited call for activity b1) in the period from 24 Oct 2011 to 30 Dec 2011. Altogether 9 projects were received and the financial requirements of projects almost three times exceed the allocation for the call. As of 31 Mar 2012, the submitted projects accounted for 235.8 % of the allocation, which represents EUR 638.24 million.

The number of projects with issued Decision has not changed since the previous MC since the evaluation of projects submitted under the third call was not completed by the end of March 2012 and all the Decisions for projects recommended for financing under the first two calls were issued by the middle of 2011. There are a total of 18 projects with issued Decision, of which one project was withdrawn from implementation, but based on the NCA methodology is included in the number of projects with issued Decision. The decrease in the financial volume of projects with issued Decision from EUR 237.95 million to EUR 235.81 million is caused by the cut of eligible expenditure of one project.

The volume of funds reimbursed to beneficiaries and the volume of certified expenditure has doubled. Altogether 15.1 % of the allocation, equalling EUR 40.89 million, has been reimbursed. It is mainly because of the expenditure on construction works which started to be incurred in approximately half of the projects under implementation.

The aggregate applications for payment accounted for by the PCA covered EUR 36.01 million (13.3 %), the certified expenditure amounted to EUR 20.84 million (7.6 %).

Table No 30 – Cumulative progress at the level of Intervention area 5.1 (in mil. CZK/EUR)

| 5.1 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 6 707,95 | 270,95 | 51 | 15 815,05 | 235,8% | 638,27 | 18 | 5 842,81 | 87,1% | 235,81 | 1 013,28 | 15,1% | 40,89 | 894,06 | 13,3% | 36,01 | 510,78 | 7,6% | 20,84 |
| Previous MC | 6 148,33 | 250,31 | 42 | 14 025,79 | 228,1% | 571,01 | 18 | 5 844,76 | 95,1% | 237,95 | 508,01 | 8,3% | 20,68 | 512,69 | 8,3% | 20,87 | 269,34 | 4,4% | 10,87 |

In Intervention area 5.2, all the monitored values have been continuously growing. The situation reflects the progress achieved in Intervention area 5.2, which envisages continuous rise in the number of implemented projects. It is thanks to the distribution of the drawdown over the individual years of IUDP implementation.

As of 30 Sep 2011, 895 project applications in the amount of EUR 195.15 million were received, which represents 63.5 % of the allocation for this intervention area. A total of 803 projects amounting to EUR 127.91 million have been approved. Funds have been gradually reimbursed to beneficiaries, the volume of reimbursed funds has reached EUR 77.95 million. The volume of certified expenditure in the monitored period increased by EUR 12.86 million to the total of EUR 47.03 million, representing 18.6 % of the allocation.

Table No 31 – Cumulative progress at the level of Intervention area 5.2 (in mil. CZK/EUR)

| 5.2 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 6 207,49 | 251,03 | 895 | 3 943,46 | 63,5% | 159,15 | 803 | 3 169,46 | 51,1% | 127,91 | 1 931,36 | 31,1% | 77,95 | 1 669,98 | 26,9% | 67,54 | 1 152,69 | 18,6% | 47,03 |
| Previous MC | 5 564,92 | 226,56 | 810 | 3 416,34 | 61,4% | 139,08 | 658 | 2 683,16 | 48,2% | 109,24 | 1 171,97 | 21,1% | 47,71 | 1 152,69 | 20,7% | 46,93 | 841,30 | 15,1% | 34,17 |

Progress in Intervention area 5.3 reflects the status of implementation of the intervention area. Since the previous MC meeting Decisions have been issued for 3 projects under the 8th call. A total of 94.3 % of the allocation, representing EUR 17.72 million has been committed to projects with issued Decision. In the monitored period the beneficiaries were paid by 7.5 % more funds,  i. e. by EUR 1.79 million. The progress in certified expenditure as against the previous MC meeting equals EUR 1.67 million, a total of EUR 12.70 million has been certified, which represents 70.4 % of the allocation.

Table No 32 – Cumulative progress at the level of Intervention area 5.3 (in mil. CZK/EUR)

| 5.3 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 465,75 | 18,27 | 579 | 501,63 | 107,7% | 20,24 | 518 | 439,08 | 94,3% | 17,72 | 380,75 | 81,8% | 15,37 | 364,74 | 78,3% | 14,18 | 327,73 | 70,4% | 12,70 |
| Previous MC | 448,78 | 18,27 | 579 | 501,63 | 111,8% | 20,42 | 515 | 431,25 | 96,1% | 17,56 | 333,66 | 74,3% | 13,58 | 327,73 | 73,0% | 13,34 | 287,04 | 64,0% | 11,03 |

The following is applicable to all the tables above:

Source: Current MC – MSC2007 as of 4 Apr 2012

Previous MC – MSC2007+ as of 4 Oct 2011

CZK/EUR exchange rate: Current MC – 24.778

Previous MC (“a” column) – 24.563

Source of funding – public funds total

Overview of ongoing calls

Altogether 903 project applications in the amount of EUR 330.52 million have been submitted, 803 projects in the amount of EUR 217.89 million have been approved.

In Intervention area 5.1, a time-limited call was announced for activity b) with the allocation of EUR 26.91 million, which consists of the additional funds approved by the MC and EC and available funds from the withdrawn project from previous calls. By the end of March, 9 projects in the amount of EUR 72.21 million were submitted under this call. The financial requirements of submitted projects exceed the allocation for the call almost three times. At present, all projects are subject to evaluation of formal requisites and no project has so far been approved.

In Intervention area 5.2, a continuous call is under way, project applications are continuously submitted. As at 31 Mar 2012, 895 applications in the amount of EUR 258.31 million were submitted. In 803 projects the Decision has been issued covering the total amount of EUR 217.89 million.

Table No 33 – Overview of ongoing and announced calls in the period from 1 Oct 2011 to 31 Mar 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Interven-tion area/activi-ty | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 14. | 07 | 22.5.2009 |  | continuous | 5.2 a),b),c) | 165 946 629 | 895 | 258 306 814 | 803 | 217 888 947 |
| 43. | 03 | 24.10.2011 | 30.11.2011 | time-limited | 5.1 b) | 26 914 198 | 9 | 72 211 610 |  | 0 |
| IA 5.1 total |  |  |  |  |  | 26 914 198 | 9 | 72 211 610 | 0 | 0 |
| IA 5.2 total |  |  |  |  |  | 165 946 629 | 894 | 258 306 814 | 803 | 217 888 947 |
| IA 5.3 total |  |  |  |  |  | 0 | 0 | 0 | 0 | 0 |
| PA 5 total |  |  |  |  | 192 860 827 | 903 | 330 518 425 | 803 | 217 888 947 |

Source: IS Monit7+ as of 3 Apr 2012

CZK/EUR exchange rate: 24.778

Source of funding – public funds total

IUDP implementation

Status of IUDP implementation

The Integrated Urban Development Plans of IOP have been implemented in 41 municipalities. As at 31 Mar  2012, a total of 181 calls were announced in all the municipalities, of which 131 calls were  closed and the remaining 50 calls, the majority of which are continuous calls, are still under way. The state of play of the calls in individual municipalities varies. There are cases reported, in which no project was submitted in the announced call, but there are also cases where the demand of submitted projects highly exceeds the allocation for the given call.

Table No 34 – Number of calls announced for IUDP

| Activity 5. 2. | Number of calls announced before 31 Mar 2012 |
| --- | --- |
|  | Number of calls total | Of which closed calls | Of which open calls |
| a) revitalisation of public spaces | 46 | 12 | 34 |
| b) regeneration of residential buildings | 118 | 110 | 8 |
| c) pilot projects | 7 | 3 | 4 |
| Combined calls for a) + b) | 8 | 6 | 2 |
| Combined calls for a) + b) + c) | 2 | 0 | 2 |
| Total | 181 | 131 | 50 |

Source: IOP MA as of 31 Mar 2012

The MA monitored primarily the compliance with the requirement of absorption of at least 25 % of total eligible expenditure of IUDP by the end of 2011. Based on the preliminary evaluation, the MA extended the deadline for the submission of applications for payment included in the absorption of allocation in 2011, to 31 Dec 2011. Thanks to that the requirements was met almost by all the towns. By 31 Dec 2011, the municipalities of Děčín, Most and Ostrava failed to submit the application for payment in the adequate volume. The IOP MA therefore proposed to these towns to cut the allocation of the total eligible expenditure. The Addenda to the Agreements on ensuring the implementation of IUDP, modifying the volume of allocation, will be disseminated among them in the course of April. In the monitored period, the IOP MA cut the allocation of IUDP Ústí nad Labem upon its own request. Due to low absorption capacity the town requested the cut of the ERDF allocation in the amount of EUR 1.5 million. The MA provided for the cut through the Addendum to the Agreement on ensuring the implementation of IUDP Ústí nad Labem No 3.

Despite the referred to cuts in funds allocated to some IUDPs, the absorption of allocation for Intervention area 5.2 is not put at risk. Since the beginning of 2012, the MA has evaluated the fulfilment of the requirement of absorption of allocation for this year. The IOP MA believes that there are no other towns that would encounter difficulties in terms of low absorption capacity.

Table No 35 -  Information on IUDP allocation for Intervention area 5.2

| Name of the applicant | Approved assistance from IOP (from ERDF) | Submitted projects (ERDF) | Forecast absorption 2010 | Forecast absorption 2011 | Forecast absorption as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- |
|  | EUR | EUR | (%) | (%) | (%) |
| Bohumín | 2 581 191 | 1 740 704 | 13,44 | 41,02 | 54,65 |
| Brno | 5 258 220 | 3 023 386 | 7,41 | 23,45 | 30,73 |
| Břeclav | 2 090 289 | 402 615 | 10,32 | 31,34 | 30,44 |
| České Budějovice | 6 849 922 | 2 492 253 | 15,45 | 59,38 | 57,63 |
| Český Těšín | 4 078 349 | 2 723 352 | 5,04 | 40,93 | 46,21 |
| Děčín | 4 235 187 | 134 397 | 4,49 | 15,29 | 13,62 |
| Frýdek-Místek | 5 237 029 | 1 362 823 | 3,60 | 27,54 | 45,78 |
| Havířov | 6 835 603 | 4 006 079 | 0,00 | 35,68 | 41,43 |
| Hodonín | 3 099 232 | 1 557 486 | 13,31 | 45,99 | 58,85 |
| Hradec Králové | 6 633 156 | 1 835 666 | 2,95 | 21,11 | 30,83 |
| Cheb | 3 729 669 | 1 416 619 | 21,24 | 17,96 | 52,40 |
| Chomutov | 6 489 612 | 1 921 628 | 26,83 | 34,16 | 41,93 |
| Chrudim | 3 217 388 | 3 001 087 | 15,29 | 75,21 | 56,99 |
| Jablonec nad Nisou | 4 393 360 | 2 837 248 | 18,38 | 44,62 | 40,19 |
| Jirkov | 4 006 329 | 2 024 318 | 42,04 | 65,25 | 81,84 |
| Karlovy Vary | 3 243 289 | 866 475 | 7,26 | 34,56 | 40,85 |
| Karviná | 5 750 823 | 2 452 936 | 13,69 | 36,19 | 51,31 |
| Kladno | 6 213 506 | 6 261 153 | 17,45 | 54,93 | 84,09 |
| Kopřivnice | 3 799 948 | 2 445 472 | 12,35 | 27,52 | 47,10 |
| Kroměříž | 3 816 513 | 2 112 624 | 24,50 | 53,02 | 73,07 |
| Liberec | 6 020 554 | 556 575 | 0,59 | 21,83 | 32,85 |
| Litvínov | 3 336 657 | 2 097 381 | 16,24 | 25,89 | 28,39 |
| Mladá Boleslav | 3 836 636 | 3 972 392 | 11,97 | 77,99 | 82,62 |
| Most | 6 502 569 | 276 760 | 2,88 | 2,19 | 13,83 |
| Náchod | 4 233 175 | 1 493 799 | 12,09 | 35,23 | 45,67 |
| Nový Jičín | 3 666 244 | 2 065 528 | 27,88 | 45,33 | 62,33 |
| Olomouc | 7 179 511 | 3 742 517 | 35,38 | 27,06 | 28,88 |
| Opava | 6 440 187 | 3 050 034 | 1,54 | 37,35 | 44,35 |
| Orlová | 3 197 484 | 711 763 | 17,44 | 26,97 | 55,30 |
| Ostrava | 6 943 367 | 1 060 101 | 0,00 | 12,67 | 18,98 |
| Pardubice | 6 237 014 | 4 152 886 | 16,90 | 40,72 | 47,62 |
| Písek | 3 938 336 | 1 166 549 | 16,32 | 36,40 | 35,95 |
| Přerov | 3 479 083 | 861 790 | 6,87 | 33,78 | 32,06 |
| Příbram | 5 099 733 | 4 327 804 | 20,68 | 42,86 | 52,61 |
| Strakonice | 4 776 436 | 2 951 855 | 35,40 | 34,19 | 60,01 |
| Tábor | 4 161 657 | 1 963 895 | 11,37 | 78,66 | 74,52 |
| Třebíč | 3 902 239 | 1 770 263 | 24,52 | 28,80 | 36,10 |
| Uherské Hradiště | 3 553 928 | 1 823695 | 40,01 | 33,21 | 51,71 |
| Ústí nad Labem | 6 769 518 | 3 285 486 | 0,00 | 26,64 | 31,58 |
| Vsetín | 3 903 030 | 2 699 363 | 4,08 | 51,80 | 60,67 |
| Znojmo | 3 837 349 | 1 456 110 | 6,69 | 37,29 | 24,65 |
| Total | 192 573 322 | 26 094 467 | 15,12 | 36,49 | 45,43 |

Source: IS Monit7+ as of 31 Mar 2012

CZK/EUR exchange rate: 24.80

Status of implementation of projects under activity 5.2

In the monitored period the number of submitted applications in Intervention area 5.2 increased to the total of 895 projects as against September 2011. The towns in their strategy of IUDP implementation focused at first on the support for regeneration of residential buildings. More demanding projects and projects of long-term nature implemented by towns in the field of revitalisation of public spaces were mostly left by IUDP towns until later. The implementation of this type of projects is only being launched by the towns. In some towns the financially demanding projects in the field of revitalisation of public spaces cannot be implemented in consequence of financial crisis.

Status of implementation of pilot projects

Calls for the submission of projects are currently announced in all the six towns. As of 31 Mar 2012, a total of 36 submitted projects are registered under activity 5.2c). The investment projects supplement the projects on social inclusion financed mostly from OP HRE, Intervention areas 3.2 Support for social integration of members of Roma communities and 5.1 International cooperation (exchange of experience with social inclusion) and Intervention area 3.1b of IOP. Moreover, implemented within the pilot projects are also the projects from the Operational Programme Education for Competitiveness, which fall under Intervention area 1.2 Equal opportunities for children and pupils.

The IOP MA in cooperation with OP HRE endeavours to ensure the maximum possible consistency in the administration of pilot projects and OP HRE projects.

An essential activity in support of pilot projects was the 9th meeting of the Working Group Pilot held on 7 Feb 2012 (for more information see Chapter 4.4.3).

### 3.5.3 Fulfilment of indicators

Table No 36 – Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Achieved value as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 410401 | Number of regenerated immovable cultural monuments | Number | 0 | 70 | 74 | 3 |
| 410402 | Number of newly built or modernised cultural facilities | Number | 0 | 5 | 4 | 0 |
| 330100 Core 39 | Number of projects improving the attractiveness of towns | Number | 0 | 1000 | 787 | 611 |
| 331000 | Number of established Urban Development Funds | Number | 0 | 1 | N/A | N/A |
| 330103 | Number of projects improving the attractiveness of housing in the territory | Number | 0 | 41 | 81 | 81 |
| 330101 | Number of projects improving the conditions of rental houses (residential buildings) | Number | 0 | 950 | 514 | 514 |
| 330102 | Number of pilot projects – support for selected Roma localities | Number | 0 | 7 | 16 | 16 |
| 330400 | Number of projects on creating planning analytical materials of regions | Number | 0 | 10 | 9 | 9 |
| 330401 | Number of assisted projects on creating planning analytical materials of municipalities | Number | 0 | 140 | 170 | 170 |
| 330411 | Number of assisted projects on creating new or updating the existing territorial plans | Number | 0 | 60 | 331 | 300 |
| 330415 | Area of municipalities covered by the planning analytical materials of municipalities | km2 | 0 | 34 800 | 63 398,03 | 63 398,03 |
| 330416 | Area of municipalities covered by the new territorial plan | km2 | 0 | 140 | 8 418,25 | 7 228,82 |

Source: MSC2007 as of 31 Mar 2012

Table No 37 – Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Achieved value as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 410404 | Number of created methodologies in the cultural heritage area | Number | 0 | 20 | 13 | 0 |
| 410411 | Increase in the number of visitors to monuments and cultural facilities | % | 100 | 125 | 152 | 100 |
| 331200 | Number of renovated apartments | Number | 0 | 24 500 | 36 164 | 26 190 |
| 331300 | Area of revitalised territory | m2 | 0 | 4 108 000 | 1 618 100,98 | 1 138 536,60 |
| 331500 | Energy savings in rental houses (residential buildings) | % | 0 | 20 | N/A | 31,6 |
| 330418 | Increase in the area of development areas, development axes and specific areas covered by new territorial plans | % | 0 | 0,18 | N/A | 18,25 |
| 330417 | Increase in the area of the CR which will be covered by planning analytical materials of municipalities | % | 0 | 18,5 | 80,3 | 80,3 |

Source: MSC2007 as of 31 Mar 2012

Chart No 29 -  Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

In the period from 30 Sep 2011 to 31 Mar 2012, in Intervention area 5.1 the commitment of approved projects did not increase in any of the indicators since no new Decisions were issued.  The achieved value went up in indicator No  410401 – Number of regenerated immovable cultural monuments. The indicator was fulfilled by the implemented project National Museum of Photography and Tapestry Workshop – Centre of Indigenous Crafts and Unique Technologies, with the place of implementation in Jindřichův Hradec. The achieved value of the other indicators remained unchanged – i.e. it is identical with their baseline value.

Chart No 30 -  Information on IUDP allocation for Intervention area 5.2

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

In Intervention area 5.2, the lower fulfilment of the MI Area of revitalised territory is brought about especially by later implementation of projects. At the beginning of implementation the top priority was the regeneration of activities focused on reconstruction of residential buildings. Another factor can also be the impact of financial crisis, due to which the towns lack funds necessary for the implementation of large, financially demanding projects. In some cases, funds are transferred between individual supported activities in IUDP. Potential non-fulfilment of the MI at the programme level in the field of revitalisation of territory was offset by the excessive fulfilment of the MI concerning the regeneration of residential buildings. At present, however, the MA cannot confirm this development due to the share of contracted projects. The IOP MA aims to safeguard the conditions for the fulfilment of both the monitoring indicators.

Indicator No 330103  Number of projects improving the attractiveness of housing in the territory has been set out for  41 projects, i.e. the number of towns with IUDP. Since the individual towns divided the projects on revitalisation of public spaces into more projects, the achieved value thus exceeds the original binding value.

Indicator No 331200 Number of renovated apartments currently exceeds the originally planned value primarily because in some projects, that are implemented within one regenerated residential building, the values of MI are calculated for each project separately. In case the individual works on the residential building are distributed to multiple projects, the MI values are summed up separately even though it still concerns one residential building. The MA intends to modify the target value of this MI in the second half of 2012.

In indicator No 331500 Energy savings in residential prefabricated buildings the target value is exceeded due to more energy savings than originally expected in projects on regeneration of residential buildings. Another factor is also the duplicity in adding up the monitoring indicators as in case of indicator No 331200 Number of regenerated apartments. The monitoring indicator No 331500 Energy savings in residential prefabricated buildings will also be modified in the second half of 2012 so that it reflects the actual number of regenerated residential buildings.

Chart No 31 – Comparison of physical and financial progress

Source: IS Monit7+ as of 31 Mar 2012

The explanation of both the bars of individual indicators is given in the introduction to Chapter No 3 Progress at the level of priority axis.

The commitment of approved projects in case of indicators in Intervention area 5.3 in activity a) is identical with the target value. The expenditure of all the projects under activity a) has been certified. The target values of indicator No 330400 has almost been fulfilled in case of projects of regions.

The submitted project applications have reached the forecast target value of the number of projects for the creation of planning analytical materials of regions, one project was withdrawn in the course of administration. In case of projects directed at the creation of planning analytical materials of municipalities with extended powers, the target values of indicators (330401 and 330415) have been exceeded. Since there were merely a total of 204 potential applicants (excluding Prague), the submission of applications for support by a higher number of applicants had not been anticipated. The target value of indicator No 330415 was set out based on the expected value of indicator No 330401. The area was calculated as the area of 140 smallest municipalities with extended powers, but in the end 170 applications submitted by municipalities have been granted support.

All the achieved values of indicators for activity b) as at 31 Mar 2012 exceeded the target values. When setting the indicator No 330411, the calculations were made based on the price of territorial plans that was several times higher, i.e. the price valid at the time of preparation of the Programming Document. The calculations considered the maximum price of CZK 4 million per 1 territorial plan, including the expert opinions, but the average application for support claims CZK 800 thousand only, which resulted in the excess of the target value. When the target value of indicator No 330416 was set out, the calculations were made based on the anticipated value of indicator No 330411. The area was calculated as the area of 60 smallest municipalities with more than 500 inhabitants, which complied with the conditions of the prepared calls for 5.3b).

In indicator No 330418, reported is not the commitment of approved projects, but the achieved value as of 31 Mar 2012. The value of indicator is ascertained by the semi-budgetary organisation of MRD, the Institute for the Territorial Development, which has so far not modified the existing methodology for the calculation in order to ascertain the value of commitment. The achieved value of the indicator many times exceeds the target value due to the reasons stated in indicators No 330411 and 330416, on which it is based.

### 3.5.4 Problems and measures taken

Intervention area 5.1

Archaeological survey in projects – the projects are obliged to conduct an archaeological survey of the site as a precondition for the issuance of a building permit and implementation of the construction. In case of a breach of instructions of the archaeological conservation of monuments (regional department for the conservation of monuments, Institute of Archaeology, etc.), the beneficiary is at risk of legal sanctions which can also result in the suspension of works.

Measures taken: The MoI IB brings the attention of beneficiaries to this obligation and recommends to select the contractor of archaeological surveys prior to the project implementation or shortly after the commencement of implementation. In case of archaeological surveys, it is possible, upon the agreement with the competent authorities, to carry on the construction in other parts concerned by the project so that the deadline of project completion is not endangered.

Quality of activities of implementation teams – in some projects (e.g. after changes in staffing)  lower quality of work performed was recorded.

Measures taken: The MoC IB set out the rules for cutting down the expenditure on the project team in case of poor quality of performed work. The rules for the cuts will be laid down in the revision of the Handbook for Applicants and Beneficiaries in April 2012.

State aid – in Intervention area 5.1 only projects which do not constitute unauthorised state aid are admissible. Compliance of projects with the state aid rules is assessed during the evaluation of project eligibility based on the opinion of an external expert. The risk of any potential prohibited state aid is checked by all the risk analyses (ex-ante, interim, ex-post) of projects.

Measures taken: An external analysis on state aid related matters is conducted in projects implemented under Intervention area 5.1. The analysis shall evaluate whether there is any risk of unauthorised state aid in 17 projects under implementation and, where necessary, it shall propose measures to eliminate such identified risks. The conduct of an analysis was outsourced in 2011, the outputs are expected in the first half of 2012.

Changes (postponements) in the timetables of activities in projects, inaccurate forecasts of absorption

Measures taken: The revision of the Handbooks for Applicants and Beneficiaries with effect from 2 Apr 2012 includes the obligation for the beneficiary to notify the update of the financing plan for future monitoring periods (including needs, sources, budget) before the 15th day of the month following the end of the monitored period.

Intervention area 5.2

Failure to meet the condition of absorption of 25 % of total eligible expenditure of IUDP ensuing from the Agreement on ensuring the implementation of IUDP. The most frequent reason was the low absorption capacity in some towns, which was not correctly assessed by towns during the preparation of IUDP document.

Measures taken: The IOP MA allowed the towns with IUDP to submit individual applications for payment until 31 Dec 2012 instead of the original deadline of 30 Sep 2011. Thanks to that the majority of towns, at risk of failure to meet the conditions for the absorption of allocation, succeeded in submitting the adequate volume of payment requests by the end of 2011. Despite the intensified support by IOP MA, the following towns failed to absorb 25 % of the allocation by the end of 2011: Děčín, Most and Ostrava, to which the ERDF allocation was cut in the form of the Addendum to the Agreement ensuring the implementation of IUDP. The cuts of the allocated amounts were calculated by IOP MA as a difference between the absorbed percentage and the value of absorption stated in the Agreement on ensuring the implementation of IUDP. The total cuts by IOP MA with respect to towns concerned is EUR 2 800 199.

The municipality of Ústí nad Labem due to low absorption capacity asked for the reduction of IUDP allocation. The IOP MA, through Addendum to the Agreement on ensuring the implementation of IUDP decreased the ERDF allocation by EUR 1 548 244.

These funds will be used by IOP MA to cover the CZK/EUR exchange rate reserve. Thus it will be possible to decrease the current exchange rate reserve in towns, which successfully absorb the allocation, beyond the scope of financing plan in IUDP. The IOP MA envisages the decrease of exchange rate reserve in the second half of 2012.

Notwithstanding the individual cases when some towns failed to fully absorb the allocated funds, the failure to absorb the total allocation at the level of Intervention area 5.2 is not at risk.

The tendency of towns with IUDP, that had to cope with financial crisis, is to detour from the originally planned projects of revitalisation of public spaces on the grounds of the lack of their own funds. By doing so, the municipalities also want to satisfy the increased demand for assistance in the area of regeneration of residential buildings that was far higher than at the time of drafting the IUDP of individual towns.

Measures taken: The IOP MA will probably decrease the original number of projects planned for Intervention area 5.2a) in some towns and will allow for their transfer to Intervention area 5.2b), which continues to report adequate absorption capacity. It can be expected that the achieved value of the indicator Area of revitalised territory will be lower than originally planned. The IOP MA envisages that the final value will not differ much from the originally planned value.

Wrongly implemented tenders. In a few cases the projects were rejected during the ex-ante check, or the eligible expenditure of the project is subsequently cut down. In some cases, such phenomenon can jeopardise the fulfilment of the requirement of absorption of IUDP allocation. The highest risk is faced by large projects implemented by towns in the field of revitalisation of public spaces.

Measures taken

The IOP MA offered to individual towns with IUDP to participate in a seminar on public contracts held at the level of individual regions by NCA. Moreover, in the monitored period an information seminar was held for MA and CRD staff on the amendment to Act on public contracts. The matters related to public contracts are regularly covered by the MA and CRD representatives during the seminars with IUDP managers.

Intervention area 5.3

In this intervention area, no major issues occurred, no calls were announced and no projects were received in the monitored period. The approved projects have reached 23 % of the total allocation for this intervention area. The assistance was smoothly reimbursed to beneficiaries.

### 3.5.5 Example of a project

Intervention area 5.1 – National support for utilising the cultural heritage potential

Name of the project, registration number: Terezín – project on revival of historical monuments

(CZ.1.06/5.1.00/01.06156)

Beneficiary: Terezín – town of change, interest association of legal persons

Project funding: total budget CZK 499 336 800,- , of which CZK 424 436 276 SF contribution and CZK 74 900 524 SB contribution

Terezín fortress is an important cultural monument included in the UNESCO World Heritage List. The project aims to liven up the historical premises of the fortress town of Terezín by building a cultural and historical education complex.

Altogether five parts of the premises will be renovated thanks to the assistance and they will be used in the period of sustainability:

- Kavalír II inner parts – Museum of Artillery will be set up, including the individual exhibits, historical commentaries on artillery as well as military equipment will be developed for visitors, seminars on historical and military topics are planned;

- Kavalír II Green roofs – following the renovation, tours of battery positions will be offered, regular live performances on life of troops in Terezín Fortress will be given;

- Retranchement V – the “Centre for the documentation of renovation and use of military systems” and a permanent exhibition of the period guardhouse (commentaries concerning the life of guards, officers and soldiers in the 18th century) will be set up;

- Riding school – at this place an exhibition of the period military camp and life therein will be created, including the historical equipment  and facilities (period kitchen, hospital, crafts), another part will be used for training of period military formations;

- Artillery barracks – development of a museum illustrating the everyday life in the 18th century. Special education and retraining events will be held in reconstructed premises. Another activity is the organisation of seminars and conferences on holocaust.

Intervention area: 5.2 Improving the environment in problematic housing estates

Name of the project, registration number:   Regeneration of a residential building with apartments of special purpose (META);  CZ.1.06/5.2.00/07.06361

Beneficiary: Statutory Town of Kladno

Project funding: total budget CZK 56 240 000,-, of which CZK 19 121 600,-  SF contribution and CZK 3 374 400,-  SB contribution

The project concentrates on an overall regeneration of a “META” residential building with special purpose apartments. The house is used for sheltered housing of persons with reduced mobility and orientation – these persons are therefore the end users of project outputs. The building was constructed as a prefabricated house at the end of 1980s. Its current technical condition and requirements for its use by persons with reduced mobility and orientation require a radical reconstruction.

The project is implemented by the Statutory Town of Kladno, which also owns and runs the “META” building.

Through this project the applicant wanted to improve the quality of housing of persons with reduced mobility and orientation. It will be achieved especially by thermal insulation of the building envelope, replacement of windows and doors, and reconstruction of enclosed balconies.

Before the project implementation

After the project implementation

Intervention area 5.3 – Modernisation and development of systems for creating territorial policies

Name of the project, registration number: Territorial plan of the municipality of Frenštát pod Radhoštěm,  CZ.1.06/5.3.00/08.06336

Beneficiary: Town of Frenštát pod Radhoštěm

Project funding: total budget CZK 552 000,-, of which CZK 469 200,- SF contribution and CZK 82 800,- SB contribution

As a result of development of the territory and amendment to legislation and based on the requirements of natural and legal persons, the Council of the town of Frenštát pod Radhoštěm decided to have a new Territorial plan of Frenštát pod Radhoštěm made.

The territorial plan is elaborated for the whole administrative territory of the town of Frenštát pod Radhoštěm, which forms the cadastral territory of Frenštát pod Radhoštěm with the area of 1143 ha.

The project aims to elaborate a proposal for the Territorial plan of Frenštát pod Radhoštěm by an expert designer. A component part of the project is the evaluation of impacts of the territorial plan on sustainable development of the territory, including the SEA of the territorial plan.

Expenditure of the project has been certified.

An indicative section of the main drawing of the TP

## 3.6 Priority axis 6a, 6b – Technical assistance

### 3.6.1 Focus of priority axes/intervention areas

The priority axes comprise activities which are inseparable as to their geographical scope and which have an impact on the whole territory of the CR. Their content is therefore identical, regardless their classification by objective. Priority axes 6a and 6b focus on the support of effective management of the Integrated Operational Programme throughout the programming period 2007 – 2013.

The Priority axis covers the Convergence objective (6a) and the Regional Competitiveness and Employment objective (6b).

Specific goals:

- Reinforcing administrative capacities involved in programme implementation at the level of the Managing Authority and Intermediate Bodies,

- Ensuring effective management, monitoring, evaluation, controls and absorption capacity in implementing the operational programme at the level of the Managing Authority and Intermediate Bodies.

Beneficiaries:

- Managing Authority,

- Intermediate Bodies.

### 3.6.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention areas 6.1a and 6.1b progress has been reported in all the monitored stages of project implementation since the previous MC meeting. 3 project applications were submitted, thus as of 31 Mar 2012 a total of 31 project applications in the amount of EUR 41.05 million were submitted. The volume of approved projects increased from EUR 32.22 million to EUR 39.73 million, 8 projects were approved. The beneficiaries were paid a total of EUR 12.68 million compared to the previous MC when EUR 11.41 million was reimbursed. As of 31 Mar 2012, 38.9 % of the allocation for these intervention areas was reimbursed. The least progress was exhibited  in the aggregate payment claims accounted for by the PCA, in which an increase by EUR 0.53 million is reported. The total amount included in aggregate payment claims is EUR 11.93 million. Expenditure in the amount of EUR 11.23 million, representing 34.6 % of the allocation was certified.

Table No 38 -  Cumulative progress at the level of Intervention area 6.1a and 6.1b (in mil. CZK/EUR)

| 6.1a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 793,88 | 31,97 | 31 | 998,79 | 125,8% | 40,31 | 31 | 966,49 | 121,7% | 39,01 | 308,61 | 38,9% | 12,45 | 292,28 | 36,8% | 11,71 | 274,96 | 34,6% | 11,03 |
| Previous MC | 785,37 | 31,97 | 28 | 896,50 | 114,2% | 36,50 | 23 | 777,23 | 99,0% | 31,64 | 274,99 | 35,0% | 11,20 | 274,96 | 35,0% | 11,19 | 197,55 | 25,2% | 7,83 |
| 6.1b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 14,59 | 0,59 | 0 | 18,36 | 125,8% | 0,74 | 0 | 17,77 | 121,8% | 0,72 | 5,68 | 38,9% | 0,23 | 5,38 | 36,8% | 0,22 | 5,06 | 34,7% | 0,20 |
| Previous MC | 14,44 | 0,59 | 0 | 16,48 | 114,1% | 0,67 | 0 | 14,29 | 99,0% | 0,58 | 5,06 | 35,0% | 0,21 | 5,06 | 35,0% | 0,21 | 3,63 | 25,2% | 0,14 |

In Intervention areas 6.2a and 6b, 51 project applications in the amount of EUR 14.63 million were submitted. Decision was issued for 48 projects amounting to EUR 14.63 million, the volume of which represents 63.2 % of the allocation. The volume of funds reimbursed to beneficiaries increased from EUR 12.03 million to EUR 13.06 million, which equals 13.9 % of the allocation. Slightly less progress was achieved in the volume of funds included in aggregate payment claims, which still accounts for 13.1 % of the allocation, representing EUR 2.69 million. The certified expenditure reached EUR 2.65 million, which equals 13.0 % of the allocation for the intervention areas.

Table No 39 -  Cumulative progress at the level of Intervention area 6.2a and 6.2b (in mil. CZK/EUR)

| 6.2a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 521,37 | 21,01 | 51 | 369,31 | 70,8% | 14,90 | 48 | 329,47 | 63,2% | 13,30 | 72,65 | 13,9% | 2,93 | 68,55 | 13,1% | 2,74 | 67,69 | 13,0% | 2,70 |
| Previous MC | 516,10 | 21,01 | 48 | 364,30 | 70,6% | 14,83 | 40 | 301,18 | 58,4% | 12,26 | 68,55 | 13,3% | 2,79 | 67,69 | 13,1% | 2,76 | 60,63 | 11,7% | 2,41 |
| 6.2b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 9,59 | 0,39 | 0 | 6,79 | 70,8% | 0,27 | 0 | 6,06 | 63,2% | 0,24 | 1,34 | 13,9% | 0,05 | 1,26 | 13,2% | 0,05 | 1,25 | 13,0% | 0,05 |
| Previous MC | 9,49 | 0,39 | 0 | 6,70 | 70,6% | 0,27 | 0 | 5,54 | 58,4% | 0,23 | 1,26 | 13,3% | 0,05 | 1,25 | 13,1% | 0,05 | 1,12 | 11,8% | 0,04 |

The following is applicable to all the tables above:

Source: Current MC – MSC2007 as of 4 Apr 2012

Previous MC – MSC2007+ as of 4 Oct 2011

CZK/EUR exchange rate: Current MC – 24.778

Previous MC (“a” column) – 24.563

Source of funding – public funds total

Overview of ongoing calls

In priority axes 6a and 6b two calls were under way in the monitored period.  A total of 58 project applications in the amount of EUR 46.13 million have been submitted and 56 projects in the amount of EUR 44.18 million have been approved.

In Intervention areas 6.1a and 6.1b one continuous call was under way with the allocation of EUR 32.93 million. Under this call 31 project applications in the amount of EUR 41.05 million have been submitted. All the projects in the amount of EUR 39.72 million have been approved. One project has been withdrawn following the issuance of the Decision on providing a grant, the amount of approved funds minus the project withdrawn is EUR 29.82 million.

In Intervention areas 6.2a and 6.2b one continuous call was under way with the allocation of EUR 12.91 million. 27 project applications in the amount of EUR 5.08 million have been submitted and 25 projects in the amount of EUR 4.46 million have been approved. One project has been withdrawn following the issuance of the Decision on providing a grant, the amount of approved funds covered by projects that are still under implementation has thus decreased to EUR 24.40 million.

Table No 40 – Overview of ongoing and announced calls in the period from 1 Oct 2011 to 31 Mar 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Interven-tion area/activi-ty | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 2. | 01 | 5.6.2008 | 30.9.2015 | continuous | 6.1 a)-e) | 32 337 528 | 31 | 40 309 348 | 31 | 39 005 808 |
|  |  |  |  |  |  | 594 585 |  | 741 162 |  | 717 194 |
|  |  |  |  | Call total | 32 932 113 | 31 | 41 050 510 | 31 | 39 723 002 |
| 35. | 10 | 27.9.2010 |  | continuous | 6.2 a)-g) | 12 681 510 | 27 | 4 984 571 | 25 | 4 378 886 |
|  |  |  |  |  |  | 233 173 |  | 91 651 |  | 80 514 |
|  |  |  |  | Call total | 12 914 682 | 27 | 5 076 222 | 25 | 4 459 400 |
| IA 6.1 total |  |  |  |  |  | 32 932 113 | 31 | 41 050 510 | 31 | 39 723 002 |
| IA 6.2 total |  |  |  |  |  | 12 914 682 | 27 | 5 076 222 | 25 | 4 459 400 |
| CONV total |  |  |  | 45 019 037 | 58 | 45 293 919 | 56 | 43 384 694 |
| RCE total |  |  |  |  | 827 758 | 0 | 832 812 | 0 | 797 707 |
| PA 6 total |  |  |  |  | 45 846 795 | 58 | 46 126 731 | 56 | 44 182 402 |

Source: IS Monit7+ as of 3 Apr 2012

CZK/EUR exchange rate: 24.778

Source of funding – public funds total

### 3.6.3 Fulfilment of indicators

The achieved value as of 31 Mar 2012 and commitments of approved projects in Intervention areas 6.1 and 6.2 correspond with the rate of absorption of funds of IOP TA projects.  They cannot be compared with the target values since the target values were set based on the original methodology for IOP TA indicators and the commitments of approved projects in IOP TA were set (changed in the already implemented projects) in line with the revised methodological sheets of IOP TA indicators of 2009.

Table No 41 – Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value CONV | Target value RCE | Commitment of approved projects CONV | Commitment of approved projects RCE | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 480500 | Number of elaborated studies and reports (incl. evaluation ones) | Number | 0 | 13 | 1 | 1 003 | 24 | 619 |
| 480700 | Number of developed methodological and technical and information materials | Number | 0 | 82 | 2 | 226 | 18 | 118 |
| 481100 | Number of held training courses, seminars, workshops, conferences | Number | 0 | 69 | 1 | 288 | 6 | 126 |
| 481600 | Number of persons who attended the educational courses - total | Number | 0 | 1372 | 28 | 9 836 | 1 100 | 5 692 |
| 480800 | Implemented cooperation with mass media and communication with the general public | Number | 0 | 29 | 1 | 85 | 1 | 59 |
| 480900 | Number of organised information and publicity activities | Number | 0 | 30 | 2 | 175 | 45 | 82 |
| 483100 | Number of full-time employees of the implementation structure | Number | 0 | 89 | 1 | 387,11 | 6,99 | 244,24 |

Source: MSC2007 as of 31 Mar 2012

Table No 42 – Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value CONV | Target value RCE | Commitment of approved projects CONV | Commitment of approved projects RCE | Value achieved as of 31 Mar 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 481900 | Number of trained persons – total | Number | 0 | 1 078 | 22 | 2 774 | 30 | 1 742 |
| 480300 | Number of meetings of (monitoring, advisory and management) committees | Number | 0 | 13 | 1 | 14,73 | 0,27 | 8 |
| 482500 | Number of performed controls | Number | 0 | 1 323 | 27 | 7 443,14 | 143,38 | 5 304 |

Source: MSC2007 as of 31 Mar 2012

### 3.6.4 Problems and measures taken

Risk of ineligible activities and expenditure. In the monitored period the IOP MA focused on monitoring the absorption of Technical assistance funds  in order to achieve the maximum degree of eligibility of expenditure in terms of economy, efficiency and effectiveness.

Measures taken

The IOP MA decided to introduce stricter rules applicable prior to the submission of project applications to the Selection Committee for IOP TA projects and for  the approval of new activities in IOP TA projects. The revision of the Handbook for Applicants and Beneficiaries for Priority Axes 6a and 6b effective from 1 September 2011 enshrines the principle that the expenditure on activities covered by IOP TA, not approved in writing beforehand by the IOP MA, will be ineligible. These matters were explained in detail to beneficiaries at the meeting of the WG for TA on 20 September 2011. The submitted project applications of IBs, however, failed to observe the rules of eligibility of expenditure even after the meeting of the WG for IOP TA. Several rounds of comments were held before the IOP MA agreed with their submission to the Selection Committee for IOP TA projects (SC for IOP TA) for approval.  The meetings of the SC for IOP TA in the monitored period were held on 1 Dec 2011 (4 project applications were approved: 3 of MRD CR and 1 of CRD CR) and on 20 Mar 2012 (4 project applications were approved – 3 of MoC CR and 1 of MRD CR).

Problems with submitted project applications still prevail. The IOP MA intensified the regular consultations with competent employees of IBs.

Problems faced in the administration of IOP TA projects. In the monitored period, the most significant problem faced in the administration of IOP TA projects was a large number of public contracts common for more projects, evidencing the expenditure, labour costs in particular, assignment of expenditure to the respective contract or project.

Measures taken:  regular consultations  at the CRD CR branch and with IOP MA staff, meetings of WG for IOP TA.

# 4 ADMINISTRATION OF THE PROGRAMME

## 4.1 Information on the Conduct and Results of Audits and Financial Controls

Audit of the European Commission

Audit of the European Commission carried out at the Audit Authority

In the Report on Implementation of IOP for the period from 1 Apr 2011 to 30 Sep 2011 the IOP MA informed about the audit carried out by the Directorate General for Regional Policy of the European Commission on 12 – 16 September 2011 under the No 2011/CZ/REGIO/J4/870/8. The auditee was the Audit Authority, or the Authorised Audit Entity. The IOP MA, IBs and selected beneficiaries cooperated with the EC auditors during the audit. As of 31 Mar 2012, the IOP MA did not receive any information on potential findings related to the IOP. On 27 Feb 2012, a draft interim report on the audit concerning the Integrated Operational Programme was received by the Ministry of Finance and on 28 Mar 2012 it was received by the IOP Managing Authority.

Considered by the auditors to be the main preliminary findings concerning the IOP MA are the system of reporting and addressing of irregularities and the set out system of waiver of penalties for the breach of budgetary discipline. They also point at the fact that in 7 of 8 projects selected in the sample by the audit mission, a finding with an impact on eligibility of expenditure was identified by the Authorised Audit Entity. The auditors believe that this fact indicates that the errors were not discovered during the 1st stage controls conducted by IOP MA, or IB. Based on this conclusion, the EC auditors recommended to adopt measures to improve the control systems of IOP MA and IB.

The referred to findings in the draft audit report are of preliminary nature, the final report on the conducted audit will be drawn up once the report is commented upon and the comments are settled by the EC.

Audit of the European Commission at the Paying and Certifying Authority (PCA)

The audit commenced in November 2011 at the Paying and Certifying Authority focuses on verifying the keeping accounts of amounts that shall be recovered, amounts withdrawn on the grounds of cancelling all or part of the contribution to an operation (Article 61 (f), Article 70 of the General Regulation and Article 20 (2) of the Implementing Regulation). The audit concentrates primarily on verification of processes at the level of PCA. The EC also reserved the right to conduct verifications at the level of concerned Managing Authorities, among which is the IOP MA. The IOP MA provided the auditors with information required by Annex No 3 to the Implementing Regulation.

Controls conducted by the Paying and Certifying Authority

In the monitored period, no controls were conducted by the Paying and Certifying Authority.

Controls conducted by the Supreme Audit Office

SAC control at the Ministry of Health

In December 2011, a control of SAC was launched at the Ministry of Health of the CR, covering  all the activities of the ministry. The SAC inspectors required information concerning the IOP Technical assistance projects. The SAC control was not completed as of 31 Mar 2012. It is expected to be completed in the middle of 2012.

SAC control at the Ministry for Regional Development

In January 2012, the Supreme Audit Office commenced a control at the Ministry for Regional Development of the CR with the view to verify whether the auditee provides funds earmarked for the Integrated Operational Programme for 2007–2013 in compliance with legislation and the set out requirements, in an efficient and economic manner. The control was not completed as of 31 Mar 2012.

System audit conducted by the Authorised Audit Entity

Audit of the system of implementation for the Integrated Operational Programme No 28/2011/AAE

The audit of IOP implementation entities was launched in September 2011. The subject matter of the audit was to verify the effective functioning of the management and control system of IOP, with focus on changes in the descriptions of management and control systems (MCS) binding documentation, verification of quality and adequacy of corrective measures taken to address the risks and findings defined in the framework of system audits No 4/08/AAE, 7/09/AAE, 10/09/AAE and 17/10/AAE and to verify the functioning of key requirements on the IOP implementation system. The audit also aimed to verify the design and effectiveness of control systems in the field of public procurement controls and the control of keeping separate accounts of project transactions. Moreover, the audit examined the design of the system for addressing irregularities and analysed the absorption of financial allocation.

The audit was commenced at the IOP Managing Authority and all the intermediate bodies (Ministry of Health of the CR, Ministry of Culture of the CR, Ministry of Interior of the CR, Ministry of Labour and Social Affairs and the Centre for Regional Development of the CR). The audit was completed in January 2012 by issuance of the final audit report.

The following findings are considered by the auditors as the main findings identified at IOP MA

- Insufficient separation of incompatible functions in the performance of preliminary control in projects under Priority axis 6 – Technical assistance, failure to prevent the conflict of interest, insufficient provision of preliminary controls in IOP TA projects. The auditors recommended to IOP MA to guarantee effective conduct of preliminary control in IOP TA projects, the performance of which will not affect the independence of administrators of controls.  The auditors also recommended to ensure effective separation of incompatible functions throughout the process of administration of IOP TA projects. The IOP MA accepted these recommendations and undertook to modify the processes and procedures followed in IOP MA controls of IOP TA projects within the revision of IOP MA OM that is currently under way.

- Low effectiveness of the performance of tasks delegated by the IOP Managing Authority to the Intermediate Bodies of the Ministry of Labour and Social Affairs and the Centre for Regional Development of the CR. The auditors recommended to the IOP MA to set out administrative and approval procedures for the MoLSA IB and CRD IB  that would smoothly come after one another and thus prevent any delays in the administration of projects. The auditors also recommended  to the IOP MA to focus on quality and consistency of administrative and approval procedures spread among the two independent IBs in the framework of controls and verifications of the performance of delegated activities. The IOP MA deals with the cooperation between these two IBs at regular meetings of IOP MA with the IB directors and these matters are also verified during controls of delegated activities at these IBs. There will also be an update of the Handbook of work procedures of MoLSA and the Methodological Guideline No 18 Programmes of the EU-IOP for activities delegated to CRD in the Intervention area 3.1 and 3.3 that is now under revision.

At some IOP Intermediate Bodies the auditors identified the following findings with medium materiality.

- IB of the Ministry of Culture -  findings consisting in the ineffectiveness of verification of the process of award and implementation of public contracts. The auditors recommended to the MoC CR to conduct an audit of a representative sample of projects with the view to identify any other potential deficiencies in the system of evaluation of public contracts. The MoC CR did not accept this recommendation stating that it currently conducts a control of 100 % of public contracts awarded by 31 Dec 2010. The updated version 1.2 of MoC IB OM of 8 Aug 2011 specified the procedures of controls of public contracts and updated the checklists. In August 2011, the e-KOZA information system, designed for the administration and control of public contracts by beneficiaries, was put into operation.

- IB of the Ministry of Labour and Social Affairs – findings consisting in inadequately long time interval between the receipt of the primary application to the issuance of the Decision on providing a grant. The auditors recommended to MoLSA to analyse the reasons of such protractions in administration of projects and based on that to modify the duration of administration and processing of the application until the stage of issuance of the Decision in order to prevent any negative impact on administrative and approval procedures. The MoLSA accepted this recommendation given by the auditors to this finding to a certain degree only and undertook to analyse the reasons behind the protractions in the administration of projects.

At the other Intermediate Bodies only the findings of low materiality were identified.

Audits on operations conducted by the Authorised Audit Entity

Audit on IOP operations No 23/2011/AAE

The audit on operation 23/2011/AAE was conducted in 29 projects in Intervention areas 1.1, 2.1, 3.2, 5.1, 5.3 and 6.1 with already certified expenditure. The audits on operations were commenced from January to June 2011 and concluded in the period May to November 2011. As at 29 Nov 2011, the IOP Managing Authority received copies of all the reports from audit on operations No 23/2011/AAE.

Areas with the highest frequency of mistakes and the largest volume of ineligible expenditure,  regardless the intervention area, are mainly the following:

- public procurement procedures

- spending of public funds in keeping with the 3 E principles (effectiveness, economy, efficiency)

The audits on operations conducted by AAE revealed that the highest error rate (approximately 36.56 %) was identified in Intervention area 1.1, mainly due to errors in the implementation of public procurement procedures. According to the AAE finding, the contracting entity included in the contract documentation an unjustified requirement for the submission of ISO standard certification in the framework of technical qualification requirements and it failed to produce the output from the public contract delivery and wrongfully used negotiated procedure with publication. In other audited projects, the tenders/public procurement procedures lacked certain elements of transparency. There were cases in which the IOP MA disagrees with the quantification of ineligible expenditure amounting to 100% of the contract value.

In Intervention area 2.1 – CzechPOINT type projects – the conducted audits on operations identified the error rate of 15.67 %. The most frequent problems consisted in the non-compliance with the principle of non-discrimination, transparency and equal treatment in the implementation of small-scale public contracts and in the non-compliance with the economy principle. The IOP MA disagrees with the AAE findings related to the award of small- scale public contracts since the value of contracts is below CZK 100 thousand, the IOP MA believes that with respect to the proportionality principle the set out procedures for the award of small-scale public contracts were adequate.

The largest number of projects and the volume of expenditure were audited in Intervention area 3.2 with the final error rate of 10.21 %. The conducted audits on operations of AAE most frequently identified two findings having an impact on eligibility of expenditure.

- Non-compliance with the adequacy principle in prices of selected devices and equipment

The AAE auditors worded these findings at all the relevant beneficiaries under Activity 3.2a) based on a single qualified estimate of an external expert. As a result of this assessment by a single expert, the findings were identified that the purchase price of devices and equipment was inadequate compared to the average prices of similar types of devices and equipment available in the territory of the CR or abroad in the given period of time. In many of these cases the AAE auditors quantified ineligible expenditure in consequence of non-compliance with the principle of economy, effectiveness and efficiency in spending public funds as defined in Act No 320/2001 Coll., on financial control. The IOP MA believes that such a finding is insufficiently grounded since the AAE auditors examined only the adequacy of prices, i.e. the principle of economy. Although the auditors claim that the principle of efficiency was violated, no audit on operations concluded that the devices and equipment were used inefficiently or ineffectively. When assessing the applications, the Ministry of Health of the CR puts stress on the economy of spent public funds and to some extent also on efficiency, which was set by the MoH with the use of technical specification of devices and equipment in the Standards of fit-out of national networks (Standards). The Standards specified the devices that can be purchased under Activity 3.2a).

At the MoH, the assessment of the terms of reference and prices of devices is outsourced to independent and specialised experts. Concurrently, the IOP MA, based on its own control of delegated activities, arrived at the conclusion that the control system effective at the time of administration of projects from the 5th call for Intervention area 3.2 of IOP comprised a number of improvements, especially in the field of public procurement control, where checklists for the control of public contracts had been extended and standardised, and also procedures for ex-ante risk analysis had been modified. In the course of the following calls, the MoH introduced  additional measures, particularly with respect to the engagement of more external experts in the process of evaluation and control. Therefore, the final determination of common prices is not an outcome of a single opinion of an external expert only, as was the case of AAE during the audit on operations, but is a result of a number of consecutive processes. For this reason the IOP MA cannot accept the amount of ineligible expenditure quantified by the AAE in individual projects based solely on a single qualified estimate, with no account taken of other aspects.

- Non-compliance with the principle of economy, effectiveness and efficiency in spending funds

on management and monitoring of projects

The IOP MA agrees with AAE that necessary for proving the eligibility of expenditure is  the documenting its physical and temporal context. Nonetheless, in a number of cases the IOP MA cannot agree with the level of detail required by the AAE from beneficiaries in evidencing the declared activities, which is beyond the requirements for documenting the eligibility of expenditure. Pursuant to Council Regulation (EC) No 1083/2006, the expenditure shall be inter alia identifiable, demonstrable and verifiable by the received accounting documents. The expenditure on the provision of services in the field of project management and monitoring is supported by the declaration of activities of individual employees, based on which the efficiency of expenditure or the connection of a given activity to the project, is proven. The supplier of these services was selected by the beneficiary in a duly conducted tender. If the beneficiary, based on a tender, entered with the supplier into a contract for the provision of services at prices not considered common at the given time and place by the AAE, he must have also made a mistake in the process of selecting the supplier - e.g. by a wrongly set foreseen value, inappropriately set qualification parameters, etc. Such errors in selection of suppliers were not identified by the AAE.

The IOP MA also questions the AAE procedures applied to quantification of error rate of ineligible expenditure and the number of hours, which the AAE considers adequate with respect to the scope and complexity of activities. In some cases, the AAE quantifies the error rate based on the hourly rate of CZK 850, which is considered by AAE a common price across the CR, without any justification of the way of calculation of this hourly rate. In other cases, on the contrary, the amount of ineligible expenditure is quantified based on the hourly rate given in the contract concluded with the service supplier.

In Intervention area 3.4, one project was audited, with no impact on eligibility of expenditure.

Of three audited projects under Intervention area 5.1, a suspected irregularity was identified in two projects with the total error rate of 14.57 %. According to AAE, the tenderers in the conducted public procurement procedures failed to prove the meeting of qualification requirements in accordance with Act No 137/2006 Coll., on public contracts.  The IOP MA disagrees with this finding since the contracting entity proceeded in line with the Act on public contracts and procedures valid for the selected type of public procurement procedure. With respect to one AAE finding, the IOP MA disagrees with the amount of quantified ineligible expenditure.

In Intervention area 5.3, two projects were audited, in which no finding with an impact on eligibility of expenditure was discovered.

In both the audited projects under Intervention area 6.1, the auditors identified a suspected irregularity  (the total error rate for the given Intervention area is 0.64 %). In one project, the AAE identified the finding consisting in the failure to keep separate accounts for all transactions related to the operations. The IOP MA disagrees with this finding.

All suspected irregularities were notified through MSC2007 to the local contact point of AFCOS.  The suspected irregularities are in dependence on its nature always notified to the competent authority – to the Tax Office with geographic and subject matter jurisdiction in case of suspected breach of budgetary discipline and to the Office for the Protection of Competition in case of suspected violation of Act on public contracts. In 3 projects the investigation of the Tax Office was completed, it did not confirm the AAE findings and the irregularities will be settled as unconfirmed. Controls of Tax Offices or OPC  were also completed in other 4 projects, during which the additional 6 findings detected by AAE were not confirmed. In these projects, more controls are under way or other findings are still investigated, which is why these suspected irregularities are still pending.

Audit on IOP operations No 31/2012/AAE

The audit on IOP operations No 31/2012/AAE was commenced on a sample of projects in February 2012. It focuses on projects submitted under all intervention areas, except for Intervention areas 3.1 and 3.3. The auditors intend to control a total of 59 projects throughout this audit. The audit aims to verify the eligibility of expenditure certified in 2011, including the verification of the observance of conditions of the Decision on providing a grant to projects implemented under IOP.  So far the audits have been commenced in projects under Intervention areas 3.2, 5.2 and 6.1. The final reports are envisaged to be submitted starting with September 2012.

Controls by the Managing Authority

Controls of delegated activities

In the monitored period, controls of delegated activities were under way, commenced in the previous period, with focus on the verification of compliance of activities performed by the IBs with procedures set out in the IOP Operational Manual, IB manuals and Handbooks for Applicants and Beneficiaries, namely during the control of eligibility, control of formal requisites, evaluation of projects, ex-ante risk analysis and ex-ante control of projects and administration of applications for payment. In the framework of these controls, also verified was the observance of procedures for entering data in IS Monit7+. The focal point of controls were the controls of administrative nature or monitoring visits, which constitute a more flexible tool for early imposition of corrective measures, major stress was also put on time-consuming on-the-spot public administration checks.

In the period from 1 Oct 2011 to 31 Mar 2012, the IOP MA commenced 18 controls of Intermediate Bodies at the CRD, MoI, MoLSA, MoC and MoH. An overview of all the controls, their status and results is given in the attached table. In the monitored period, of 18 commenced controls 7 controls were completed and in 1 control a corrective measure was imposed. In the monitored period the total of 21 controls of delegated activities commenced in the previous year were completed, of which 13 controls were without a finding, in 1 control a corrective measure was imposed and 7 controls were with a negative finding. These findings mostly consisted in discrepancies between the data in IS Monit 7+ and the reality or in the failure to meet the deadlines for examinations of irregularities.

No serious systemic deficiencies were identified during these controls. In controls, during which significant findings had been identified, corrective measures were imposed. Where corrective measures are imposed, the IOP MA continuously monitors their fulfilment. Material findings were identified especially at the Intermediate Body of the Ministry of Interior. The MoI failed to elaborate detailed plans of controls, failed to conduct on-the-spot checks of all the projects, which according to the verified risk analyses were to be included in the sample and it also failed to monitor the amount of ineligible expenditure during the on-the-spot checks in the defined sample of projects/expenditure. The evaluations of control activities were not done by the set out deadlines, the supporting documents were not forwarded to the IOP MA in time. The IOP MA imposed upon the MoI corrective measures and monitors and evaluates their fulfilment. Findings of other conducted delegated activities are stated in Table No 43.

With respect to the error rate identified during the controls of delegated activities and other control authorities, the IOP MA identified the risk of inadequate number of checks of delegated activities, which is brought about by the IOP MA understaffing. As a corrective measure conducive to the reduction of this risk the IOP MA commenced public procurement procedure for the selection of an external supplier, who will expand the control teams of IOP MA and thus will increase the number of controls. It will support the conduct of controls and certainly not substitute the controls conducted by IOP MA. The plan of IOP MA controls for 2012 comprises an increased number of controls of delegated activities and it specifies the risks at each IB, on which the controls of delegated activities shall focus in 2012.

Table No 43 – Summary of checks of delegated activities at IBs conducted in the period from 1 Oct 2012 to 31 Mar 2012.

| Or-der | Number of the check | Date of the check | Name of the check | Type of the check | Description of findings | Status of the check |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 53/2011 | 14.10.2011 | Control of delegated activities at MoI – administration of applications for payment | Administrative check | 1) Finding in project CZ.1.06/1.1.00/07.06410: The deadline for the Final evaluation of the action shall be after the deadline for project implementation. This rule is not observed in case of the Letter of the SFD director of 7 Oct 2011. 2) Finding in project CZ.1.06/1.1.00/07.06410: In letter concerning the acceptance of changes of 29 Oct 2010 and 28 Dec 2010 the beneficiary was not invited to sign the conditions and the conditions were not attached. The SFD violated the MIP version 1.3, Chapter 21.3.10. Approved substantial changes were incorporated in the letter of SFD director of 7 Oct 2011.This error cannot be remedied by the subsequent measure. 3) Finding in project CZ.1.06/1.1.00/07.06410: The list of invoices to the application for payment 02/06410 stated a higher amount of labour costs than is the value stated in "Recapitulation of labour costs" (by CZK 2 271.74-). The MoI failed to conduct sufficient control of the Monitoring Report and the Application for Payment in line with point 24.3.8 of MIP (version 1.4) and with Chapter B.3.1 of IOP OM (version 1.3).The deficiency was removed in the course of the control. | Completed - negative (with finding) |
| 2. | 67/2011/I | 10.11.2011 | Administrative public administration check – revision of CRD opinion | Ex-ante administrative public administration check | - | Completed - positive (no finding) |
| 3. | 62/2011/I | 11.11.2011 | Control of delegated activities - CRD CR | On-the-spot check |  | Commen-ced |
| 4. | 65/2011/I | 14.11.2011 | Control of delegated activities - MoI | On-the-spot check | The MoI failed to elaborate detailed plans of controls, to update the annual plan of controls as of 30 Jun 2011 and to hand over the updated annual plan of controls to the IOP MA 10 days following its approval at the latest. The semi-annual evaluation of the performance of checks failed to refer to the percentage of projects/ expenditure covered by the on-the-spot checks. Moreover, the MoI did not monitor the amount of ineligible expenditure during the on-the-spot checks in relation to the set out sample of projects to be checked. In majority of checks the MoI does not enter the volume of checked expenditure in IS Monit7+. This value is pivotal for verifying and monitoring whether the required size of the sample based on the method for selection of projects for on-the-spot checks was observed. The MoI failed to conduct on-the-spot checks in all projects that should have been included in the sample based on the risk analyses conducted in line with the IOP MIP version 1.3. All selected projects included in the sample for on-the-spot checks showed the risks in line with the conducted risk analyses. | Corrective measure imposed |
| 5. | 66/2011/I | 15.11.2011 | Control of delegated activities – MoH | On-the-spot check | Data in IS Monit7+ is inconsistent with reality. A deadline was set to correct the situation. | Completed - negative (with finding) |
| 6. | 64/2011/I | 16.11.2011 | Control of delegated activities – MoLSA | On-the-spot check | - | Completed - positive (no finding) |
| 7. | 63/2011/I | 23.11.2011 | Control of delegated activities – MoC | On-the-spot check |  | Commen-ced |
| 8. | 70/2011/I | 24.11.2011 | Control of delegated activities of MoC – administration of applications for payment | Administrative check | In the course of the check, documents were missing (absence of complete separate accounts in application 07/06156) and there was discrepancy in amounts in F01 form in application 10/05498. These deficiencies were rectified by MoC CR staff immediately during the check by provision of the missing documents and correction of data in IS Monit7+ and in F01 form. | Completed - positive (no finding) |
| 9. | 69/2011/I | 05.12.2011 | Administrative public administration check - revision of results of controls of applications for payment – CRD | Ex-ante administrative public administration check |  | Commen-ced |
| 10. | 4/2012/I | 04.01.2012 | Administrative check SVJ (Association of housing units owners) Heyrovského – IUDP | Administrative check |  | Commen-ced |
| 11. | 2/2012/I | 11.01.2012 | Monitoring visit Ostrava – IUDP | Interim monitoring visit |  | Commen-ced |
| 12. | 5/2012/I | 31.01.2012 | Revision of the control activity of MoI CR IB of all public procurement procedures/ten-ders | On-the-spot check |  | Commen-ced |
| 13. | 3/2012/I | 01.02.2012 | Monitoring visit Brno – IUDP | Interim monitoring visit |  | Commen-ced |
| 14. | 6/2012/I | 10.02.2012 | Administrative public administration check of public procurement procedure – CRD. | Administrative check |  | Commen-ced |
| 15. | 7/2012/I | 10.02.2012 | Administrative public administration check of public procurement procedure – CRD. | Administrative check | The check did not identify any deficiencies at CRD, it confirmed its conclusions, i.e. error made by the beneficiary, namely the failure to observe the procedures laid down in the Handbook for Applicants and Beneficiaries version 05, Act No 137/2006 Coll., binding procedures for the award of public contracts in line with the annex to the HAB. | Completed - positive (no finding) |
| 16. | 8/2012/I | 23.02.2012 | Control of delegated activities at MoH - administration of applications for payment | Administrative check |  | Commen-ced |
| 17. | 11/2012/I | 07.03.2012 | Monitoring visit Kladno | Interim monitoring visit |  | Commen-ced |
| 18. | 9/2012/I | 28.03.2012 | Control of delegated activities at MoI – administration of applications for payment | Administrative check |  | Commen-ced |

Checks (verifications) of projects of individual Intermediate Bodies

Checks on projects are the responsibility of the MA who delegates the conduct of checks, with the exception of a part of Technical Assistance projects, to the individual Intermediate Bodies, see the table called Overview of entities conducting the checks on projects. The IOP MA is entitled to carry out its own checks on any of the projects during all stages of project administration. The IOP MA also uses the assistance of experts during the checks of physical implementation of projects under the NCA project for support of the conduct of controls. In accordance with Article 13 of Commission Regulation (EC) No 1828/2006 the verifications shall cover administrative, financial, technical and physical aspects of operations, as appropriate. The IOP Operational Manual lays down the minimum requirements for all the Intermediate Bodies concerning the procedures during the checks on projects and the minimum scope of the sample for checks pursuant to Article 13 of Commission Regulation (EC) No 1828/2006. The Intermediate Bodies in line with the IOP Operational Manual have elaborated their own detailed procedures for the conduct of checks, including the set methodology for selection of a sample of projects for on-the-spot checks, in case the on-the-spot check is not conducted in 100 % of projects.

Table No 44 -  Overview of entities conducting checks of projects

| Intervention area | Ex-ante check | Interim check | Ex-post check |
| --- | --- | --- | --- |
|  | administrative | on-the-spot | administrative | on-the-spot | administrative | on-the-spot |
| 1.1 | MoI | MoI | MoI | MoI | MoI | MoI |
| 2.1 | CRD, MoI | MoI | CRD | CRD, MoI | CRD | CRD, MoI |
| 3.1 | CRD, MoLSA | MoLSA | CRD | CRD, MoLSA | CRD | CRD, MoLSA |
| 3.2 | MoH | MoH | MoH | MoH | MoH | MoH |
| 3.3 | CRD, MoLSA | MoLSA | CRD | CRD, MoLSA | CRD | CRD, MoLSA |
| 3.4 | CRD, MoI | MoI | CRD | CRD, MoI | CRD | CRD, MoI |
| 4.1 | CRD, MA | CRD, MA | CRD | CRD, MA | CRD | CRD, MA |
| 5.1 | MoC | MoC | MoC | MoC | MoC | MoC |
| 5.2 | CRD, MA | CRD, MA | CRD | CRD, MA | CRD | CRD, MA |
| 5.3 | CRD, MA | CRD, MA | CRD | CRD, MA | CRR | CRD, MA |
| 6.1 | CRD, MA | - | CRD, MA | MA | CRD, MA | MA |
| 6.2 | CRD, MA | - | CRD, MA | MA | CRD, MA | MA |

Source: MA as of 31 Mar 2012

The MA carries out its own checks on projects, particularly upon the initiatives of IBs, beneficiaries and other entities and based on risk analyses of individual IB. In the period from 1 Oct 2011 to 31 Mar 2012, the MA commenced 3 checks of projects and completed 1 check of projects directed at the public procurement procedure, and it also completed 3 checks focused on the procedures followed by the contracting authority in the award of public contracts that had been commenced in 2010.

Due to the risk of breach of the public procurement procedures, the IOP MA launched the checks of contract documents prior to the announcement of the public procurement to minimise the deficiencies caused by wrongly set tender conditions. These checks are conducted on a sample of projects exceeding CZK 100 million of total eligible expenditure and public procurement procedures involving the amount exceeding CZK 30 million, that are also submitted under the intervention areas administered by the Intermediate Bodies of the Ministry of Interior and the Ministry of Health. These Intermediate Bodies were considered risky based on the control activity of IOP MA and results of controls conducted by other control bodies. In case of higher error rate in public contracts in the other intervention areas, the sample can be broadened to cover other Intermediate Bodies and intervention areas.

In the period from 1 Oct 2012 to 30 Mar 2012, the Intermediate Bodies carried out a total of 646 checks at applicants and beneficiaries. A more detailed breakdown of checks by the form and the time at which the check is conducted is given in the table below.

Table No 45 - Overview of checks conducted in the period from 1 Oct 2011 to 31 Mar 2012 in the breakdown by intervention area

| Row heading | Ex-ante admin. check | Interim admin. check | Ex-post admin. check | Ex-ante physical on-the-spot check | Interim physical on-the-spot check | Interim physical check with reimbursement | Ex-post physical on-the-spot check | Sum total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1- MoI | 0 | 2 | 2 | 0 | 5 | 0 | 0 | 9 |
| 2.1-MoI | 2 | 0 | 19 | 0 | 0 | 0 | 0 | 21 |
| 2.1-CRD | 0 | 59 | 0 | 0 | 2 | 29 | 6 | 96 |
| 3.1MoLSA | 11 | 3 | 0 | 0 | 1 | 0 | 0 | 15 |
| 3.1-CRD | 0 | 10 | 0 | 0 | 0 | 3 | 2 | 15 |
| 3.2-MoH | 0 | 2 | 0 | 0 | 11 | 0 | 4 | 17 |
| 3.3MoLSA | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 3 |
| 3.3-CRD | 0 | 2 | 0 | 0 | 0 | 1 | 0 | 3 |
| 3.4-MoI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3.4-CRD | 0 | 3 | 1 | 0 | 1 | 1 | 0 | 6 |
| 4.1-CRD | 4 | 12 | 0 | 0 | 2 | 4 | 0 | 22 |
| 5.1-MoC | 0 | 0 | 0 | 0 | 5 | 0 | 0 | 5 |
| 5.2-CRD | 8 | 214 | 1 | 0 | 16 | 63 | 23 | 325 |
| 5.3-CRD | 0 | 46 | 23 | 0 | 4 | 4 | 18 | 95 |
| 6.1-CRD | 0 | 9 | 0 | 0 | 2 | 1 | 0 | 12 |
| 6.2-CRD | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 |
| Sum total | 26 | 363 | 46 | 0 | 50 | 106 | 55 | 646 |

Source: IS Monit7+IOP as of 31 Mar 2012

Of the total number of checks conducted in the monitored period, 105 checks were on-the-spot checks.

According to the following overview, of the total of 646 checks 93 checks were completed with a negative result (with finding) and 443 checks with a positive result (no finding), in 2 checks a corrective measure was imposed. In checks with a negative result (with finding), the most frequent deficiency consisted in the non-compliance with the public procurement legislation, ineligible activities and expenditure (e.g. implementation of activities not planned in the project, implementation of activities beyond the planned scope, temporal discrepancy of eligibility of expenditure, etc.). In multiple checks deficiencies in the archiving of documents and deficiencies concerning the late submission of the applications for payment or violation of the conditions of support were identified.

Table No 46 -  Overview of checks conducted in the period from 1 Oct 2011 to 31 Mar 2012 in the breakdown by check status

| Row heading | Check was cancelled | Completed - negative (with finding) | Completed - positive (no finding) | Corrective measure imposed | Commenced | Scheduled | Sum total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1- MoI | 0 | 2 | 3 | 0 | 4 | 0 | 9 |
| 2.1-MoI | 0 | 12 | 5 | 0 | 4 | 0 | 21 |
| 2.1-CRD | 1 | 14 | 53 | 0 | 13 | 15 | 96 |
| 3.1MoLSA | 0 | 0 | 7 | 0 | 6 | 2 | 15 |
| 3.1-CRD | 0 | 1 | 14 | 0 | 0 | 0 | 15 |
| 3.2-MoH | 0 | 4 | 10 | 1 | 2 | 0 | 17 |
| 3.3MoLSA | 0 | 0 | 2 | 0 | 0 | 1 | 3 |
| 3.3-CRD | 0 | 0 | 2 | 0 | 1 | 0 | 3 |
| 3.4-MoI | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3.4-CRD | 0 | 1 | 3 | 0 | 1 | 1 | 6 |
| 4.1-CRD | 0 | 6 | 12 | 0 | 4 | 0 | 22 |
| 5.1-MoC | 0 | 0 | 4 | 1 | 0 | 0 | 5 |
| 5.2-CRD | 9 | 45 | 233 | 0 | 5 | 33 | 325 |
| 5.3-CRD | 1 | 8 | 81 | 0 | 2 | 3 | 95 |
| 6.1-CRD | 0 | 0 | 12 | 0 | 0 | 0 | 12 |
| 6.2-CRD | 0 | 0 | 2 | 0 | 0 | 0 | 2 |
| Sum total | 11 | 93 | 443 | 2 | 42 | 55 | 646 |

Source: IS Monit7+IOP as of 31 Mar 2012

The breakdown by the number of checks conducted by individual Intermediate Bodies under the respective intervention areas is presented in the following table.

Table No 47 -  Overview of checks conducted in the period from 1 Oct 2011 to 31 Mar 2012 in the breakdown by the number of checks by IB

| Control authority | Intervention area | Sum total |
| --- | --- | --- |
|  | 1.1 | 2.1 | 3.1 | 3.2 | 3.3 | 3.4 | 4.1 | 5.1 | 5.2 | 5.3 | 6.1 | 6.2 |  |
| CRD CR | - | 96 | 15 | - | 3 | 6 | 22 | - | 325 | 95 | 12 | 2 | 576 |
| Ministry of Culture CR | - | - | - | - | - | - | - | 5 | - | - | - | - | 5 |
| Ministry of Labour and Social Affairs | - | - | 15 | - | 3 | - | - | - | - | - | - | - | 18 |
| Ministry of Interior CR | 9 | 21 | - | - | - | 0 | - | - | - | - | - | - | 30 |
| Ministry of Health CR | - | - | - | 17 | - | - | - | - | - | - | - | - | 17 |
| Sum total | 9 | 117 | 30 | 17 | 6 | 6 | 22 | 5 | 325 | 95 | 12 | 2 | 646 |

Source: IS Monit7+ IOP as of 31 Mar 2012

Other controls of IOP MA – Priority axis 6

In the monitored period from 1 Oct 2011 to 31 Mar 2012, the IOP Managing Authority commenced a total of 3 checks of 4 projects. In 2 projects with negative finding, the use of a wrong form for project quality evaluation was discovered, or the non-observance of the Procedure for evaluation of project quality, in 1 project no deficiency was identified.  The Budget Department carried out the control of altogether 6 stages, of which 2 in Intervention area 6.1 and 4 in Intervention area 6.2. It concerned controls of the provision of administrative capacity, communication and publicity activities, education and training of IOP staff, MONIT support services, expansion of technical infrastructure for IOP. No finding was identified during all these controls.

## 4.2 Implementation of the Communication Plan and Activities in the Field of Publicity

In the given period, one of the pivotal communication activities, namely the creation and launch of the quality of life  microsites, www.kvalitazivota.eu, has been successfully performed. This website offers straightforward information on projects implemented in the Czech Republic and financed from the EU funds, to be specific from the Integrated Operational Programme. The title of the website is derived from the main objective of this programme – to improve the quality of life of the general public.

In the given period also the main publicity activity of IOP in 2011 took place – the annual conference.

The annual conference of IOP directed at the professional public was a success. The main topic on its agenda was the Integrated Urban Development Plans. The conference was held at the Cultural Centre in Písek, which was the co-organising partner of the event held on 13–14 October 2011. It was attended by almost one hundred persons, predominantly the representatives of all the involved towns, but also the representatives of other entities involved in IUDP implementation.

The conference dealt with the state of play of Integrated Urban Development Plans and also presented the news such as the introduction of Jessica financial instrument. Great attention was paid to the potential of IUDP to mitigate the negative implications and to prevent the emergence of socially excluded areas. A component part of the conference was a field trip to Portyč, the housing estate in Písek, which is being reconstructed with the support from IOP, and the presentation of a new publication on IUDP in the Czech Republic.

IOP pod lupou (Under the Magnifying Glass) Newsletter

In the period from 1 Oct 2011 to 31 Mar 2012, IOP pod lupou (Under the Magnifying Glass) quarterly continued to be published and gave details on several successful projects, current calls and planned events. In the given period 2 issues of IOP pod lupou newsletter were published, including a special issue offering information on IOP successful projects.

A detailed list of all the implemented activities, including seminars for beneficiaries and applicants is given in Annex No 1.

The list of aid beneficiaries under IOP is published and monthly updated on:

http://www.strukturalni-fondy.cz/Programy-2007-2013/Tematicke-operacni-programy/Integrovany-operacni-program/Projekty/Podporene-projekty

## 4.3 Conducted Evaluations and Studies

In the period from October 2011 to March 2012, 1 internal evaluation of MA included in the Evaluation Plan for 2012 was completed.  One evaluation included in the Evaluation Plan for 2011 scheduled for the end of 2011 was not carried out – Evaluation of the design and conduct of controls of projects in accordance with Article 13 of Commission Regulation (EC) No 1828/2006 at the level of MA and IB with focus on the method of selecting a sample for on-the-spot checks of projects/expenditure. Similar evaluation is currently under way within the NCA project called Professional assistance in the conduct of checks of projects and only based on the outputs of the referred to NCA project the MA will decide whether to conduct its own evaluation.

The Evaluation Plan for 2012 comprises also an external Evaluation of communication and publicity activities for 2011, which was put off to 2013 following the consideration of its benefits. Annual  external evaluations have not proven their worth due to their lengthy preparation and processing and it is more suitable and cost-effective to conduct an external evaluation every other year.

In 2012, the corrective measures from the Actions Plans from evaluations completed in 2011 continue to be taken and their implementation is described in Annex No 2

### 4.3.1 Evaluation carried out by the Managing Authority

Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP

Its conduct ensues from the Evaluation Plan of IOP approved at the 8th meeting of the Monitoring Committee on 24 Nov 2011.

The aim of the project: the main aim of this evaluation was to identify and evaluate the procedural and systemic barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP and to propose measures to eliminate them or to reduce their impacts. The key methodological tools were the analysis of data from IS Monit7+, analysis of documentation, one-to-one interviews, a questionnaire survey targeted at applicants and beneficiaries, and a focus group composed of the implementation structure representatives.

Implementation period: January – March 2012

Type of evaluation: internal

Evaluator: IOP MA in cooperation with CRD and MoLSA

Brief summary of results:

As at 30 Mar 2012 a draft final report was drawn up, which is currently commented on and it is expected to be finalised by mid-May.

### 4.3.2 Evaluation and studies carried out by the Intermediate Bodies

The Intermediate Bodies did no conduct any evaluation in the monitored period. The MoH evaluation called “Evaluation of Intervention area 3.2 with respect to the accomplishment of defined objectives and experience with the use of support in the Czech health care sector”, included in the Evaluation Plan for 2011, was rescheduled and included in the plan for 2012.

## 4.4 Other Activities of the Managing Authority and the Monitoring Committee

### 4.4.1 Activities of the Managing Authority

4.4.1.1. Meetings of Deputy Ministers of ministries implementing the IOP

With regard to the status of implementation of the programme and addressed problems, which many times went beyond the competence of IOP IB directors, the top officials of MRD continued to convene the meetings of the Interministerial Commission of Deputy Ministers implementing the IOP.

In the monitored period two meetings were held with the view to discuss the postponements in implementation of the Integrated Operational Programme in the 3rd quarter of 2011, forecast fulfilment of n+3 rule in 2011 and the outlook for 2012, major risks faced in the implementation of the Integrated Operational Programme by individual Intermediate Bodies, and specific problems in individual intervention areas.

Conclusions of the meeting of Interministerial Commission of Deputy Ministers implementing IOP

- Volume of funds covered by the Decisions equals 72 % of the allocation, volume of reimbursed and certified funds is 18 %, or 10.4 %, which still ranks IOP among the weakest OPs.

- In the monitored period the number of projects with issued Decision increased by 172 projects with the total value of CZK 4 billion.

- The accomplishment of the plan for January – November 2011 period ranges from 26 % in MoLSA to approximately 50 % in MoH and MRD.

- Mr Braun, the First Deputy Minister, pointed at an extremely high number of rejected projects during ex-ante checks at MoLSA, at the possibility of excessive or duplicate requirements for beneficiaries and simplification of Handbooks for Beneficiaries.

- The MRD in cooperation with MoLSA and CRD, as a follow-up to the approved Evaluation Plan, prepares an internal evaluation of processes in implementation and requirements placed upon the applicants and beneficiaries

- Mr Braun, the First Deputy Minister, recommended to the MoC CR and MoI CR to set out the limits for absorption of funds under individual projects for individual years and potential cuts of unabsorbed funds at beneficiaries who fail to meet the set out targets of absorption.

- Mr Braun, the First Deputy Minister, highlighted the importance of the observance of deadlines at individual stages of project cycle; the application of the terms and conditions of the contract, the purpose of which is to enforce the supplier′s obligations, as a partial evaluation criterion and the use of random selection by casting lots in the award of public contracts in IOP.

4.4.1.2   Bilateral meetings between IOP MA and IOP IBs

In the period from 1 Oct 2011 to 31 Mar 2012, several bilateral meetings with the Ministry of Labour and Social Affairs of the CR and the Centre for Regional Development of the CR took place, at which the following topical issues were addressed:

- Status of absorption in intervention areas of the respective IOP IBs,

- Forecast absorption, project implementation,

- Controls,

- Issuance of the Registration of action/Decision,

- Seminars for beneficiaries, technical assistance,

- Public contracts,

- Approval of documentation,

- Measures taken by IBs to improve the absorption,

- Revision of Handbooks for Applicants and Beneficiaries,

- Calculation of target values of monitoring indicators,

- Progress in the administration of project applications, etc.

4.4.1.3 Education and training

Table No 48 – Overview of conducted education and training activities

| Evaluation of education plans / Activity | Role of the MA | Comments |
| --- | --- | --- |
| Education and training organised by the Managing Authority for Intermediate Bodies | Organisation of education and training activities which reflect topical issues in IOP implementation and the topics of which are not covered by external training courses offered in the market. | In the period from 1 October 2011 to 31 March 2012, the MA held a total of 11 education and training activities during which 114 persons were trained. The thematic areas covered by the education and training activities focused on risk management analysis, publicity and promotion of the programme, monitoring and evaluation, financial management, preparation and management of projects, public procurement, elaboration of annual reports and reports on implementation of IOP. |
| Education and training at the MA | Organisation of education and training activities based on the individual education plans of MA staff, or the IOP annual plan. | From 1 October 2011 to 31 March 2012, a total of 148 employees of IOP MA were trained during 47 education and training activities. From 1 October 2011 to 31 March 2012, the largest number of staff was trained in thematic areas focused on financial management control, public procurement, IOP legislation, risk management analysis, monitoring and evaluation, publicity and promotion of the programme and computer skills. The smallest number of persons was trained in thematic areas focused on IOP information systems, financial and management control, state aid. |

4.4.1.4. Meeting with the EC concerning MoI and MoLSA

The meeting was instigated by the European Commission that is dissatisfied with the results achieved in the implementation of intervention areas related to Smart Administration strategy and results in the implementation of intervention areas under the responsibility of MoI CR and MoLSA.

The meeting was held in Prague on 30 Mar 2012 and was attended by the representatives of DG Regio, DG Employment, IOP MA, OP HRE MA, MoI CR IB, MoLSA IB, CRD and representatives of IOP beneficiaries.

On the agenda of the meeting was especially the institutional infrastructure of Smart Administration, risks associated with the launch of projects on basic registers, progress achieved in the implementation of intervention areas under the responsibility of MoI CR and MoLSA since the 8th IOP MC meeting and measures taken to improve the existing situation in IOP.

Key conclusions of the meeting

- The European Commission expressed strong dissatisfaction with the number of the so called “sleeping projects” and with a very low volume of funds in completed tenders, a notable progress has to be achieved before the 9th IOP MC meeting in Intervention area 1.1.

- MoI CR shall submit to the European Commission at the 9th IOP MC meeting a list of sleeping projects with the final decision as to whether or not the projects will be implemented (the decision is taken by the Government Council for Information Society) in Intervention area 1.1 (in case it is decided to implement the projects the MoI CR shall present the progress in the implementation of individual projects).

- The European Commission recommended to transfer the remaining activities in Intervention areas 2.1 and 3.4 from MoI CR to CRD CR and IOP MA. The transfer of activities in Intervention area 2.1 has been agreed with the MoI CR, in Intervention area 3.4 the transfer of activities is currently under negotiations.

- IOP MA shall inform the European Commission at the 9th IOP MC meeting on the transfer of remaining administrative activities from MoI CR to CRD CR and IOP MA.

- MoLSA and CRD CR shall accept all the recommendations ensuing from the Final report from evaluation  called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“.

- MoLSA in cooperation with CRD CR and IOP MA shall draw up an Action Plan for the implementation of individual recommendations ensuing from the evaluation called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“ and shall forward it through IOP MA to the European Commission.

### 4.4.2 Activities of the Monitoring Committee

In the period from October 2011to March 2012m, the 8th regular meeting of the Monitoring Committee of IOP was held at Don Giovanni hotel in Prague 3 on 24 November 2011.

At the 8th meeting of IOP MC changes in the evaluation of IUDP and the Evaluation Plan of IOP for 2012 were submitted for approval. The changes in the evaluation of IUDP and the Evaluation Plan of IOP for 2012 were approved.

Presented to the IOP MC members for information was the Report on Implementation of IOP as of 30 Sep 2011, Report on meeting the conclusions of the 7th meeting of IOP MC, request made by the European Commission for the Audit Authority to conduct an audit of projects in activities b), c), e) of Priority axis 4 focused on economy and effectiveness of spent funds, information on the approval of changes in the IOP Programming Document, information on the preparations for the implementation of Jessica financial instrument and the timetable of the implementation of Jessica financial instrument, information on assessing the expenditure related to administrative capacity and expenditure on outsourcing of IOP IBs.

A plethora of recommendations and tasks for MA and individual IBs were worded at the meeting (for more details see Chapter 2.5).

### 4.4.3 Activities of Working Groups

Working groups represent a tool for communication on topical themes or problems. The respective working groups meet usually 4x a year, the minutes are taken from their meetings and the WGs are subject to evaluation. In collaboration with WG members, the evaluation considers the frequency of meetings in the year concerned, the attendance, the fulfilment of tasks assigned at the working group meetings, the involvement and activity of members, the satisfaction of members with the organisation of WG and the benefits of the respective working group.

Working groups can respond in a flexible fashion to the emerging problems in IOP implementation. To a great degree they are also used as an education and training tool.

In the period from 1 Oct 2011 to 31 Mar 2012, meetings of the following IOP MA working groups were convened:

- WG for communication

- WG Pilot

- WG Technical assistance

- WG Financial management

- WG IS and monitoring

- WG Jessica

- WG for public contracts

- WG for reducing the risks in SmartAdministration

- WG Evaluation

In the monitored period, no meetings of the WGs of the IOP Monitoring Committee were convened:

- WG for risk management

- WG for Intervention area 5.2

- WG for Intervention area 3.1, 3.2 and 3.4

- WG for Intervention area 4.1 – activities in tourism are twice a year discussed at the meeting of regional representatives for tourism, regional coordinators and representatives of the Czech headquarters of tourism – CzechTourism.

- WG for Intervention area 5.1 – activities of this working group were replaced by the participation of the director of the Strategy and Aid Policy Department of the MoC in the meeting of the expert working group of the Association of Regions of the CR for EU funds, at which representatives of regions and the Regional Operational Programmes meet.

- WG for Intervention area 5.3 – Intervention area 5.3 of IOP is on the agenda of WG for coordination of urban policy, which is managed by the Regional Policy Department of the MRD, and IOP MA participates in its meetings just like the other representatives of operational programmes and professional associations. The IA 5.3 of IOP was not discussed at any of the meetings held in 2011.

Main conclusions from meetings of the working groups

WG for communication

In the monitored period the working group met two times. The main point on agenda of the November meeting was the introduction of the new communication strategy of IOP called “Quality of My Life”, which will facilitate an effective presentation of the achieved results of IOP over the remaining years of the current programming period. It shall also serve as an easily accessible source of information on IOP projects, not only for the general public, but also for mass media. The new strategy, built around the principle that can be briefly characterised as the “integrated approach” follows from the final report of the Evaluation of communication and publicity activities of IOP, commissioned by IOP MA, that was completed in April 2011.

The main point on the agenda of the March meeting was the presentation of the new “Quality of life” website offering information on successful projects in IOP.

WG Pilot

In the monitored period the working group met on 7 Feb 2012. The topic of the meeting was the evaluation of progress in implementation of pilot projects in IUDP towns with the participation of all involved entities (IOP MA, MoI CR, MoLSA, Agency for Social Inclusion). Based on the presentations of individual IUDP towns, the IOP MA concluded that the implementation of the pilot project is satisfactory and is not at risk at the time being. In spite of that it brought the attention of representatives of IUDP towns to the requirement of absorbing at least 40 % of IUDP allocation in 2012. All the pilot towns were also informed by the IOP MA about its monitoring visits that shall be paid in the course of 2012 in their towns in order to verify the status of implementation on the spot.

WG Technical assistance

In the monitored period the working group met on 20 Jan 2012. The main and only topic on the agenda was the following IOP MA proposal – Methodological Guideline for reimbursement of bonuses following the absorption of allocation drafted in line with Government Resolution No 1332 of 26 Oct 2009 on the Methodology of financial remuneration of employees implementing the National Strategic Reference Framework in 2007-2013 programming period, including the explanation of all the annexes to the methodological guideline, requisites for documenting the entitlement to the bonus of individual employees and the timetable of approval of the methodological guideline and payment of bonuses.

WG Financial management

In the monitored period three meetings of the working group were held. The topic on the agenda of meetings held on 16 and 31 January 2012 were the changes in VAT regime, the so called reverse charge duty, in construction and assembly works and their impact on individual ways of financing.

Discussed was the opinion on the reverse charge duty issued by an external expert as the supporting material for incorporating the payment procedures in IB manuals and HAB.

During the meeting held on 27 Mar 2012, a training was provided on the amendment to Act No 218/2000 Coll., budgetary rules. The MoF CR representative presented an interpretation of changes in individual provisions and answered the questions of MA and IBs.

WG IS and monitoring

In the monitored period two meetings of the working group took place. The topic of the meeting held in November 2011 was the preparation of supporting documents for the annual report and report on implementation, and analysis of the fulfilment of indicators.

The working group meeting held on 21 Feb 2012 was devoted to the monitoring indicators, their creation, definition, changes, entering into IS and reporting in the annual report and report on implementation.

WG Jessica

In the monitored period four meetings of the working group were held. The members of the working group were informed about the following:

- Accomplishment of the task assigned at the 8th IOP MC meeting, namely to send information on progress in implementation of Jessica FI;

- Approval of the Investment strategy of the implementation of JESSICA FI in IOP on 17 January 2012 by the top officials of the ministry;

- Consultation with the European Commission on 15 February 2012 concerning the change in the Decision on state aid in Intervention area 5.2;

- Making IS BENEFIT7 available for the submission of project application, including the incorporated requirements for mandatory annexes

- Approval and issuance of the addendum to the Methodological Guideline of MRD on main principles for preparation, evaluation and approval of IUDP and the current version of the Methodological Guideline of MRD on main principles for the preparation, evaluation and approval of IUDP with procedures for implementation of JESSICA FI in IOP through Decision of the Minister No 29/2012 of 27 February 2012;

- Legislative process of amending Act No 211/2000 Coll., on the State Housing Development Fund;

- Preparation of conditions of the Decision for providing a grant for the Holding Fund;

- Preparation of procedures for the implementation of FI to be included in the IOP Operational Manual.

WG for public contracts

In the monitored period the working group was convened four times. The discussions concentrated especially on matters related to the amendment to Act on public contracts No 55/2012 Coll., i.e. reducing the thresholds of small-scale public contracts, the obligation to use the e-marketplace for some types of commodities. The meeting concluded that once the amendment to Act on public contracts takes effect, the small-scale public contracts up to CZK 200 000 net of VAT will follow the procedure for contracts of category 1. The small-scale public contracts exceeding CZK 200 000 net of VAT will follow the procedure for small-scale public contracts of category 3.

WG for reducing the risks in Smart Administration

The working group was set up in January 2012 as one of the IOP MA measures to improve and accelerate the absorption at MoI CR. It is a working group composed of directors and heads of units of IOP MA, SFD, Programme Management Department and CRD. Meetings are held once in 1-2 weeks and address particular tasks with strict deadlines.

The aim of the working group is also to coordinate the preparations for the transfer of remaining administrative activities in Intervention area 2.1 or also 3.4.

WG Evaluation

The Working Group for evaluation of IOP met once in the monitored period. The meeting in the form of the 1st block of training courses intended for IOP was organised by the Czech Evaluation Company. The goal of the first block of training courses was to teach the trainees to independently define the causal relationships of  intervention, to word evaluation questions and to propose quality evaluation criteria.

WG for evaluation of NCA

The IOP representative also takes part in the meetings of the Working Group for evaluation of NCA, which convened twice in 2011 (20 Apr 2011 and 25 Oct 2011), the IOP representative attended only the meeting held in October.

At this meeting, the topical evaluations at the level of NSRF were presented. First of all, there was a presentation of the main results of ex-post evaluation of CSF and SPD (2004-2006), the course of the Mid-term evaluation of physical and financial progress of NSRF (MID-TERM evaluation) and preparations of the Strategic evaluation pursuant to Article 29 of the General Regulation – STRATeval 2012. The representative of the Regional Policy Development and Strategy Department of MRD introduced two contracts related to the Regional Development Strategy of the CR, and the Analysis and Strategy Department of MRD presented an evaluation called “Background studies for the preparation of the CR for the use of EU funds in 2014+ period”. Later, a new activity under the umbrella of NCA was presented, namely the metaevaluation of performed activities, and a discussion on the scope of provided information was opened. At the end of the meeting, the representatives of the Managing Authorities of individual OPs had the opportunity to present their currently conducted evaluations.

## 4.5 Administrative Capacity of Implementation Structure Entities of the Programme

The MA monitors and registers the administrative capacity of entities involved in the IOP implementation. The following two tables of administrative capacity were elaborated pursuant to the NCA guideline for drafting the report on implementation.

The table includes all the units and their employees involved in IOP implementation, expressed in full time equivalent. Apart from the Managing Authority and Intermediate Bodies staff, it also comprises those MRD technical sections that cooperate with the Managing Authority in the field of tourism, territorial (spatial) planning and housing support. Also included are the MRD Financial Section and the section of the Authorised Audit Entity that are responsible for IOP.

The table presents the structure of entities involved in IOP implementation. The “Number of employees” column gives the number of employees involved in IOP implementation expressed in full time equivalent (FTE). An employee with a full-time position (who spends 100 % of his working time on IOP implementation) is assigned the value of 1.0 FTE, while an employee with a quarter-time position who spends 25 % of his time on IOP implementation is assigned the value of 0.25 FTE.

Table No 49 – Status of administrative capacity of IOP implementation structure

| Authority | Department | Unit | Number of employees (FTE) | Total for the authority (FTE) |
| --- | --- | --- | --- | --- |
| Managing Authority | Operational Programmes Management Department | Secretariat to the Department | 2,00 | 47,85 |
|  |  | Management Unit | 9,60 |  |
|  |  | Methodology Unit | 9,25 |  |
|  |  | Monitoring Unit | 5,00 |  |
|  |  | Control Unit | 9,00 |  |
|  | Budget Department | EU Programmes Administration Unit | 9,00 |  |
| Persons responsible in the Technical sections of the Ministry for Regional Development CR | Housing Policy Department | National Programme Administration and IOP Unit | 2,00 |  |
|  | Tourism Department | Integration and Tourism Competitiveness Unit | 1,00 |  |
|  | Spatial Planning Department | Spatial Development Unit | 1,00 |  |
| Financial Section | Accounting and Financial Services Department | European Funds Accounting Unit and Budgetary Chapter Accounting Unit | 3,20 | 3,20 |
| Ministry of Culture CR | Strategy and Aid Policy Department | Project Implementation Unit | 10,00 | 17,00 |
|  |  | Financial Management Unit | 3,00 |  |
|  |  | Strategy and Methodological Support Unit | 4,00 |  |
| Ministry of Health CR | European Funds Department | Methodology Unit | 3,00 | 20,50 |
|  |  | Project Management Unit | 4,00 |  |
|  |  | Project Financing Unit | 5,00 |  |
|  |  | Monitoring, Control and Technical Assistance Unit | 6,00 |  |
|  |  | Director, assistant, administrative officers | 2,50 |  |
| Ministry of Interior CR | Structural Funds Department | Organisational and TA Unit | 8,34 | 39,01 |
|  |  | Methodology and Monitoring Unit | 4,40 |  |
|  |  | IOP Implementation Unit | 7,08 |  |
|  |  | Project Financing Unit | 2,51 |  |
|  |  | Project Control Unit | 7,88 |  |
|  |  | Publicity and Absorption Capacity Unit | 1,50 |  |
|  |  | Project Evaluation Unit | 3,42 |  |
|  | Financial Department of MOI CR | Financial Management of Payments Unit | 3,88 |  |
| Ministry of Labour and Social Affairs CR | EU Funds Implementation Department | Programme Implementation Unit - employment | 2,30 | 22,26 |
|  |  | Programme Implementation Unit – social integration and services | 7,60 |  |
|  | Programme Financing Department | Financial Management of Assistance and IOP Unit | 10,23 |  |
|  |  | Other MoLSA units involved in IOP implementation (Finance and Budget Unit, Human Resources Unit, Public Contracts Unit, Financial Accountancy and Cost Accounting Unit) | 2,13 |  |
| Centre for Regional Development of the CR |  | SF Management for Objective 1 and Objective 2 Section | 5,00 | 38,45 |
|  |  | Financial Management Section | 4,00 |  |
|  |  | Regional Branches Section | 29,45 |  |
| AAE | Internal Audit and Authorised Audit Entity Department | Internal Audit Unit | 0,00 | 10,00 |
|  |  | Authorised Audit Entity Unit | 10,00 |  |
| Total |  |  | 198,27 | 198,27 |

Source: MA and IB as of 31 Mar 2012

The following table contains comparisons between the current status of IOP administrative capacity and the status as of 30 Sep 2011. It also includes the target number of employees until the end of 2013.

Table No 50 -  Monitoring of the status of administrative capacity in 2007 – 2013 programming period

| Number of employees of IOP implementation structure expressed in FTE (target number of employees until the end of 2013) |
| --- |
|  | FTE as of 30 Sep 2011 | FTE – as of 31 Mar 2012 | Target FTE for 2012 | Target FTE for 2013 | Target FTE for 2014 |
| Managing Authority | 44,00 | 43,85 | 44,00 | 44,00 | 44,00 |
| Persons responsible in technical sections of MRD CR | 4,00 | 4,00 | 4,00 | 4,00 | 4,00 |
| Financial Section | 3,20 | 3,20 | 3,20 | 3,20 | 3,20 |
| Ministry of Culture CR | 16,00 | 17,00 | 17,00 | 17,00 | 17,00 |
| Ministry of Health CR | 20,50 | 20,50 | 24,50 | 24,50 | 24,50 |
| Ministry of Interior CR | 36,31 | 39,01 | 39,00 | 39,00 | 39,00 |
| Ministry of Labour and Social Affairs CR | 23,25 | 22,26 | 23,30 | 23,30 | 23,30 |
| Centre for Regional Development CR | 38,58 | 38,45 | 38,45 | 39,00 | 39,00 |
| AAE | 9,00 | 10,00 | 10,00 | 10,00 | 10,00 |
| Total | 194,84 | 198,27 | 203,45 | 204,00 | 204,00 |

Source: MA and IB as of 31 Mar 2012

Comments on administrative capacity of individual IOP entities are presented in the following table.

| Managing Authority | Following the increase in the number of IOP MA staff on account of expansion of IOP MA agenda namely by the preparation of the new programming period, application of JESSICA financial instrument in the framework of IOP and extension of the scope of control activities in August and September 2011, the number of employees of IOP MA, persons responsible in technical sections of MRD CR and the Financial Section did not increase, i.e. the number of IOP MA employees remained unchanged. |
| --- | --- |
| Centre for Regional Development CR | The number of employees expressed in FTE reflects the currently valid agreements concluded with the founder – MRD CR. The system of administrative capacities was designed to ensure a smooth performance of all the activities executed by the IOP IB at the CRD CR. In the monitored period the number of employees of CRD CR IB did not further increase. |
| Ministry of Interior CR | In MoI CR IB - Structural Funds Department the administrative capacity diminished in the previous period. The main reason was the departure of staff due to restructuring, which was conducive to more changes in staffing. The increase in the number of staff reported in the monitored period, i.e. since 30 Sep 2011, reflects the fact that new staff was recruited in response to the prior understaffing. |
| Ministry of Culture CR | In MoC CR IB the staffing capacity increased by 1 employee due to insufficient capacity of lawyers performing the control of public contracts, tenders and contracts with suppliers. |
| Ministry of Labour and Social Affairs CR | At MoLSA CR IB the staffing capacity dropped. Primarily due to the reduction in the number of part-time employees involved in IOP implementation (e.g. one employee of the Financial and Budget Unit, Financial Accountancy and Cost Accounting Unit, Public Contracts Unit, Legal Unit, Audit and Control Unit, i.e. in all units directly involved in IOP administration at MoLSA CR IB). |
| Ministry of Health CR | Following the changes in staffing in previous periods at MoH CR IB, there were no changes in staffing capacity in the monitored period. |
| AAE | The capacities are continuously achieved pursuant to the Government Resolution No 884/2007 and in line with the project Ensuring staffing capacities of MRD AAE and work in the group of auditors. In the monitored period the number of employees increased by 1 employee. |

The following table monitors the turnover rate of staff by individual type position as of 31 Mar 2012.

Table No 51 -  Monitoring of turnover rate by type position and implementation entity

| Turnover of employees of OP implementation structure by type position | Number of employees at the given position by share of their involvement in implementation as of 30 Sep 2011 | Number of employees at the given position by share of their involvement in implementation as of 31 Mar 2012 | Number of terminated/changed employment contracts at the given type position by the share* of their involvement in OP implementation | Number of terminated/changed employment contracts at the given type position by the share* of their involvement in OP implementation (only maternal leave, retirement, death etc. | Number of commenced employment contracts at the given type position by the share* of their involvement in OP implementation |
| --- | --- | --- | --- | --- | --- |
|  | MA + AAE | IB | MA + AAE | IB | MA + AAE | IB | MA + AAE | IB | MA + AAE | IB |
| Administrator of the monitoring system |  |  | 4,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |
| Administrative officer |  |  | 1,00 | 7,94 | 0,00 | 0,00 | 0,00 | 1,56 | 0,00 | 1,56 |
| OP analyst |  |  | 0,00 | 0,40 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 1,00 |
| AAE auditor for OP |  |  | 13,00 | 0,00 | 1,00 | 0,00 | 2,00 | 0,00 | 3,00 | 0,00 |
| Financial manager |  |  | 12,25 | 21,26 | 0,00 | 0,70 | 2,00 | 2,17 | 2,00 | 3,17 |
| Communication officer |  |  | 0,60 | 2,74 | 0,00 | 0,00 | 0,00 | 0,78 | 1,20 | 0,78 |
| Controller |  |  | 9,00 | 6,17 | 0,00 | 0,00 | 1,00 | 0,39 | 0,00 | 2,33 |
| Coordinator of evaluation |  |  | 0,95 | 1,28 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |
| Coordinator of controls and irregularities |  |  | 0,00 | 2,05 | 0,00 | 0,00 | 0,00 | 0,39 | 0,00 | 0,00 |
| Coordinator of technical assistance |  |  | 2,00 | 3,55 | 0,00 | 0,00 | 0,00 | 1,00 | 0,00 | 1,00 |
| Coordinator of education and training |  |  | 1,00 | 0,39 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 |
| Methodologist of OP management |  |  | 8,25 | 3,29 | 0,00 | 0,00 | 1,00 | 1,00 | 0,00 | 1,17 |
| Lawyer |  |  | 0,00 | 5,34 | 0,00 | 0,00 | 0,00 | 0,00 | 0,00 | 2,56 |
| Project manager |  |  | 0,00 | 28,36 | 0,00 | 1,00 | 0,00 | 10,22 | 0,00 | 10,16 |
| Senior officer |  |  | 6,00 | 15,04 | 0,00 | 0,00 | 0,00 | 6,68 | 0,00 | 3,03 |
| Other positions |  |  | 6,00 | 0,00 | 0,00 | 0,00 | 2,00 | 0,00 | 2,00 | 0,00 |
| Total number of employees |  |  | 64,05 | 97,81 | 1,00 | 1,70 | 8,00 | 24,19 | 8,20 | 26,76 |

Source: MA and other implementation entities as of 31 Mar 2012

Note: *In case the employee devoted less than 100 % of his time to work activities related to programme implementation, share of his work devoted to the programme is given

# 5 MAIN CONCLUSIONS

In the period from 1 Oct 2011 to 31 Mar 2012, a total of 1 111 project applications in the amount of EUR 552.02 million were submitted in fourteen calls. As of 31 Mar 2012, altogether 8 221 project applications in the amount of EUR 2 388.88 million were submitted, which represents 125 % of the allocation for the programme. A total of 7 319 projects in the amount of EUR 1 462.01 million were approved, which equals 77 % of the allocation. Funds in the amount of EUR 488.31 million, representing 22 % of the allocation for the programme, were paid to beneficiaries. Expenditure in the amount of EUR 260.97 million, i.e. 14 % of the allocation for the programme, was certified.

The following important events took place in the monitored period:

In December 2011 the EC approved the revision of the IOP Programming Document.

The n+3 target for 2011 was achieved, in case of RCE objective a part of the first advance payment had to be used.

Since the high anticipated error rate stated in the Annual Control Report of AA for 2010 was investigated, the MA in February 2012 withdrew the 8th interim application for payment (EUR 28.14 million under CONV objective and EUR 1.44 million under RCE objective). For the same reason, the MA upon agreement with the PCA did not submit the supporting documents for the regular 9th certification of expenditure for the period from 1 Nov 2011 to 31 Jan 2012 (EUR 23.14 million under CONV objective and EUR 0.02 million under RCE objective). Once the issue is settled, the MA will be able to request a new extraordinary certification of expenditure covering the expenditure since 16 Sep 2011.

The EC informed the CR by letter of 20 Mar 2012 that it would not reimburse the interim applications for payment of OPs financed from ERDF and CF and adopted the Action Plan for the improvement of management and control system of the Structural Funds in the CR. The MA shall cooperate in the implementation of corrective measures in line with the NCA, PCA and AA instructions. The EC set the deadline for implementation of corrective measures at 1 Jul 2012.

The IOP implementation continues, beneficiaries are reimbursed funds from national sources, the MA prepares aggregate applications and submits them to the PCA.

The remaining administrative activities in Intervention area 2.1 are currently being transferred by the IOP MA to IOP MA and CRD. The purpose of this systemic change is to improve the quality and to accelerate the administration in Intervention area 2.1.. By reducing the agenda, the SFD will have capacity available to reinforce the administration and controls in Intervention area 1.1.

The Managing Authority commenced the internal evaluation called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“. The main aim is to identify and evaluate the procedural and systemic barriers to the absorption in intervention areas reporting the lowest progress in implementation and to propose measures to eliminate them or to reduce their impacts.

The pivotal task in 2012 is the achievement of n+3 target. Judging from the forecasts based on financing plans and timetables of submitted projects, the target should be achieved with the use of a part of the advance payments. The risk consists in the failure to meet the project timetables and in the large volume of ineligible expenditure, e.g. on the grounds of errors in public procurement procedures.

# LIST OF ABBREVIATIONS

| AA | Audit Authority |
| --- | --- |
| ACR | Annual Control Report |
| ARS | Aid Registration System |
| ASOA | Administration of state-owned assets |
| AWA | Agreement on work activities |
| AWP | Agreement on work performance |
| Conv. | Convergence objective |
| CoP | Communication Plan |
| CRD | Centre for Regional Development |
| CZK | Czech crown – currency |
| DOZP/HPD | Home for people with disabilities |
| DSS | Social care home |
| EC | European Commission |
| ERDF | European Regional Development Fund |
| ESF | European Social Fund |
| EU | European Union |
| EUR | Euro – currency |
| FI | Financial Instrument |
| GA | Government Agency |
| GD FRS HZS | General Directorate of the Fire Rescue Service |
| GFD | General Financial Directorate |
| HAB | Handbook for Applicants and Beneficiaries |
| HF | Holding Fund |
| IB | Intermediate Body |
| ICT | Information and communication technologies |
| ImS | Implementation system |
| IOP | Integrated Operational programme |
| IOP MC | IOP Monitoring Committee |
| IOP OM | IOP Operational Manual |
| IRS | Integrated Rescue System |
| IUDP | Integrated Urban Development Plan |
| LTO | Local tax office |
| MA | Managing Authority |
| MIP | Manual of Internal Procedures |
| MoC | Ministry of Culture |
| MoH | Ministry of Health |
| MoI | Ministry of Interior |
| MoLSA | Ministry of Labour and Social Affairs |
| MR | Monitoring Report |
| MRD | Ministry for Regional Development |
| NCA | National Coordination Authority |
| NCT | National Centre for Support of the Transformation of Social Services |
| NSRF | National Strategic Reference Framework |
| OP | Operational Programme |
| OP HRE | Operational Programme Human Resources and Employment |
| OPC | Office for the Protection of Competition |
| OPTA | Operational Programme Technical Assistance |
| PA | Priority axis /priority area |
| PCA | Paying and Certifying Authority - National Fund |
| RCE | Regional Competitiveness and Employment objective |
| ROP | Regional Operational Programme |
| SA | Smart Administration |
| SAPD MoC | Strategy and Aid Policy Department of the Ministry of Culture |
| SB | State budget |
| SF | Structural Funds |
| SFD | Structural Funds Department |
| T | Tourism |
| TA | Technical assistance |
| SCC | Social care centre |
| WG | Working Group |

# ANNEXES

Annex No 1 –  Publicity activities in the period from 1 Oct 2011 to 31 Mar 2012

Annex No 2 – Action Plans

## Annex No 1 – Publicity Activities in the period from 1 Oct 2011 to 31 Mar 2012

| MA/IB | Name | Topic | Target group | Funds from IOP TA (EUR) | More information |
| --- | --- | --- | --- | --- | --- |
| MA | www.strukturalni-fondy.cz/iop website | On-going publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | Website is being updated continuously throughout the year. Updated information is supplied in the following sections: news, calls, for applicants, list of beneficiaries, tenders. |
| MA | Number of replies to enquiries through iop@mmr.cz | Enquiries concerning IOP | Applicants General public | 0 | 10/2011-3/2012- 5 enquiries |
| MA | Promotional merchandise | Promotional and presentation merchandise and supplies | Participants in seminars General public Monitoring Committee Implementation entities | 9509 | Production of e.g. a calendar, a notebook, folders, business cards |
| MA | Seminar for applicants under Intervention area 5.3 | Information for applicants under IA 5.3 | Applicants | 7632 | 10 Nov 2011 Prague. Number of participants: 40 29 Nov 2011 Brno. Number of participants: 35 |
| MA | IOP annual conference | Improving the environment in problematic housing estates – IUDP | Professional public, Mass media | 7661 | 13–14 October 2011, Písek. Number of participants approx. 100 persons |
| MA | “IOP pod lupou” (IOP under the Magnifying Glass) newsletter | Topical information on IOP Successful projects Calls FAQ etc. | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 10934 | In period from 10/2011 to 3/2012 two issues were published. Circulation of 5,000 copies. It contains the articles by MA and IB, information on the current calls, FAQ, summary of absorption of funds by individual NUTS 2 region, etc. Invoices related to both the issues were issued in the monitored period. |
| MA | Seminars for IUDP managers | Information for IUDP managers | IUDP managers | Included under the amount of Seminars for applicants | 15 Nov 2011 Prague. Number of participants: 33 22 Nov 2011 Olomouc. Number of participants: 27 |
| MA | Simple information portal – microsites | Information on successful projects | Applicants and beneficiaries General public Mass media | 6794,73 | Information on successful IOP projects |
| CRD | Seminars on 2.1 | Training of beneficiaries under Intervention area 2.1 – 6th, 8th , 9th , 11th , 12th call | Beneficiaries | 0 | 5 Oct 2011, 24 Jan 2012, 26 Jan 2012 (all in Prague) – a total of 160 participants (the seminar was held by MoI CR) |
| CRD | Seminars on 5.2 | Training of applicants in Intervention area 5.2-Improving the environment in problematic housing estates | Applicants Beneficiaries | 0 | 10 Nov 2011 (Prague) and 22 Nov 2011 (Olomouc) – held in cooperation with MRD + 5 Mar 2012 (Chrudim) – held in cooperation with the municipal authority and cooperatives- a total of 120 participants |
| CRD | Seminar on 5.3 | Training of applicants and beneficiaries under Intervention area 5.3b | Applicants, beneficiaries | 0 | 15 Nov 2011 (Prague) and 29 Nov 2011 (Brno) – 200 participants (the seminar was held by MRD) |
| CRD | Lecture of an expert | Introduction to the situation in Intervention area 5.2- Improving the environment in problematic housing estates | Applicants, beneficiaries, professional public | See below | Lecture by an expert on “Improving the environment in problematic housing estates“ at the conference called Regeneration of the Housing Stock, Hradec Králové, 9 Nov 2011, a total of 408 participants |
| CRD | Article in professional journals | Introduction to the situation in Intervention area 3.4 - Services in security, risk prevention and management | Applicants, beneficiaries, professional public, general public | 11085,64 | A specialised article “European assistance and protection of population in crisis situations“ published in the following periodicals: Veřejná správa (25/2011), Moderní obec (12/2011), Výstavba měst a obcí (4/2011), Obec a finance (5/2011) and Eurozpravodaj (4/2011) |
| CRD | Article in professional journals | Introduction to the situation in Intervention area 5.2- Improving the environment in problematic housing estates | Applicants, beneficiaries, professional public, general public | 0 | A specialised article “European assistance helps improve the environment of Czech housing estates“ – IUDP topic. Focus on Central Bohemia, magazine Panelák No 37 and www.panelovydum.cz server; the article was published in a modified version under the title “Money from EU Structural Funds for regeneration of residential buildings“ also on www.bydletvpanelu.cz |
| CRD | Regeneration of Residential Buildings conference | Presentation of CRD CR activities, including consultation, intermediary and control activities of CRD in selected EU programmes | Applicants, beneficiaries, professional public, general public | 2373 | 8 – 9 Nov 2011 Total number of participants in the conference -408 |
| CRD | Days of Small Municipalities conference | Presentation of CRD CR activities, including consultation, intermediary and control activities of CRD in selected EU programmes | Representatives of self-governments | 0 | 1 Nov 2011 (Prague), 3 Nov 2011 (Vyškov), 28 Feb 2012 (Prague), 1 Mar 2012 (Vyškov) – approx. 350 participants in each conference |
| CRD | www.risy.cz website | Ongoing publishing and updating of information | Applicants and beneficiaries, general public, professional public |  | Website is updated throughout the year |
| CRD | www.crr.cz website | Ongoing publishing and updating of information | Applicants and beneficiaries, general public, professional public | 0 | Website is updated throughout the year, starting from 3 Feb 2012 the website has a new graphic design and a modified content |
| CRD | Wall calendar Revitalisation of housing estates 2012 | Wall calendar from photo documentation of IA 5.2 of IOP | General public | 2421,5 | 400 pcs of wall calendar |
| CRD | Promotional merchandise | Promotional merchandise with IOP logos | General public | 15320,36 | A total of 5000 pcs of 11 types of promotional merchandise (flash discs, USB hub, umbrella, sports bottle, sticky note pads, micro cloth, pen gift sets, picnic blanket, game set, set of chocolates, ballpoint pen) |
| CRD | Number of replies to enquiries | IOP enquiries | Applicants and beneficiaries | 0 | 10/2011-3/2012: a total of 43 registered e-mail enquiries;1 100 unregistered e-mail enquiries (estimate); 1 500 telephone enquiries (estimate) |
| MoC | www.kultura-evropa.eu web portal | Continuous publishing and update of information on Intervention area 5.1 | Applicants and beneficiaries General public | 3244,8 | The website is being updated by the IB throughout the year. Updated information is supplied particularly in the following sections: news, calls for applicants, list of beneficiaries, tenders. |
| MoC | A seminar - meeting with project representatives | A seminar held on 6 Apr 2011 with aid beneficiaries under IOP 5.1 | Beneficiaries | 1128,9 | 18 Oct 2011; Prague; 44 participants |
| MoC | Seminar for applicants under IA 5.1 of IOP – call No 3 | Seminar for applicants for support under IA 5.1 of IOP | Applicants | 0 | 2 Nov 2011; Prague; 15 participants |
| MoC | Consultations on projects | Consultations with project and financial managers | Beneficiaries | 0 | 32 consultations, a total of 159 participants |
| MoC | Number of replies to enquiries sent via www.kultura-evropa.eu iop@mkcr.cz | Enquiries concerning IOP 5. 1 a,b,c | Applicants and beneficiaries General public | 0 | 10/2011-3/2012: a total of 15 enquiries |
| MoC | Photo documentation of projects | For the purpose of creating printed materials, e.g. drawing and colouring books + other potential use | General public | 2469,93 | Photographs have been taken of a total of 17 projects. |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – drawing and colouring books – Part 1 | General public | 3632,25 | Drawing and colouring book |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – drawing and colouring books – Part 2 + A6 notepads | General public | 5085,15 | Drawing and colouring book + A6 notepads |
| MoC | Text services | Creation of textual content for the cover of A6 notepad double page | General public | 193,72 | A6 notepads |
| MoC | Graphic services | Creation of the graphic design of the New Year's card 2012 | General public | 282,5 | PF 2012 |
| MoC | Printed materials | Drawing and colouring books, A6 notepads, PF 2012 | Applicants and beneficiaries+general public | 15632,45 | Publicity of projects under IA 5.1 of IOP and programme publicity Drawing and colouring book 10000 pcs A6 notepads 10000 pcs PF 2012 200 pcs |
| MoC | Promotional merchandise | 16x exhibition panels + full preparation and design of the exhibition, graphic design of the exhibition | General public + professional public | 9632,25 | Production of exhibition panels which will be used for publicity of successful projects under IA 5.1 of IOP at an international exhibition in Tel-Aviv. Information will be presented on exhibition panels in two languages. |
| MoLSA | www.mpsv.cz website | Ongoing publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | The website is updated throughout the year. Updated information concerns particularly the following sections: news, calls, tenders, replies to the most frequently asked questions, events, list of beneficiaries, tenders, contacts, dates of Selection Committee meetings. |
| MoLSA | Number of replies to enquiries related to Intervention areas 3.1 and 3.3 | Enquiries related to IOP | Applicants General public | 0 | 10/2011-3/2012: For Intervention area 3.1 a total of 283 e-mail enquiries, 81 one-to-one consultations For Intervention area 3.3 a total of8celkem 1va.maderova@mpsv.cz. ncíh ozvučení je potřeba 95 e-mail enquiries, 106 telephone enquiries, 37 one-to-one consultations |
| MoLSA | Seminars and training courses for applicants and potential beneficiaries | Continuous call No 4 for IA 3.3 | Applicants and beneficiaries | 0 | 16 Jan 2012; Prague; 5 participants, 16 – 17 Feb 2012, Křešice, 16 participants |
| MoLSA | Seminars and training courses for applicants and beneficiaries | Continuous call No 1, 6,7, 8 for IA 3.1 | Applicants and beneficiaries | 222,17 | Prague 7x, České Budějovice 1x, Liberec 1x, Hradec Králové 1x, Karlovy Vary 1x: A total of 11 seminars for activities a),b),c); a total of 224 persons |
| MoLSA | Articles in press | IA 3.1 | General public | 1937,2 | Information on the call for 3.1b in Moderní Obec periodical. |
| MoLSA | Articles in press | IA 3.1 | General public | 0 | Information on the absorption of funds in Intervention area 3.1a) call No 7 of IOP will be published in the March issue of the Newsletter of the National Centre. |
| MoLSA | Conferences and other specialised seminars and a public hearing for the sake of publicity of activities under IA 3.1 | IA 3.1 | General public, Professional public | 0 | On 6 Oct 2011, participation of MoLSA representative as a lecturer on the topic of “Transformation of social services” in the Chamber of Deputies of the Parliament of the CR On 12 Oct 2011, the MoLSA took an active part in the Introductory conference to the project called Support to the process of transformation of residential social services held in the Moravian-Silesian region. On 22 Nov 2011, the MoLSA took an active part in a public hearing in the Senate on the topic of “Transformation of social services: exercise of rights of disabled persons“ On 1-2 Nov 2011, the MoLSA took an active part in the conference “Life in community“ attended by approximately 250 persons from among professional and general public On 13 Dec 2011, the MoLSA participated in the conference called “Architecture of social services in common environment“. |
| MoI | www.osf-mvcr.cz website | Ongoing publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 6765,5 | Website is updated throughout the year. Website traffic 10/2011-03/2012 – 78 548 visits |
| MoI | Number of replies to enquiries related to IA 1.1, 2.1, 3.4 | Enquiries regarding the IOP | Applicants and beneficiaries General public | 0 | 10/2011-3/2012: a total of approximately 9000 enquiries (e-mail, telephone and one-to-one consultations; online advisory centre on www.osf-mvcr.cz ) |
| MoI | Seminar for beneficiaries | Seminar for beneficiaries under IA 2.1 of IOP Copyright, IT licences with respect to the Act on public contract | Beneficiaries under IA. 2.1 | 1307,61 | 5 Oct 2011 in Prague, 50 participants |
| MoI | Workshop for IOP beneficiaries | In cooperation with MoI CR departments; Topics: project budget, elaboration of necessary supporting documents and tables in ARS/ASOA |  | 339,01 | 10 Nov 2011 in Prague, 35 participants |
| MoI | Seminar for public administration | Copyright, IT licences with respect to the Act on public contract | Beneficiaries from among public administration | 1525,54 | 15 Nov 2011 in Prague, 40 participants |
| MoI | Seminar for beneficiaries | Seminar on most frequent mistakes in the completion of monitoring reports and applications for payment | Beneficiaries under IA 1.1 | 847,52 | 15 Nov 2011 in Prague, 33 participants |
| MoI | Seminar for beneficiaries | Introduction to most frequent mistakes in the completion of monitoring reports and their annexes, tenders, project publicity, etc. | Beneficiaries under IA 2.1 | 823,31 | 24 Jan 2012 in Prague, 70 participants |
| MoI | Seminar for beneficiaries | Introduction to most frequent mistakes in the completion of monitoring reports and their annexes, tenders, project publicity, etc. | Beneficiaries under IA 3.4 | 823,31 | 26 Jan 2012 in Prague, 71 participants |
| MoI | Seminar on public contracts | Matters related to tenders, documents for tenders | Beneficiaries from among public administration | 1259,18 | 21 Feb 2012 in Prague, 27 participants |
| MoI | PR for general and professional public | PR | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 10712,12 | Based on a small-scale public contract Provision of public relations services to the general and professional public. Implemented by Bison&Rose company. In the framework of this cooperation the following materials were published (10/2011-12/2011): Barometer of absorption of regional authorities (together with OP HRE):13 barometers http://www.osf-mvcr.cz/barometr-cerpani-krajskych-uradu-v-cr Project of the month –November http://www.osf-mvcr.cz/projekt-mesice Press releases: 1 press release http://www.osf-mvcr.cz/evropska-komise-schvalila-cesku-zaslani-dalsich-1-273-7 PR articles: 1 PR article http://www.osf-mvcr.cz/policie-vybavi-auta-spickovou-technikou-za-evropske-penize Editorials: 1 editorial http://www.osf-mvcr.cz/podnikatele-snaze-ziskaji-dovozni-licence |
| MoI | Advertisements in CDIS Revue | Interview with the Director of SFD | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 2421,5 | October 2011 in Issue No 4 |
| MoI | Newsletter No 4/2011 | Police will equip their vehicles with state-of-the-art technology | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 3006,9 | November 2011, 5000 copies http://www.osf-mvcr.cz/newsletter |
| MoI | Expert assistance | Provision of consultations to beneficiaries in IA 1.1 | Beneficiaries | 16951,73 | Based on the above-the-threshold public contract Expert assistance to final aid beneficiaries in selected calls of IOP and OP HRE - implemented by Naviga4, s.r.o company |
| MoI | Delivery of promotional merchandise |  | Applicants and beneficiaries General public Professional public Evaluators Implementation entities | 38170,51 | Continuously |
| MoI | Publication called Successful projects | Presentation of 20 IOP + OP HRE projects | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 67355,11 | Circulation of 1000 pcs, February 2012 |
| MoI | Launch of the web application of successful projects | Together with OP HRE | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | Included in the price referred to above | February 2012 |
| MoH | www.mzcr.cz website | Ongoing publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | Continuous publishing of information and updates of information on www.mzcr.cz website, especially in sections of calls, project implementation, publicity etc. It is done throughout the year. |
| MoH | One-to-one, written, telephone and e-mail communication | Consultancy | Applicants and beneficiaries General public | 0 | Information to potential applicants/beneficiaries. From 1 Oct 2011 to 31 Mar 2012 altogether 15 one-to-one consultations were registered. |
| MoH | Seminar for beneficiaries | Training course for beneficiaries under the 8th call for IA3.2 of IOP | Beneficiaries | 662,8 | Within the announced 8th call the following seminars were held: on 16 Jan and 17 Jan 2012 Seminars for beneficiaries in Prague. A total of 53 persons participated in these seminars. |
| MoH | Seminar for applicants | Training course for applicants under the 9th and 10th call for IA 3.2 of IOP | Applicants | 482,28 | Within the announced 9th and 10th call Seminars for applicants were held in Prague on 26 Mar and 28 Mar. 2012. A total of 50 persons participated in the seminars. |
| MoH | Press releases and press conferences | Press releases and conferences concerning the calls and the implementation of IOP IA 3.2, etc. | Applicants and beneficiaries Evaluators General public Implementation entities Mass media | 0 | On 21 Dec 2011 a press release was issued called “Ministry of Health will support the development of specialised stroke and cerebrovascular centres in the Czech Republic by one billion Czech crowns “ based on the outputs of the Selection Committee for the 8th call. |
| MoH | Promotional merchandise | Promotional and presentation merchandise and supplies | Applicants and beneficiaries General public | 6151,42 | Provision of a portfolio of promotional merchandise to ensure publicity of Intervention area 3.2 of the Integrated Operational Programme |

Error rate pursuant to the Annual Control Report of for 2011

## Annex No 2 – Action Plans

Action Plan from the Evaluation of Communication and Publicity Activities of IOP

| Recommendation of the evaluator | IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOM-PLISHED | CORRECTIVE MEASURE | DEAD-LINE | ACCOM-PLISHED |
| To direct the regular meetings of publicity staff of individual Intermediate Bodies toward the creation of uniform concept of IOP publicity. | Meetings of Working Group for communication of IOP | The next meeting in 07/2011, then on a continuous basis | 14. 7. 2011, 3. 11. 2011, 17. 1. 2012 | Participation in meetings of the Working Group for communication of IOP | Next meeting in 07/2011 | 14. 7. 2011, 3. 11. 2011, 17. 1. 2012 |
| To create a concept which should focus on the provision of information to the public on how and by what the individual areas supported from IOP improve and enhance the quality of life. For the sake of setting the concept “Quality of My life” to motion and for the sake of successful implementation of communication activities it is useful to have the whole process supervised by an expert, who has experience with marketing communication and introduction of similar changes in communication. | To translate the theoretical concept to specific tools of communication and publicity. To prepare a tender and to hire a creative supervisor, who will be tasked to compile a “cookbook” for the application of the concept primarily with the use of the following three tools: 1. Internet (microsites), 2. printed matters, 3. events | 06-09/2011 | On 14.8.2011 the services of a creative supervisor were ordered, in November 2011 the manual of the “Quality of My Life” concept was introduced | One representative of each IB shall participate in the communication with the creative supervisor and will thus help finetune the concept. | 06-09 2011 | 30.8.2011 meeting of the WG for communication of IOP with the creative supervisor |
| To use the topical themes to promote the IOP benefits – e.g. in the light of health care crisis to provide for media coverage of the benefits of Priority axis 3, to which the largest volume of funds of the whole programme is allocated, the interest of media in this priority axis, however, was inadequate bearing in mind the amount of allocation. | Creation of microsites in the spirit of the “Quality of My Life” concept, which will in a visually-attractive and user-friendly form present the IOP successful projects. Publishing of information on successful projects on the Structural Funds website, in IOP newsletter, elaboration of a publication with successful projects, etc. | Continuously | On 4. 1. 2012 an invitation to tender was published for the creation of the IOP information portal (microsites), 3/2012 creation of kvalitazivota.eu microsites |  |  |  |
| In order to increase the impact of IOP communication and publicity activities on the general public, it is suitable to exploit especially the TV and Internet campaigns that would concentrate on the presentation of implemented projects and their benefits for the general public. | TV – since it is very costly, this tool will be exploited only exceptionally Internet – once the simple information interface (microsites) is created, to launch a web campaign for this interface, where the information, pictures, video recordings etc. on successful IOP projects will be posted. | 11/2011 – 1/2012 | The launch of internet campaign was postponed due to later creation of microsites to the next technical assistance project to be commenced on 1 May 2012 | WG for communication participates on an ongoing basis | 11/2011 – 1/2012 |  |
| For the professional public, a suitable tool seems to be the Internet in general (Internet campaign) and the IOP website. | Internet - once the simple information interface (microsites) is created, to launch a web campaign for this interface, where the information, pictures, video recordings etc. on successful IOP projects will be posted. | 12/2011 - 2/2012 | 3/2012 creation of microsites. The internet campaign will be launched within the new Technical assistance project to be commenced on 1 May 2012 | WG for communication participates on an ongoing basis | 12/2011 – 2/2012 |  |
| It is necessary to add the strategic background to the individual annual CoPs, which means to evaluate the progress in the fulfilment of CoP objectives to get a complete picture of key tasks in the long run and then to decide about the priorities for the given year. | To conduct annual external evaluations of communication activities and based on these evaluations to create a “strategic background“, which will partly be evaluated internally and partly externally in the framework of annual evaluations (always in the following year). In 2011, the main aim is to develop the referred to concept, the partial evaluation of which will be an integral part of the annual evaluation. | 1st Q 2012, 1st Q 2013 etc. | Conduct of external evaluation was postponed to 2013. It has been concluded that there is no reason for conducting evaluations every year and it is more fitting and cost -effective to conduct an external evaluation every two years. |  |  |  |
| The annual CoPs should specify and quantify the communication objectives. It is then possible to evaluate the level of fulfilment of these objectives in individual years. The level of fulfilment of objectives of the framework CoP can be evaluated in relation to the defined target values of impact indicators. | To set out impact indicators on the basis of annual evaluations and to reflect them in individual annual communication plans. | 1st Q 2012, 1st Q 2013 etc. | Communication objectives for 2012 were set out based on the evaluation of communication plans for 2011 and also monitored are communication objectives defined by the external evaluation in the first half of 2011. | To set out impact indicators on the basis of annual evaluations and to reflect them in individual annual communication plans. |  | Communication objectives for 2012 were set out based on the evaluation of communication plans for 2011 and also monitored are communication objectives defined by the external evaluation in the first half of 2011. |

## Action Plan from the Evaluation of the Progress of Implementation of IOP Priority axis 4 (National support of tourism) with respect to the achievement of the set out programme objectives

| Recommendation of the evaluator | IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOMPLISHED | CORRECTIVE MEASURE | DEAD-LINE | ACCOM-PLISHED |
| Recommended prices common at the given time and place (page 4) | a) To conduct an analysis of evaluation of economy, efficiency and effectiveness of project costs b) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria c) To modify the structure of the Supporting documents for quality evaluation – to modify the structure of detailed itemised budget; to detail the content of the baseline analysis – to add the requirement for calculation of costs, preliminary market research to ascertain the prices, to insist on the specification of project activities d) To modify the list of eligible expenditure – only such expenditure will be eligible that has a direct link to project activities (to exclude labour costs and expenditure beyond the mandatory publicity from eligible expenditure) e) To train the evaluators – when evaluating the prices the evaluator shall give justification with a reference to the source used | a) 2nd Q 2012 b) 31. 5. 2011 c) 5. 9. 2011 d) 5.9.2011 e) 4., 6. 10.2011 | a) Accomplished to a certain degree – in January 2012 doc. Vaníček conducted an evaluation of economy and efficiency of CzechTourism projects based on project applications. The IOP MA commissioned the conduct of analysis of tools for 3E control across IOP. Outputs will be available in 6/2012. Moreover, the IOP MA commissioned the elaboration of external opinions focused on 3E in individual CzT projects and in projects %5901, %5902 with Ernst & Young experts. b) Yes c) Yes d) Yes e) Yes |  |  |  |
| To modify the system of evaluation (page 4, 30, 48,33,35) | a) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria b) To issue a methodological guideline introducing new evaluation criteria c) To issue a methodological guideline - to modify the procedure for evaluation of project quality d) To train the evaluators | a) 31. 5. 2011 b) 13. 7. 2011 c) 31. 8. 2011 d) 9/2011 | a) Yes b) Yes c) Yes – from 5.9.2011 d) Yes - 4., 6. 10.2011 |  |  |  |
| To push stronger for the submission of quality projects (page 24, 27, 29, 68) | a) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria b) To modify the structure of the Supporting documents for quality evaluation – to modify the structure of detailed itemised budget; to detail the content of the baseline analysis – to add the requirement for calculation of costs, preliminary market research to ascertain the prices, to insist on the specification of project activities c) To train the CRD for eligibility checks – to return the project application for completion in the event the project activities are not specifically described and a detailed project budget is not included | a) 31. 5. 2011 b) for the next call c) for the next call | a) Yes b) Yes – from 5.9.2011 c) Yes – from 13. 9. 2011 |  |  |  |
| To ensure the adherence to set out project timetables (page 35) | a) To consistently see to the adherence to procedures of administration of changes in projects | a) Continu-ously | a) Continuously | a) The CRD shall consistently see to the adherence to the procedure of administration of changes in projects – imposition of sanctions in case of late submission of the Notification of changes in the project (once a delay occurs in the timetable of implementation) b) Recommendation to Tourism Dept. and CzT beneficiaries to optimize the timetables of project implementation | a) Continuou-sly b) 31. 8. 2011 | a) Continuou-sly b) Accomplished – Tourism Department made changes in its projects, CzT cut the project budgets, where savings were achieved based on tenders. |
| To ensure maximum economy and effectiveness of expenditure (page 35 - points 2 and 4) | a) To conduct an analysis of evaluation of economy, efficiency and effectiveness of project costs; to conduct a survey in order to identify the possibilities of exploiting external experts for the 3E assessment b) To modify the list of eligible expenditure – only such expenditure will be eligible that has a direct link to project activities (to exclude labour costs and expenditure beyond the compulsory publicity from eligible expenditure) c) To supplement HAB with the information that no new activities can be added to projects d) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria e) To modify the structure of the Supporting documents for quality evaluation – to modify the structure of detailed itemised budget; to detail the content of the baseline analysis – to add the requirement for calculation of costs, preliminary market research to ascertain the prices, to insist on the specification of project activities f) To train the evaluators – the evaluators can propose the cuts in eligible expenditure in the event of non-compliance with 3E; consistent justification of 3E evaluation | a) 2nd Q 2012 b) for the next calls c) for the next calls d) 31. 5. 2011 e) for the next calls f) 9/2011 | a) To a certain extent- MA in cooperation with CRD is preparing a selection procedure for experts in the field of tourism, who would e.g. help increase the expertise of conducted controls focused on 3E. b) To a certain degree - reduced was only expenditure on compulsory publicity c) Yes – from 5.9.2011 d) Yes e) Yes – from 5.9.2011 f) Yes - 4. and 6. 10. 2011 | During the controls of applications for payment the CRD shall consistently adhere to the procedures for 3E control | Continuously |  |
| To modify the PD for reasons of non-fulfilment of the objective “To increase the number of entities connected to the reservation system“ and non-fulfilment of MI No 413305 Number of new information and reservation systems in tourism and No 413311 Number of entities operating in tourism connected to the reservation system. (page 41 and 45) | To draft a proposal for changes in PD and to send it to the EC for approval | 7/2011 | Yes – sent to SFC2007 29.7.2011 |  |  |  |
| To introduce ceilings for labour costs for individual positions in the project team (page 47) | Partly accepted – the list of eligible expenditure will be modified – labour costs will not be considered eligible in the following calls | For the following calls | No – Labour costs continue to be eligible expenditure in the amount of 9 % of total eligible expenditure of the project. The remuneration of project team members shall be with respect to the nature of beneficiaries (GA and organisations established by them) in line with Government Order No 564/2006 Coll., as amended. |  |  |  |
| To introduce fixed price ceilings in key budget items (page 49, 67) | Partly accepted – fixed price ceilings are not set, therefore they cannot be incorporated in the documentation a) To conduct an analysis of evaluation of economy, efficiency and effectiveness of project costs b) To conduct a survey in order to identify the possibilities to use external experts for 3E evaluation c) To suggest to the PCA and NCA to propose a system solution of evaluation and control of 3E | a) 2/ 2012 b) 12/2011 c) accomplished | a) Partly accomplished - IOP MA commissioned a conduct of analysis of tools for 3E control across IOP. Outputs will be available in 6/2012. b) MA in cooperation with CRD is preparing a selection procedure for experts in the field of tourism, who would e.g. help increase the expertise of conducted controls focused on 3E c) Yes |  |  |  |
| Introduction of the annex to the Supporting documents for evaluation of project quality – itemised budget of key project expenditure in a recommended structure (page 47) | To modify the structure of the Supporting documents for evaluation of quality – to modify the structure of a detailed itemised budget; | For the following calls | Yes – from 5.9.2011 |  |  |  |
| To launch the preparation of the State Tourism Policy Concept for 2013+ period | To write a letter to the Deputy Minister for Regional Development and Tourism with an appeal to accelerate the preparations of the State Tourism Policy Concept for 2013+ period | June 2011 | Yes – on 16.6.2011 the letters was sent |  |  |  |

Action Plan from Evaluation of Possibilities and Feasibility of the Transfer of Funds in the Framework of IOP

| IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- |
| IA | Recommenda-tion/finding of the evaluator | CORRECTIVE MEASURE | DEAD-LINE | ACCOMPLISHED | CORRECTIVE MEASURE | DEAD-LINE | IB | ACCOMPLISHED |
| 1.1 | Fairly unclear methodology of monitoring of MI values by IB | 1) To require the ongoing values of MI (at least during the compilation of annual report and report on implementation) | Continu-ously | 1) Accom-plished, on 8.8.2011 the MoI sent the values of ratio indica-tors | 1) Establishment of a closer cooperation between the financial and project manager should contribute to better control of the fulfilment of MI 2) Within the revision of the set of indicators the SFD initiated the introduction of additional indicators expressed in numbers, which facilitate better monitoring of progress in the fulfilment of the MI concerned. | 1) Continu-ously 2) Prepa-ration of PD revision by 31.7.11 | 1)MoI 2)MoI | 1) As of 1.7. transfer between offices, PM-FM pairs assessing the same projects were formed 2) Indicators expressed in numbers were included in the National Code List. |
| 2.1 | Lack of relevant data and data with reporting value for the existing ratio values of MI | 1) To communicate intensively with IB on continuous exchange of original values | Continu-ously | Accomplished continuously | 1) To communicated the running values of ratio indicators to the MA (at least during the elaboration of the annual report and report on implementation) | Continu-ously | MoI | 1) Values of ratio indicators were sent to the MA on 8.8.2011, methodology for the calculation of ratio indicators is currently drafted in cooperation with the MA |
| 3.2 | Potential overstatement of target values of MI in activity 3.2c) or low efficiency or inadequate economy of support | 1) To control the fulfilment of the Action plan elaborated based on the audit of the 1st call | Continu-ously | Accomplished – control of the fulfil-ment of Action plan as of 31.03.12 | 1) More thorough analysis of implemented projects 2) Accomplished – call for activity 3.2c) was announced on 7. 3. 2012. External experts were involved in 3E control of projects. | 2) Continu-ously | MoH | 1) Audit of the 1st call was completed in April 2011 |
| 3.3 | Increase in allocation for 3.3a) from 3.3c) | 1) Discussed at the MC meeting 2) Following the approval, the preparation of justification of changes in the Programming Document 3) Preparation of the changed version of the Programming Document | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2)Sent to the EC on 28.7. 3) Sent to the EC on 28.7. | 1) Cooperation on the justification of changes in PD 2) Cooperation on the preparation of the changed version of PD | 1) By 31.7.11 2) By 31.7.11 | MoLSA | 1) Sent to the EC on 28.7. 2) Sent to the EC on 28.7. |
| 3.3 | Decrease in the allocation for 3.3c) | 1) Discussed at the MC meeting 2) Following the approval, the preparation of justification of changes in the Programming Document 3) Preparation of the changed version of the Programming Document | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2) sent to the EC on 28.7. 3) sent to the EC on 28.7. | 1) Cooperation on justification of changes in PD 2) Cooperation on the preparation of the changed version of PD | 1) By 31.7.11 2) By 31.7.11 | MoLSA | 1) Sent to the EC on 28.7. 2) Sent to the EC on 28.7. |
| 3.4 | Cancellation of the major project under 3.4 | 1) Discussed at the MC meeting 2) Following the approval, the preparation of justification of changes in the Programming Document 3) Preparation of the changed version of the Programming Document | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2) Sent to the EC on 28.7. 3) Sent to the EC on 28.7. | 1) Cooperation on justification of changes in PD 2) Cooperation on the preparation of the changed version of PD | 1) By 31.7.11 2) By 31.7.11 | MoI | 1) Sent to the EC on 28.7. 2) Sent to the EC on 28.7. |
| 3.4 | Cancellation of activity 3.4c) | 1) Discussed at MC meeting 2) Following the approval the preparation of justification of changes in the Programming Document 3) Preparation of the Programming Document version with tracked changes | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2) Sent to the EC on 28.7. 3) Sent to the EC on 28.7. | 1) Cooperation on justification of changes in PD 2) Cooperation on the preparation of PD version with tracked changes | 1) By 31.7.11 2) By 31.7.11 | MoI | 1) Sent to the EC on 28.7. 2) Sent to the EC on 28.7. |
| 3.4 | Modification/ extension of activity 3.4d) | 1) Discussed at MC meeting 2) Following the approval the preparation of justification of changes in the Programming Document 3) Preparation of the changed version of the Programming Document | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2) Sent to the EC on 28.7. 3) Sent to the EC on 28.7. | 1) Cooperation on justification of changes in PD 2) Cooperation on the preparation of the changed version of PD | 1) By 31.7.11 2) By 31.7.11 | MoI | 1) Sent to the EC on 28.7. 2) Sent to the EC on 28.7. |
| 3.4 | Increase in the allocation for 3.4d) from 3.4c) by allocation for the major project | 1) Discussed at MC meeting 2) Following the approval the preparation of justification of changes in the Programming Document 3) Preparation of the changed version of the Programming Document | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2) Sent to the EC on 28.7. 3) Sent to the EC on 28.7. | 1) Support for the applicants in the preparation of implementation of projects promoting the capability of IRS units which ensure adequate absorption capacity for the drawdown of allocation | After the approval of PD revision | MoI/ GD FRS | 1) Revision of PD was approved on 21.12., call announced as of 2.2.2012 |
| 5.1 | Increase in 5.1b) by additional funds pursuant to Article 17 of Interinstitu-tional Agreement | 1) Discussed at the MC meeting 2) Following the approval the preparation of justification of changes in the Programming Document 3) Preparation of the changed version of the Programming Document | 2) By 31.7.11 3) By 31.7.11 | 1) On 31.5.11 approved by the IOP MC 2) Sent to the EC on 28.7. 3) Sent to the EC on 28.7. | 1) Cooperation on justification of changes in PD 2) Cooperation on the preparation of the changed version of PD | 1) By 31.7.11 2) By 31.7.11 | MoC | 1) Sent to the EC on 28.7. 2) Sent to the EC on 28.7. |
| 5.1 | Insufficiently covered by indicators – result indicator 41.04.04 – Number of created methodologies in the cultural heritage area measures rather the outputs of activity a) | 1) Conduct of an analysis, to what extent the specific goals and activities can be measured by the existing indicators or other indicators (statistical or by data collected through specific surveys) | Decem-ber 2011 | 1) 1.7.2011 | 1) Cooperation on the conduct of an analysis of the measurability of specific goals and activities by the existing indicators 2) Modification of the definitions of indicators (detailed description, setting the baseline and target values, record keeping) – to be covered by the HAB revision | 1) Decem-ber 2011 2) July 2011 | MoC | 1) 1.7.2011 2) 1.7.2011 |
| 3.1 3.3 3.4 | To monitor the progress in the IAs at risk and the implementation of adopted measures | 1) Regular evaluation of progress 2) Regular meetings with IB 3) Evaluation of effectiveness of adopted measures | Continu-ously | 1) Being accomp-lished on a monthly basis 2) Being accomp-lished in line with WG deadlines 3) Being accomp-lished |  |  |  |  |
| 3.1 3.3 3.4 | To minimise the communication misunderstand-ings between the individual IBs as well as other problems related to the involvement of two IBs | 1) Regular communication with IB and responsible persons 2) Regular meetings at the level of IB directors 3) Regular meetings of working groups | Continu-ously | 1) Being accom-plished 2) Being accom-plished 3) Being accom-plished |  |  |  |  |
| 3.1 3.3 3.4 | To ensure the enforceability of the set out deadlines for work procedures | 1) Monitoring the observance of deadlines 2) Administrative checks of the observance of deadlines 3) Monitoring the submission of applications for payment and comparing it against the forecasts | Continu-ously | 1) Being accomplished 2) Check of the MoI deadlines, completed on 27.5.11, it will be the subject matter of checks in 2012 3) Being accompli-shed |  |  |  |  |

Action Plan from Analysis of Administrative Capacities and Outsourcing of IOP Intermediate Bodies

| Conclusions | IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEAD-LINE | ACCOMPLI-SHED | CORRECTIVE MEASURE | DEAD-LINE | TO BE DONE BY | ACCOM-PLISHED |
| 1. Total financial costs of IB in relation to the administered allocation Major differences in financial costs related to the administered allocation of the programme between the group of Intermediate Bodies (MoH, CRD and MoC) with CZK 1 000 per 1 million of administered allocation and MoI, MoLSA with costs by 50 – 80 % higher. | IOP MA in cooperation with the Intermediate Bodies will conduct an in-depth analysis of the extreme values with the view to clarify this difference, or to eliminate it. | By 31.12.11 | Based on the data as of 31.12.2011 an analysis will be conducted covering the whole year of 2011 | With regard to the extreme values, the individual IBs shall propose adequate measures to eliminate the risks arising from these results and shall inform the IOP MA about the proposed measures. | 15.11.2011 | MoI MoLSA | MoI – sent to the MA on 8.11. 2011 Settlement of comments sent to the MA on 8.12.2011 MoLSA – in the course of November and December 2011 the MoLSA held internal working meetings in order to reduce the administrative costs of minor part-time employment contracts of MoLSA staff involved in the IOP implementation. The internal meetings at MoLSA resulted in the reduced total number of MoLSA staff involved in the IOP implementation by 13 persons, i.e. from original 48 (July 2011) to 35 (December 2011). |
| 2. Total financial costs of administration of 1 project incurred by the IB Semi-annual costs per 1 approved project at the MoC and MoLSA exceed CZK 300 thousand as compared to the other IBs, where they range from 8 to 100 thousand. | IOP MA in cooperation with the Intermediate Bodies will conduct an in-depth analysis of the extreme values with the view to clarify this difference, or to eliminate it. | By 31.12.11 | Based on the data as of 31.12.2011 an analysis will be conducted covering the whole year of 2011 | With regard to the extreme values, the individual IBs shall propose adequate measures to eliminate the risks arising from these results and shall inform the IOP MA about the proposed measures. | 15.11.2011 | MoC MoLSA | MoC – 1. 2. 2012 the reasoning of the extreme value was sent MoLSA cooperates with IOP MA on the evaluation of barriers to absorption of funds under IA 3.1 and IA 3.3. Based on this evaluation it will be possible to reflect the proposed measures including potential modification in procedures and deadlines of administration of projects under IA 3.1. and IA 3.3, which increase the costs of MoLSA – IOP IB. |
| 3. Number of FTE in relation to the administered allocation Number of FTE involved in the administration of IOP at MoLSA per 1 billion of allocation is the highest of all the IBs (10.99 FTE), in the other IBs it ranges from 3.34 to 5.83 FTE per CZK 1 billion of the administered allocation. |  |  |  | MoLSA shall present reasons for the high number of part-time employees involved in IOP administration and covered from IOP TA and shall explain why the number has doubled since the end of 2010. | 15.11.2011 | MoLSA | Accomplished together with the corrective measure referred to under point 1 above. Starting with 1.12.2011 the number of part-time contracts was reduced by 3.1 FTE and by 13 persons involved |
| 4. Comparison of the structure of total financial costs of IBs High share of costs of outsourcing at MoI with respect to the high number of FTE, compared to the other IBs. | Revision of HAB in IOP TA, the IOP MA shall approve the project application and project budget prior to the project submission. Expenditure on activities, not approved in advance by the IOP MA in writing, will be considered ineligible. | 1.9.2011 | 1.9.2011 | The MoI shall submit to the IOP MA an analysis of the need for individual outsourced services and description of the management and control system of suppliers of outsourced services. | 15.11.2011 | MoI | MoI - Sent to the MA on 8.11. Settlement of comments sent to the MA on 8.12. |
| 5. Comparison of the structure of FTE Increasing share of FTE and costs of AWP/ AWA at the expense of skeleton staff at the MoI. |  |  |  | The MoI shall submit to the IOP MA an analysis of the need of AWP/AWA, which will contain: - detailed justification for the need of such a high number of FTE under AWP/AWA, - identification of activities performed by these persons, - management and control system of the work done under these agreements, - system of education and development of these employees. In case there is no system of management, control , education and development in place at the MoI, the MoI shall submit it to the MA by 31 Dec 2011. | 15.11.2011 | MoI | MoI - Sent to the MA on 8.11. Settlement of comments sent to the MA on 8.12. |
| 6. Mapping the administrative capacity | The IOP MA shall map the performance of administrative capacity at individual IBs. | Always as of 30.6. |  |  |  |  |  |
|  | The IOP MA shall extend the scope of regular reporting of administrative capacities as of 31 Dec of each calendar year and shall incorporate in this report also the obligatory description of the forecast for the following year. | By 31 January for the previous year | 31.1.2012 sent by all the IBs | The IBs will incorporate the description of the need for the following year in the Report on administrative capacities. | By 20 January for the previous year | All IBs | 31.1.2012 sent by all the IBs |
|  | The IOP MA shall prepare a form for reporting administrative capacities and shall send it to the IBs. | 31.11.2011 | 10.1.2012 the form sent to the IB |  |  |  |  |
| 7. Recommendations for controls | The IOP MA shall target the control of delegated activities on administrative capacity. | Continuously |  |  |  |  |  |
|  | The IOP MA shall reflect the risks ensuing from this evaluation in the update of the Catalogue of IOP Risks. | 31.12.2011 | It will be reflected in the Catalogue of Risks as of 31.12.2011 |  |  |  |  |
|  | The IOP MA shall prepare the “Analysis of matters related to 3E evaluation in IOP“ with the view to identify the possibilities of 3E control in IOP projects, incl. the possibilities of 3E control in TA projects. | 2nd Q 2012 |  |  |  |  |  |
| 8. Recommendation concerning the simplification for 2014-2020 period | For the preparation of 2014-2020 period to verify the effectiveness and cost-effectiveness with the involvement of 2 IBs in the implementation of one IA in the context of elimination of a risk or anticipated effect related to the involvement of 2 IBs. | Continuous-ly |  |  |  |  |  |

Action plan from the Audit on implementation of projects under the 1st call for Intervention area 3.2 of the Integrated Operational Programme

| Recommendation of the evaluator | Intermediate Body of the Ministry of Health |
| --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOMPLISHED |
| In this context we recommend to draft binding model purchase contracts for medical devices or purchase contracts for services (management and publicity), with the beneficiary being entitled to deviate from the binding model in duly justified cases. In our opinion, the requirements for EF Department capacity would decrease since only the changes made by the beneficiary (in the change procedure) and not the whole document would have to be checked. Similar procedure could be followed in case of contract documents, or other documents, that the MoH is obliged to check and that show a certain degree of uniformity. | a) To elaborate a model structure of contract documents in individual types of contracts – devices, management and publicity, and to post it on the web. | 30.9.2011 | a) Accomplished - on 19.10.2011 the model contract documents for the purchase of devices and calls for small-scale public contracts for the purchase of management and publicity services were published on www.mzcr.cz website. On 20.3. the model contract documents for purchase of devices (below-the-threshold and above-the-threshold open procedure) were published on www.mzcr.cz website in line with amendment to APC effective from 1.4.2012. |
|  | b) To stipulate that the draft contract, including the trade terms, shall always be included in contract documents in contracts of higher value | By the announcement of the next call, otherwise as recommended | b) Partly accomplished – incorporated in HAB for the 9th and 10th call as a recommendation – recommendations from the audit of implementation of projects of the 1st call were influenced by the fact that within the projects devices and equipment were simply purchased, which is why it is not difficult to draft a contract. Since in the 9th and 10th call much more complicated projects will be implemented, it would be a great challenge for lawyers of the beneficiary to draft a binding draft contract. The binding draft contract as an integral part of the conditions of the tender will be required in case another call is announced for Intervention area 3.2a, with a simple purchase only. |
|  | c) To elaborate a model structure of a draft contract in individual types of contracts – devices, management and publicity, and to post it on the web. | 30.9.2011 new deadline set at 31.05.2012 | September 2011 – partly accomplished, see point a) |
| Therefore we recommend to complement the existing or to draft a new checklist of documents which shall be a component part of documents included in the project file for each public procurement procedure. The existence of such a checklist would considerably reduce or eliminate the potential omission of any important document caused by human factor. This checklist would be made by the beneficiary at the commencement of works on public procurement procedure and submitted at fixed intervals to the project manager at the MoH for check, together with the documents that the beneficiary is obliged to forward to the implementing authority. In order to simplify the follow-up check, we recommend expanding the scope of documents archived by the MoH in order to have the full set of documents available at the MoH. To this end e.g. the checklist recommended in the point above can be used. | a) To propose a binding form of the structure of documents for tenders in the project file in archives. | 31.8.2011 new deadline set at 31.05.2012 |  |
|  | b) To include in the individual checklists for the check of individual steps of tenders and public procurement procedures the notes referring to the specific documents, pursuant to which the given question is checked, since the wording of majority of questions is pretty vague | 30.9.2011 New deadline set at 31.05.2012 |  |
|  | c) To use a list of mandatorily created and archived documents by individual type of tender/ public procurement procedure in the checks of the course of tenders and to send this list to beneficiaries, who will gradually mark in the list those documents which are already available to them in the tender and will send it together with the documents to be checked. | 30.9.2011 | On 28.7.2011 a new tab Documents to public contracts was created on www.mzcr.cz website in the European funds/IOP/Documents section. Under this tab the recommended list of documents for individual types of tenders by the foreseen value was published, which was defined in the corrective measure, posted under this tab were also e.g. model checklists for individual stages of control of public contracts by EF Department in order to inform the beneficiary about the pitfalls of the conduct of public contracts. Under this tab also other documents defined in the framework of other corrective measures will be published. Moreover, an information e-mail about the creation of the new tab, together with the List of documents for public contracts, was sent to beneficiaries. |
| We also recommend introducing a uniform system of files or directories in paper and electronic project files. This unification should consist in the development of a single structure of files (directories), creating versions of documents, rules for assigning names to files (directories) etc. We recommend arranging all the documents in the project files by their logical place in the process of public procurement procedure and not according to the date of delivery (naturally, the date of delivery has to be properly recorded). | a) To create a uniform binding structure of project files on “O” (the shared disc), which shall correspond to the structure of the paper file in the archive. | 31.8.2011 | On 18.8.2011 at the meeting of the department, the binding structure of project files on the O disc was presented. The employees received the graphic layout both in paper version and on the O disc. Gradual modification of files for individual calls will be done, which is under the responsibility of individual financial and project managers. The drafted proposal for the structure of the paper file will be used starting with projects under the 8th call. |
| We recommend to reconsider the approach to public contracts in case the contracting entity receives one bid only; if in such a case the beneficiary withdrew the public procurement and announced a new one, it would contribute to better transparency of the process of the award of public contracts and perhaps also to a lower purchase price. In case the contracting entity received again the bid from one supplier only, the public procurement procedure would take place in a standard manner. This procedure is common in some other operational programmes (e.g. OP Environment). | a) The obligation to withdraw a public contract in case of the receipt of one bid only. | Accomplished | January 2011 –through the adoption of Anti-corruption Strategy of MoH |
|  | b) To set up a system which makes it possible to continue with the public procurement procedure in case of one bid only, i.e. potential exceptions to the Order of the Minister, which is too strict and does not facilitate the possibility suggested in the recommendation – i.e. to continue in a public procurement procedure in case of repeated public contract or in other special cases. | 31.7.2011 | On 8.8.2011 the meeting of senior officials approved the Procedure for the control of the Order of Minister No 11/2011 Anti-Corruption Strategy for directly managed organisations, on this procedure was sent to beneficiaries and published on www.mzcr.cz website under the tab Documents for public contracts. Simultaneous, the IB and MA were informed about this document by the person responsible. |
| We recommend considering the practice of stating the technical qualification prerequisites in the form of a reference to the financial volume of past contracts in order to avoid excessive concentration in the sector. The qualification defined in financial terms results in the putting up of major barriers to the entry in the sector and in forming monopolistic and oligopolistic structures composed of established players. | a) To set out general rules for the application of technical qualification prerequisites – setting out of recommended limits of the volume of reference contracts and the amount of turnover with respect to the object of the contract. | 31.7.2011 | On 8.8.2011 the meeting of senior officials approved the Procedure for the control of the Order of Minister No 11/2011 Anti-Corruption Strategy for directly managed organisations, on this procedure was sent to beneficiaries and published on www.mzcr.cz website under the tab Documents for public contracts. Simultaneous, the IB and MA were informed about this document by the person responsible. |
| For the sake of better comparability and check of items, we recommend obligating the bidders in the next calls to identify the devices in line with the relevant standards of fit-out so that each item is easily identifiable and comparable in the budget, tender documents, bids and the contract. Unambiguous identification should consist in the consistent description of the item in line with the standard as well as the stated number of pieces. | a) To introduce a clear requirement that the names (of devices) of items shall be the same as the names used in the standards for fit-out. The same names shall be used in the project budget and the tender documents, draft contract, concluded contract and ideally also in the invoice. The specific type of a device with its name shall be a mandatory component of the contract, hand-over protocol and invoice. | By the announcement of the next call | a) Partly accomplished – it is stated in HAB for the 9th and 10th call as a recommendation to always use the same names , these calls are not intended for activity 3.2a, where the standards of purchased devices and equipment are set out. The corrective measure will be fully implemented in case a new call is announced for Intervention area 3.2a. |
|  | b) To consistently check the observance of this rule at individual stages of the project (e.g. at the stage of submission of the application, evaluation of the notification of changes, evaluation of tender documents etc.). | By the announcement of the next call | a) Partly accomplished – it is stated in HAB for the 9th and 10th call as a recommendation to always use the same names , these calls are not intended for activity 3.2a, where the standards of purchased devices and equipment are set out. The corrective measure will be fully implemented in case a new call is announced for Intervention area 3.2a. |
| The quality of elaboration of the checked tender documents created by the beneficiaries varies a lot, mainly as concerns the details of technical parameters. In this context we recommend that the Ministry of Health develops a uniform methodology for the creation of tender documents in tenders for the purchase of medical devices. This methodology should among other things contain the principles governing the setting up of a team responsible for the creation of tender documents (the team should be composed of medical doctors, a biomedical engineer, a clinical engineer, an IT expert, an economist, an expert at trade in medical devices and a trade law expert) so that the professional aspects of the purchase as well as necessary check are guaranteed through the participation of multiple independent professions. Moreover, the principles governing the creation of tender documents should prevent the emergence of a situation in which the parameters are set in a way to fit one supplier only. Since the quality of checked bids varied a lot and the technical parameters of devices included in the bid were not always adequately described, the methodology should also include the standards for the elaboration of technical description of items included in the bid. | a) To elaborate a uniform methodology for technical specification in public procurement procedures. | 31.12.2011 New deadline set at 31.5.2012 | Ad a) and b) On 8.8.2011 the Meeting of senior officials approved the document with the summary of corrective measures, implemented by the European Funds Department within the reinforced risk management, within which provided to the Meeting of senior officials was also the summary of recommendations from KPMG audit (this Action Plan) stressing the need to address the corrective measure ensuing from this recommendation in a comprehensive manner across the MoH. The Director General in charge of the directly managed organisations was request to consider the beneficial nature of this methodology for the health care sector. He considered this methodology beneficial. Currently, the drafting of this methodology was commenced. Beyond the scope of this recommendations, on 15.8.the MoH started to conduct the Analysis of the market with medical devices and equipment based on the results of public procurement procedures published on the Public Procurement Information system since the beginning of 2008, which can be used by the MoH as one of the input sources when drafting the methodology. The analysis has already been conducted. Its output was presented at the Meeting of senior officials on 7.11.2011. |
|  | b) The elaborate recommendations for the creation of tender documents concerning the principles of their creation, namely in the form of recommendations of the MoH for directly managed organisations and through its application also for the other beneficiaries. | 31.12.2011 New deadline set at 31.5.2012 |  |
| The tender documents should always state detailed information on the specific medical purpose for which the respective medical device is intended. Together with this purpose also stated should be the specific medical interventions to be performed by the device, their frequency and the resulting realistic usage of the device in the context of past and foreseen mix of activities performed by the respective workplace. The statement of the purpose will facilitate the selection of a more suitable device and also a more effective subsequent checks. Well described purpose stated in tender documents (together with the price limit that cannot be exceeded) can help prevent the purchase of devices with inadequate parameters at extortionate price. The support granted from EU Structural Funds frequently leads to the situation when the beneficiary with an approved budget states the maximum price and asks the manufacturer to offer the best device available at this price. This essentially rational conduct is conducive to the purchase of overly advanced (therefore also overly expensive) devices. | a) To stipulate that the medical purpose shall be stated in the tender documents. | Accomplished | January 2011 – accomplished by the adoption of Anti-Corruption Strategy of MoH |
|  | b) To perform consistent check of the statement of the medical purpose in the framework of checks of tender documents. | Continuously | Being accomplished on a continuous basis |
|  | c) The obligation to state the medical purpose in the technical specification annex already at the time of submission of the application for support – modification in the Handbook for applicants and beneficiaries. | By the announcement of a new call | c) Incorporated during the preparation of the 9th and 10th call, nonetheless it does not concern the calls under which primarily the medical devices and equipment will be purchased, i.e. it is irrelevant for them. |
|  | d) To conduct the check of eligibility of the medical purpose already during the check of applications for support in the framework of expert evaluation with respect to the following criteria: 2.2 Need of the project, 3.2 Technical and technological feasibility of the project, 3.4 Consistency of the project with the set out indicators and objectives – modifications in the Handbook for evaluators, presentations at the Seminars for evaluators. | By the announcement of a new call | See point c) The obligation to state the medical purpose in the technical specification annex already at the time of submission of the application for support – this obligation has already been stated in the HAB, Chapter C.2.6.2 Project documentation, point 3 |
| KPMG recommends considering the setting out of a financial limit for publicity in the future calls for IOP Intervention area 3.2 at the above referred to level. | a) To set out the financial limits for the item of publicity. | Accomplished | Starting with the 2nd call, precise limits are set out by the Handbooks for Applicants and beneficiaries |
| KPMG recommends considering the setting out of a financial limit for management services in the future calls for IOP Intervention area 3.2 at the above referred to level. | a) To set out the financial limits for the item of project management and monitoring. | Accomplished | a) Starting with the 2nd call, precise limits are set out by the Handbooks for Applicants and beneficiaries |
| KPMG clearly recommends applying the possibility of splitting the contracts pursuant to Section 98 of Act on public contracts for the purchase of medical technology in all the cases when the object of the contracts allows it. The conducted analysis indicates that in the prevailing majority of public procurement procedures implemented under the 1st call it was possible. This manner of the contract award will better contribute to the sound competition between the suppliers of medical technology and will help prevent the development of oligopolistic market structures and limit the tendency of strong players to divide the market between them by concluding cartel agreements. KPMG also recommends that in case the beneficiary in the framework of a grant project wishes to announce an above-the-threshold public contract for the purchase of medical technology without the possibility of contract splitting, this procedure is duly justified to the implementing authority. The MoH as the implementing authority should have the final say in the approval of such contracts. | a) To set the obligation of contract splitting pursuant to Section 98 in the relevant cases. | Accomplished | a) January 2011 – accomplished by the adoption of Anti-Corruption Strategy of MoH |
|  | b) To consistently check the application of Section 98 and the manner of splitting the contracts. The obligation is stipulated in the Order of the Minister No 5/2011 | Continuously | b)Starting with August 2011, the checklists for contract documents and the course of tenders started to be used, they include questions derived from the Anti-Corruption Strategy. Therefore a separate checklist is not used, which reduces the risk of omissions. |

Action Plan from the Interim Analysis of Communication Needs of the Ministry of Interior in the Field of EU Structural Funds

| Recommendation of the evaluator | Intermediate Body of the Ministry of Interior |
| --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOMPLISHED |
| SA communication |  |  |  |
| 1. SA communication should meet the objective of increased satisfaction of citizens with the public administration and better perception (image) of public administration by the general public | 1.1. Implementation of the “Quality of life” concept | 31.12.2015 |  |
| 2. SA communication should meet the objective of the increased transparency of public administration | 2.1 Direct communication with citizens - web; events | 31.12.2015 |  |
|  | 2.2 Introduction of particular persons | 31.12.2015 |  |
|  | 2.3 Presentation of particular projects in order to lift the barriers | 31.12.2015 |  |
| 3. SA communication should inform the professional public on its impacts | 3.1 Newsletter, seminars, workshops, one-to-one consultations, programming documents, methodologies, guidelines and handbooks | 31.12.2015 |  |
| COMMUNICATION STRATEGY |  |  |  |
| 4. Communication activities should focus primarily on the target group of general public | 4.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists, updates of websites, exploitation of social networks, events, promotional merchandise | 31.12.2015 |  |
| 5.To attach sufficient importance to information provided to the professional public; to introduce them to SA projects so that they are aware of its consequences and are able to further disseminate this information | 5.1 To be delivered through the newsletter, atlas of projects, workshops, one-to-one consultations | 31.12.2015 |  |
| 6. To present the SA projects in the broadest possible portfolio of media (ranging from television, through press up to social media) | 6.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists | 31.12.2015 |  |
| 7. To base the selection of suitable means of communication on the knowledge of what means are used by the respective target group | 7.1 Development of partial communication plans for 2011 – 2015 | 31.12.2015 |  |
| 8. To introduce primarily the common results of both the programmes (reduction in time spent at offices; support of investments in IT through education and training of clerks) | 8.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists, updates of websites, exploitation of social networks, events | 31.12.2015 |  |
| 9. To present the information on projects in a comprehensible manner; to give as many specific examples as possible. It is best served by the presentation of specific stories | 9.1 To be delivered through commercial supplements, media relations, press releases, meetings with journalists, atlas of projects | 31.12.2015 |  |
| 10. In SA project communication the total volume of support should always be mentioned | 10.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists, events, newsletter, atlas of projects | 31.12.2015 |  |
| “QUALITY OF LIFE CONCEPT “ |  |  |  |
| 11. When developing a single concept, to proceed from the conclusion of the Evaluation of IOP communication and publicity activities – single image communication strategy, to which all the staff contribute; cooperation among all the Incom and Excom units; uniform communication | 11.1 Involvement of all the InCom and ExCom unit, development of a single concept, agreement on single communication | 31.12.2011 | Provision of information to communication staff of IB |
| 12. To exploit the “Quality of life“ concept as the fundamental unifying communication objective | 12.1 Involvement of all the InCom and ExCom unit, development of a single concept, agreement on single communication | 31.12.2011 | Communication staff of IB is familiar with the concept and applies it in communication activities |
| RECOMMENDED TOOLS |  |  |  |
| DIRECT COMMUNICATION |  |  |  |
| 13. To continue to perform the already established activities | 13.1 To be delivered through technical seminars, one-to-one consultations, newsletter | 31.12.2015 |  |
| 14. At seminars to better respond to the participants' feedback (availability, specific examples, financial aspects, supporting documents) | 14.1 To better focus the content of seminars | 31.12.2011 | Being accomplished on a continuous basis - feedback – satisfaction questionnaires at each seminar – majority of participants are satisfied with the seminars and with the content, the content is clearly defined in the invitation to the seminar |
| 15. To focus on improved provision of seminars – regional coverage, capacity, parking places, services | 15.1 To outsource the implementation of the seminar | 31.12.2011 | 10.10.2011 A contract was concluded with Valero s.r.o. based on the tender |
| PUBLICATIONS |  |  |  |
| 16. To more intensively respond to the ongoing feedback concerning the Newsletter, especially with respect to its content, form of presented information and requirements | 16.1 To create a mechanism for feedback | 31.12.2011 | It will be included in the new tender for supplier of the newsletter, currently the contract documents are being finalised (also with respect to amendment to Act on public contracts) and the expected date of publication is June 2012. |
|  | 16.2 To continuously monitor the feedback in line with the proposed mechanism | 31.12.2015 |  |
| 17. To consider the scope of texts in the Newsletter which is sometimes overabundant | 17.1 To modify the content and design of the Newsletter; updates | 30.6.2012 |  |
| 18. To consider the publishing of a technical publication that would present selected projects implemented under the SA and supported from the European funds | 18.1 Publishing of the Atlas of projects | 31.12.2013 |  |
| MEDIA |  |  |  |
| 19. To continue to use the free of charge space in periodicals for advertisements whenever possible | 19.1 To be delivered through the establishment of relationships with journalists (media relations) | 31.12.2015 |  |
| 20. Special commercial supplement | 20.1 Creation | 30.6.2012 |  |
|  | 20.2 Creation of commercial supplements | 31.12.2013 |  |
| JOURNALISTS |  |  |  |
| 21. To consider the selection of attractive topics for press releases | 21.1 To be delivered through press releases | 31.12.2015 |  |
| ONLINE COMMUNICATION |  |  |  |
| 22. To create a special microsite for the presentation of the Quality of Life concept | 22.1 Creation of the microsite | 31.12.2012 |  |

# Footnotes

Number of submitted applications and number of Projects with issued Decision/signed Contract in multi-objective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero (except for Priority axis 4).

In Intervention area 3.1 the total amount of funds paid to beneficiaries (column d) is lower than the amount of funds included in aggregate applications for payment (column e), it is due to the technical aspects of the output report in MSC2007, which serves as a source of data for this table. It is caused by projects financed in ex-ante financing regime with the use of the so called limit (funding from an account for a limited amount), in which a part of the expenditure of the stage is financed through an order, i.e. in ex-post financing regime. The expenditure financed by an order is not included in column d in the table, but in column e.

This excessive demand for funds is caused particularly by the fact that the majority of projects in call No 01 for activities a) and b) was resubmitted following their rejection during the checks of formal requisites and eligibility.

Number of submitted applications and number of Projects with issued Decision/signed Contract in multiobjective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero (except for Priority axis 4).

In Intervention areas 1.1, 4.1a, 4.1b and 5.1 the amount of funds with issued Decision dropped in the monitored period dropped on the grounds of changes in projects.

Targets for the fulfilment of n+3/n+2 rule in individual years are set in accordance with Regulation of the EP and of the Council (EC) No 539/2010 of 16 June 2010 -  1/6 of the allocation for 2007 is spread over the years 2008-2013.

For the purpose of monitoring the statistical data on rejected projects it is essential to distinguish between the rejected and denied projects. Rejected projects = all projects in negative statuses. Denied projects = all projects in negative statuses with the exception of status N5 Project application withdrawn by the applicant and status N7 Project not completed/withdrawn. There is a difference between the case of a project rejected by the administrator or withdrawn by the applicant/beneficiary himself.

Number of submitted applications and number of Projects with issued Decision/signed Contract is due to the multiobjective nature of these priority axes given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero.

Number of submitted applications and number of Projects with issued Decision/signed Contract in multiobjective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero.

Number of submitted applications and number of Projects with issued Decision/signed Contract in multiobjective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero.