Report on implementation

Integrated Operational Programme

for the period

1 Apr 2012 – 30 Sep 2012

Intended for the 10th meeting of IOP Monitoring Committee

held on 21 Nov 2012

TABLE OF CONTENTS

INTRODUCTION	8

1 PROGRAMME IDENTIFICATION	9

2 OVERVIEW OF PROGRAMME IMPLEMENTATION	11

2.1 Summary Tables on Progress Achieved in IOP Implementation	11

2.2 Progress in the Fulfilment of Indicators at the Programme Level	18

2.3 Core activities in the period from 1 Oct 2011 to 31 Mar 2012	18

2.3.1 IOP milestones in the period from 1 Oct 2011 to 31 Mar 2012	18

2.3.2 Overview of on-going and newly announced calls in the period from 1 Apr 2012 to 30 Sep 2012	20

2.3.3 Changes in the IOP underlying documents and amendments thereto	21

2.4 Main Problems Encountered in programme Implementation and Measures Taken to Overcome Them	23

2.4.1 Addressing the error rate of IOP in the Annual Report for 2011	23

2.4.4 Coordination, monitoring and implementation of Smart Administration Strategy	27

2.5 Measures Adopted in Response to the Conclusions of the Previous Monitoring Committee Meeting	27

2.6 Analysis of Risks in relation to the Fulfilment of n+3/n+2 rule	28

2.6.1 Analysis of risks in relation to the fulfilment of n+3 rule by the Managing Authority and Intermediate Bodies	34

2.6.2 Forecast of the progress in IOP absorption (in EUR)	47

2.7 Analysis of Risks in Relation to Future Progress in Programme Implementation	57

2.8 Foreseen Timetable of the Announcement of Calls	61

2.9 Overview of Approved Projects	62

2.10 Progress in the Implementation of Financial Instruments	65

3 PROGRESS AT THE LEVEL OF PRIORITY AXIS	66

3.1 Priority axis 1a, 1b – Modernisation of public administration	66

3.1.1 Focus of priority axes/intervention areas	66

3.1.2 Progress achieved in the implementation of priority axes/intervention areas	67

3.1.3 Fulfilment of indicators	70

3.1.4 Problems and measures taken	71

3.1.5 Example of a project	72

3.2 Priority axis 2 – Introducing ICT in territorial public administration	73

3.2.1 Focus of priority axes/intervention areas	73

3.2.2 Progress achieved in implementation of priority axes/intervention areas	74

3.2.3 Fulfilment of indicators	75

3.2.4 Problems and measures taken	77

3.2.5 Example of a project	77

3.3 Priority axis 3 – Improving public services quality and accessibility	78

3.3.1 Focus of priority axes/intervention areas	78

3.3.2 Progress achieved in implementation of priority axes/intervention areas	79

3.3.3 Fulfilment of indicators	84

3.3.4 Problems and measures taken	91

3.3.5 Example of a project	96

3.4 Priority axis 4a, 4b – National support of tourism	100

3.4.1 Focus of priority axes/intervention areas	100

3.4.2 Progress achieved in implementation of priority axes/intervention areas	101

3.4.3 Fulfilment of indicators	104

3.4.4 Problems and measures taken	106

3.4.5 Example of a project	106

3.5 Priority axis 5 – National support of territorial development	107

3.5.1 Focus of priority axes/intervention areas	107

3.5.2 Progress achieved in implementation of priority axes/intervention areas	109

3.5.3 Fulfilment of indicators	114

3.5.4  Problems and measures taken	119

3.5.5 Example of a project	121

3.6 Priority axis 6a, 6b – Technical assistance	124

3.6.1 Focus of priority axes/intervention areas	124

3.6.1 Focus of priority axes/intervention areas	124

3.6.2 Progress achieved in implementation of priority axes/intervention areas	125

3.6.3 Fulfilment of indicators	128

3.6.4 Problems and measures taken	129

4 ADMINISTRATION OF THE PROGRAMME	130

4.1 Information on the Conduct and Results of Audits and Financial Controls	130

4.2 Implementation of the Communication Plan and Activities in the Field of Publicity	140

4.3 Conducted Evaluations and Studies	143

4.3.1 Evaluations conducted by the Managing Authority	143

4.3.2 Evaluation and studies carried out by the Intermediate Bodies	146

4.4 Other Activities of the Managing Authority and the Monitoring Committee	146

4.4.1 Activities of the Managing Authority	146

4.4.2 Activities of the Monitoring Committee	149

4.4.3 Activities of Working Groups	149

4.5 Administrative Capacity of Implementation Structure Entities of the Programme	152

5 MAIN CONCLUSIONS	157

LIST OF ABBREVIATIONS	158

ANNEXES	160

Annex No 1 – Publicity activities in the period from 1 Apr 2012 to 30 Sep 2012	161

Annex No 2 – Action Plans	171

Annex No 3 – System of monitoring of sleeping and risky projects	228

Annex No 4 – List of Sleeping Projects	231

Annex No 5 – Action Plan of NCA for IOP	233

Annex No 6 – Summary of Measures Taken in Response to the Conclusions of the Previous Meeting of IOP MC	254

List of Tables:

Table No 1 -	Allocation by year and objective (in EUR)	9

Table No 2 -	Intermediate Bodies broken down by intervention area	10

Table No 3 -	Status of IOP absorption cumulatively as of 30 Sep 2012 (in million CZK/EUR)	12

Table No 4 -	Progress achieved in IOP absorption in the period from 1 Apr 2012 to 30 Sep 2012 (in million CZK/EUR)	15

Table No 5 -	Overview of on-going and newly announced calls in the period from 1 Apr 2012 to 30 Sep 2012	21

Table No 6 -	Summary of sleeping and risky projects as of 10 Sep 2012	24

Table No 7 -	Fulfilment of n+3/n+2 rule (in EUR) under CONV objective	28

Table No 8 -	Fulfilment of n+3/n+2 rule (in EUR) under RCE objective	29

Table No 9 -	Average rate of ineligible expenditure based on the submitted applications for payment	30

Table No 10 -	Rate of fulfilment of forecasts necessary to fulfil the n+3 rule in 2012	48

Table No 11 -	Comparison of forecasts and the actually submitted applications for payment by intervention area	51

Table No 12 -	Comparison between the forecast and the actual value of submitted applications for payment by ministry	52

Table No 13 -	Comparison between the forecast and the actual value of approved applications for payment by intervention area	54

Table No 14 -	Comparison between the forecast and the actual value of approved applications for payment by ministry	55

Table No 15 -	Absorption of the total allocation as against the funds committed to completed tenders	56

Table No 16 -	Timetable of planned calls	61

Table No 17 -	Cumulative progress at the level of Intervention areas 1.1a and 1.1b (in mil. CZK/EUR)	68

Table No 18 -	Overview of on-going calls in the period from 1 Apr to 30 Sep 2012 in Priority axis 1a and 1b	69

Table No 19 -	Output indicators	70

Table No 20 -	Result indicators	70

Table No 21 -	Cumulative progress at the level of Intervention area 2.1 (in mil. CZK/EUR)	74

Table No 22 -	Output indicators	75

Table No 23 -	Result indicators	75

Table No 24 -	Cumulative progress at the level of Intervention area 3.1 (in mil. CZK/EUR)	79

Table No 25 -	Cumulative progress at the level of Intervention area 3.2 (in mil. CZK/EUR)	80

Table No 26 -	Cumulative progress at the level of Intervention area 3.3 (in mil. CZK/EUR)	81

Table No 27 -	Cumulative progress at the level of Intervention area 3.4 (in mil. CZK/EUR)	81

Table No 28 -	Overview of on-going calls in the period from 1 Apr to 30 Sep 2012 in Priority axis 3	83

Table No 29 -	Output indicators	84

Table No 30 -	Result indicators	85

Table No 31 -	Cumulative progress at the level of Intervention area 4.1a and 4.1b (in mil. CZK/EUR)	101

Table No 32 -	Overview of on-going calls in the period from 1 Apr to 30 Sep 2012 in Priority axis 4a and 4b	103

Table No 33 -	Output indicators	104

Table No 34 -	Result indicators	104

Table No 35 -	Cumulative progress at the level of Intervention area 5.1 (in mil. CZK/EUR)	109

Table No 36 -	Cumulative progress at the level of Intervention area 5.2 (in mil. CZK/EUR)	110

Table No 37 -	Cumulative progress at the level of Intervention area 5.3 (in mil. CZK/EUR)	110

Table No 38 -	Overview of on-going calls in the period from 1 Apr to 30 Sep 2012	112

Table No 39 -	Number of calls announced for IUDP	112

Table No 40 -	Information on IUDP allocation for Intervention area 5.2	113

Table No 41 -	Output indicators	114

Table No 42 -	Result indicators	115

Table No 43 -	Cumulative progress at the level of Intervention area 6.1a and 6.1b (in mil. CZK/EUR)	125

Table No 44 -	Cumulative progress at the level of Intervention area 6.2a a 6.2b (in mil. CZK/EUR)	126

Table No 45 -	Overview of on-going calls in the period from 1 Apr to 30 Sep 2012	127

Table No 46 -	Output indicators	128

Table No 47 -	Result indicators	128

Table No 48 -	Summary of checks of delegated activities at IBs conducted in the period from 1 Apr 2012    to 30 Sep 2012.	135

Table No 49 -	Overview of entities conducting checks of projects	138

Table No 50 -	Overview of checks conducted in the period from 1 Apr 2012 to 30 Sep 2012 in the breakdown by intervention area	139

Table No 51 -	Overview of checks conducted in the period from 1 Apr 2012 to 30 Sep 2012 in the breakdown by check status	139

Table No 52 -	Overview of checks conducted in the period from 1 Apr 2012 to 30 Sep 2012 in the breakdown by number of checks per IB	140

Table No 53 -	Overview of conducted education and training activities	148

Table No 54 -	Status of administrative capacity of IOP implementation structure	152

Table No 55 -	Monitoring the status of administrative capacity in 2007 – 2013 programming period	154

Table No 56 -	Monitoring of turnover rate by type position and implementation entity	156

List of Charts:

Chart No 1 -	Progress in IOP absorption as of 30 Sep 2012	18

Chart No 2 -	Sleeping and risky projects of IOP	25

Chart No 3 -	Overview of sleeping ad risky projects by intervention area	26

Chart No 4 -	Fulfilment of n+3 rule under CONV objective in 2011 and forecast for 2012 and 2013	31

Chart No 5 -	Fulfilment of n+3 rule under RCE objective in 2011 and forecast for 2012 and 2013	32

Chart No 6 -	Absorption of IOP funds with respect to n+3 rule	33

Chart No 7 -	Overview of certified expenditure and funds included in aggregate payment claims under IOP	34

Chart No 8 -	Fulfilment of  n+3 rule by the Ministry for Regional Development	35

Chart No 9 -	Fulfilment of n+3 rule in Intervention area 2.1	36

Chart No 10 -	Fulfilment of n+3 rule in Intervention area 3.4	37

Chart No 11 -	Fulfilment of n+3 rule in Intervention area 4.1	38

Chart No 12 -	Fulfilment of n+3 rule in Intervention area 5.2	38

Chart No 13 -	Fulfilment of n+3 rule in Intervention area 5.3	39

Chart No 14 -	Fulfilment of n+3 in Intervention area 6.1	40

Chart No 15 -	Fulfilment of n+3 rule in Intervention area 6.2	41

Chart No 16 -	Fulfilment of n+3 rule by the Ministry of Interior	42

Chart No 17 -	Fulfilment of n+3 rule by the Ministry of Labour and Social Affairs	43

Chart No 18 -	Fulfilment of n+3 rule in Intervention area 3.1	44

Chart No 19 -	Fulfilment of n+3 rule in Intervention area 3.3	45

Chart No 20 -	Fulfilment of n+3 rule by the Ministry of Health	46

Chart No 21 -	Fulfilment of n+3 rule by the Ministry of Culture	47

Chart No 22 -	Rate of fulfilment of forecasts of the submitted applications for payment by intervention area	48

Chart No 23 -	Rate of fulfilment of forecasts of the approved applications for payment by intervention area	49

Chart No 24 -	Rejected projects by intervention area	63

Chart No 25 -	Rejected project by status	64

Chart No 26 -	Comparison of physical and financial progress	71

Chart No 27 -	Comparison of physical and financial progress	76

Chart No 28 -	Comparison of physical and financial progress	86

Chart No 29 -	Comparison of physical and financial progress	88

Chart No 30 -	Comparison of physical and financial progress	89

Chart No 31 -	Comparison of physical and financial progress	90

Chart No 32 -	Comparison of physical and financial progress	105

Chart No 33 -	Comparison of physical and financial progress	116

Chart No 34 -	Comparison of physical and financial progress	117

Chart No 35 -	Comparison of physical and financial progress	118

# INTRODUCTION

The Integrated Operational Programme is implemented in the 2007-2013 programming period. The programme focuses on addressing common regional issues in the field of infrastructure for public administration, public services and territorial development: development of information technologies in public administration, improving the infrastructure for social services, public health, employment services and services in the field of security, risk prevention and management, support of tourism, cultural heritage, improving the environment in housing estates and development of systems for creation of territorial policies. The Managing Authority of IOP is the Ministry for Regional Development of the CR, the activities of Intermediate Bodies are performed by the Ministry of Interior of the CR, the Ministry of Labour and Social Affairs of the CR, the Ministry of Health of the CR, the Ministry of Culture of the CR and the Centre for Regional Development of the CR.

The total IOP allocation amounts to EUR 1 861.6 million, major part of which in the amount of EUR 1 827.0 million is channelled to the Convergence objective (assistance intended for the entire territory of the CR, except for the City of Prague), and EUR 34.5 million goes to the Regional competitiveness and employment objective (assistance intended for the territory of the City of Prague).

Details concerning the progress and implementation of IOP in the period from 1 Apr 2012 to 30 Sep 2012 are presented in this Report on Implementation intended for the 10th meeting of the IOP Monitoring Committee, compiled by the IOP Managing Authority in cooperation with other actors involved in the programme.

# 1 PROGRAMME IDENTIFICATION

The Integrated Operational Programme is implemented in the Czech Republic based on the National Strategic Reference Framework 2007-2013 programming period.

The IOP opted for the strategy of assistance at national level with all-national impact on improving the quality of life of inhabitants and enhancing attractiveness of the CR for investors as a result of better effectiveness and accessibility of public administration and public services. Due to the systemic concept of the assistance, it is necessary for the selected areas to be targeted at the whole territory of the CR, the City of Prague inclusive. Therefore, the IOP is designed as a multi-objective programme – in line with Article 32 para 1 of the General Regulation and on the basis of discussions with the EC,  apart from the main focus of assistance on the support to regions under the Convergence objective, it also facilitates the support granted under the Regional competitiveness and employment objective (RCE).

Allocation by year and objective (in EUR)

| Year | ERDF Convergence objective | ERDF RCE objective | Total |
| --- | --- | --- | --- |
| 2007 | 192 686 939 | 3 951 894 | 196 638 833 |
| 2008 | 202 164 946 | 4 030 931 | 206 195 877 |
| 2009 | 211 684 389 | 4 111 551 | 215 795 940 |
| 2010 | 221 648 970 | 4 193 781 | 225 842 751 |
| 2011 | 237 465 225 | 4 277 657 | 241 742 882 |
| 2012 | 247 398 119 | 4 363 210 | 251 761 329 |
| 2013 | 278 308 099 | 4 450 474 | 282 758 573 |
| Total for 2007 – 2013 | 1 591 359 687 | 29 379 498 | 1 620 736 185 |

Source: Programming Document, December 2011

In accordance with Government Resolution No 175/2006 the Ministry for Regional Development was designated to act as the IOP Managing Authority. The MA fulfils its tasks in line with Article 60 of Council Regulation (EC) No 1083/2006. Pursuant to Article 59 para 2, or Article 42 para 1 of Council Regulation (EC) No 1083/2006 the MA delegates some of the tasks to the Intermediate Bodies.

Due to insufficient administrative capacity, i.e. understaffing of the MoLSA and MoI, the MRD in 2009 concluded with the MoLSA and MoI the Addendum No 1 to the Agreement on delegating the tasks of the IOP Managing Authority. The Addenda concerned the involvement of CRD in the administration of projects under Intervention areas 2.1, 3.1, 3.3 and 3.4. Since 1 Jul 2012 there has been a change in delegated activities under Intervention areas 2.1 and 3.4. The remaining administrative activities have been transferred from the Ministry of Interior of the CR to the Ministry for Regional Development of the CR and the Centre for Regional Development of the CR.

The powers with respect to the individual IOP intervention areas are listed in the table below.

Intermediate Bodies broken down by intervention area

| Intervention area | Intermediate Body |
| --- | --- |
| 1.1 a, b Developing information society in public administration | Ministry of Interior CR (SF Department) |
| 2.1 Introducing ICT in territorial public administration | Centre for Regional Development CR |
| 3.1 Social integration services | Ministry of Labour and Social Affairs CR (EU Funds Implementation Department and Programme Financing Department), Centre for Regional Development CR |
| 3.2 Public health services | Ministry of Health CR (EU Funds Department) |
| 3.3 Employment services | Ministry of Labour and Social Affairs CR (EU Funds Implementation Department and Programme Financing Department), Centre for Regional Development CR |
| 3.4 Services in security, risk prevention and management | Centre for Regional Development CR |
| 4.1 a, b National support of tourism | Centre for Regional Development CR |
| 5.1 National support for utilising the cultural heritage potential | Ministry of Culture (Strategy and Aid Policy Department) |
| 5.2 Improving the environment in problematic housing estates | Centre for Regional Development CR |
| 5.3 Modernisation and development of systems for creating territorial policies | Centre for Regional Development CR |
| 6.1 a, b Activities connected with the IOP management and 6.2 a, b Other costs of the IOP technical assistance | Centre for Regional Development CR |

# 2 OVERVIEW OF PROGRAMME IMPLEMENTATION

## 2.1 Summary Tables on Progress Achieved in IOP Implementation

In line with the NCA guidelines for the elaboration of the Report on implementation the Submitted project applications column includes all the applications registered in IS Monit7+ as of 30 Sep 2012, namely also those that were rejected and will not be implemented. Projects with issued Decision/signed Contract column represents the financial volume of projects for which the Decision on providing a grant or the Statement of expenditure were issued.

Contrary to the previous reports, this column does not include prematurely terminated projects. In consequence for the sake of comparability of data the values of projects with issued Decision/Statement of expenditure given in the previous report were recalculated.

The approved projects in this report shall mean the projects with the issued Decision/Statement of expenditure (stated in the relevant tables). The monitored period shall mean the period from 1 Apr 2012 to 30 Sep 2012, i.e. the period covered by this report.

Status of IOP absorption cumulatively as of 30 Sep 2012 (in million CZK/EUR)

| PA/IA | 2007-2013 allocation | Submitted applications | Projects with issued Decision/Signed contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR |  | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| 1 | 9 762,08 | 393,52 | 79 | 11 570,01 | 119% | 465,43 | 54 | 8 771,95 | 90% | 353,69 | 2 990,89 | 31% | 121,14 | 2 700,20 | 28% | 109,45 | 775,68 | 8% | 31,94 |
| 1.1a | 9 064,79 | 365,41 | 79 | 10 743,58 | 119% | 432,18 | 54 | 8 145,38 | 90% | 328,43 | 2 777,26 | 31% | 112,49 | 2 507,33 | 28% | 101,63 | 720,27 | 8% | 29,66 |
| 1.1b | 697,29 | 28,11 | 0 | 826,43 | 119% | 33,24 | 0 | 626,57 | 90% | 25,26 | 213,63 | 31% | 8,65 | 192,87 | 28% | 7,82 | 55,41 | 8% | 2,28 |
| 2 | 5 002,47 | 200,98 | 5 839 | 5 465,67 | 109% | 219,87 | 5 484 | 4 519,02 | 90% | 181,53 | 818,69 | 16% | 32,68 | 777,01 | 16% | 31,00 | 265,10 | 5% | 10,63 |
| 2.1 | 5 002,47 | 200,98 | 5 839 | 5 465,67 | 109% | 219,87 | 5 484 | 4 519,02 | 90% | 181,53 | 818,69 | 16% | 32,68 | 777,01 | 16% | 31,00 | 265,10 | 5% | 10,63 |
| 3 | 16 003,60 | 641,30 | 672 | 18 592,85 | 116% | 747,93 | 307 | 11 539,51 | 72% | 461,73 | 4 325,66 | 27% | 171,54 | 4 233,45 | 26% | 167,83 | 1 870,60 | 12% | 74,69 |
| 3.1 | 2 316,39 | 93,18 | 352 | 2 756,80 | 119% | 110,90 | 47 | 751,05 | 32% | 30,21 | 61,24 | 3% | 2,46 | 64,14 | 3% | 2,58 | 30,85 | 1% | 1,27 |
| 3.2 | 7 321,14 | 292,33 | 188 | 8 270,96 | 113% | 332,72 | 152 | 5 994,49 | 82% | 238,96 | 3 550,17 | 48% | 140,64 | 3 455,01 | 47% | 136,81 | 1 664,18 | 23% | 66,58 |
| 3.3 | 1 362,46 | 54,81 | 24 | 1 817,90 | 133% | 73,13 | 8 | 604,93 | 44% | 24,34 | 83,72 | 6% | 3,37 | 83,76 | 6% | 3,37 | 9,53 | 1% | 0,40 |
| 3.4 | 5 003,61 | 200,98 | 108 | 5 747,18 | 115% | 231,19 | 100 | 4 189,04 | 84% | 168,21 | 630,53 | 13% | 25,06 | 630,53 | 13% | 25,06 | 166,03 | 3% | 6,45 |
| 4 | 1 905,94 | 76,74 | 150 | 3 513,73 | 184% | 141,35 | 46 | 1 177,07 | 62% | 47,42 | 241,91 | 13% | 9,80 | 223,59 | 12% | 9,06 | 177,38 | 9% | 7,20 |
| 4.1a | 1 769,80 | 71,26 | 75 | 3 262,77 | 184% | 131,25 | 23 | 1 092,99 | 62% | 44,03 | 224,63 | 13% | 9,10 | 207,61 | 12% | 8,41 | 164,70 | 9% | 6,69 |
| 4.1b | 136,14 | 5,48 | 75 | 250,95 | 184% | 10,09 | 23 | 84,08 | 62% | 3,39 | 17,28 | 13% | 0,70 | 15,98 | 12% | 0,65 | 12,68 | 9% | 0,51 |
| 5 | 13 441,96 | 540,25 | 1 589 | 21 233,68 | 158% | 854,16 | 1 396 | 9 999,65 | 74% | 401,78 | 4 042,89 | 30% | 162,15 | 4 024,73 | 30% | 161,42 | 1 969,97 | 15% | 79,74 |
| 5.1 | 6 741,52 | 270,95 | 51 | 15 815,05 | 235% | 636,19 | 19 | 5 981,77 | 89% | 240,38 | 1 397,57 | 21% | 55,98 | 1 390,03 | 21% | 55,67 | 489,84 | 7% | 20,02 |
| 5.2 | 6 233,50 | 251,03 | 959 | 4 917,01 | 79% | 197,80 | 868 | 3 588,58 | 58% | 144,64 | 2 228,30 | 36% | 89,92 | 2 219,85 | 36% | 89,58 | 1 152,41 | 18% | 47,02 |
| 5.3 | 466,94 | 18,27 | 579 | 501,63 | 107% | 20,18 | 509 | 429,31 | 92% | 16,76 | 417,02 | 89% | 16,26 | 414,86 | 89% | 16,18 | 327,73 | 70% | 12,70 |
| 6 | 1 343,22 | 53,96 | 95 | 1 444,62 | 108% | 58,11 | 87 | 981,72 | 73% | 39,42 | 419,15 | 31% | 16,79 | 409,61 | 30% | 16,40 | 343,99 | 26% | 13,79 |
| 6.1a | 796,08 | 31,97 | 36 | 1 035,39 | 130% | 41,65 | 33 | 754,54 | 95% | 30,30 | 333,91 | 42% | 13,38 | 324,54 | 41% | 13,00 | 270,08 | 34% | 10,84 |
| 6.2a | 522,89 | 21,01 | 59 | 383,15 | 73% | 15,41 | 54 | 209,45 | 40% | 8,40 | 77,67 | 15% | 3,10 | 77,67 | 15% | 3,10 | 67,69 | 13% | 2,70 |
| 6a | 1 318,97 | 52,98 | 95 | 1 418,54 | 108% | 57,06 | 87 | 963,99 | 73% | 38,71 | 411,58 | 31% | 16,48 | 402,21 | 30% | 16,11 | 337,78 | 26% | 13,54 |
| 6.1b | 14,63 | 0,59 | 0 | 19,04 | 130% | 0,77 | 0 | 13,87 | 95% | 0,56 | 6,14 | 42% | 0,25 | 5,97 | 41% | 0,24 | 4,97 | 34% | 0,20 |
| 6.2b | 9,61 | 0,39 | 0 | 7,04 | 73% | 0,28 | 0 | 3,85 | 40% | 0,15 | 1,43 | 15% | 0,06 | 1,43 | 15% | 0,06 | 1,25 | 13% | 0,05 |
| 6b | 24,25 | 0,97 | 0 | 26,08 | 108% | 1,05 | 0 | 17,72 | 73% | 0,71 | 7,57 | 31% | 0,30 | 7,40 | 31% | 0,30 | 6,21 | 26% | 0,25 |
| Total | 47 459,27 | 1 906,75 | 8 424 | 61 820,56 | 130% | 2 486,85 | 7 374 | 36 988,92 | 78% | 1 485,56 | 12 839,20 | 27% | 514,09 | 12 368,59 | 26% | 495,16 | 5 402,71 | 11% | 217,99 |

Source: MSC2007 as of 3 Oct 2012; CZK/EUR exchange rate (for conversion of columns a) – d): 24.859; for conversion of columns e) – f) the exchange rate valid at the time of entry into IS VIOLA is used

Source of funding – public funds total

Cumulatively as of 30 Sep 2012, a total of 8 424 project applications were submitted in IOP in the amount of EUR 2 486.85 million, which represents 130 % of the total allocation for the programme. The project applications submitted in the given intervention areas highly exceeded the allocation, namely in Intervention area 5.1 (235 % of the allocation), 4.1a and 4.1b (184 %), 3.3 (133%), 6.1a and 6.1b (130 %). The excessive demand for funds under Intervention area 5.1 is caused by the fact that majority of projects under the call No 01 for activities a) and b) was submitted again after being rejected during the check of formal requisites and eligibility. Also in Intervention areas 4.1a and 4.1b, 3.3 and 6.1a and 6.1b the excessive demand for funds is brought about by a high share of projects rejected most often during the eligibility check or scoring. In Intervention areas 6.1a and 6.1b, after deducting the project withdrawn from implementation the volume of submitted projects has almost reached 100% of the allocation.

Of all the submitted project applications a total of 7 374 projects in the amount of EUR 1 485.56 million were approved, which represents 78 % of the total allocation. The highest share of approved projects is reported by Intervention areas 6.1a and 6.1b (95%), 5.3 (92 %), 1.1a and 1.1b and 2.1 (90 %). The lowest share of approved projects, on the contrary, is exhibited by Intervention areas 3.1 (32 %) and 3.3 (44 %), 6.2a and 6.2b (40 %).

The beneficiaries were paid funds amounting to EUR 514.09 million, representing 27 % of the total programme allocation. The largest share of funds paid to beneficiaries with respect to the allocation is shown by Intervention area 5.3 (89%), 3.2 (48 %), 6.1a and 6.1b (42 %), with the largest volume of funds reimbursed in Intervention area 3.2 (EUR 140.64 million), 1.1a and 1.1b (EUR 121.14 million) and 5.2 (EUR 89.92 million). The lowest amount of funds was reimbursed in Intervention areas 3.1 (3 % representing EUR 2.46 million) and 3.3 (6 % representing EUR 3.37 million).

The aggregate payment claims (applications for payment) accounted for by the PCA totalled EUR 495.16 million, which represents 26 % of the total allocation. The trend is the same as in the volume funds reimbursed to beneficiaries. The largest volume of funds included in aggregate payment claims accounted for by the PCA is reported in Intervention area 3.2 (EUR 136.81 million), 1.1a and 1.1b (EUR 109.45 million), while the lowest volume is seen in Intervention areas 3.1 (EUR 2.58 million) and 3.3 (EUR 3.37 million).

The certified expenditure submitted to the EC equals a total of EUR 217.99 million and 11 % of the total allocation. The largest volume of certified expenditure is reported by Intervention area 3.2 (EUR 66.58 million, i.e. 23% of the allocation) and 5.2 (EUR 47.02 million representing 18 % of the allocation). With respect to the allocation, the highest volume of certified expenditure was shown in Intervention area 5.3, namely EUR 12.70 million representing 70 % of the allocation.

Progress achieved in IOP absorption in the period from 1 Apr 2012 to 30 Sep 2012 (in million CZK/EUR)

| PA/IA | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| 1 | 9 762,08 | 393,52 | 0 | 0,00 | 0% | 0,00 | -2 | -227,38 | -2% | -9,15 | 992,30 | 10% | 39,92 | 1 178,18 | 12% | 47,31 | -166,51 | -2% | -6,60 |
| 1.1a | 9 064,79 | 365,41 | 0 | 0,00 | 0% | 0,00 | -2 | -211,14 | -2% | -8,49 | 921,42 | 10% | 37,07 | 1 094,03 | 12% | 43,93 | -154,61 | -2% | -6,13 |
| 1.1b | 697,29 | 28,11 | 0 | 0,00 | 0% | 0,00 | 0 | -16,24 | -2% | -0,65 | 70,88 | 10% | 2,85 | 84,16 | 12% | 3,38 | -11,89 | -2% | -0,47 |
| 2 | 5 002,47 | 200,98 | 0 | 0,00 | 0% | 0,00 | -1 | -85,38 | -2% | -3,43 | 264,64 | 5% | 10,65 | 390,48 | 8% | 15,54 | -0,44 | 0% | -0,02 |
| 2.1 | 5 002,47 | 200,98 | 0 | 0,00 | 0% | 0,00 | -1 | -85,38 | -2% | -3,43 | 264,64 | 5% | 10,65 | 390,48 | 8% | 15,54 | -0,44 | 0% | -0,02 |
| 3 | 16 003,60 | 641,30 | 124 | 1 568,89 | 10% | 63,11 | 58 | 1 123,25 | 7% | 45,18 | 432,75 | 3% | 17,41 | 521,96 | 3% | 20,92 | -909,05 | -6% | -35,33 |
| 3.1 | 2 316,39 | 93,18 | 95 | 811,19 | 35% | 32,63 | 16 | 421,07 | 18% | 16,94 | 22,36 | 1% | 0,90 | 22,84 | 1% | 0,91 | 0,00 | 0% | 0,00 |
| 3.2 | 7 321,14 | 292,33 | 24 | 384,56 | 5% | 15,47 | 19 | -146,02 | -2% | -5,87 | 317,82 | 4% | 12,79 | 406,52 | 6% | 16,30 | -909,05 | -12% | -35,33 |
| 3.3 | 1 362,46 | 54,81 | 5 | 373,14 | 27% | 15,01 | 0 | -6,53 | 0% | -0,26 | 74,20 | 5% | 2,98 | 74,24 | 5% | 2,98 | 0,00 | 0% | 0,00 |
| 3.4 | 5 003,61 | 200,98 | 0 | 0,00 | 0% | 0,00 | 23 | 854,73 | 17% | 34,38 | 18,37 | 0% | 0,74 | 18,37 | 0% | 0,74 | 0,00 | 0% | 0,00 |
| 4 | 1 905,94 | 76,74 | 2 | 35,00 | 2% | 1,41 | 8 | 519,75 | 27% | 20,91 | 36,12 | 2% | 1,45 | 21,72 | 1% | 0,86 | 0,00 | 0% | 0,00 |
| 4.1a | 1 769,80 | 71,26 | 1 | 32,50 | 2% | 1,31 | 4 | 482,62 | 27% | 19,41 | 33,54 | 2% | 1,35 | 20,17 | 1% | 0,80 | 0,00 | 0% | 0,00 |
| 4.1b | 136,14 | 5,48 | 1 | 2,50 | 2% | 0,10 | 4 | 37,13 | 27% | 1,49 | 2,58 | 2% | 0,10 | 1,55 | 1% | 0,06 | 0,00 | 0% | 0,00 |
| 5 | 13 441,96 | 540,25 | 64 | 973,55 | 7% | 39,16 | 78 | 860,06 | 6% | 34,60 | 717,50 | 5% | 28,86 | 1 095,94 | 8% | 43,70 | -21,22 | 0% | -0,83 |
| 5.1 | 6 741,52 | 270,95 | 0 | 0,00 | 0% | 0,00 | 2 | 367,00 | 5% | 14,76 | 384,29 | 6% | 15,46 | 495,96 | 7% | 19,66 | -20,95 | 0% | -0,82 |
| 5.2 | 6 233,50 | 251,03 | 64 | 973,55 | 16% | 39,16 | 77 | 497,06 | 8% | 20,00 | 296,94 | 5% | 11,95 | 549,86 | 9% | 22,04 | -0,27 | 0% | -0,01 |
| 5.3 | 466,94 | 18,27 | 0 | 0,00 | 0% | 0,00 | -1 | -4,00 | -1% | -0,16 | 36,27 | 8% | 1,46 | 50,12 | 11% | 2,00 | 0,00 | 0% | 0,00 |
| 6 | 1 343,22 | 53,96 | 13 | 51,38 | 4% | 2,07 | 11 | 38,19 | 3% | 1,54 | 30,88 | 2% | 1,24 | 42,14 | 3% | 1,69 | -4,97 | 0% | -0,19 |
| 6.1a | 796,08 | 31,97 | 5 | 36,60 | 5% | 1,47 | 3 | 29,03 | 4% | 1,17 | 25,30 | 3% | 1,02 | 32,26 | 4% | 1,29 | -4,88 | -1% | -0,19 |
| 6.2a | 522,89 | 21,01 | 8 | 13,84 | 3% | 0,56 | 8 | 8,47 | 2% | 0,34 | 5,02 | 1% | 0,20 | 9,12 | 2% | 0,36 | 0,00 | 0% | 0,00 |
| 6a | 1 318,97 | 52,98 | 13 | 50,45 | 4% | 2,03 | 11 | 37,50 | 3% | 1,51 | 30,32 | 2% | 1,22 | 41,38 | 3% | 1,66 | -4,88 | 0% | -0,19 |
| 6.1b | 14,63 | 0,59 | 0 | 0,67 | 5% | 0,03 | 0 | 0,53 | 4% | 0,02 | 0,47 | 3% | 0,02 | 0,59 | 4% | 0,02 | -0,09 | -1% | 0,00 |
| 6.2b | 9,61 | 0,39 | 0 | 0,25 | 3% | 0,01 | 0 | 0,16 | 2% | 0,01 | 0,09 | 1% | 0,00 | 0,17 | 2% | 0,01 | 0,00 | 0% | 0,00 |
| 6b | 24,25 | 0,97 | 0 | 0,93 | 4% | 0,04 | 0 | 0,69 | 3% | 0,03 | 0,56 | 2% | 0,02 | 0,76 | 3% | 0,03 | -0,09 | 0% | 0,00 |
| Total | 47 459,27 | 1 906,75 | 203 | 2 628,81 | 6% | 105,75 | 152 | 2 228,48 | 5% | 89,64 | 2 474,20 | 5% | 99,53 | 3 250,43 | 7% | 130,02 | -1 102,18 | -2% | -42,98 |

Source: MSC2007 as of 3 Oct 2012; CZK/EUR exchange rate (for conversion of columns a) – d): 24.859; for conversion of columns e) – f) the exchange rate valid at the time of entry into IS VIOLA is used

Source of funding – public funds total

In the period from 1 Apr 2012 to 30 Sep 2012, a total of 203 applications in the amount of EUR 105.75 million were submitted. The most notable progress was achieved in Intervention areas 5.2 (EUR 39.16 million) and 3.1 (EUR 32.63 million), 3.2 (EUR 15.47 million) and 3.3 (EUR 15.01 million). In the monitored period, no project application was submitted under Intervention areas 1.1a and 1.1b, 2.1, 3.4, 5.1 and 5.3.

In the monitored period, 156 projects were approved and 4 projects were withdrawn, which means that in total the number of approved projects rose by 152 and the amount by EUR 89.64 million. The most remarkable progress was reported in Intervention area 5.2 (77 approved projects in the amount of EUR 20.00 million), 3.4 (23 approved projects in the amount of EUR 34.38 million), 3.1 (16 approved projects in the amount of EUR 16.94 million). In Intervention area 3.2, a total of 19 projects was approved, compared to the previous period the amount dropped by EUR 5.87 million due to the withdrawal of two projects. In Intervention area 3.3 no projects were approved, for 7 of 8 approved projects the Decision on providing a grant was issued for a lower amount. In the monitored period the amount declined by EUR 0.26 million.

The beneficiaries were reimbursed EUR 99.53 million, with the largest volume of funds paid to beneficiaries in the monitored period in Intervention areas 1.1a and 1.1b (EUR 39.92 million), in 5.1 (EUR 15.46 million), 3.2 (EUR 12.79 million), 5.2 (EUR 11.95 million) and 2.1 (EUR 10.65 million).

In the monitored period the aggregate payment claims accounted for by the PCA covered the amount of EUR 130.02 million and this trend corresponds to the progress seen in the reimbursement of funds to beneficiaries. In Intervention areas 1.1a and 1.1b EUR 47.31 million was reimbursed, in 5.1 EUR 19.66 million, in 3.2 EUR 16.30 million, in 5.2 EUR 22.04 million and in Intervention area 2.1 EUR 15.54 million.

In the monitored period no expenditure was certified (see Chapter 2.4.1 Addressing the error rate in IOP in the Annual Control Report for 2011). Due to the exclusion of those applications for payment in which a suspected irregularity is investigated, the amount of certified expenditure dropped by EUR 42.98 million.

The progress in IOP absorption in the period from 1 Apr 2012 to 30 Sep 2012 is illustrated in Chart No 1. The blue parts of bars indicate the status of absorption as of 31 Mar 2012, the violet parts of bars show the progress in the period from 1 Apr 2012 to 30 Sep 2012 and the total heights of bars represent the cumulative status of absorption as of 30 Sep 2012.

Progress in IOP absorption as of 30 Sep 2012

Source: MSC2007 as of 3 Oct 2012;  CZK/EUR exchange rate (for conversion of columns up to the funds paid to beneficiaries): 24. 859;  starting with the “funds included in aggregate payment claims” the exchange rate valid at the time of entry into IS VIOLA was used

Source of funding – public funds total

## 2.2 Progress in the Fulfilment of Indicators at the Programme Level

In line with the NCA guidelines for the elaboration of report on implementation, the chapter shall give only the indicators monitored by the Managing Authority, i.e. not the indicators monitored by external sources such as CSO, Eurostat, etc.

In the IOP at the level of the programme, 3 impact indicators are monitored, the achieved values of which are not generated at the project level and are monitored by the external source.

Due to the referred to facts no indicator is given in this chapter.

## 2.3 Core activities in the period from 1 Oct 2011 to 31 Mar 2012

### 2.3.1 IOP milestones in the period from 1 Oct 2011 to 31 Mar 2012

One of the milestones of the monitored period was the launch of full operation of basic registers on 1 Jul 2012.

Basic registers constitute one of the main pillars of eGovernment. The main goal is to make it easier for citizens, companies and other entities to communicate with the public administration, i.e. to minimise the number of visits to authorities and to exploit the potential of 21st century technologies for an on-line access from anywhere and at any point of time. Concurrently, the public administration shall provide for safe, effective and transparent exchange of accurate and up to date (the so called reference) data.

Apart from increased effectiveness of state administration, when the clerk does not have to make sure that the data is topical and correct, the processing of applications is sped up and the administrative burden is reduced. The citizen no more has to go to authorities e.g. when changing the name, place of permanent residence or a property ownership. In case this data is changed, it suffices to notify the closest authority thereof. Moreover, it is also possible to inform about the change also commercial institutions. If the citizen gives his approval, the authority sends a notification to the bank concerning the change of the name.

The creation and functioning of basic registers is stipulated by Act No 111/2009 Coll., on basic registers. The act establishes the respective basic registers and their administrators, defines their content, method of data entering, registered entities, provision of data and the associated rights and obligations. The act sets the date for the launch of operation of basic registers to be 1 July 2012.

The key element of the basic register system is the reference data which represents the most important data on natural persons, legal persons, government agencies, natural persons doing business, international organisations, territorial elements in the territory of the CR and agendas within the remit of public authorities based on the relevant legislation.

The basic registers started to operate on 1 July 2012 with a relatively small amount of reference data. Since the establishment of basic registers, each reference data is registered and also updated at one single place. The other systems take over this reference data in their own databases.

Thanks to these registers the citizens have acquired a powerful control tool. They enjoy the right to find out what officers have accessed the data kept on them and once a year they can require this information through CzechPOINT contact points. In case they avail of a data box, they will automatically receive the statement with this information.

The system of basic registers contains the following registers

- Registry of Persons (administered by the Czech Statistical Office)
Data on legal persons, natural persons doing business or public authorities.

- Registry of Inhabitants (administered by the Ministry of Interior CR)
Updated reference data on all citizens of the Czech Republic, foreigners with  residence permit in the CR, foreigners who were granted asylum or subsidiary protection in the territory of the CR and other natural persons to be registered in the Registry of Inhabitants pursuant to other laws and regulations.

- Registry of Territorial Identification Addresses and Real Estate (administered by the Czech Office for Surveying, Mapping and Cadastre)
Data on general territorial elements such as territory of the state, regions, municipalities or parts of municipalities, plots or streets.

- Registry of Rights and Obligations (administered by the Ministry of Interior CR)
Data on powers of public authorities, rights and obligations of persons.

- Information System of Basic Registers (administered by the Ministry of Interior CR)
It provides an operational framework for four basic registers. It is administered by the National Registers Authority.

- ORG - convertor (administered by the Office for Personal Data Protection)
The key project for personal data protection in registers; thanks to ORG convertor it is no more possible to obtain information on inhabitants virtually from any public administration information system with the knowledge of only a single indicator.

The basic registers have been running for 82 days and as of 20 Sep 2012 have executed thirty million transactions. In addition, more than sixty seven thousand statements have been issued through CzechPOINT contact points and non-stop online access to data without regular downtimes was launched on 17 Sep 2012. During almost three months no incidents occurred in the operation of basic registers.

All the milestones of IOP are summed up in the table below.

| Date | Activity |
| --- | --- |
| 4 Apr 2012 | Submission of the 3rd aggregate application for payment to the MoF |
| 5 Apr 2012 | Submission of the 4th aggregate application for payment to the MoF |
| 6 Apr 2012 | Submission of the 5th aggregate application for payment to the MoF |
| 30 Apr 2012 | Closing of the call No 13 of MoI for Intervention area 3.4, activity d) |
| 3 May 2012 | Submission of the 6th aggregate application for payment to the MoF |
| 4 May 2012 | Submission of the 7th aggregate application for payment to the MoF |
| 10 May 2012 | Closing of the call No 10 of MoH for Intervention area 3.2, activity b) |
| 17 May 2012 | Closing of the call No 9 of MoH for Intervention area 3.2, activity c) |
| 22 May 2012 | Submission of the 8th extraordinary aggregate application for payment to the MoF |
| 8 Jun 2012 | Submission of the 9th aggregate application for payment to the MoF |
| 12 Jun 2012 | Completion of an analysis of work procedure optimisation called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3“ |
| 1 Jul 2012 | Launch of full operation of the system of basic registers |
| 1 Jul 2012 | Transfer of delegated activities under Intervention areas 2.1 and 3.4 from MoI to MRD |
| 12 Jul 2012 | Submission of the 10th aggregate application for payment to the MoF |
| 28 Jul 2012 | Extension of call No 8 of MoLSA for Intervention area 3.1, activity c) |
| 1 Aug 2012 | Approval of the Action Plan for the Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 |
| 3 Aug 2012 | Submission of the 11th aggregate application for payment to the MoF |
| 8 Aug 2012 | Announcement of the 11th call of MoH for Intervention area 3.2, activity b) |
| 10 Aug 2012 | Announcement of the 15th call of MRD for Intervention area 3.4, activity d) |
| 16 Aug 2012 | Announcement of the 12th call of MoH for Intervention area 3.2, activity c) |
| 4 Sep 2012 | Announcement of the 14th call of MoI for Intervention area 1.1, activity a) |
| 6 Sep 2012 | Submission of the 12th aggregate application for payment to the MoF |
| 5 Sep 2012 | Commencement of the AA audit “Compliance with procedures in the fulfilment of administrative capacity in NSRF implementation structure “ |
| 7 Sep 2012 | Submission of the 13th aggregate application for payment to the MoF |
| 21 Sep 2012 | Submission of the 14th extraordinary aggregate application for payment to the MoF |
| 19-20 Sep 2012 | IOP Annual Conference in Ostrava – Quality of Life – Forms of social integration supported by EU |

### 2.3.2 Overview of on-going and newly announced calls in the period from 1 Apr 2012 to 30 Sep 2012

In the period from 1 Apr 2012 to 30 Sep 2012, the project applications were submitted under 15 calls for Intervention areas 1.1a a 1.1b, 3.1, 3.2, 3.3, 3.4, 4.1a a 4.1b, 5.2, 6.1a a 6.1b and 6.2a a 6.2b. In the monitored period 4 calls were announced. As at 30 Sep 2012, a total of 1 294 project applications in the amount of EUR 450.42 million were submitted under these calls. Altogether 1 013 projects in the amount of EUR 293.05 million were approved.

Detailed information on the calls is given under individual priority axes in Chapter 3.

Overview of on-going and newly announced calls in the period from 1 Apr 2012 to 30 Sep 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Inter-vention area/ac-tivity | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 2. | 01 | 5.6.2008 | 30.9.2015 | continuous | 6.1 a-e | 32 586 086 | 36 | 42 107 793 | 34 | 40 486 340 |
|  |  |  |  |  |  | 599 155 |  | 774 229 |  | 744 416 |
|  |  |  |  | Call total | 33 185 241 | 36 | 42 882 022 | 34 | 41 230 755 |
| 15. | 07 | 22.5.2009 |  | continuous | 5.2 a,b,c | 167 222 155 | 958 | 175 165 152 | 881 | 149 183 688 |
| 24. | 04 | 11.11.2009 | 30.6.2013 | continuous | 3.3 a,b | 39 092 793 | 16 | 65 140 385 | 7 | 23 748 163 |
| 36. | 10 | 27.9.2010 |  | continuous | 6.2 a-g | 12 778 984 | 35 | 5 585 935 | 33 | 4 757 022 |
|  |  |  |  |  |  | 234 965 |  | 102 708 |  | 87 467 |
|  |  |  |  | Call total | 13 013 949 | 35 | 5 688 643 | 33 | 4 844 489 |
| 40. | 06 | 31.5.2011 | 30.6.2013 | continuous | 3.1 b | 10 591 455 | 27 | 14 791 004 | 0 | 0 |
| 41. | 07 | 7.7.2011 | 30.6.2013 | continuous | 3.1 a | 32 658 058 | 34 | 32 344 862 | 7 | 6 387 902 |
| 42. | 08 | 29.7.2011 | 29.6.2012 | continuous | 3.1 c | 8 958 626 | 116 | 14 088 689 | 1 | 35 650 |
| 43. | 12 | 7.9.2011 |  | continuous | 4.1 a,c,e | 37 261 593 | 10 | 41 627 865 | 3 | 17 793 282 |
|  |  |  |  |  |  | 2 866 276 | 10 | 3 202 143 | 3 | 1 368 714 |
|  |  |  |  | Call total | 40 127 870 | 20 | 44 830 008 | 6 | 19 161 996 |
| 46. | 13 | 2.2.2012 | 30.4.2012 | continuous | 3.4 d | 40 668 592 | 28 | 40 668 592 | 23 | 34 757 819 |
| 47. | 9. | 7.3.2012 | 17.5.2012 | time-limited | 3.2 c | 9 569 080 | 8 | 5 565 279 | 6 | 4 758 137 |
| 48. | 10. | 7.3.2012 | 10.5.2012 | time-limited | 3.2 b | 9 569 080 | 16 | 9 254 337 | 15 | 8 939 512 |
| 49. | 11. | 8.8.2012 | 8.10.2012 | time-limited | 3.2 b | 11 961 350 | 0 | 0 | 0 | 0 |
| 50. | 15. | 10.8.2012 | 28.11.2012 | time-limited | 3.4 d | 6 459 129 | 0 | 0 | 0 | 0 |
| 51. | 12. | 16.8.2012 | 16.10.2012 | time-limited | 3.2 c | 20 334 296 | 0 | 0 | 0 | 0 |
| 52. | 14. | 4.9.2012 | 30.11.2012 | continuous | 1.1 a | 6 664 181 | 0 | 0 | 0 | 0 |
|  |  |  |  |  |  | 512 629 | 0 | 0 | 0 | 0 |
|  |  |  |  | Call total | 7 176 810 | 0 | 0 | 0 | 0 |
| CONV total |  |  |  |  | 446 375 460 | 1 284 | 446 339 893 | 1 010 | 290 847 513 |
| RCE total |  |  |  |  | 4 213 026 | 10 | 4 079 080 | 3 | 2 200 596 |
| IOP total |  |  |  |  | 450 588 486 | 1 294 | 450 418 973 | 1 013 | 293 048 110 |

Source: IS Monit7+ as of 2 Oct 2012

CZK/EUR exchange rate: 24.859

Source of funding – public funds total

### 2.3.3 Changes in the IOP underlying documents and amendments thereto

Update of IOP OM and IB OM, IOP MA OM

In July 2012, the MA commenced the revision of the Operational Manual of IOP. It was induced by amendments to legislation, corrective measures adopted in response to audit and evaluation findings, and efforts to complement and specify all the activities of MA and IB, to streamline the procedures and more clearly describe individual activities. The final version of IOP OM 1.4 will be distributed by the MA in December 2012 following the incorporation of comments. The OM revision will be followed by the revision of manuals of Intermediate Bodies that will be available in the first quarter of 2013.

On 24 Apr 2012, the MA finalised the first revision of the Operational Manual of IOP MA. It aimed to specify the activities of MA and complement the procedures for individual stages of programme implementation.

MA does not have an administrative capacity for the implementation of financial instrument JESSICA in IOP due to the complexity of the IOP and the state of funds. MA in relation to the amendment of the SFHD Act and the provisions 2.2.11 of Methodical communication on financial engineering instruments COCOF 10-0014-04 from 21.2.2011 identified the State Fund for Housing Development as the most appropriate body, which could spread over the FI JESSICA at the central level by the creation of a holding fund. SFHD with its nature is a financial institution with sufficient experience and know-how for successful administration of the operational program resources and fulfills the mission of the public housing policy in line with the fulfillment of Living concept of the Czech Republic until 2020.

Methodological Guidelines and Binding Opinions of IOP MA

Methodological Guideline No 33  Change in activities of the IOP Managing Authority delegated to the Ministry of Interior and the Centre for Regional Development of the CR, in force as of 1 Jul 2012.

This guideline  was issued in order to meet the task assigned by the 8th meeting of the IOP Monitoring Committee “, namely to inform the MC members on measures to improve absorption and management of projects in intervention areas falling under the powers of MoI“, and the task assigned by the 9th meeting, namely “to transfer the administration of projects, including adequate administrative capacity under Intervention area 2.1 by 29 Jun 2012; to make a decision on the transfer of activities and job positions under Intervention area 3.4 by 1 Jul 2012“.

Methodological Guideline No 34  Check lists for the purpose of control pursuant to Article 13, in force as of 31 Aug 2012

This methodological guideline was issued by the IOP MA to meet the requirements of the European Commission on achieving a consistent level of control system of programmes financed from EU SF.

Binding Opinion No 2 which reflects the update of the Binding Procedures, which came into force on 15 Jun 2012.

Binding Opinion No 3 which reflects the changed procedure at the beneficiary – government agencies, which came into force on 2 Jul 2012.

The binding opinion was issued in response to the amendment to Act No 218/2000 Coll., on budgetary rules and on amendments to some related laws, which amends the procedure to be taken by the provider in case of a breach of stipulated conditions by the beneficiary and which took effect on 30 Dec 2011.

Binding opinion No 4 which reflects the obligation to inform about the ownership and controlling structure of a legal person, which came into force on 10 Sep 2012.

This binding opinion was issued in response to the amendment to Act No 218/2000 Coll., on budgetary rules and on amendments to some related laws, which in Section 14 para 3 (e) newly stipulates the obligation of legal persons as of 1 Aug 2012 to disclose with the application for support the information on their ownership and controlling structure. The newly worded Section 18a stipulates the scope of documents and data relevant for the provision of assistance which are handed over by the provider to the Ministry of Finance of the CR. The documents and data will be posted on its website.

## 2.4 Main Problems Encountered in programme Implementation and Measures Taken to Overcome Them

### 2.4.1 Addressing the error rate of IOP in the Annual Report for 2011

The IOP error rate in the Annual Report for 2011 in the amount of 13.79 % was quantified based on the conducted DAB audit on operations in 2010-2011 period. In projects, in which the DAB identified ineligible expenditure, the IOP MA registered a suspected irregularity and referred the case to the Local Tax Office (LTO) and the Office for the Protection of Competition (OPC) for further  investigation. A prevailing part of these suspected irregularities have not been confirmed by the competent authorities. In some cases, concerning particularly the non-compliance with 3E principles when purchasing medical devices, the investigation has so far not been closed. Matters related to the purchase of medical devices have been handed over by the General Financial Directorate to the OPC with a suspected cartel agreement among major suppliers of medical devices.

The IOP MA disagreed with the quantified error rate and findings of the DAB audit on operations and presented to the AA its arguments disproving the DAB findings. As the MA concluded, the error rate should be below 2 %. The IOP MA disagrees primarily with the DAB finding concerning the purchase of medical devices since the ineligible expenditure was quantified by DAB based on a single expert opinion only, which according to the IOP MA lacks adequate professional value.

Based on additional investigations, results of concluded investigations of the LTO/OPC, results of the conducted audit of the EC No 2011/CZ/REGIO/J4/870/8 and based on the submitted IOP MA arguments, the Audit Authority revised the original error rate. After taking into account the non-confirmed irregularities, the error rate was decreased to 3.32 %. A detailed justification of the decreased error rate was sent by the Audit Authority to the EC on 4 Sep 2012. Additional documents were upon request of the EC sent by the AA on 27 Sep 2012.

Based on the DAB audit findings accepted by the IOP MA and based on the risks identified by the IOP MA in relation to the outputs of DAB  audits on operations, the IOP MA identified, adopted and implemented a number of measures such as:

- In line with amendment to Act No 137/2006 Coll., on public contracts, the IOP MA and IBs amend, complement and modify the checklists for control of public contracts in order for them to reflect the legislation in force and the findings of audit and control activities both of the IOP implementation structure and external entities, in the field of award of public contracts;

- IOP MA and IBs incorporated in their procedures the checklists used by the EC auditors for verifications pursuant to Article 13, controls of public contracts and state aid;

- In the framework of the current revision of the Operational Manual of IOP (IOP OM), the IOP MA shall complement e.g. the following:

  - Procedures for checking the observance of principles of economy, efficiency and effectiveness in the award of public contracts;

  - Obligation to check a public contract prior to the signing of the contract with a contractor/supplier (until now it was only optional);

- IOP MA modified the IOP risk management system so that with respect to 5 most significant risks faced by the programme it monitors at each IB the fulfilment of corrective measures to eliminate these risks or to reduce their impact on a monthly basis;

- IOP MA delegated the conduct of on-the-spot checks pursuant to Article 13 of the Implementing Regulation to IOP IB, nonetheless it also conducts control of implementation (or administrative checks) on a sample of projects in risky intervention areas;

- In order to enhance the expertise of control teams, the IOP MA exploits the services of external experts and professionals under the NCA project called “Support for the MA in the field of conduct of controls“ and it is also signed a contract with an external supplier facilitating an increased number of controls of delegated activities;

- IOP MA in cooperation with an external expert finalises the Analysis of evaluation and control of 3E (economy, efficiency and effectiveness) principles;

- IOP MA keeps organising training courses for IOP MA and IB staff that cover challenging or currently addressed topics. In the period from July to September, the training courses focused on the conduct of verifications pursuant to Article 13, identification and investigation of irregularities, criminal acts related to EU SF and state aid (see Chapter 4.4.1.3 Education and Training) were held.

Due to a high expected error rate given in the Annual Control Report of AA for 2011, upon an agreement between the MA, PCA and EC no expenditure incurred following 16 Sep 2012 is certified.

The implementation of IOP continues, the funds are paid to beneficiaries from national sources, the MA prepares aggregate applications for payment and submits them to the PCA. As of 30 Sep 2012, the expenditure prepared for certification by the IOP MA equals EUR 191.15 million under the Convergence objective and EUR 4.45 million under the RCE objective.

With respect to the achievement of n+3 target for 2012 (see Chapter 2.6), it is vital to recommence the certification of expenditure and to send the interim applications for payment to the EC.

2.4.3.1 Sleeping and risky projects of IOP

In the light of prevailing problems to meet the forecast absorption, starting with July 2012 the IOP MA introduced a system of monitoring and subsequently also management of sleeping and risky projects. The failure to fulfil the forecast absorption is caused primarily by non-compliance with the timetables of project implementation and postponement of activities to next project stages. Also considered were the conclusions of the 9th meeting of IOP MC, conclusions of the meeting with the EC on Smart Administration, the document of MRD-NCA on risky operational programmes submitted to the Government , and the document of IOP MA compiled and submitted to the Government in the spring of this year on risks faced in IOP implementation.

The IOP MA identified six risk parameters related to insufficient absorption, conduct of tenders and extension of project implementation, see Annex No 3 – System of monitoring of sleeping and risky projects. Based on these parameters it generated a report from IS Monit 7+ containing 451 projects under implementation which exhibited at least one risk parameter. The IOP Intermediate Bodies identified the specific problem in individual projects and assigned to it a matching measure as well as the deadline of its expected resolution. The IOP MA, having verified the adequacy of the selected measure, classified the level of risk of individual projects (sleeping, high-risk, risky, no-risk project). The final summary for the whole IOP is given in the following table and in Chart No 2, the overview by intervention area is given in Chart No 3.

Summary of sleeping and risky projects as of 10 Sep 2012

| IB | IA | Sleeping | High-risk | Risky | No-risk | Total |
| --- | --- | --- | --- | --- | --- | --- |
|  |  | number | volume in EUR | number | volume in EUR | number | volume in EUR | number | volume in EUR | number | volume in EUR |
| MoI CR | 1.1 | 5 | 42 141 976 | 9 | 78 939 536 | 7 | 33 286 153 | 10 | 86 612 669 | 31 | 240 980 333 |
| MoC CR | 5.1 | 1 | 7 920 811 | 4 | 48 216 643 | 1 | 13 641 886 | 0 | 0 | 6 | 69 779 340 |
| MoH CR | 3.2 | 5 | 6 273 756 | 10 | 19 084 492 | 30 | 35 262 724 | 9 | 5 258 099 | 54 | 65 879 071 |
| CRD | 2.1 | 4 | 2 157 405 | 13 | 29 115 219 | 17 | 42 470 206 | 9 | 12 969 360 | 43 | 86 439 189 |
|  | 3.1 | 0 | 0 | 2 | 1 081391 | 4 | 2 395 524 | 2 | 2 279 450 | 8 | 5 756 365 |
|  | 3.3 | 1 | 510 041 | 0 | 0 | 3 | 6 415 349 | 0 | 0 | 4 | 6 925 390 |
|  | 3.4 | 1 | 2 038 578 | 4 | 22 721 935 | 33 | 37 156 395 | 4 | 3 995 776 | 42 | 65 912 684 |
|  | 4.1 | 0 | 0 | 3 | 3 226 804 | 2 | 8 058 671 | 1 | 445 700 | 6 | 11 731 175 |
|  | 5.2 | 0 | 0 | 0 | 0 | 0 | 0 | 13 | 14 763 089 | 13 | 14 763 089 |
| IOP TOTAL | 17 | 61 042 566 | 45 | 202 386 020 | 97 | 178 686 908 | 48 | 126 051 143 | 207 | 568 166 637 |

Source: IS Monit7+IOP and IOP MA in cooperation with IBs as of 10 Sep 2012

CZK/EUR exchange rate: 24.859

Note: CRD - only projects above CZK 10 million (EUR 0.4 mil.)

Sleeping and risky projects of IOP

Source: IOP MA in cooperation with IB as of 10 Sep 2012

The IOP Intermediate Bodies focus primarily on projects classified as sleeping or high-risk projects and regularly, on a monthly basis, inform the IOP MA on progress made in the implementation of these projects.

The reports from IS Monit7+ will be generated on a quarterly basis and subsequently the same procedure will follow in order to update the monitoring of sleeping and risky projects.

Overview of sleeping ad risky projects by intervention area

Source: IOP MA in cooperation with IBs as of 10 Sep 2012

2.4.3.2 Transfer of delegated activities under Intervention areas 2.1 and 3.4 from MoI CR to MRD CR and CRD CR

On account of highly unsatisfactory situation in the implementation of intervention areas under the responsibility of the MoI CR, one of the measures to improve and accelerate the absorption was a change in delegated activities under Intervention areas 2.1 and 3.4 as at 1 Jul 2012. It consisted in a transfer of the remaining administrative activities from the Ministry of Interior of the CR (IOP Intermediate Body) to the Ministry for Regional Development of the CR (IOP Managing Authority) and the Centre for Regional Development of the CR.

This change was made as a result of conclusions of the 9th meeting of the IOP Monitoring Committee held on 31 May 2012, conclusions of the meeting with the European Commission on Smart Administration held on 30 Mar 2012, and subsequent agreement between the Minister of Interior and the Minister for Regional Development. The preparation of the change as such took more than six months and covered the modification of work procedures, revision of the content of handed over project files, checking of data entered in IS Monit7+, provision of staff capacities and drafting the amended agreement on delegating certain activities between MRD and MoI CR.

It aimed at the improved quality, reduced error rate and accelerated administration in Intervention areas 2.1 and 3.4 of IOP. Being relieved of this agenda, the SFD will subsequently have capacity to reinforce the administration and control of projects in Intervention area 1.1 of IOP. This change is also expected to reduce the SFD expenditure on outsourced activities and expenditure incurred in relation to the performance of delegated activities.

The agendas of MoI CR associated with the Smart Administration Strategy, physical responsibility for the field of introducing ICT in territorial public administration and services in security, risk prevention and management remain the responsibility of MoI CR.

Changes in the Agreement on delegating were discussed and approved by the Deputy Minister for Regional Development and the Deputy Minister of Interior and signed by both the ministers on 28 Jun 2012.

On 10 Jul 2012, the IOP MA in response to the change in delegated activities organised a seminar for beneficiaries under Intervention areas 2.1 and 3.4, on the occasion of which it introduced and explained to the beneficiaries all the changes, the updated Handbooks for Applicants and Beneficiaries and the timetable of the process of issuing the Decision on providing a grant by MRD as the new grant provider. The process of issuance of legal acts took longer than anticipated by the IOP MA, nevertheless it is foreseen by the IOP MA that once the IT problems, lengthy discussions of budgetary measures between MoI CR and MRD and complications arising from pilot testing of the State Treasury system at MRD are done with, the last legal acts will be finally issued before the end of October.

### 2.4.4 Coordination, monitoring and implementation of Smart Administration Strategy

The monitored period witnessed a considerable progress in implementation of the Smart Administration Strategy (hereinafter referred to as the Strategy) since the Basic registers of state administration were put into full operation and the last step was made to select the general contractor in other important projects of the Central Service Point and the Communication Infrastructure of Public Administration.

The Government Council for Information Society  (GCIS) approved three new strategic project outlines of the strategy. In July, the new Statute of GCIS was approved.

The Working Group for Project Evaluation identified the so called sleeping projects, the actual implementation of which considerably lags behind the planned timetable and thus threatens the due absorption of funds from ESF and has an adverse effect on the strategy implementation. In cooperation with the IOP and OP HRE Managing Authorities, crisis timetables were drawn up for these projects that were approved in the course of July and August during separate meetings with beneficiaries. Intensive discussions are held with the representatives of persons responsible for these sleeping projects and the projects are closely monitored, including the control of compliance with the approved crisis timetables.

In the framework of the strategy implementation monitoring, the Programme Management Department elaborated a periodical semi-annual report on the status of Smart Administration as at 30 Apr 2012.  Moreover, the annual report on the status of Strategy as at 30 May 2012 was elaborated and discussed by the Government. It includes the conclusions of the monitoring survey  among project holders which sums up the status of projects and their distribution among individual sources of funding and their link to the specific goals of the Smart Administration Strategy.

The publicity of Smart Administration also covered the update of the www.smartadministration.cz  website and a series of activities to make the strategy visible, including conferences and seminars.

## 2.5 Measures Adopted in Response to the Conclusions of the Previous Monitoring Committee Meeting

The previous 9th meeting of the IOP Monitoring Committee was held on 31 May 2012. The meeting arrived at a number of conclusions and assigned multiple tasks to the MA and individual IBs which are attached to this Report as Annex No 6.

## 2.6 Analysis of Risks in relation to the Fulfilment of n+3/n+2 rule

In order to fulfil the n+3 rule by the end of 2011 – 2013 period, the allocation for 2008 – 2010 shall be certified, while for the fulfilment of n+2 rule by the end of 2013-2015 period the allocation for 2011-2013 period shall be certified. In 2013 both the targets for n+3 and n+2 rule shall be achieved, i.e. the allocation for 2010 and 2011 shall be absorbed. In 2010, the n+3 rule was cancelled and the allocation for 2007 was spread over the following years of the programming period. The specific amounts of allocations (“Total EU allocation for 2007-2013 – annual“ column) and targets (“a” column – “n+3/n+2 targets - aggregate“) are given in the two tables below in a breakdown by objective. For the fulfilment of n+3/n+2 rule, the advance payments can be considered (column ”b” in the tables – “Advance payments from the EC – annual“), which will reduce the target for the given year.

Due to the anticipated high error rate stated in the Annual Control Report of AA for 2011, upon agreement between the MA, PCA and EC no expenditure incurred following 16 Sep 2011 has been certified, see Chapter 2.4.1 Addressing the error rate of IOP in the Annual Control Report for 2011.

The major prerequisite for the fulfilment of n+3 rule in 2012 is the relaunch of certification of expenditure. In case the expenditure incurred following 16 Sep 2011 is certified by the end of the year, the IOP MA will fulfil the n+3 rule by using a part of the advance payments received from the EC. The IOP MA aims to minimise the volume of advance payments used to fulfil the n+3 rule in 2012.

The following table clearly illustrates the targets for the fulfilment of n+3/n+2 rule under the Convergence objective in the individual years and the volume of expenditure certified so far, including the advance payments.

The target for 2011, that had to be absorbed in order to fulfil the n+3 rule under the Convergence objective by the end of 2011, equals EUR 234.28 million. By the end of 2011, expenditure totalling EUR 247.0 million was submitted for certification, thus the target was met. In February 2012, the PCA withdrew the 8th interim application for payment upon request of IOP MA and the amount of certified expenditure dropped to EUR 218.82 million.

In order to meet the n+3 target in 2012 the expenditure in the amount of EUR 478.08 million has to be certified and the expenditure in the volume of EUR 119.49 million shall be submitted by the MA for certification by the end of the year. As of 30 Sep 2012, expenditure in the amount of EUR 182.64 million is prepared by the MA for certification.

Fulfilment of n+3/n+2 rule (in EUR) under CONV objective

| Financing plan – year | Total EU allocation for 2007-2013 – annual | n+3/n+2 targets – aggregate ( | EC advance payments – annual | Interim /final applications for payment submitted to the EC – annual | Advance payments from EC + payment claims from the CR – annual | Advance payments from EC + payment claims - aggregate | Difference between the thresholds and payments – aggregate |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | a | b | C | d=b+c | E | f=e-a |
| 2007 | 192 686 939 |  |  |  | 0 | 0 |  |
| 2008 | 202 164 946 |  | 77 650 533 |  | 77 650 533 | 77 650 533 |  |
| 2009 | 211 684 389 |  | 62 120 427 | 5 008 671 | 67 129 098 | 144 779 631 |  |
| 2010 | 221 648 970 | - |  | 80 625 348 | 80 625 348 | 225 404 979 |  |
| 2011 | 237 465 225 | 234 279 436 |  | 133 186 699 | 133 186 699 | 358 591 678 | 124 312 242 |
| as of 30 Sep 2012 | 247 398 119 | 478 078 315 |  |  | 0 | 358 591 678 | -119 486 637 |
| 2013 | 278 308 099 | 1 001 421 489 |  |  |  |  |  |
| 2014 |  | 1 280 934 098 |  |  |  |  |  |
| 2015 |  | 1 591 356 687 |  |  |  |  |  |
| Total | 1 591 356 687 | 1 591 356 687 | 139 770 960 | 218 820 718 | 358 591 678 | 358 591 678 |  |

Note: The  n+3 rule is applicable for 2007-2010 period, the n+2rule is applicable for 2011-2013 period, the  n+3/n+2 rule  coincide in 2013. In 2010, the n+3 rule was cancelled and the allocation for 2007 was spread over the following years of the programming period.

Source: IOP MA, MSC2007 as of 30 Sep 2012

The fulfilment of n+3/n+2 rule under the Regional competitiveness and employment objective is illustrated in the following table, where the first target for the fulfilment of n+3 rule (column ”a” – “n+3/n+2 targets – aggregate“) was binding in 2011 and equals EUR 4.7 million. By the end of 2011 expenditure in the volume of EUR 4.4 million was submitted for certification. In order to meet the target, the advance payments in the amount of EUR 0.3 million were used. Following the withdrawal of the 8th interim application for payment the amount of certified expenditure under the RCE objective equals EUR 3.0 million.

In order to meet the n+3 target in 2012 the MA shall submit the expenditure in the volume of at least EUR 3.82 million for certification by the end of the year. As of 30 Sep 2012, expenditure in the amount of EUR 4.54 million is prepared by the MA for certification.

Fulfilment of n+3/n+2 rule (in EUR) under RCE objective

| Financing plan – year | Total EU allocation for 2007-2013 – annual | n+3/n+2 targets – aggregate ( | EC advance payments – annual | Interim /final applications for payment submitted to the EC – annual | Advance payments from EC + payment claims from the CR – annual | Advance payments from EC + payment claims - aggregate | Difference between the thresholds and payments – aggregate |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | a | b | C | d=b+c | e | f=e-a |
| 2007 | 3 951 894 |  |  |  | 0 | 0 |  |
| 2008 | 4 030 931 |  | 1 468 975 |  | 1 468 975 | 1 468 975 |  |
| 2009 | 4 111 551 |  | 1 175 180 | 3 569 | 1 178 749 | 2 647 724 |  |
| 2010 | 4 193 781 | - |  | 850 986 | 850 986 | 3 498 710 |  |
| 2011 | 4 277 657 | 4 689 580 |  | 2 137 974 | 2 137 974 | 5 636 684 | 947 104 |
| as of 30 Sep 2012 | 4 363 210 | 9 459 780 |  |  | 0 | 5 636 684 | -3 823 096 |
| 2013 | 4 450 474 | 19 248 516 |  |  |  |  |  |
| 2014 |  | 24 270 375 |  |  |  |  |  |
| 2015 |  | 29 379 498 |  |  |  |  |  |
| Total | 29 379 498 | 29 379 498 | 2 644 155 | 2 992 530 | 5 636 684 | 5 636 684 |  |

Note: The  n+3 rule is applicable for 2007-2010 period, the n+2rule is applicable for 2011-2013 period, the  n+3/n+2 rule  coincide in 2013. In 2010 the n+3 rule was cancelled and the allocation for 2007 was spread over the following years of the programming period.

Source: IOP MA, MSC2007 as of 30 Sep 2012

The Managing Authority monthly monitors the fulfilment of n+3 rule in 2012 by individual objective, grant provider and intervention area. The progress and the volume of absorbed funds in the monitored stages of administration are compared against the targets for 2012 and 2013 and the targets minus the advance payments from the EC, see the following charts by objective and charts for individual grant providers and intervention areas in Chapter 2.6.1 The Analysis of risks in relation to the fulfilment of n+3/n+2 rule by the Managing Authority and Intermediate Bodies.

In the following charts illustrating the fulfilment of n+3 rule the given volumes of funds are broken by the stage of project administration:

- Committed allocation is the allocation for the on-going calls and financial requirements of projects submitted in the already closed calls.

- Submitted projects comprise the funds of submitted project applications which were not rejected.

- Recommended for financing covers the funds of projects recommended for financing by the Selection Committee.

- Implementation of a project stage completed bar gives cumulative sums total of all the amounts under the completed project stages.

- Reimbursed applications for payment (payment claims) are the applications for payment that were paid already to aid beneficiaries.

- Certified bar gives the current volume of certified expenditure.

- The last two bars represent the forecast of certified expenditure in 2012 and 2013. The IOP MA in cooperation with IOP IBs based on its task C/10 “to prepare measures to improve the reporting value of forecast absorption”, assigned by the last meeting of the Monitoring Committee, recalculated the forecast of certified expenditure for 2013. The forecasts based on the planned timetables of projects were decreased by the average rate of ineligible expenditure ascertained by comparing the volume of submitted and approved applications for payment.

The table below illustrates the average rate of ineligible expenditure. The values were calculated by IOP MA based on the volume of submitted and approved applications for payment for individual ministries. The average rate was then applied when making the forecasts for respective intervention areas and the summary forecasts for respective objectives.

Average rate of ineligible expenditure based on the submitted applications for payment

| Intervention area | 1.1 | 2.1 | 3.1 | 3.2 | 3.3 | 3.4 | 4.1 | 5.1 | 5.2 | 5.3 | 6.1 | 6.2 | IOP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Rate of ineligible expenditure | 11,79% | 11,79% | 0,10% | 0,01% | 0,10% | 11,79% | 1,36% | 0,00% | 1,36% | 1,36% | 1,36% | 1,36% | 4,51% |

Source: IS Monit7+IOP as of 15 Jun 2012

The following chart depicts the fulfilment of n+3/n+2 rule in 2012 and 2013 under the Convergence objective. The volume of funds at individual stages of project administration and especially the forecast of certified expenditure by the end of 2012 is compared against the target for 2012 (EUR 478.08 million – orange line), or reduced by the advance payments received from the EC (EUR 338.31 million – yellow line). The forecast of certified expenditure by the end of 2013 is compared against the target for 2013 (EUR 1 022.23 million – light blue line), or reduced by the advance payments received from the EC (EUR 882.46 million – dark blue line).

In the event that the certification of expenditure takes place by the end of 2012, judging from the volume of reimbursed applications for payment and the forecast of future absorption the certification of expenditure in the volume of EUR 426.43 million can be foreseen. The target for 2012 would be achieved with the use of approximately one third of advance payments. By the end of 2013, according to the timetables of projects the certified expenditure could reach the amount of EUR 995.63 million. Provided there is no major postponement in project timetables, we may expect the fulfilment of n+3 and n+2 rules in 2013 with the use of advance payments.

Fulfilment of n+3 rule under CONV objective in 2011 and forecast for 2012 and 2013

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

Note: The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

The chart illustrating the fulfilment of n+3 rule for the Regional competitiveness and employment objective gives the volume of funds at individual stages of project administration and compares the forecast of certified expenditure in 2012 against the target for 2012 (EUR 9.46 million – orange line), or reduced by the advance payments received from the EC (EUR 6.82 million – yellow line). The forecast of certified expenditure by the end of 2013 is compared against the target for 2013 (EUR 19.25 million – dark blue line), or reduced by the advance payments received from the EC (EUR 16.60 million – light blue line).

The forecast certified expenditure indicates that as long as the certification of expenditure is relaunched during 2012, the volume of certified expenditure by the end of 2012 will reach EUR 7.19 million and the n+3 rule will be fulfilled with the use of most of the advance payments from the EC. By the end of 2013, according to the timetables of projects the certified expenditure could reach EUR 16.26 million, with the target being EUR 19.25 million. Provided there is no major postponement in project timetables, we may expect the fulfilment of n+3 and n+2 rules in 2013.

Fulfilment of n+3 rule under RCE objective in 2011 and forecast for 2012 and 2013

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

Note: The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

The following chart sums up the fulfilment of n+3 rule in 2012 expressed in percentage.

The n+3 target for the Convergence objective equals 30.04 % of the allocation, so far the expenditure amounting to 11.5 % of the allocation has been certified and the aggregate payment claims accounted for by the PCA have covered 25.96 % of the allocation.

Under the Regional competitiveness and employment objective, the n+3 target accounts for 32.20 % of the allocation and the certified expenditure amounts to 8.80 % of the allocation. The aggregate payment claims accounted for by the PCA cover 25.28 % of the allocation.

Absorption of IOP funds with respect to n+3 rule

Source: IS Monit7+ as of 3 Oct 2012

The chart below shows the monthly progress (violet part of bars) in the volume of funds included in aggregate payment claims and the volume of certified expenditure (yellow bars) for the period from January 2011 to September 2012.

As of 30 Sep 2012, the funds included in aggregate payment claims amounted to EUR 421.84 million. A total of seven certifications of expenditure were performed, the last one in 2011. The certified expenditure totals EUR 221.81 million. The most remarkable increase in the volume of aggregate payment claims by EUR 51.80 million occurred in September 2012. It is obvious from the chart that the volume of funds included in aggregate payment claims reached the n+3 target minus the advance payments in May 2012.

Overview of certified expenditure and funds included in aggregate payment claims under IOP

Source: Internal sources of IOP MA and PCA as of 30 Sep 2012; CZK/EUR exchange rate used at the time of accounting for in IS VIOLA

Source of funding: Community contribution

The IOP MA is fully aware of the risk of non-fulfilment of n+3/n+2 rule in 2013, especially due to the postponements of project timetables and tenders, and thus prepares measures to prevent it. The measures are to be introduced in October 2012, namely the limited approval of changes in timetables of stages, division of projects into stages with the view to increase the funds certified by the end of 2013, discussions with OPC concerning the closing of investigations which are the reason for suspension of administration of applications for payment, continuous consultations on applications for payment with beneficiaries.

### 2.6.1 Analysis of risks in relation to the fulfilment of n+3 rule by the Managing Authority and Intermediate Bodies

The n+3 rule shall be fulfilled at the level of objectives. For the purpose of monitoring the absorption of funds and programme management, the MA monitors the fulfilment of n+3/n+2 rule also by individual ministry and intervention area.

Ministry for Regional Development

The projects in Intervention areas 4.1a and 4.1b, 5.2, 5.3 and Priority axis 6 fall under the responsibility of the Ministry for Regional Development. Since 1 Jul 2012, the Ministry for Regional Development has been the grant provider also for projects in Intervention areas 2.1 and 3.4. In these intervention areas the projects in the total amount of EUR 542.17 million were submitted, projects in the amount of EUR 509.71 million are under implementation and implementation of stages amounting to EUR 199.34 million was completed. As of 30 Sep 2012, the funds paid to beneficiaries amounted to EUR 166.00 million.

The certified expenditure amounts to EUR 83.11 million and by the end of 2012 its volume is expected to reach EUR 180.36 million. The 2012 target is EUR 203.52 million, or EUR 144.04 million when considering the advance payments. The 2013 target is EUR 444.52 million, or EUR 385.05 million when considering the advance payments. Based on the timetables of projects, the IOP MA expects that the expenditure in the volume of EUR 428.32 million will be certified by the end of 2013.

- Fulfilment of  n+3 rule by the Ministry for Regional Development

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

The total amount of submitted projects in Intervention area 2.1 equals EUR 157.06 million and projects with the same volume of funds are under implementation. The completed stages amount to EUR 38.38 million and EUR 31.68 million was paid to beneficiaries. The certified expenditure accounts for EUR 9.03 million and by the end of 2012 is expected to increase to EUR 25.12 million. The 2012 target amounts to EUR 52.59 million, or EUR 37.22 million when considering the advance payments. The IOP MA anticipates that by the end of 2012 the certified expenditure will reach EUR 97.54 million, the 2013 target is EUR 109.51 million, or EUR 94.15 million, when the received advance payments are deducted.

The amount of forecast certified expenditure can be lower in consequence of delays in project implementation, postponements in the timetables of project activities and consequent inclusion of  expenditure in later certification.

Fulfilment of n+3 rule in Intervention area 2.1

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

In Intervention area 3.4 projects in the total amount of EUR 149.36 million were submitted and projects amounting to EUR 144.39 million are under implementation. The completed project stages total EUR 25.58 million and funds totalling EUR 21.56 million were paid to beneficiaries. The certified expenditure reached EUR 5.48 million and by the end of 2012 its volume is expected to increase to EUR 22.26 million. The 2012 target is EUR 52.59 million, or EUR 37.21 million. By the end of 2013, the IOP MA anticipates that expenditure amounting to EUR 109.07 million will be certified. The 2013 target for this intervention area is EUR 109.51 million, or EUR 94.13 million.

The volume of certified expenditure in 2012 and 2013 can be put at risk by delays in project implementation, postponements in the timetables of project activities resulting in later certification of expenditure.

Fulfilment of n+3 rule in Intervention area 3.4

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

In Intervention area 4.1a and 4.1b the submitted project applications amount to EUR 54.80 million and projects totalling EUR 40.06 million are under implementation. The volume of completed stages is EUR 8.79 million and funds amounting to EUR 8.02 million were paid to beneficiaries. The certified expenditure as of 30 Sep 2012 amounts to EUR 6.12 million. By the end of 2012, the forecast volume of certified expenditure is EUR 7.05 million, with the 2012 target being EUR 20.15 million, or EUR 14.28 million, when considering the advance payments. By the end of 2013, the IOP MA expects the expenditure in the amount of EUR 28.16 million to be certified, with the 2013 target being EUR 41.88 million, or EUR 36.01 million.

In order to fulfil the n+3/n+2 rule it is vital to accelerate the administration of tenders, applications for payment, and to divide or cut the project stages. The receipt of projects in the upcoming period will be reinforced by increasing the funds for the call No 12, in which sufficient absorption capacity was identified. Altogether 14 projects in the amount of EUR 36.28 million were submitted in call No 12.

Fulfilment of n+3 rule in Intervention area 4.1

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

In Intervention area 5.2 the submitted project applications total EUR 132.40 million, of which projects amounting to EUR 119.76 million are under implementation. The volume of completed stages is EUR 93.19 million and funds amounting to EUR 76.18 million were paid to beneficiaries. The certified expenditure accounts for EUR 39.96 million and by the end of 2012 it should reach EUR 95.71 million. The 2012 target is EUR 52.64 million. By the end of 2013, the certified expenditure should amount to EUR 149.81 million, with the 2013 target being EUR 140.48 million.

The administration of projects and reimbursement of applications for payment is smooth and the IOP MA does not anticipate any problems in the years to come.

Fulfilment of n+3 rule in Intervention area 5.2

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

The submitted project applications in Intervention area 5.3 amount to EUR 14.68 million and projects of the same amount are under implementation. The beneficiaries were paid a total of EUR 14.22 million. The volume of certified expenditure is EUR 10.80 million as of 30 Sep 2012. By the end of 2012, the certified expenditure should reach EUR 14.20 million, with the 2012 target being EUR 11.42 million. By the end of 2013, the expenditure in the amount of EUR 14.67 million should be certified, with the 2013 target being EUR 13.74 million.

In the monitored period the applications for payment were reimbursed smoothly, their volume exceeds the target for 2012 as well as for 2013. Following the recalculation of the exchange reserve, additional funds were allocated to the call for activity 5.3b), which is scheduled by the IOP MA for November 2012. No difficulties to achieve the n+3/n+2 targets in individual years are anticipated.

Fulfilment of n+3 rule in Intervention area 5.3

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

In intervention areas 6.1a a 6.1b the submitted project applications accounted for EUR 26.35 million and projects in the amount of EUR 26.27 million are under implementation. The volume of funds in completed stages of projects equals EUR 14.24 million and beneficiaries were paid EUR 11.63 million. The certified expenditure as of 30 Sep 2012 totals EUR 9.39 million and by the end of 2012 should reach EUR 13.16 million. The 2012 target is EUR 8.53 million. By the end of 2013 the certified expenditure should reach EUR 22.42 million, the 2013 target is EUR 17.74 million.

Fulfilment of n+3 in Intervention area 6.1

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

The volume of submitted project applications in Intervention areas 6.2a and 6.2b is EUR 7.53 million and projects in the amount of EUR 7.49 million are under implementation. The completed stages of projects total EUR 4.60 million and beneficiaries were paid EUR 2.70 million. The certified expenditure equals EUR 2.34 million and by the end of 2012 should reach EUR 2.85 million, with the 2012 target being EUR 5.60 million, or EUR 3.97 million when the advance payments received from the EC are deducted. By the end of 2013, the expenditure in the amount of EUR 6.64 million should be certified. The 2013 target is EUR 11.66 million, or EUR 10.03 million when the advance payments received from the EC are deducted.

As of 1 Sep 2011, the procedure governing the approval of expenditure on activities in IOP TA projects was made more stringent and all the IOP TA expenditure shall be approved by IOP MA before it is discussed by the Selection Committee for IOP Technical assistance projects. More stress is placed on economy, effectiveness and efficiency of the use of funds, which was conducive to lower absorption of IOP TA resources. The IOP MA adheres to the principle that the main objective of drawing the IOP TA resources it not the absorption all the allocated funds, but the economic, efficient and effective use of funds to cover the costs associated with the management, monitoring, control, analysis, publicity and provision of information at the level of IOP.

Fulfilment of n+3 rule in Intervention area 6.2

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

Ministry of Interior

As of 1 Jul 2012, there was a transfer of delegated activities in Intervention areas 2.1 and 3.4 from the Ministry of Interior to the Ministry for Regional Development and the Centre for Regional Development. The Ministry of Interior continues to be responsible for Intervention area 1.1a and 1.1b. Of the total amount of EUR 293.52 million, all the funds are allocated to projects under implementation. The amount covered by completed stages equals EUR 115.29 million and EUR 96.00 million was paid to beneficiaries.

The certified expenditure totals EUR 27.09 million and by the end of 2012 the IOP MA expects to increase its volume to EUR 89.51 million. The 2012 target is EUR 103.31 million, or EUR 73.20 million, when considering the advance payments. The n+3 rule should thus be fulfilled in 2012 with the use of a part of the advance payments. The 2013 target is EUR 214.77 million, or EUR 184.66 million. Based on the planned timetable of projects, the IOP MA expects that the expenditure amounting to EUR 234.12 million will be certified by the end of 2013, the n+3/n+2 rule should thus be fulfilled without the use of advance payments.

Factors influencing the risk of failure to achieve the n+3 target for 2012 are associated with the reasons behind the delays in project implementation, postponement of timetables of project activities and the related postponement in reimbursement of funds.

The IB applies extraordinary measures to the so called “sleeping and risky projects”  (binding crisis timetables, bilateral and trilateral meetings, detailed reporting, etc.) and also intensifies, also based on the recommendations of the National Coordination Authority and upon the consultation with the IOP Managing Authority, the communication with all the beneficiaries under Intervention area 1.1a and 1.1b in the framework of regular monthly meetings of working teams, the so called task-force of the project.

Fulfilment of n+3 rule by the Ministry of Interior

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

Ministry of Labour and Social Affairs

In Intervention areas 3.1 and 3.3, which fall within the remit of the Ministry of Labour and Social Affairs, as of 30 Sep 2012 the submitted project applications totalled EUR 101.95 million, of which projects amounting to EUR 80.89 million were recommended for financing by the Selection Committee and projects amounting to EUR 41.42 million are under implementation. The volume of funds of completed project stages equals EUR 6.13 million, of which EUR 5.07 million was paid to beneficiaries.

The certified expenditure totals EUR 1.41 million and by the end of 2012 is anticipated to reach EUR 4.49 million. Since the 2012 target, after the deduction of advance payments, is EUR 69.32 million, the fulfilment of n+3 rule in the intervention areas of MoLSA is not foreseen in 2012. The estimated volume of certified expenditure in 2013 is EUR 33.88 million and the 2013 target is EUR 69.32 million, when the received advance payments are deducted. The n+3/n+2 rule is not foreseen to be fulfilled in 2013 either.

Fulfilment of n+3 rule by the Ministry of Labour and Social Affairs

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

In Intervention area 3.1 the submitted project applications reached the total amount of EUR 57.79 million; projects totalling EUR 48.06 million were recommended for financing by the Selection Committee and projects amounting to EUR 20.53 million are under implementation. The completed project stages represent EUR 3.26 million and EUR 2.20 million was paid to beneficiaries. The certified expenditure totalled EUR 1.08 million and by the end of 2012 this amount should increase to EUR 2.13 million. The 2012 target is EUR 24.38 million, or EUR 17.25 million when subtracting the advance payments received from the EC. By the end of 2013 the certified expenditure should reach EUR 23.32 million, with the target for 2013 being EUR 50.77 million, or EUR 43.64 million when considering the advance payments received from the EC.

The MoLSA adopted measures directed at speeding up of project administration as well as subsequent support for the absorption of funds. In newly announced calls No 06 – 08,  the MoLSA makes changes conducive to the simplification of preparation of projects and their administration. In addition, the time consuming and financially demanding projects were divided into shorter stages so as to enable gradual reimbursement of funds and subsequent certification of expenditure. The adopted measures to minimise the failure to reach the n+3 target are described in more detail in Chapter 3.3.4  Problems and measures taken in Intervention area 3.1.

Fulfilment of n+3 rule in Intervention area 3.1

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

In Intervention area 3.3 the submitted project applications total EUR 44.16 million, projects with the financial volume of EUR 32.82 million were recommended for financing by the Selection Committee and projects in the amount of EUR 20.88 million are under implementation. The completed project stages represent EUR 2.87 million and all these funds were paid to beneficiaries. The certified expenditure reached EUR 0.34 million and by the end of 2012 its volume is foreseen to reach EUR 2.35 million. The 2012 target is EUR 14.34 million, or EUR 10.16 million when subtracting the advance payments received from the EC. By the end of 2013, the certified expenditure should reach EUR 10.56 million. The 2013 target is EUR 29.87 million, or EUR 25.68 million when subtracting the advance payments received from the EC.

The main reason behind the low volume of certified expenditure is particularly the late announcement of calls and in activity c) low interest of regions, because of which the call No 05 had to be closed in December 2011. Another factor is the postponement of the timetable of project implementation and the duration of individual stages. The MoLSA has identified projects in which it is fitting to sub-divide the stages and it has sent a letter to selected beneficiaries requesting the division of stages in order to facilitate gradual certification of expenditure.

Fulfilment of n+3 rule in Intervention area 3.3

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

Ministry of Health

Intervention area 3.2 falls within the remit of the Ministry of Health. Of the submitted project applications in the amount of EUR 204.81 million, projects amounting to EUR 195.57 million are under implementation. The amount of EUR 131.90 million is represented by completed stages of projects, of which EUR 121.40 million was paid to beneficiaries.

The certified expenditure totals EUR 56.59 million and by the end of 2012 it is anticipated to increase to EUR 117.85 million. The 2012 target is EUR 76.49 million. In 2013, the volume of certified expenditure is expected to reach EUR 186.77 million, with the target being EUR 159.29 million. The volume of certified expenditure should exceed the target for 2013.

A potential risk endangering the achievement of n+3 target in 2013 in Intervention area 3.2 is constituted by the so called sleeping projects. These are projects in which no visible progress was reported. In these sporadic cases the MoH CR in cooperation with the MA intensified communication with beneficiaries, adopted individual timetables of project implementation to facilitate gradual absorption of funds under these projects.

Since the beneficiaries have already had the opportunity to study in detail the changes brought about by the amendment to Act on public contracts, it may be assumed that the slowdown of absorption of funds caused by the extension of project implementation reported in this monitored period and the accompanying risk of non-fulfilment of n+3 rule will not be repeated again.

Fulfilment of n+3 rule by the Ministry of Health

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

Ministry of Culture

The Ministry of Culture is responsible for Intervention area 5.1, under which projects in the total volume of EUR 215.18 were submitted and projects amounting to EUR 192.38 million are under implementation. The volume of completed project stages totals EUR 48.93 million and EUR 47.63 million was paid to beneficiaries.

The certified expenditure accounts for EUR 17.02 million and by the end of 2012 the IOP MA anticipates its volume to reach EUR 41.40 million. The 2012 target, once the advance payments are subtracted, is EUR 46.34 million. In this intervention area the volume of certified expenditure will not achieve the target for 2012 . The IOP MA anticipates that in 2013 expenditure in the amount of EUR 120.10 million will be certified, with the 2013 target being EUR 123.09 million once the advance payments are subtracted. The IOP MA assumes that in 2013 the volume of certified expenditure will not be sufficient to exceed the n+3/n+2 target.

The non-fulfilment of n+3/n+2 rule can be brought about by factors identified by the MoC. In order to minimise their affect the MoC adopted the following measures:

Extension of project implementation, postponements in project timetables – the MoC reinforced the supervision over the fulfilment of timetable of project implementation which is continuously monitored, a crisis timetable of project implementation and absorption of funds was put in place and approved by beneficiaries. The beneficiaries monthly report to the Ministry of Culture and subsequently to IOP MA, and where necessary, trilateral meetings between beneficiaries, MoC and IOP MA are held.

The obligation to merge the quarterly stages in case the volume of eligible expenditure is lower than the threshold of CZK 10 million has been removed from the Handbooks for Applicants and Beneficiaries, which is expected to bring about smoother absorption of funds. Conversely, it was included in the Handbook for Applicants and Beneficiaries that the notification of a change, through which the beneficiary requests an extension of project implementation by more than 3 months, shall be subject to approval by the IOP MA.

Substandard activities of project teams – The MoC shall cut the eligible expenditure on salaries of project team members on the grounds of repeated erroneous or insufficient outputs.

Demanding public procurement procedures, delays in their conduct, appeals lodged by unsuccessful applicants to the OPC – in case of time consuming controls performed by OPC or TO, the IOP Managing Authority or the MoC send a letter to the respective authority requesting to accelerate the investigation.

Fulfilment of n+3 rule by the Ministry of Culture

Source: IS Monit7+ as of 30 Sep 2012; CZK/EUR exchange rate: 24.859

Source of funding: Community contribution

### 2.6.2 Forecast of the progress in IOP absorption (in EUR)

Based on the conclusions of the 9th meeting of the Monitoring Committee C/8, C/9 a (see Annex No 6 – Summary of measures taken with respect to the conclusions of the previous meeting of IOP MC) the MA in cooperation with IOP IB elaborated the monthly forecast absorption for the period from July 2012 until the end of 2013 and quarterly forecasts for 2014 a 2015. The forecasts are calculated in line with the measure to improve the reporting value of absorption forecasts, elaborated by the IOP MA based on the task C/10 and sent to the MC members on 31 Jul 2012.

The measures to improve the reporting value of absorption forecasts consist in the fact that the values calculated based on the temporal and financial timetables of projects reflect the modifications arising from the submitted requests for a change in projects and estimates of new projects that should be submitted under the on-going or planned calls. The final forecasts are reduced by the average rate of ineligible expenditure ascertained by the comparisons between the volume of submitted and approved applications for payment.

The table “Rate of fulfilment of forecasts necessary for the fulfilment of n+3 rule in 2012” shows the level of forecasts of submitted applications for payment which has to be attained in order to fulfil the n+3 rule without the use of advance payments. The IOP MA monthly evaluates the attainment of forecasts of the submitted applications for payment as against the necessary level of their attainment. It is obvious from the table that Intervention areas 1.1, 3.2, 5.2, 5.3 and 6.1 can achieve the n+3 target in 2012, when the advance payments are subtracted. In the other intervention areas the forecasts would have to be attained to more than 100%.

Rate of fulfilment of forecasts necessary to fulfil the n+3 rule in 2012

| Intervention area | 1.1 | 2.1 | 3.1 | 3.2 | 3.3 | 3.4 | 4.1 | 5.1 | 5.2 | 5.3 | 6.1 | 6.2 | IOP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Necessary rate of fulfilment of forecasts | 95,42% | 127,82% | 817,45% | 63,96% | 519,01% | 224,93% | 184,15% | 122,93% | 66,70% | 81,51% | 56,46% | 155,01% | 102,86% |

Source: IS Monit7+IOP as of 2 Jul 2012

Comparisons of the forecasts of submitted applications for payment against the actuals and the necessary rate of fulfilment of forecasts for the period from July to September 2012 are shown in Chart No 22.

Rate of fulfilment of forecasts of the submitted applications for payment by intervention area

Source: IS Monit7+IOP as of 30 Sep 2012

Sufficient volume of applications for payment in the 3rd quarter of 2012 for the fulfilment of n+3 rule without the use of advance payments was submitted by beneficiaries in Intervention areas 1.1, 3.2. 5.2 and 5.3  To the least degree the forecasts are fulfilled in Intervention areas 6.2 (11.64 %), 2.1 (25.12 %), 3.1 (32.95 %) and 3.4 (39.95 %), in which the rate of fulfilment has to exceed 100%. The specification of reasons and solutions of this situation is described in Chapters 2.6.2.1 and 2.6.2.2.

Rate of fulfilment of forecasts of the approved applications for payment by intervention area

Source: IS Monit7+IOP as of 30 Sep 2012

The fulfilment of forecasts of the approved applications for payment is best achieved in Intervention areas 1.1 (151.39 %), 3.3 (100.00 %), 5.3 (85.49 %), 5.2 (84.56 %) and 5.1 (81.56 %), whereas on the contrary the forecasts were not fulfilled in Intervention area 3.1 (0 %) and low fulfilment was reported by Intervention areas 6.1 (16.68 %), 6.2 (6.19 %) and 3.4 (40.64 %).

The following chapters 2.6.2.1 and 2.6.2.2 offer detailed comparisons between the forecasts and the actuals and quantify the difference between them and the rate of fulfilment of forecasts.

2.6.2.1 Submitted applications for payment (payment claims) – forecast (in EUR) and comparison with the actual status

In the period from July 2012 to September 2012, the forecasts of the submitted applications for payment were fulfilled to the level of 85.2 % for the programme as a whole,  there were however differences reported in individual intervention areas and IBs.

To the highest level the forecasts were fulfilled in Intervention area 5.2, where the applications for payment were submitted for the amount higher by EUR 5.35 million than planned.

The forecasts were most frequently exceeded by MoH IB (Intervention area 3.2), with the fulfilment to the level of 165.8 %, which represents the amount higher by EUR 0.83 million in the applications for payment submitted from July to September 2012. The overfulfilment of forecasts is caused especially by the fact that one beneficiary did not use the possibility to submit the application for payment of a larger volume of funds by the deadline set by the Handbook for Applicants and Beneficiaries.

In Intervention 5.3 the forecasts were fulfilled to the level of 102.8 %, which corresponds to the completion of implementation of the remaining projects in the 8th call as of 30 Jun 2012 and to the submission of the applications for payment before the end of July 2012.

In Intervention area 1.1a and 1.1b the value achieved was by EUR 1.37 million less than predicted, the forecasts were fulfilled to the level of 94.8 %. The fulfilment of forecasts was improved thanks to the new measures applied in the course of the monitored period (one-to-one meetings concerning sleeping projects, drafting the crisis timetables and regular  meetings of working teams in all the projects) and the release of administrative capacities of MoI for this intervention area.

In Intervention area 5.1 the forecasts were fulfilled to the level of 74.2 % since in reality the applications for payment were submitted for the amount  by EUR 2.03 million lower than the forecast amount of EUR 7.86 million. The lower volume of submitted applications for payment was caused primarily by protracted public procurement procedures and poor-quality work of some implementing teams. In the event of repeated erroneous or insufficient outputs of project teams, the MoC will cut the eligible expenditure on their salaries. Also the transfer of unabsorbed funds to next stages will be limited if the beneficiary fails to produce a convincing objective reason.

The approval of public procurement procedures has so far been reflected in IS after the submission of the monitoring report by the beneficiary, the MoC will therefore enter the topical information on public procurement procedures on an on-going basis based on the notification of a change received from beneficiaries by the deadline set in IOP OM.

In Intervention area 2.1 the forecasts were fulfilled to the level of 25.1 %, as against the forecast of EUR 6.80 million EUR 1.92 million was submitted. Low fulfilment of forecasts of the submitted applications for payment is influenced especially by the postponements in timetables of tenders, postponements of activities to next project stages, extension of deadlines of individual stages and extension of implementation of the whole project.

In Intervention area 3.1 the forecasts are fulfilled to the level of 33.0 %, which is brought about by the high number of projects not approved during the administration of project applications. As stated in Chapter 3.3.4 in Intervention area 3.1, the MoLSA decided to speed up the process of absorption by dividing the time consuming projects with high financial requirements into shorter stages.

In Intervention area 3.4 the forecasts were fulfilled to the level of 39.9 %. Low fulfilment of forecasts of the submitted applications for payment is caused primarily by delays in the implementation of the whole set of projects from the 11th call in connection to the implementation of an umbrella project of the Integrated Rescue System.

In Intervention area 4.1a the forecasts were fulfilled to the level of 47.9 % and in Intervention area 4.1b to the level of 49.8 %. The difference between these intervention areas is caused by later submission of one application for payment under 4.1a compared to the application for payment under 4.1b. The failure to fulfil the predicted values of applications for payment were caused by delays in the administration of tenders and applications for payment and the ex-ante checks under way which resulted in the postponements in timetable of projects and the subsequent submission of applications for payment. The IOP MA holds working meetings attended by main beneficiaries and CRD monitors the timetables of the conduct of tenders and discusses the division of projects into stages which is more effective with respect to the absorption.

In Intervention area 6.2a and 6.2b the projects are divided into stages that run throughout the  programming period and the IOP TA funds should be used by the Intermediate Bodies (IB) mainly for activities related to programme publicity and education and training activities, but the IBs absorb these funds to a negligible degree only. E.g., the education and training activities are mostly covered from the SB resources, the IBs frequently exploit the education and training activities provided by individual ministries. In the field of publicity, the activities stated in project applications are not fulfilled especially due to changes among senior officials of individual IBs accompanied by changes in plans concerning the use of IOP TA funds in the field of publicity. For these reasons the submitted applications for payment in IOP TA in this intervention area fulfil the forecasts to the level of 11.6%.

Comparison of forecasts and the actually submitted applications for payment by intervention area

| Priority axis / | Submitted applications for payment (payment claims) – forecast and actual (EUR) | SUM TOTAL for the period from July to September | Difference between the actual and the forecast | Rate of fulfilment of the forecast |
| --- | --- | --- | --- | --- |
| Intervention areas | July 12 | August 12 | September 12 | October 12 | November 12 | December 12 |  |  |  |
| 1.1a | 18 117 032 | 8 242 074 | 0 | 11 038 168 | 4 397 868 | 0 | 26 359 106 | -1 370 376 | 94,8% |
| Actual | 17 313 375 | 5 034 862 | 2 640 492 | - | - | - | 24 988 729 |  |  |
| 1.1b | 1 393 618 | 634 006 | 0 | 849 090 | 338 298 | 0 | 2 027 624 | -105 414 | 94,8% |
| Actual | 1 331 798 | 387 297 | 203 115 | - | - | - | 1 922 210 |  |  |
| 2.1 | 4 381 019 | 2 417 043 | 0 | 13 433 850 | 3 965 720 | 0 | 6 798 062 | -5 090 319 | 25,1% |
| Actual | 812 367 | 180 638 | 714 738 | - | - | - | 1 707 743 |  |  |
| 3.1 | 898 376 | 320 216 | 417 173 | 4 195 829 | 2 585 459 | 190 575 | 1 635 765 | -1 096 772 | 33,0% |
| Actual | 224 629 | 282 863 | 31 500 | - | - | - | 538 993 |  |  |
| 3.2 | 1 261 135 | 0 | 0 | 3 745 431 | 9 333 966 | 0 | 1 261 135 | 829 303 | 165,8% |
| Actual | 514 071 | 300 850 | 1 275 517 | - | - | - | 2 090 438 |  |  |
| 3.3 | 0 | 0 | 0 | 297 381 | 591 864 | 0 | 0 | 0 | - |
| Actual | 0 | 0 | 0 | - | - | - | 0 |  |  |
| 3.4 | 545 589 | 2 477 272 | 61 491 | 4 061 212 | 481 777 | 0 | 3 084 352 | -1 852 291 | 39,9% |
| Actual | 324 520 | 896 986 | 10 555 | - | - | - | 1 232 061 |  |  |
| 3 | 2 705 100 | 2 797 487 | 478 664 | 12 299 854 | 12 993 066 | 190 575 | 5 981 251 | -2 119 760 | 64,6% |
| Actual | 1 063 221 | 1 480 699 | 1 317 573 | - | - | - | 3 861 492 |  |  |
| 4.1a | 1 755 507 | 72 045 | 0 | 2 536 082 | 0 | 0 | 1 827 552 | -952 366 | 47,9% |
| Actual | 370 878 | 201 908 | 302 400 | - | - | - | 875 186 |  |  |
| 4.1b | 135 047 | 5 542 | 0 | 180 809 | 0 | 0 | 140 589 | -70 565 | 49,8% |
| Actual | 28 529 | 15 531 | 25 963 | - | - | - | 70 024 |  |  |
| 5.1 | 7 864 355 | 0 | 0 | 10 941 711 | 0 | 0 | 7 864 355 | -2 028 314 | 74,2% |
| Actual | 5 836 041 | 0 | 0 | - | - | - | 5 836 041 |  |  |
| 5.2 | 1 547 376 | 0 | 436 225 | 16 772 074 | 24 140 631 | 56 018 | 1 983 601 | 5 350 706 | 369,7% |
| Actual | 2 190 304 | 810 245 | 4 333 758 | - | - | - | 7 334 306 |  |  |
| 5.3 | 780 165 | 0 | 0 | 0 | 0 | 0 | 780 165 | 21 737 | 102,8% |
| Actual | 801 902 | 0 | 0 | - | - | - | 801 902 |  |  |
| 5 | 10 191 896 | 0 | 436 225 | 27 713 785 | 24 140 631 | 56 018 | 10 628 120 | 3 344 129 | 131,5% |
| Actual | 8 828 247 | 810 245 | 4 333 758 | - | - | - | 13 972 250 |  |  |
| 6.1a | 1 871 442 | 0 | 0 | 840 680 | 146 725 | 0 | 1 871 442 | -1 301 883 | 30,4% |
| Actual | 569 560 | 0 | 0 | - | - | - | 569 560 |  |  |
| 6.2a | 743 817 | 0 | 0 | 52 646 | 0 | 0 | 743 817 | -657 236 | 11,6% |
| Actual | 86 581 | 0 | 0 | - | - | - | 86 581 |  |  |
| 6a | 2 615 260 | 0 | 0 | 893 327 | 146 725 | 0 | 2 615 260 | -1 959 119 | 25,1% |
| Actual | 656 141 | 0 | 0 | - | - | - | 656 141 |  |  |
| 6.1b | 34 410 | 0 | 0 | 15 457 | 2 698 | 0 | 34 410 | -23 938 | 30,4% |
| Actual | 10 472 | 0 | 0 | - | - | - | 10 472 |  |  |
| 6.2b | 13 676 | 0 | 0 | 968 | 0 | 0 | 13 676 | -12 084 | 11,6% |
| Actual | 1 592 | 0 | 0 | - | - | - | 1 592 |  |  |
| 6b | 48 086 | 0 | 0 | 16 425 | 2 698 | 0 | 48 086 | -36 022 | 25,1% |
| Actual | 12 064 | 0 | 0 | - | - | - | 12 064 |  |  |
| Forecast TOTAL | 41 342 564 | 14 168 197 | 914 888 | 68 961 389 | 45 985 006 | 246 593 | 56 425 650 | -8 359 812 | 85,2% |
| Actual TOTAL | 30 416 620 | 8 111 179 | 9 538 039 | - | - | - | 48 065 838 |  |  |

Source: IS Monit7+ as of 30 Sep 2012

Source of funding: Community contribution

CZK/EUR exchange rate: 24.859

Comparison between the forecast and the actual value of submitted applications for payment by ministry

| IOP | Submitted applications for payment (payment claims) – forecast and actual (EUR) | SUM TOTAL for the period from July to September | Difference between the actual and the forecast | Rate of fulfilment of the forecast | Ministry |
| --- | --- | --- | --- | --- | --- |
|  | July 12 | August 12 | September 12 | October 12 | November 12 | December 12 |  |  |  |  |
| Forecast | 19 510 650 | 8 876 079 | 0 | 11 887 258 | 4 736 166 | 0 | 28 386 729 | -1 475 790 | 94,8% | MoI |
| Actual | 18 645 173 | 5 422 159 | 2 843 607 | - | - | - | 26 910 939 |  |  |  |
| Forecast | 898 376 | 320 216 | 417 173 | 4 493 210 | 3 177 323 | 190 575 | 1 635 765 | -1 270 588 | 33,0% | MoLSA |
| Actual | 224 629 | 282 863 | 31 500 | - | - | - | 538 993 |  |  |  |
| Forecast | 1 261 135 | 0 | 0 | 3 745 431 | 9 333 966 | 0 | 1 261 135 | 829 303 | 165,8% | MoH |
| Actual | 514 071 | 300 850 | 1 275 517 | - | - | - | 2 090 438 |  |  |  |
| Forecast | 7 864 355 | 0 | 0 | 10 941 711 | 0 | 0 | 7 864 355 | -2 028 314 | 74,2% | MoC |
| Actual | 5 836 041 | 0 | 0 | - | - | - | 5 836 041 |  |  |  |
| Forecast | 11 808 049 | 4 971 902 | 497 715 | 37 893 778 | 28 737 551 | 56 018 | 17 277 666 | -4 588 239 | 73,4% | MRD |
| Actual | 5 196 705 | 2 105 307 | 5 387 415 | - | - | - | 12 689 427 |  |  |  |

Source: IS Monit7+ as of 30 Sep 2012

Source of funding: Community contribution

CZK/EUR exchange rate: 24.859

2.6.2.2 Submitted applications for payment (payment claims) – forecast and the comparison with the actual status

The highest fulfilment of approved applications for payment is reported by Intervention area 1.1a and 1.1b, reflected also in this area are the adopted measures in the form of one-to-one meetings on sleeping projects and setting the crisis timetables as well as releasing the administrative capacities of MoI for IA 1.1a and 1.1b. In the course of August, following the completion of the control of tenders the projects Registry of Inhabitants and Registry of Rights and Obligations were approved. Under these projects applications for payment of large volume of funds were approved, which were foreseen to be submitted in January and July.

The forecasts of approved applications of payment were fulfilled to the full in Intervention area 3.3, where continuous certification of expenditure was safeguarded by sending a letter to the respective beneficiaries requesting a division into stages.

In Intervention area 5.3 the forecasts of approved applications for payment were fulfilled to the level of 85.5 %. Of the forecast value of EUR 1.09 million, EUR 0.93 million was approved. This corresponds with the fulfilment of forecasts in submitted applications for payment.

In Intervention area 5.2 the forecasts were fulfilled to the level of 84.6 %, the applications for payment are continuously submitted and approved.

In Intervention area 5.1 the forecasts were fulfilled to the level of 81.6 %. This reflects the fulfilment of forecasts of submitted applications for payment.

In intervention area 2.1 the forecasts were fulfilled to the level of 70.3 %. Of the forecast value of applications for payment of EUR 9.55 million, EUR 6.71 million was approved. As opposed to the submission of applications for payment, the actions are accelerated and forecasts are fulfilled to the higher level.

In Intervention area 3.2 the forecasts are fulfilled to the level of 70.3 %. Delays in approval of applications for payment occurred in September 2012, when the forecasts were no fulfilled to the full. The beneficiary postponed the submission of the application for payment which shall be approved only in October.

In Intervention area 4.1a and 4.1b the forecasts of applications for payment were fulfilled to the level of 60.1 %. Of the forecast value of EUR 2.20 million, EUR 1.32 million was approved. This value of approved applications for payment is by EUR 0.88 million lower than the forecast. The reason behind is the delay in implementation and administration of projects which has a direct impact on the achievement of n+3 target as well as on the volume of submitted and approved applications for payment. The IOP MA adopted a series of measures in the form of regular working meetings, monitoring of timetables of the conduct of tenders and discussions concerning more efficient division of projects into stages.

In Intervention area 3.4 the forecasts of approved applications were fulfilled to the level of 40.6 %. In reality, EUR 0.24 million was approved in August 2012, which had not been planned, while in September, on the contrary, the planned EUR 0.58 million was not approved. The situation corresponds with the status of fulfilment of forecasts of submitted applications for payment.

The forecasts were not fulfilled in Intervention area 3.1, where no applications for payment were approved in the period from July to September 2012, even though their forecast value was EUR 1.17 million. The most frequent reason is the fact that the beneficiary submitted the notification on a change together with the application requesting an extension of the stage or project implementation by up to 6 months and also the fact that the given application for payment is still administered by the CRD and was not submitted to the MoLSA.

Conducive to the very low fulfilment of forecasts in approved applications for payment in Intervention areas 6.1a and 6.1b, 6.2a and 6.2b were the following reasons:

- During the drafting of project applications the financial requirements for individual activities were overrated, mainly in long-term projects under Intervention area 6.1, the implementation of which was commenced in 2007, when the whole sum allocated to this intervention area was included by the IB in the budget of the projects;

- Protracted administration of the approval of applications for payment due to high error rate in the drafted applications for payment, mainly in the parts related to tenders and labour costs;

- Cancellation or merging of individual stages of projects most often due to the postponement of implementation of planned activities and extension of deadlines for the conduct of tenders.

Comparison between the forecast and the actual value of approved applications for payment by intervention area

| Priority axis / | Approved applications for payment (payment claims) – forecast and actual (EUR) | SUM TOTAL | Difference between the actual and the forecast | Rate of fulfilment of the forecast |
| --- | --- | --- | --- | --- |
| Intervention areas | July 12 | August 12 | September 12 | October 12 | November 12 | December 12 |  |  |  |
| 1.1a | 326 467 | 659 802 | 18 722 716 | 9 231 448 | 5 719 707 | 5 318 462 | 19 708 986 | 10 129 249 | 151,4% |
| Actual | 858 113 | 24 104 046 | 4 876 075 | - | - | - | 29 838 234 |  |  |
| 1.1b | 25 113 | 50 754 | 1 440 209 | 710 111 | 439 977 | 409 112 | 1 516 076 | 779 173 | 151,4% |
| Actual | 66 009 | 1 854 157 | 375 083 | - | - | - | 2 295 249 |  |  |
| 2.1 | 565 723 | 4 547 117 | 4 433 314 | 2 517 057 | 5 251 483 | 8 182 367 | 9 546 153 | -2 831 876 | 70,3% |
| Actual | 0 | 157 341 | 6 556 937 | - | - | - | 6 714 277 |  |  |
| 3.1 | 220 487 | 616 047 | 328 848 | 320 216 | 1 510 079 | 3 177 234 | 1 165 382 | -1 165 382 | 0,0% |
| Actual | 0 | 0 | 0 | - | - | - | 0 |  |  |
| 3.2 | 1 071 965 | 0 | 1 451 764 | 3 087 614 | 1 849 540 | 1 895 891 | 2 523 729 | -748 523 | 70,3% |
| Actual | 1 261 135 | 4 426 | 509 645 | - | - | - | 1 775 206 |  |  |
| 3.3 | 0 | 405 698 | 1 684 138 | 0 | 0 | 297 381 | 2 089 836 | -1 | 100,0% |
| Actual | 405 698 | 0 | 1 684 137 | - | - | - | 2 089 835 |  |  |
| 3.4 | 0 | 0 | 581 654 | 2 477 272 | 1 741 426 | 2 381 277 | 581 654 | -345 275 | 40,6% |
| Actual | 0 | 236 378 | 0 | - | - | - | 236 378 |  |  |
| 3 | 1 292 452 | 1 021 745 | 4 046 404 | 5 885 101 | 5 101 045 | 7 751 783 | 6 360 601 | -2 259 182 | 64,5% |
| Actual | 1 666 833 | 240 804 | 2 193 782 | - | - | - | 4 101 419 |  |  |
| 4.1a | 0 | 289 359 | 1 755 507 | 72 045 | 617 453 | 1 918 629 | 2 044 866 | -815 230 | 60,1% |
| Actual | 936 510 | 180 819 | 112 307 | - | - | - | 1 229 636 |  |  |
| 4.1b | 0 | 22 258 | 135 047 | 5 542 | 33 222 | 147 587 | 157 305 | -62 724 | 60,1% |
| Actual | 84 153 | 1 789 | 8 639 | - | - | - | 94 581 |  |  |
| 5.1 | 0 | 0 | 7 864 355 | 0 | 0 | 10 941 711 | 7 864 355 | -1 450 236 | 81,6% |
| Actual | 0 | 5 992 172 | 421 947 | - | - | - | 6 414 119 |  |  |
| 5.2 | 750 706 | 3 508 041 | 1 704 955 | 523 455 | 8 115 827 | 9 820 032 | 5 963 701 | -921 042 | 84,6% |
| Actual | 932 118 | 2 227 394 | 1 883 147 | - | - | - | 5 042 659 |  |  |
| 5.3 | 39 527 | 53 144 | 1 001 049 | 0 | 0 | 0 | 1 093 719 | -158 645 | 85,5% |
| Actual | 0 | 297 804 | 637 270 | - | - | - | 935 074 |  |  |
| 5 | 790 233 | 3 561 184 | 10 570 358 | 523 455 | 8 115 827 | 20 761 743 | 14 921 776 | -2 529 923 | 83,0% |
| Actual | 932 118 | 8 517 370 | 2 942 365 | - | - | - | 12 391 852 |  |  |
| 6.1a | 312 252 | 44 897 | 1 871 442 | 0 | 604 359 | 236 321 | 2 228 592 | -1 856 971 | 16,7% |
| Actual | 50 864 | 0 | 320 756 | - | - | - | 371 621 |  |  |
| 6.2a | 77 224 | 0 | 743 817 | 0 | 52 646 | 0 | 821 041 | -770 259 | 6,2% |
| Actual | 0 | 31 148 | 19 634 | - | - | - | 50 782 |  |  |
| 6a | 389 476 | 44 897 | 2 615 260 | 0 | 657 005 | 236 321 | 3 049 633 | -2 627 230 | 13,9% |
| Actual | 50 864 | 31 148 | 340 390 | - | - | - | 422 403 |  |  |
| 6.1b | 5 741 | 826 | 34 410 | 0 | 11 112 | 4 345 | 40 977 | -34 144 | 16,7% |
| Actual | 935 | 0 | 5 898 | - | - | - | 6 833 |  |  |
| 6.2b | 1 420 | 0 | 13 676 | 0 | 968 | 0 | 15 096 | -14 163 | 6,2% |
| Actual | 0 | 573 | 361 | - | - | - | 934 |  |  |
| 6b | 7 161 | 826 | 48 086 | 0 | 12 080 | 4 345 | 56 073 | -48 306 | 13,9% |
| Actual | 935 | 573 | 6 259 | - | - | - | 7 767 |  |  |
| Forecast TOTAL | 3 396 624 | 10 197 943 | 43 766 901 | 18 944 761 | 25 947 800 | 44 730 349 | 57 361 469 | -266 049 | 99,5% |
| Actual TOTAL | 4 595 536 | 35 088 046 | 17 411 837 | - | - | - | 56 551 302 |  |  |

Source: IS Monit7+ as of 30 Sep 2012

Source of funding: Community contribution

CZK/EUR exchange rate: 24.859

Comparison between the forecast and the actual value of approved applications for payment by ministry

| IOP | Approved applications for payment (payment claims) – forecast and actual (EUR) | SUM TOTAL for the period from July to September | Difference between the actual and the forecast | Rate of fulfilment of the forecast | Ministry |
| --- | --- | --- | --- | --- | --- |
|  | July 12 | August 12 | September 12 | October 12 | November 12 | December 12 |  |  |  |  |
| Forecast | 351 580 | 710 556 | 20 162 925 | 9 941 560 | 6 159 684 | 5 727 574 | 21 225 062 | 10 908 422 | 151,4% | MoI |
| Actual | 924 122 | 25 958 204 | 5 251 158 | - | - | - | 32 133 483 |  |  |  |
| Forecast | 220 487 | 1 021 745 | 2 012 986 | 320 216 | 1 510 079 | 3 474 615 | 3 255 218 | -1 165 383 | 64,2% | MoLSA |
| Actual | 405 698 | 0 | 1 684 137 | - | - | - | 2 089 835 |  |  |  |
| Forecast | 1 071 965 | 0 | 1 451 764 | 3 087 614 | 1 849 540 | 1 895 891 | 2 523 729 | -748 523 | 70,3% | MoH |
| Actual | 1 261 135 | 4 426 | 509 645 | - | - | - | 1 775 206 |  |  |  |
| Forecast | 0 | 0 | 7 864 355 | 0 | 0 | 10 941 711 | 7 864 355 | -1 450 236 | 81,6% | MoC |
| Actual | 0 | 5 992 172 | 421 947 | - | - | - | 6 414 119 |  |  |  |
| Forecast | 1 752 593 | 8 465 641 | 12 274 871 | 5 595 371 | 16 428 497 | 22 690 558 | 22 493 105 | -7 810 329 | 65,3% | MRD |
| Actual | 2 004 581 | 3 133 245 | 9 544 950 | - | - | - | 14 682 776 |  |  |  |

Source: IS Monit7+ as of 30 Sep 2012; Source of funding: Community contribution;CZK/EUR exchange rate: 24.859

Since 2011 the IOP MA has intensively monitored the absorption of the total allocation by intervention area, bearing in mind the planned development in the submission of applications for payment and completed tenders.

The original summaries announced major differences between the values of forecast applications of payment and the volume of implemented tenders to the tune of billion CZK. The major difference was caused by the lack of updatedness of data on completed tenders entered in IS Monit7+ IOP. This shortcoming was removed in cooperation with IOP IB.

As of 30 Sep 2012, these differences are not that striking. The negative difference between the tendered funds and submitted applications for payment when considering the forecast applications for payment in October is seen in Intervention areas 2.1, 3.4 and 5.3. In the other intervention areas the funds from completed tenders cover the volume of submitted and forecast applications for payment.

Absorption of the total allocation as against the funds committed to completed tenders

CZK/EUR exchange rate: 24.859

Source of funding: public funds total

* the value is the sum total of amounts from the Decision/Statement of expenditure of projects that passed the P4.1status  - Decision on providing a grant/Statement of expenditure was issued and the following statuses, this column does not include projects that has not been completed

** the value is the sum total of the contractual amounts of eligible expenditure on tenders that were completed and are relevant or approved – namely only in projects in positive status.

*** for ex-ante payments the value covers the advance payments or  the so called limit

Note: If the value stated in the “Reimbursed “ column is higher than the value  in the “Value of awarded contracts” column, it can concern the small-scale contracts which are not subject to tenders  (these are contracts the forecast value of which in case of supplies and services is below CZK 2 000  000,- net of VAT and in case of construction works below CZK 6 000 000 net of VAT)

## 2.7 Analysis of Risks in Relation to Future Progress in Programme Implementation

The IOP MA coordinates the management of risks faced by the IB and MA in IOP implementation. It shares the information with the NCA in the form of a summary report on IOP risk management, namely always following the approval of the Catalogue of IOP Risks. It continuously monitors the measures adopted to eliminate the risks and their effectiveness.

The most significant risks related to programme implementation and the implemented and proposed measures to eliminate them are summarised in the table below.

| Name of the risk | Description of the risk | Measures implemented to eliminate the risk and the risk development | Proposed measures to eliminate the risk in the future |
| --- | --- | --- | --- |
| Non-adherence to the Agreements on delegating activities to IB and binding procedures pursuant to the IOP OM and IOP IB manuals | Overall responsibility for programme implementation is born by the IOP MA which has delegated a part of its activities to IBs. IOP MA checks the correctness of conducted activites. In order to ensure the adherence to the agreements on delegating activities and programme documentation and it cannot impose sanctions. The non-compliance with procedures can have a serious negative effect on programme implementation. It can result in improper decisions, disputes and complaints. The failure to meet the deadlines set in the binding documentation hinders the planning of follow-up activities and financial management of the programme. It can lead to additional costs at beneficiaries. | Control of the adherence to agreements and conduct of delegated activities by IBs, adoption of corrective measures and monitoring of their fulfilment - - in the first half of 2012 a total of 12 checks of delegated activities were commenced, of which 2 were concluded (with no finding), 4 were newly incoporated in the plan (1 check of delegated activities was cancelled); the plan for each quarter includes 1 check of delegated activities at each IB | To include more checks in the plan |
|  |  | Provision of information on risks arising from insufficient tools for the management of IB and addressing disputable issues - the number of pieces of information forwarded to the senior management = 2 pieces of information for the minister (16 May 2012 and 20 Jun 2012) and 3 pieces of information for the 1st Deputy Minister (13 Feb 2012, 21 Mar, and 7 Jun) | To carry on risk management and continuously provide information thereon. |
|  |  | Use of external assistance in the field of control of physical implementation of projects through the NCA project called “Controls” 11 expert opinions were commissioned, of which in risky Intervention areas: IA1.1: 2 expert opinions and IA 4.1: 4 expert opinions with the use of expert assistance from the NCA project called “Controls“. | To conclude a contract with the supplier for the support of IOP MA in the field of conduct of controls. |
|  |  | More specific description of the performance of activities in IOP OM and IB OM, elimination of redundant and duplicate steps - The revised version of MA OM was issued, the IB procedures were revised: MoLSA Handbook of Work Procedures, MG18 of CRD for MoLSA, MG18 of CRD for MRD, MG18 of CRD for MoI was cancelled. | Revision of IOP OM 1.4 which will be followed by the revision of manuals of all IBs. |
|  |  | Introduction of additional IB reporting: CRD, MoC, MoLSA concerning the monitoring of projects in which the submission of the application for payment is foreseen in individual months. Reporting was incorporated in the Monthly Monitoring Report (MMR). | Introduction of reporting also by other IBs. |
| Insufficient audit trail | Incomplete procedures for keeping information and documentation, absence of or non-adherence to the binding procedures of archiving documents and audit trails, failure to enter the data in information systems. The prevailing type of communication among the implementation structure staff is e-mail correspondence which is not appropriately archived. There is a risk of the loss of important documents. | Check of the adherence to archiving procedures and safeguarding of the audit trail as a part of every on-the-spot check of delegated activities – it was covered by check No 5/2012 | To include in all the future checks of delegated activities. |
|  |  | Check of the data entered in IS Monit in terms of its completeness and correctness as an integral part of every check of delegated activities – it was covered by check No 5/2012 | To include in all the future checks of delegated activities. |
| Lack of suitable and quality under developed and submitted projects | The failure to absorb is one of the main risks faced by the programme, which may be caused by a number of other risks – too complicated requirements for the applicant and beneficiary, delays in the announcement of calls and insufficient volume of funds allocated to the call, delays in administration, delays in project implementation, inadequate preparedness of projects, insufficient absorption capacity, insufficient administrative capacity, errors in project implementation, irregularities. Delays in the timetable of project implementation caused by protracted administration associated with the announcement of tenders, changed attitude of the beneficiary to the implemented projects and their major reduction, high number of projects rejected during quality evaluation. | Monitoring and management of the volume of announced funds allocated to individual calls by the MA at motnhly meetings with IBs. | To carry on the implementation of this corrective measure. |
|  |  | Timetable of calls is updated and posted on the website on a quarterly basisdl neo Bohatcová + komentář: formálních náležitostí aj.) bylo zjištěno zpo | Updates in line with the actual needs and their posting. |
|  |  | Continuous monitoring and evaluation of absorption capacity (annualy) through the analysis of absorption capacity. Continuous monitoring and evaluation of forecast absorption and its fulfilment is done on a monthly basis. The importance of absorption is stressed at the meetings with IBs, seminars for applicants and beneficiaries and during the meetings with beneficiaries. | Modification of the eligibility of bonuses pursuant to the Government Resolution No 1332 with the maximum amount of the bonus depending on the degree forecast fulfilment. |
|  |  | Identification of problem areas and preparation of training courses and seminars for applicants and beneficiaries held by the MA: 20 Jun 2012 a seminar for beneficiaries under IA 4.1 of IOP 21 Jun 2012 a seminar for beneficiaries under IUDP and Jessica financial instrument 25 Jun 2012 a seminar for beneficiaries under IUDP and Jessica financial instrument 10 Jul 2012 a seminar for beneficiaries under IA 2.1 and 3.4 of IOP In the period from 1 Jan 2012 to 30 Jun 2012, the Managing Authority trained 93 officers, of whom 6 from the MA (training courses held by the IB are listed in this report in Chapter 4.4.1.3. Education and Training, Table No 53 Overview of conducted education and training activities). | To carry on the provision of appropriate training courses. |
|  |  | Once in 6 months the information on frequently or wrongly addressed situations is posted and updated on the website of IB, through FAQ. Check of the topicality of posted FAQ. | To check the topicality of published FAQ. |
|  |  |  | To compile a list of most frequent errors made by applicants/beneficiaries and to post it on the website of IB and on www.strukturalni-fondy.cz/iop. To check the content and topicality of information on IB website and on www.strukturalni-fondy.cz/iop. |
|  |  | Simplification of requirements on applicants and beneficiaries listed in the HAB – the revision of the Binding Procedures brought about the revision of all HABs. | Simplification of requirements on the applicant in calls. |
| Ineffective check of economy and efficiency of expenditure | Insufficient legislation and non-existence or unclear way of checking the effectiveness, efficiency and economy of expenditure. Difficult setting of prices usual for the assessment of economy in projects. | As concerns the determination of procedures for the check of public contracts and eligibility of expenditure in terms of economy and efficiency, an obligation was set in HAB to evidence, upon request, the anticipated value in small-scale public contracts and an obligation to justify the effectiveness of the public contract and definition of qualification criteria in contracts falling under the Act on public contracts. | Specification and modification of checklists for control of public contracts. |
| Violation of rules governing the award of public contracts | Violation of rules governing the award of public contracts represents one of the most frequent errors in project implementation and the largest volume of ineligible expenditure in projects. Potential assessment of correctness of the procedure taken by the contracting authority in the award of public contracts by the Office for the Protection of Competition may cause major delays in project implementation since it can take a few months before the OPC issues its opinion. Inadequate, merely formal use of checklists, fails to timely reveal the potential errors. Shortage of inhouse legal experts in the field of public contracts. Lack of checks of tender documents prior to the actual award of a public contract – the failure to dicover deficiencies in time leads to subsequent irregularities with an impact on programme absorption. | Consistent evaluation of the application of Act on public contracts in practice and proposals concerning its amendments. | Compilation of a database of OPC/RAC/SAC decisions in the field of public contracts and their use in checks of public contracts or provision of consultations to applicants/beneficiaries. |
|  |  | Incorporation of graded sanctions for violation of Act No 137/2006 Coll., on public contracts in the Conditions, Decision on providing a grant, as made possible by the amendment to Act No 218/2000 Coll., on budgetary rules. (In MoLSA IB the final wording of the Conditions is lacking and contrary to other IBs the Decisions are not issued together with the Conditions) | Implementation of the measure at MoLSA IB – incorporation of graded sanctions for the violation of Act No 137/2006 Coll., on public contracts in the Conditions for the Decision on providing a grant, as made possisble by the amendment to Act No 218/200 Coll., on budgetary rules. |
|  |  | Evaluation of the duration of OPC investigation in individual cases and sharing the information and the report on associated risks and potential suggestions with the 1st Deputy Minister for Regional Development. | Referred to the NCA. |
|  |  | Training of controllers in the respective areas – in the period from 1 Jan 2012 to 30 Jun 2012 a total of 36 training courses in the field of tenders were held, 131 persons were trained. Provision of adequate qualification of persons responsible for the assessment/control of public contracts. Extension of training plans for controllers, training courses focused on specific areas of tender controls. | Extension of training plans for controllers, training courses focused on specific areas of tender controls. |
|  |  | Specification and modification of checklists for the controls of public contracts in the framework of IOP OM revision due to the amendment to Act on public contracts in keeping with AA, NCA, or EC requirements. | To make a list of most frequent errors made by beneficiaries/applicants in the award of public contracts and to post it on IB website and on www.strukturalni-fondy.cz/iop. |
|  |  | Conduct of controls of delegated activities at some IBs, focused on procedures taken during the controls of public contracts. | Conduct of these controls at the remaining IBs ( MoC and MoLSA). |

## 2.8 Foreseen Timetable of the Announcement of Calls

The MA intends to announce the calls gradually throughout the programming period. One of the reasons is the evenly distributed release of funds which will safeguard necessary response to the needs of applicants and beneficiaries. The other reason is the effort to modify the calls based on the experience gained in the previous calls.

The planned timetable of calls and the actual opening dates of the calls (in blue) in the period from

1 Apr 2012 to 30 Sep 2012 are given in the table below.

Timetable of planned calls

| Plan/ actual | Intervention area, activity | Type of the call | Planned /actual opening date of the call | Allocation for the call in CZK (ERDF+SB)( | Note |
| --- | --- | --- | --- | --- | --- |
| Plan | 3.2 c) Management of quality and cost-effectiveness of public healthcare system (innovative devices for measuring and evaluation of quality and cost-effectiveness of health care) | Time-limited | 3rd quarter 2012 | 118 000 000 |  |
| Actual | 3.2 c) | Time-limited call No 12 | 16.8.2012 | 500 000 000 |  |
| Plan | 3.2 b) System measures in the field of prevention of health risks of population | Time-limited | 3rd quarter 2012 | 100 000 000 |  |
| Actual | 3.2 b) | Time-limited call No 11 | 8.8.2012 | 280 000 000 |  |
| Plan | 3.4 d) Acquisition of technology to safeguard better operational capability of IRS | Time-limited | 3rd quarter 2012 | 130 000 000 |  |
| Actual | 3.4 d) | Time-limited call No 15 of MRD | 10.8.2012 | 158 823 529 |  |
| Plan | 1.1a) Creation, development and maintenance of national basic and other relevant registers of public administration | Continuous (No 15) | 3rd quarter 2012 | 100 000 000 |  |
| Actual | 1.1 a) | Continuous call No 14 | 4.9.2012 | 176 470 588 |  |
| Plan | 3.2a) Modernisation and replacement of devices and equipment | Time-limited call (No 13) | 4th quarter 2012 | 300 000 000 |  |
| Actual |  |  |  |  |  |
| Plan | 3.3 c) | Continuous | 4th quarter 2012 | 82 352 941 |  |

* the volume of scheduled calls can change taking into account the exchange rate fluctuations and savings achieved in the previous calls

White cells = planned calls as of 4 Jun 2012

Blue cells = actual opening of calls

An overview of on-going calls of IOP is available on: http://www.strukturalni-fondy.cz/Narodni-organ-pro-koordinaci/Dokumenty/Publikace (overview of open calls).

## 2.9 Overview of Approved Projects

An essential parameter in the development of the programme cycle is the volume of projects approved for implementation.

A list of assisted projects and aid beneficiaries is updated by the MA at a monthly interval and published on the website: http://www.strukturalni-fondy.cz/Programy-2007-2013/Tematicke-operacni-programy/Integrovany-operacni-program/Projekty/Podporene-projekty.

More detailed information on approved projects is derived from IS Monit7+ and made available on www.risy.cz portal run by the Centre for Regional Development, which also facilitates the search for projects based on various parameters.

Information on rejected projects

The IOP MA monitors the statistics of rejected projects in the period prior to the issuance of the legal act (status N1.1, N1.2, N2.1, N2.2, N2.3, N4.1 and N5) and at the time of project implementation following the issuance of the legal act (status N7, N8). Projects can be rejected based on a decision of the applicant, who will no more seek aid, which corresponds to status N5 Project application withdrawn by the applicant and N7 Project not completed/withdrawn in IS Monit7+ IOP, or based on a decision of the MA/IB (hereinafter referred to as denied projects).

As of 30 Sep 2012, of the total of 8 384 submitted project applications 839 applications were rejected (of which 343 project applications in Intervention area 2.1 in call No 02 of the Ministry of Interior  for eGovernment in municipalities – CzechPoint – contact points), which represents 10.01 % of all the submitted project applications ..  The project applications were most frequently withdrawn by the applicant, namely in 272 cases, i.e. in 32.4 % of all the rejected projects.

Of 839 rejected projects, a total of 465 projects were denied, in 272 cases the project application was withdrawn by the applicant and 102 projects were not completed by the beneficiary. The projects are most often denied on the grounds of non-compliance with evaluation requirements, namely in 203 cases which represents 24.2 % of all the rejected projects. The eligibility criteria were not met in 131 cases (15.6 % of all the rejected projects).

The following chart gives the number and share of rejected projects by individual stage of administration.

Rejected projects by intervention area

Source: IS Monit7+ as of 30 Sep 2012

N1.1 Project application failed to meet at least one of the eligibility criteria

N1.2 Project application failed to meet formal requisites

N2.1 Project failed to meet evaluation requirements

N2.2 Letter on rejection of project application based on ex-ante check was sent

N2.3 Project was not recommended for financing by the Selection Committee

N4.1 Issuance of Decision on providing a grant/Statement of expenditure was denied

N5 Project application was withdrawn by the applicant

N7 Project was not completed/project was withdrawn

N8 Contract was terminated by the MA/IB

The chart below illustrates the share of rejected projects in individual intervention areas. The highest number of projects is rejected in Intervention areas 4.1 (64.00 %), 3.1 (57.53 %) and 5.1 (55.56 %). The lowest share of rejected projects is on the very contrary reported by Intervention areas 3.4 (2.78 %), 6.1 (2.78 %), 5.2 (4.07 %), 2.1 (5.90 %) and 6.2 (6.78 %).

Rejected project by status

Source: IS Monit7+ as of 30 Sep 2012

In Intervention area 3.1, of the total number of 332 submitted project applications 57.53 % of project applications was rejected which equals 191 projects. Of this number 168 project applications (88 %) were rejected under activity 3.1c) Investment support to social economy.

In activity 3.1c) the main reason for rejection is the non-compliance with the evaluation requirements (115 project applications which equals 68 % of projects rejected in activity 3.1c)). The project applications predominantly fail to sufficiently evidence the project sustainability and describe and evidence the necessity of project implementation with regard to the target group and market.

In order to eliminate this problem the MoLSA opted for the following corrective measures:

- Increased number of seminars for applicants,

- Increased number of one-to-one consultations with applicants,

- Modification of FAQ on the website,

- Participation in seminars and conferences on which this activity is presented,

- Revision of the currently announced call.

The percentage of rejected project applications is decreasing only very slowly. In the monitored period 95 project applications were submitted, of which 24 projects are now at a negative status. In the monitored period the share of rejected project applications is 25.26%.

The second important reason is the withdrawal of the project application by the applicant, which has occurred 36 times since the beginning of announcement of calls for IA 3.1. Also in this area the share of projects withdrawn from implementation is on a decline. As of 31 Mar 2012, it accounted for 17 % of the total number of rejected projects, as of 30 Sep 2012 it is 10.84 %.

The share of rejected projects in the total number of received projects in Intervention area 4.1a and 4.1b has been consistently high. In the monitored period two projects were rejected, by which this share rose from 59.5 % to 64.00 %. In this intervention area the projects are mostly rejected due to non-compliance with the quality evaluation requirements (in a total of 54 cases) or eligibility criteria (24 project applications). The projects exhibit difficulties in the field of effectiveness, efficiency and economy, which if not being the reason of project rejection during the project evaluation result in the withdrawal of some projects from implementation. In terms of the structure of projects in the programme the projects under Intervention areas 4.1a and 4.1b constitute only 1.79 % of IOP projects and 1.15% of denied projects in the total number of IOP projects.

As of 30 Sep 2012,  in Intervention area 5.1 a total of 25 projects were rejected of the total number of 45 submitted projects, which represents 55.56 % of rejected projects. In the monitored period no project was rejected. All the projects (9 in total), submitted under the 3rd time-limited call, met the criteria of eligibility and formal requisites and obtained the required scoring. Due to the limited allocation for the call 3 projects were approved for the provision of a grant, one project was withdrawn from implementation before the issuance of the Decision on providing a grant, and additional 5 projects were included in the group of substitute projects.

2.10 Progress in the Implementation of Financial Instruments

In the monitored period the legislative steps of the amendment process to Act No 211/2000 Coll., on the State Housing Development Fund (SHDF), commenced on 20 Mar 2012 were completed by the submission of a draft amendment by a group of MPs to the Chamber of Deputies of the Parliament of the CR. The amendment was published in the Collection of Laws under No 276/2012 on 22 Aug 2012 and took effect on 6 Sep 2012. The SHDF was identified as the most fitting institution with a public mission, implementing the Housing Policy Concept in the CR, which could provide an umbrella for JESSICA financial instrument at the central level by creating a holding fund. In this context, a holding fund was set up on 12 Jul 2012 as an independent accounting unit within the existing organisational structure of SHDF.

On 16 July 2012, the IOP MA announced a call for applicants submitting the Integrated Urban Development Plans, which will incorporate the use of JESSICA FI for financing projects under activity 5.2. If the existing zones with approved IUDP fail to exhibit sufficient absorption capacity, the referred to documents make it possible to extend the defined zones. As long as the municipalities with no approved IUDP express interest and there are enough funds available under JESSICA FI, it will be possible to approve additional IUDP from among the target group of municipalities with more than 20 000 inhabitants (except for the City of Prague). To this end seminars were held on 21 June and 25 June 2012 in order to introduce the JESSICA FI to the municipalities.

The call for submission of applications for the approval of new IUDPs and extension of the existing IUDPs will be closed on 17 Dec 2012.

On 20 Jul 2012, in cooperation with and through the OPC the administrative process of pre-notification and subsequent notification of the Addendum No N342/2008 on state aid regime was commenced in relation to the implementation of pilot testing of JESSICA FI in IOP. It concerns an increase of the total amount of support provided to Intervention area 5.2 by JESSICA FI funds and the possibility to provide these funds through a new form of support, namely the soft (preference) loans. On 15 Aug 2012, the MA received additional requirements and queries from DG COMPETITION. They were settled by the requested deadlines and DG COMPETITION confirmed the receipt of supporting information on 11 Sep 2012.

Filling in the application for support in BENEFIT7 information system and the elaboration of mandatory annexes were on the agenda of numerous coordination and technical meetings between the MA and SHDF. On 25 Sep 2012, the IOP MA announced a time-limited call for submission of applications for support of the implementation of JESSICA FI. The application for support was submitted by the SHDF on 1 Oct 2012. Submitted application for aid has been assessed in accordance with chapter 12 of Examination of "Manual for the implementation of the JESSICA financial instrument in IOP." MA IOP carried out the assessment according to the general and specific acceptance criteria and formal requirements.

Before the end of 2012, the IOP MA expects to transfer the JESSICA FI allocation to the holding fund which compiles the tender dossier for the selection of Urban Development Fund (UDF). The tender is foreseen to be announced in December 2012.

# 3 PROGRESS AT THE LEVEL OF PRIORITY AXIS

The financial tables and the tables of indicators are in line with the NCA Guideline for the elaboration of the report on implementation of the programme for the Monitoring Committee.

In indicators both the commitments of approved projects and the values achieved as of 30 Sep 2012 were monitored. The commitments are calculated from the target values of projects starting with status P4 in IS Monit7+ (project with issued Decision/Statement of expenditure). The achieved values are calculated based on projects starting with status P45 in IS Monit7+ (project under implementation), with the exception of the “Number of projects” type of indicators,  in which the values are aggregated starting with status P5 (Project implementation was completed). The baseline values from 2005 are taken over from the Programming Document.

The charts “Comparison of physical and financial progress by individual intervention area” represent the comparison of physical and financial progress.  The violet bar expresses the commitment to approved projects, i.e. the total target value of the indicator, which is stated by beneficiaries in their applications and which the beneficiaries undertake to fulfil by project implementation, it is expressed in % of the total value set in the IOP Programming Document, the same value is given in the tables of indicators. The blue bar covers the funds of projects, for which the Decision is issued, expressed as a percentage of the allocation for activity, under which the relevant indicator falls).

## 3.1 Priority axis 1a, 1b – Modernisation of public administration

### 3.1.1 Focus of priority axes/intervention areas

Priority axes 1a and 1b aim to achieve faster and more reliable provision of state administration services to the public, and, by implementing electronic administration, to enable citizens and business entities to communicate simply and quickly with state administration authorities.

Specific goals:

- To improve the level of services of electronic public administration (eGovernment)

- To increase the use of the Internet by citizens for communication with public administration

- To reduce the administrative burden of citizens, entrepreneurs and public sector

Supported activities:

- Creation, development and maintenance of national basic and other relevant registers of the public administration, including safe and protected access system,

- Construction of the public administration communication infrastructure,

- Creation of access points for communication with the public administration information systems,

- Digitisation of public administration services.

Beneficiaries:

  - government agencies and semi-budgetary organisations established by them.

### 3.1.2 Progress achieved in the implementation of priority axes/intervention areas

At the end of the monitored period, a new call for submission of project applications was announced, in which no new applications were submitted before 30 Sep 2012. Thus neither the amount nor the number of submitted applications increased. 2 projects designated as “sleeping” due to the problems in implementation were withdrawn from implementation. In other projects the change Decision on providing a grant was issued for a lower amount. 54 projects with an issued Decision therefore represent 89.9 % of the allocation (EUR 353.69 million).

Some more projects continue to suffer from the failure to implement stages to the originally planned extent, postponements in the timetable of tenders and thus postponement of spending of funds to the following years. This leads to delays in reimbursement and absorption of funds. The most frequent reason behind the protractions are the complications in public procurement procedures, when in a number of cases a long time elapses before the decision of the Office for the Protection of Competition is issued. Frequently the reason is the lengthy preparation of the technical part of the tender documentation for key tenders. Changes in staffing and senior staff of projects at the beneficiary and associated changes in concepts of and opinions on project management constitute yet another barrier to continuous work on projects. Another external influence with an impact on delays in implementation (impacting the timetable of absorption), is represented by the amendment to Act No 137/2006 Coll., on public contracts, which came into force on 1 Apr 2012 and which places higher requirements on the contracting entity, also in terms of time.

Following the transfer of agenda in IA 2.1 and 3.4, administrative capacity was released at MoI IB for IA 1.1 and the implementation of new measures leading to the improvement of the status of implementation of projects and acceleration of absorption of funds. To this end intensive discussions are held with the representatives of projects designated as “sleeping and risky projects”. Some problematic projects have already been forced to withdraw from implementation and the released funds together with the quantified savings from projects are used for the announcement of new calls. Moreover, regular monthly meetings with all the beneficiaries are held, namely with the “task force of the project“, crisis timetables and regular reporting are introduced.

The amount of reimbursed funds increased as against the previous MC meeting from EUR 80.66 million to EUR 121.14 million (by 10.1 % of the allocation to IA). The aggregate payment claims accounted for by the PCA totalled EUR 109.45 million representing 27.7 %. In the monitored period no certification of expenditure took place, and on the very contrary some applications for payment were removed from certification due to a suspected irregularity and are now under investigation.

Cumulative progress at the level of Intervention areas 1.1a and 1.1b (in mil. CZK/EUR)

| 1.1a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 9 064,79 | 365,41 | 79 | 10 743,58 | 118,5% | 432,18 | 54 | 8 145,38 | 89,9% | 328,43 | 2 777,26 | 30,6% | 112,49 | 2 507,33 | 27,7% | 101,63 | 720,27 | 7,9% | 29,66 |
| Previous MC | 9 042,31 | 365,41 | 79 | 10 743,58 | 118,8% | 433,59 | 56 | 8 356,52 | 92,4% | 337,26 | 1 855,84 | 20,5% | 74,90 | 1 413,30 | 15,6% | 57,70 | 874,89 | 9,7% | 35,79 |
| 1.1b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract8 | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC9 |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 697,29 | 28,11 | 0 | 826,43 | 118,5% | 33,24 | 0 | 626,57 | 89,9% | 25,26 | 213,63 | 30,6% | 8,65 | 192,87 | 27,7% | 7,82 | 55,41 | 7,9% | 2,28 |
| Previous MC | 695,56 | 28,11 | 0 | 826,43 | 118,8% | 33,35 | 0 | 642,81 | 92,4% | 25,94 | 142,75 | 20,5% | 5,76 | 108,72 | 15,6% | 4,44 | 67,30 | 9,7% | 2,75 |

Source: Current MC – MSC2007 as of 3 Oct 2012

Previous MC – MSC2007+ as of 4 Apr 2012

CZK/EUR exchange rate: Current MC – 24.859

Previous MC (“a” column) – 24.778

Source of funding – public funds total

Overview of on-going calls

In the intervention area in September the call No 14 with the allocation of EUR 7.18 million was announced which is anticipated to be closed in November. Before 30 Sep 2012 no project applications were submitted in this call.

Overview of on-going calls in the period from 1 Apr to 30 Sep 2012 in Priority axis 1a and 1b

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | Inter-vention area/ac-tivity | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 52. | 14. | 4.9.2012 | 30.11.2012 | continuous | 1.1 a | 6 664 181 | 0 | 0 | 0 | 0 |
|  |  |  |  |  |  | 512 629 | 0 | 0 | 0 | 0 |
|  |  |  |  | Call total | 7 176 810 | 0 | 0 | 0 | 0 |
| CONV total |  |  | 6 664 181 | 0 | 0 | 0 | 0 |
| RCE total |  |  | 512 629 | 0 | 0 | 0 | 0 |
| PA 1 total |  |  | 7 176 810 | 0 | 0 | 0 | 0 |

Source: IS Monit7+ as of 2 Oct 2012

CZK/EUR exchange rate: 24.859

Source of funding – public funds total

### 3.1.3 Fulfilment of indicators

Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commit-ment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 150106 | Number of created basic registers of public administration | Number | 0 | 4 | 5 | 0 |
| 150109 | Share of registers connected to central registers | % | 0 | 75 | 22,08 | 2,50 |
| 150110 | Share of authorities using the shared CIPA | % | 0 | 80 | 20,32 | 13,80 |
| 150111 | Share of ministerial and agenda portals interconnected to the Public Administration Portal | % | 19 | 75 | 45,43 | 41,40 |
| 150112 | Share of digitized documents | % | 0 | 20 | 26,62 | 12,00 |
| 150113 | Share of authorities with electronic records management system and electronic document circulation | % | 20 | 100 | 1,10 | 0,00 |

Source: MSC2007 as of 30 Sep 2012

*  Indicator No 150108 is not monitored

Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commit-ment of approved projects | Value achieved as of 30 Sep 2 012 |
| --- | --- | --- | --- | --- | --- | --- |
| 152105 | Reduction of administrative burden of citizens, entrepreneurs and public sector | % | 100 | 75 | 87,3 | 93,4 |

Source: MSC2007 as of 30 Sep 2012

- Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

With respect to the nature of projects it is stipulated in the MoI CR calls that the data of fulfilment of indicators is reported at the date of completion of project implementation. The achieved values can thus be perceived as a progress made in projects with completed implementation. In the framework of revisions of Handbooks for Applicants and Beneficiaries some procedures governing the calculation of achieved values of indicators at the project level were specified. At present, the IOP MA checks the extreme target and achieved values in IS Monit7+, correctness of the setting and consistency of reporting the indicators. In Intervention area 1.1 it concerns the indicators No 150110, 150111, 150113.

The indicator No 150 113 was not chosen by all the applicants whose projects focus on the electronic records management system. There are a total of 7 projects under call No 7 focusing on the introduction or modification of the electronic records management system, but only 2 beneficiaries have chosen this indicator.

The indicator No 150106 is apart from all the basic registers stated in the IOP Programming Document fulfilled also by the project called Information system of basic registers, which is an essential component of the whole set of basic registers. The basic registers were launched on 1 Jul 2012, the projects are at the final stage of implementation and will be completed as of 31 Dec 2012, when the indicator will be fulfilled.

### 3.1.4 Problems and measures taken

Sleeping and high-risk projects which for a long period fail to meet the planned timetable of project implementation and the forecast absorption of funds.

Measures taken

In cooperation with the IOP MA obligatory crisis timetables for project implementation have been prepared for individual beneficiaries, whose projects were identified as “sleeping projects”. Certain projects had to be withdrawn from implementation due to the refusal of further extension of implementation. A document on sleeping projects is being prepared for the Government of the CR, aimed as a resolution to commit the ministers to ensure the proper implementation of crisis schedule for each project and ensure adequate capacity of project teams and in case of non-compliance with the crisis schedule immediately give the order to cancel the project. The IOP MA designed a system of monitoring and identification of sleeping and risky projects and it performs its monitoring and update.

Regular monthly meetings with all the beneficiaries in the framework of the “task force project“ were introduced, attended by the representatives of the Intermediate Body (project manager, financial manager and senior officer) and the project holder (chief project manager, or contractor). The agenda of the meeting covers particularly the topical information on tenders, status of accomplishment of project implementation timetable, absorption at the current stage, savings, changes in the project and recommendations given by the representatives of the Intermediate Body.

Consistent failure to fulfil the forecast absorption of funds

Measures taken

Regular updates of forecast absorption. Thanks to the transfer of delegated activities under Intervention areas 2.1 and 3.4 the project and financial managers have currently space for more thorough and better management of individual projects.

### 3.1.5 Example of a project

Intervention area: 1.1 Modernisation of public administration

Name of the project, registration number: Integration of ARES (Access to Registers of Economic Subjects / Entities) and Basic Registers system, CZ.1.06/1.1.00/07.06406

Beneficiary: Ministry of Finance of the CR

Project funding: Total budget CZK 32 196 640, of which CZK 27 367 144 the Structural Funds contribution and CZK 4 829 496 the state budget contribution

The project is implemented as a support to the creation of the Registry of Persons database and subsequently also as a support to communication among the basic and other public administration registers and with the other relevant systems of public administration. The project is intended for Basic registers and their communication with important public administration information systems. The aim is to minimise the costs incurred in relation to the creation of the Registry of Persons basic register and to reduce the costs of the use of Basic registers in the other public administration information systems. The project's aims are to be achieved by using the existing ARES mechanisms and services and their integration in the system of Basic registers. The planned activities are carried out by the Ministry of Finance in cooperation with the Ministry of Interior and persons responsible for individual public administration information systems. The project is currently at its final stage, all key tenders have been closed and checked by the MoI CR SFD. The date of project completion and fulfilment of the monitoring indicator is set at 30 Sep 2012.

## 3.2 Priority axis 2 – Introducing ICT in territorial public administration

### 3.2.1 Focus of priority axes/intervention areas

Priority axis 2 is focused on modernisation of the territorial public administration, mainly on creating the conditions for application of e-Government at the local level, on optimisation of processes in the local self-governing bodies, mainstreaming electronic communication between the individual levels of public administration by ensuring mutual compatibility of information systems and data consistency, by providing as much information as possible free of charge via the Internet.

Specific goals:

- To increase the level of services of electronic public administration at regional and local level,

- To decrease the administrative burden of citizens, entrepreneurs and public sector.

Supported activities:

- Data sharing with central registers in public administration and creation of other relevant registers for needs of territorial public administration,

- Construction of the territorial public administration communication infrastructure:

- Creation of access points for communication with the public administration information systems

- Digitisation of the public administration services, particularly by means of digitalisation of procedures of individual agendas performed by the territorial public administration bodies.

Beneficiaries:

- Regions and municipalities and organisations established and founded by them, unions of municipalities

### 3.2.2 Progress achieved in implementation of priority axes/intervention areas

In the monitored period no call was under way for the submission of project applications under Intervention area 2.1, no progress was reported in the number of submitted applications. 1 project with issued Decision on providing a grant from call No 6 was withdrawn from implementation, the amount of approved projects thus decreased to EUR 151.53 million and equals 90.3 % of the allocation.

In numerous projects the timetables of tenders were postponed and activities were transferred to next project stages, which leads also to the postponement in the absorption of funds.

A positive step was the transfer of delegated activities from MoI to IOP MA and CRD due to necessary acceleration of administrative steps and absorption of funds. Simultaneously, the IOP MA introduced a system of identification and monitoring of sleeping and risky projects, including the measures to address the individual projects.

The amount of reimbursed funds in the monitored period increased from EUR 22.36 million to EUR 32.68 million and represents 16.4 % of the allocation. The funds included in aggregate payment claims accounted for by the PCA totalled EUR 31.00 million, which represents 15.5 % of the allocation and twofold increase as against the data given as at the previous MC meeting.

Cumulative progress at the level of Intervention area 2.1 (in mil. CZK/EUR)

| 2.1 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 5 002,47 | 200,98 | 5 839 | 5 465,67 | 109,3% | 219,87 | 5 484 | 4 519,02 | 90,3% | 181,53 | 818,69 | 16,4% | 32,68 | 777,01 | 15,5% | 31,00 | 265,10 | 5,3% | 10,63 |
| Previous MC | 4 981,58 | 200,98 | 5 839 | 5 465,67 | 109,7% | 220,59 | 5 485 | 4 604,41 | 92,4% | 185,83 | 554,05 | 11,1% | 22,36 | 386,53 | 7,8% | 15,46 | 265,54 | 5,3% | 10,65 |

Source: Current MC – MSC2007 as of 3 Oct 2012

Previous MC – MSC2007+ as of 4 Apr 2012

CZK/EUR exchange rate: Current MC – 24.859

Previous MC (“a” column) – 24.778

Source of funding – public funds total

Overview of on-going calls

In the monitored period no calls for submission of project applications were under way and no new calls were announced for Intervention area 2.1.

### 3.2.3 Fulfilment of indicators

Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commit-ment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 150105 | Number of contact points of public administration (Czech Point) | Number | 1300 | 6244 | 6572 | 6557 |
| 150117 | Share of local public administration registers connected to central registers | % | 0 | 75 | 16 | 0 |
| 150115 | Share of local networks connected to CIPA | % | 10 | 85 | 79,5 | 15,5 |
| 150116 | Share of regional portals integrated into the Public Administration Portal | % | 0 | 75 | 56,67 | 0 |
| 150114 | Number of new fully digitised agendas of local public administration | Number | 0 | 10 | 106 | 1 |
| 150112 | Share of digitised documents | % | 0 | 20 | 21,68 | 0,78 |
| 150113 | Share of authorities with electronic records management system and electronic document circulation | % | 20 | 100 | 56,1 | 42,9 |

Source: MSC2007 as of 30 Sep 2012

Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 152105 | Reduction of administrative burden of citizens, entrepreneurs and public sector | % | 100,00 | 75,00 | N/A | N/A |

Source: MSC2007 as of 30 Sep 2012

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart “Comparison of physical and financial progress” are included at the beginning of Chapter 3 Progress at the level of priority axis.

With respect to the nature of projects, the data on the fulfilment of indicators is set at the date of completion of project implementation. The achieved values can thus be perceived as a progress made in projects with completed implementation. A slight progress in the monitored period was observed in the fulfilment of indicator No 150115. In the framework of revisions of Handbooks for Applicants and Beneficiaries some procedures governing the calculation of achieved values of indicators at the project level were specified. At present, the IOP MA checks the extreme target and achieved values in IS Monit7+, correctness of the setting and consistency of reporting the indicators. In this Intervention area it concerns the indicators No 150117, 150115, 150116, 150113, 152105.

Almost all the CzechPoint projects fulfilling the indicator No 150105 have been completed, the difference between the commitment of approved projects and the achieved value is caused by not completed projects, in which suspected irregularities are investigated.

The excess in indicator No 150114 is caused by the difference in the target value stated in the Programming Document and the commitment of approved projects. Contrary to the original intention to establish the records management system in regions only, the records management systems were in the end established also in municipalities in regions or in municipalities with extended powers. Another factor is the inclusion of each fully digitised agenda separately for each beneficiary, even though it may concern the identical public administration agenda.

### 3.2.4 Problems and measures taken

Low fulfilment of forecast absorption of funds and postponement of activities to next project stages, extension of project implementation

Measures taken: IOP MA designed a system of identification and monitoring of sleeping and risky projects and assigned the specific measures to individual projects. The sleeping and risky projects are regularly monitored. Extension of projects is possible only in case the project is divided into stages.

Absence of persons responsible for individual calls

Measures taken

In September 2012, the e-mail address egoncentrum@mvcr.cz administered by the Public Administration Performance Unit of MoI CR was relaunched. It is intended enquiries of technical nature. Subsequently, the enquiries will be included in FAQ section of www.egoncentrum.cz. At the same time, persons responsible for this intervention area appointed at the MoI CR.

### 3.2.5 Example of a project

Intervention area: 2.1 Introducing ICT in territorial public administration

Name of the project, registration number: Development of eGovernment services in Žďár nad Sázavou, CZ.1.06/2.1.00/06.0681

Beneficiary: Municipality of Žďár nad Sázavou

Project funding:  Total budget CZK 6 854 188.00, of which CZK 5 826 059.80 Structural Funds contribution and CZK 1 028 128.20 municipal budget contribution

The project aims to develop the necessary IT infrastructure which will allow the municipality with extended powers to get involved in the follow-up type or individual eGovernment projects and increase the effectiveness and quality of activities performed by the municipal authority and municipalities in the administrative territory of Žďár nad Sázavou municipality with extended powers (MEP).

The project is to be implemented in the administrative territory of Žďár nad Sázavou MEP.

The first stage of the project consisted in the construction of a MEP technology centre, acquisition of necessary hardware and software for the running of applications and provision of services, particularly the provision of service of untrusted repository and purchase of a records management system for municipalities and their semi-budgetary organisations, in the upgrade of records management for MEP and purchase of the records management system licence for semi-budgetary organisations established by MEP. The second stage focused on internal integration of the municipal authority. The project was completed in 2012.

## 3.3 Priority axis 3 – Improving public services quality and accessibility

### 3.3.1 Focus of priority axes/intervention areas

Activities of Priority Axis 3 follow from the interventions into the quality and effectiveness of the public administration functioning. The common goal is to improve the organisation, financing and the evaluation process of public services. The priority axis is focused on four intervention areas:

- 3.1 – Social integration services

- 3.2 – Public health services

- 3.3 – Employment services

- 3.4 – Services in security, risk prevention and management

Specific goals:

- reinforcing social integration by transforming residential social welfare facilities into other types of social services, while improving the quality and accessibility of social services to allow the clients return to the labour market and to the society in general

- innovation and modernisation of the infrastructure for care for the population’s health, with an emphasis put on the extension of national networks of specialised facilities, prevention of health risks and higher effectiveness, quality and availability in the system of providing public health services,

- enhancement of quality of employment services and support of development of new tools and  institutions of employment services, including education of employees and clients of the employment services,

- better quality  in the field of prevention and risk management through modernisation of infrastructure.

Beneficiaries:

- government agencies and semi-budgetary organisations established by them,

- regions and municipalities and organisations established by them,

- non-governmental non-profit organisations,

- entrepreneurs (persons registered in the Commercial Register, persons doing business based on a trade licence or based on special regulations)

### 3.3.2 Progress achieved in implementation of priority axes/intervention areas

In the monitored period in Intervention area 3.1 a total of 95 project applications were submitted, thus the amount of submitted applications grew from EUR 78.52 million to EUR 110.90 million, representing 119.0 % of the allocation. 16 Decisions on providing a grant were issued, thus the amount increased from EUR 13.32 million to 30.21 million, representing 32.4 %. The largest share of issued Decisions on providing a grant is shown in activity b). Due to low percentage of issued Decisions on providing a grant, new measures were adopted to accelerate the administration in this intervention area. One of the most important measures was the modification of work procedures through the issuance of a single (merged) guidance document of the Registration of action and the Decision on providing a grant.

The beneficiaries were paid EUR 2.46 million and the aggregate payment claims accounted for by the PCA amounted to EUR 2.58 million, representing 2.8 % of the allocation.

Cumulative progress at the level of Intervention area 3.1 (in mil. CZK/EUR)

| 3.1 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 2 316,39 | 93,18 | 352 | 2 756,80 | 119,0% | 110,90 | 47 | 751,05 | 32,4% | 30,21 | 61,24 | 2,6% | 2,46 | 64,14 | 2,8% | 2,58 | 30,85 | 1,3% | 1,27 |
| Previous MC | 2 308,32 | 93,18 | 257 | 1 945,62 | 84,3% | 78,52 | 31 | 329,98 | 14,3% | 13,32 | 38,88 | 1,7% | 1,57 | 41,30 | 1,8% | 1,67 | 30,85 | 1,3% | 1,27 |

In Intervention area 3.2 progress was achieved primarily in the submission of project applications under the 9th and 10th call, the number of submitted applications rose by 24 to188 totalling 113 % of the allocation (EUR 332.72 million). 21 applications were recommended for financing by the Selection Committee and legal acts for them were issued. In the monitored period  the issued legal acts amounted to EUR 14 million, two projects in the volume of EUR 20.54 million were withdrawn from implementation and in two projects the change Decision on providing a grant was issued on a lower amount (by EUR 0.10 million). The share of projects with issued Decision on providing a grant thus decreased by EUR 5.87 million, i.e. by 2.3 % to 81.9 % (EUR 238.96 million). In projects withdrawn from implementation, the applicants shall redraft the applications and submit them again in the next calls.

Owing to the amendment to Act on public contracts as of 1 Apr 2012 the implementation of projects is protracting and the absorption of funds is slowing down. As of 30 Sep 2012 the beneficiaries were paid funds in the amount of EUR 140.64 million, the aggregate payment claims covered EUR 136.81 million, representing 47.2 % of the allocation. The amount of certified expenditure thus decreased from EUR 101.91 million to EUR 66.5 million due to the removal of applications for payment from certification in consequence of a suspected irregularity that is under investigation. The certified expenditure thus reached 22.7 % of the total allocation for the intervention area.

Cumulative progress at the level of Intervention area 3.2 (in mil. CZK/EUR)

| 3.2 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 7 321,14 | 292,33 | 188 | 8 270,96 | 113,0% | 332,72 | 152 | 5 994,49 | 81,9% | 238,96 | 3 550,17 | 48,5% | 140,64 | 3 455,01 | 47,2% | 136,81 | 1 664,18 | 22,7% | 66,58 |
| Previous MC | 7 291,42 | 292,33 | 164 | 7 886,40 | 108,2% | 318,28 | 133 | 6 140,51 | 84,2% | 247,82 | 3 232,34 | 44,3% | 130,45 | 3 048,49 | 41,8% | 120,51 | 2 573,23 | 35,3% | 101,91 |

Of the total number of 24 submitted project applications in Intervention area 3.3, 5 applications were received in the monitored period and the financial volume thus rose to EUR 73.13 million, representing 133.4 % of the allocation. All the 5 applications were submitted under activity a). In the monitored period no new Decisions on providing a grant were issued and in consequence of the issuance of change Decisions on providing a grant following the completion of tenders in majority of projects the amount decreased from EUR 24.68 million to EUR 24.34 million.

The new Decisions on providing a grant were not issued mainly because the tenders for the central supplier of project documentation and investor's engineering supervision have so far not been completed. These tenders are conducted by the General Directorate of the Labour Office of the CR centrally for more labour offices (in total it concerns 10 projects). The respective Decisions on providing a grant will be issued immediately after the completion of tenders.

The volume of funds paid to beneficiaries increased by EUR 2.99 million and the funds included in aggregate payment claims grew by EUR 2.97 million. In the monitored period no expenditure was certified.

Cumulative progress at the level of Intervention area 3.3 (in mil. CZK/EUR)

| 3.3 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract16 | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 1 362,46 | 54,81 | 24 | 1 817,90 | 133,4% | 73,13 | 8 | 604,93 | 44,4% | 24,34 | 83,72 | 6,1% | 3,37 | 83,76 | 6,1% | 3,37 | 9,53 | 0,7% | 0,40 |
| Previous MC | 1 357,87 | 54,81 | 19 | 1 444,76 | 106,4% | 58,31 | 8 | 611,46 | 45,0% | 24,68 | 9,53 | 0,7% | 0,38 | 9,53 | 0,7% | 0,40 | 9,53 | 0,7% | 0,40 |

In Intervention area 3.4 in the monitored period two calls for submission of project applications were under way. In call No 13 all the applications were submitted before 31 Mar 2012 and in call No 15 (announced by the MRD following the transfer of delegated activities) no project applications were submitted before 30 Sep 2012. Thus neither the number nor the amount of submitted applications increased.

For 23 projects from the 13th call “Technology to enhance the operational capability and quality of addressing emergency situations“ the Decision on providing a grant was issued and their amount increased to EUR 168.21 million.

In the projects from the 11th call on the “Uniform standard of information systems of operational management and modernisation of technologies for the receipt of emergency calls of basic units of the Integrated Rescue System”  considerable delays in the implementation of the whole set of projects are reported connected to the implementation of the umbrella project on the Integrated Rescue System. The IOP MA holds regular monthly meetings with the respective entities of the Integrated Rescue System concerning the status and implementation of individual projects.

There was no significant progress made in the amount of funds paid to beneficiaries, which totals  EUR 25.06 million, representing 12.6 %. All these funds are accounted for in aggregate payment claims.

Cumulative progress at the level of Intervention area 3.4 (in mil. CZK/EUR)

| 3.4 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 5 003,61 | 200,98 | 108 | 5 747,18 | 114,9% | 231,19 | 100 | 4 189,04 | 83,7% | 168,21 | 630,53 | 12,6% | 25,06 | 630,53 | 12,6% | 25,06 | 166,03 | 3,3% | 6,45 |
| Previous MC | 4 986,07 | 200,98 | 108 | 5 747,18 | 115,3% | 231,95 | 77 | 3 334,31 | 66,9% | 134,57 | 612,16 | 12,3% | 24,71 | 612,16 | 12,3% | 24,32 | 166,03 | 3,3% | 6,45 |

The following is applicable to all the tables above:

Source: Current MC – MSC2007 as of 3 Oct 2012

Previous MC – MSC2007+ as of 4 Apr 2012

CZK/EUR exchange rate: Current MC – 24.859

Previous MC (“a” column) – 24.778

Source of funding – public funds total

Overview of on-going calls

In the period from 1 Apr 2012 to 30 Sep 2012 a total of 10 calls for submission of project applications were under way in each of the intervention areas of Priority axis 3. In total 245 project applications for the amount of EUR 181.85 million were submitted, of which 59 projects in the volume of EUR 78.63 million were approved.

In Intervention area 3.1 three calls were under way, announced in mid- 2011, with the total allocation of EUR 52.21 million and covering all the activities a), b) and c). Altogether 177 project applications in the amount of EUR 61.22 million were submitted, of which 8 projects in the amount of EUR 6.42 million were approved.

In Intervention area 3.2 a total of 4 time-limited calls were under way, of which two were already closed and projects were evaluated. Altogether 24 project applications in the amount of EUR 14.82 million were submitted and 21 projects in the volume of EUR 13.70 million were approved. In the last two calls announced, the number and volume of submitted applications will be shown only in the course of October and November 2012, when they are closed.

In Intervention area 3.3 one call was under way for activities a) and b) with the allocation of EUR 39.09 million. In total 16 project applications in the amount of EUR 65.14 million were submitted and 7 projects in the amount of EUR 23.75 million were approved.

In Intervention area 3.4 two calls for submission of project applications were under way. The first call was announced as a continuous call in February 2012 and closed in April 2012. The second call was announced as a time-limited call, the submitted projects will thus be shown only after its closing in November 2012. Under the continuous call No 13 a total of 28 project applications in the amount of EUR 40.67 million were submitted, of which 23 projects in the volume of EUR 34.76 million were approved.

Overview of on-going calls in the period from 1 Apr to 30 Sep 2012 in Priority axis 3

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | IA / activity | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 24. | 04 | 11.11.2009 | 30.6.2013 | continuous | 3.3 a,b | 39 092 793 | 16 | 65 140 385 | 7 | 23 748 163 |
| 40. | 06 | 31.5.2011 | 30.6.2013 | continuous | 3.1 b | 10 591 455 | 27 | 14 791 004 | 0 | 0 |
| 41. | 07 | 7.7.2011 | 30.6.2013 | continuous | 3.1 a | 32 658 058 | 34 | 32 344 862 | 7 | 6 387 902 |
| 42. | 08 | 29.7.2011 | 29.6.2012 | continuous | 3.1 c | 8 958 626 | 116 | 14 088 689 | 1 | 35 650 |
| 46. | 13 | 2.2.2012 | 30.4.2012 | continuous | 3.4 d | 40 668 592 | 28 | 40 668 592 | 23 | 34 757 819 |
| 47. | 9. | 7.3.2012 | 17.5.2012 | time-limited | 3.2 c | 9 569 080 | 8 | 5 565 279 | 6 | 4 758 137 |
| 48. | 10. | 7.3.2012 | 10.5.2012 | time-limited | 3.2 b | 9 569 080 | 16 | 9 254 337 | 15 | 8 939 512 |
| 49. | 11. | 8.8.2012 | 8.10.2012 | time-limited | 3.2 b | 11 961 350 | 0 | 0 | 0 | 0 |
| 50. | 15. | 10.8.2012 | 28.11.2012 | time-limited | 3.4 d | 6 459 129 | 0 | 0 | 0 | 0 |
| 51. | 12. | 16.8.2012 | 16.10.2012 | time-limited | 3.2 c | 20 334 296 | 0 | 0 | 0 | 0 |
| IA 3.1 Total |  |  |  |  |  | 52 208 139 | 177 | 61 224 556 | 8 | 6 423 552 |
| IA 3.2 Total |  |  |  |  |  | 51 433 807 | 24 | 14 819 616 | 21 | 13 697 649 |
| IA 3.3 Total |  |  |  |  |  | 39 092 793 | 16 | 65 140 385 | 7 | 23 748 163 |
| IA 3.4 Total |  |  |  |  |  | 47 127 721 | 28 | 40 668 592 | 23 | 34 757 819 |
| PA 3 Total |  |  |  |  |  | 189 862 461 | 245 | 181 853 148 | 59 | 78 627 182 |

Source: IS Monit7+ as of 2 Oct 012

CZK/EUR exchange rate: 24.859

Source of funding –public funds total

### 3.3.3 Fulfilment of indicators

Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 330300 | Number of projects focused on social inclusion | Number | 0 | 294 | 47 | 20 |
| 075713 | Facilities with transformation in progress | Number | 0 | 30 | 11 | 0 |
| 075714 | Number of supported organisations | Number | 0 | 30 | 9 | 3 |
| 075802 | Number of supported entities | Number | 0 | 250 | 22 | 17 |
| 080100 Core 38 | Projects on the support of health – total | Number | 0 | 110 | 152 | 78 |
| 080102 | Projects on the support of health – modernising medical equipment | Number | 0 | 50 | 84 | 46 |
| 080101 | Project on the support of health – health risk prevention | Number | 0 | 45 | 52 | 23 |
| 080702 | Number of projects focused on the introduction of standards and standard procedures of quality and cost management | Number | 0 | 15 | 16 | 9 |
| 074521 | Number of supported employment services institutions | Number | 0 | 8 | 5 | 1 |
| 074532 | Number of newly built and supported existing training centres of employment services | Number | 0 | 4 | 3 | 0 |
| 074533 | Number of newly built and supported existing information and education centres of employment services | Number | 0 | 2 | 1 | 0 |
| 260407 | Number of IRS operation centres with integrated ICT | Number | 0 | 14 | 41 | 0 |
| 260408 | Number of newly built logistics bases | Number | 0 | 1 | 1 | 1 |
| 260410 | Number of modernised or newly built contact points of Front office type connected to IRS network | Number | 0 | 369 | 369 | 278 |
| 260412 | Number of technological equipment for elimination of safety risks or their implications | Number | 0 | 2180 | 2111 | 0 |

Source: MSC2007 as of 30 Sep 2012

Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 075711 | Alternative social services | Number | 0 | 60 | 44 | 3 |
| 075712 | Number of newly established social services and activities | Number | 0 | 50 | 34 | 9 |
| 075603 | Efficiency of support | % | 0 | 60 | 66,19 | 65,98 |
| 080721 | Increase in the standard (fit-out) of specialised workplaces in national networks | % | 0 | 60 | 69,38 | 70,62 |
| 080712 | Number of prevention programmes available to citizens | Number | 0 | 45 | 58 | 22 |
| 080704 | Number of programmes introducing the standards and standard procedures for quality and cost management | Number | 0 | 40 | 19 | 11 |
| 074514 | Quality increase in working and client environment of the employment services institutions | % | 0 | 15 | 15 | 0 |
| 074512 | Increase in the capacity of training centres of employment services | % | 0 | 20 | 41 | 0 |
| 074513 | Increase in the capacity of consultancy-training centres | % | 0 | 25 | 25 | 0 |
| 260401 | Number of supported IRS units | Number | 0 | 3 | 3 | 0 |
| 260406 | Decrease in average response time to imminent or existing safety risks | % | 0 | 75 | 0 | 0 |
| 260404 | Creation of new capacities for effective provision of humanitarian aid to other countries | m2 | 0 | 2 500 | 2 500 | 2500 |

Source: MSC2007 as of 30 Sep 2012

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

Indicators in Intervention area 3.1 reflect the positive progress in absorption of funds, their fulfilment depends on successful completion of the implementation of projects focused on social integration that can be reported only in the period of sustainability.

The indicator No 75802 Number of supported entities relates to activity 3.1 c). In this activity as of

3 Oct 2012 of the target value of 250 the value of 17 was achieved, with the commitment being 22. This status is caused by low number of approved project applications. Specific measures to support the absorption are now implemented not only in activity 3.1c), but across all the Intervention areas 3.1 and 3.3. The adopted measures ensued from the Action Plan based on the evaluation called Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP. The evaluation ended in June 2012 and the measures are planned until the end of 2012. Once they are implemented, it will be possible to verify their effectiveness and impact on the increase of the number of implemented projects and the associated higher fulfilment of indicators. Low number of approved projects is reflected in the non-fulfilment of n+3/n+2 rule and also in low values of indicators achieved.

The indicator No 075713 is reported through the registration or a change in the registration of a social service, mostly after the completion of project implementation. 17 projects with issued Decision undertook to fulfil the indicator up to the level of 11 residential social service facilities with transformation in progress. The change in the registration of the service has so far not been reported in any of the supported projects. As of 30 Sep 2012, the achieved value of this indicator is zero. It is anticipated that in indicator No 75713 the value of 24 will be achieved. In 3 facilities the submission of the project application is not foreseen based on the current developments and they will not be replaced by other facilities due to the demanding preparation of the process of transformation and investment projects. Another reason is the waiver of the original plan, when the implementation of investment projects was to address also the situation of the users of facilities established by MoLSA. Situation of these users is addressed by another programme, focused exclusively on the investment support for these facilities.

The target value of indicator No 75714 is related to activity 3.1b and will be fulfilled. In this activity as of 3 Oct 2012 a total of 20 projects is approved, 9 projects are at the stage of implementation or at following stages and that is also reflected by the commitment in indicator No 75714. The implementation of 3 projects was completed. It is anticipated that the value of this indicator will be fulfilled.

Although in activity 3.1 a) no project has so far been completed, two projects achieved the target value of indicator No 075711 in the course of project implementation. The fulfilment of this indicator is anticipated.

In activity 3.1 b) as of 3 Oct 2012 a total of 20 project applications were approved, of which in 18 projects the Registration of action was issued and in 10 projects the Decision on providing a grant was issued. Implementation of 3 projects was completed, the achieved value of indicator No 075712 in these projects is 9 newly established social services.

The number of supported entities, implementing the social economy projects (indicator No 075802), does not achieve the planned target value. In spite of that the efficiency of support (indicator No 075603), related to the supported social economy projects, is fulfilled by the value of 65.98 % as of 3 Oct 2012.

Low number of completed projects is obvious from the chart called Physical and financial progress in Intervention area 3.1. The Intervention area 3.1 faces the risk of non-fulfilment of n+3/n+2 rule and low absorption of funds. This situation is reflected also in the very low fulfilment of planned target values of monitoring indicators. The delays in the implementation of projects are brought about especially by lengthy process of ex-ante checks and the issuance of legal acts for aid beneficiaries. Based on the evaluation of barriers to the absorption of funds, completed in June 2012, specific measures were adopted to support the absorption. They will be implemented by the end of 2012. Subsequently, the IOP MA and MoLSA will evaluate the results of adopted measures.

The lowest value of physical progress is reported by indicator No 75802 and the related indicator No 330300. These indicators reflect particularly the low number of supported entities in activity 3.1 c). Related to this activity is also indicator No 75603, which expresses the ratio of successfully supported persons to the total number of supported persons. This indicator, on the contrary, exhibits above-the-standard fulfilment. The supported projects use the granted assistance to the maximum possible degree for support of socially excluded persons or persons at risk of social exclusion.

In indicator No 75603 high efficiency of spent funds can be seen in Intervention area 3.1, activity c) (investment support to social economy). Even though in line with the issued Decisions on providing a grant the funds in the volume of only less than 20 % of the allocation for activity 3.1 c are spent, the commitment of the fulfilment of indicator No 75603 of these projects equals more than 110 %. The indicator of efficiency of support describes the usefulness of supported projects vis-à-vis the number of supported target groups of inhabitants.

Also in indicators No 75711 and 75712 the percentage of the commitment of approved projects is higher than the percentage of committed funds from the allocation for the given intervention area based on the issued Decisions on providing a grant.

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

The indicators in Intervention area 3.2 are being fulfilled on a continuous basis. In the monitored period the commitment of approved projects increased in output indicator No 80101 “Projects on the support of health – health risk prevention” (3.2 b) by the approval of 15 projects under the 10th call as well as in indicator No 80702 “Number of projects focused on the introduction of standards and standard procedures of quality and cost management “(3.2 c) by the approval of 6 projects under the 9th call. In these indicators there was a risk of non-fulfilment,  which is why the MoH announced the calls No 9, 10, 11 and 12, which focus on Intervention areas 3.2b and 3.2c. Judging from the commitment of approved projects as of 30 Sep 2012, the fulfilment of these output indicators can be anticipated. The commitment of approved projects suggests that the risk of non-fulfilment is faced only in the result indicator No 80704 “Number of programmes introducing the standards and standard procedures for quality and cost management“, related to activity 3.2c. For this activity the call No 12 is opened until mid-November 2012, the commitment of approved projects will be known following the evaluation of the call.

The value of indicator No 080100 “Projects on the support of health – total” for Intervention area 3.2 reached the commitment of approved projects to the level of 138 %. It can be assumed that the target value will be slightly exceeded, with approximately 80 % of the allocation being distributed.

The indicator No 80102 “Projects on the support of health –modernising medical equipment” in activity 3.2a) is fulfilled to the level of 168 % (the target value of 50 projects, the Decision on providing a grant was issued in a total of 84 projects), with the allocation being distributed to almost 100 %. At the time of setting the planned target values of indicators, the particular number of beneficiaries under Intervention area 3.2a was unknown. The number of hospitals in the individual networks of specialised workplaces was determined based on the conducted audits.

The indicator No 080721 “Increase in the standard (fit-out) of specialised workplaces in national networks” is fulfilled by the completed projects to almost 120 % already. Since it is connected to indicator No 80102, the reasons for the overfulfilment are identical.

The activity 3.2b) represented by indicator No 80101 “Projects on the support of health – health risk prevention” is fulfilled to the level of 115 % based on the commitment of approved projects. The indicator No 80712  “Number of prevention programmes available to citizens” is fulfilled to more than 120 % by the approved projects. The financial allocation has so far been used to the level of approximately 60 %. With respect to the remaining financial allocation and absorption capacity of this activity, a new call for this intervention area was announced.

The activity 3.2c) is represented by indicator No 80702 “Number of projects focused on the introduction of standards and standard procedures of quality and cost management” and by indicator No 80704 „Number of programmes introducing the standards and standard procedures for quality and cost management”, the target value of which has so far not been fulfilled. In indicator No 80702 the commitment of approved projects is slightly above 100 %. In indicator No 80704 “Number of programmes introducing the standards and standard procedures for quality and cost management” the commitment has so far reached the level of 50 %. In these values of indicators the allocation is absorbed to the level of 60 % and due to the risk of non-fulfilment of indicator No 80704 the 12th call focused on this intervention area was announced.

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

Intervention area 3.3. Since the value of output indicators No 74521, 74532, 74533 is reported only after the completion of project implementation, as of 30 Sep 2012 the achieved value in indicators No 074532 and 074533 is still zero.

The Selection Committee approved a total of 6 projects in activity a) and 3 projects in activity b). Additional 2 projects were approved together for activity a) and b). It concerns the projects of the LO of the CR - Pardubice – construction of a building and a training centre and the LO of the CR - Olomouc - Tabulový vrch II premises. Other 4 projects expected in activity a) are under administration. The commitment of approved projects in indicator No 74514 in activity a) was fulfilled, in activity b) the indicator No 74512 was exceeded. The value of indicator No 74512 is based on the number of trained staff of employment services in the constructed training centres. The indicator was exceeded because in the individual training centres the LO CR as the applicant undertook to train a higher number of persons than anticipated when the target value of the indicator was set in the Programming Document.

In activity c) 2 projects are approved, the indicator No 074513 is fulfilled.

Low number of completed projects is obvious from the Comparison of physical and financial progress chart. The Intervention area 3.3 struggles with the risk of non-fulfilment of n+3 rule and low absorption of funds. This situation is mirrored also in the very low fulfilment of the planned target values of monitoring indicators. Delays in the implementation of projects in activity a) (indicators No 74521, 74514) and activity b) (indicators No 74532, 74512) are caused especially by the time consuming nature of the preparation and implementation of tenders for the supplier of project documentation and investor's engineering supervision, including the occupational health and safety coordinator conducted by the General Directorate of the Labour Office of the CR and the issuance of legal acts for aid beneficiaries. Based on the evaluation of barriers to the absorption, completed in June 2012, specific measures to support the absorption were adopted. The allocation for activity 3.3c) (indicators No 74533 and 74513) was intended for 5 projects, but only 1 project is under implementation, which is the reason of low fulfilment of the planned target values.

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

In the monitored period the commitment of approved projects rose in indicator No 260412, which is linked to the call No 13, under which legal acts were issued in the course of June. A slight progress in the monitored period was reported in the fulfilment of indicator No 260410, with the projects on contact and coordination centres of the second wave being gradually completed and indicators being fulfilled.

In indicator No 260407 the physical commitment considerably exceeds the financial progress. The reason behind is the fact that in the call the regional standardised projects were divided into projects for the Police CR units, FRS CR units and regions (Emergency Medical Service), whereas the Programming Document reckons with 14 projects with all units in the regions being reported together by the value of 1.  The indicator No 260401 relates exclusively to the umbrella project of the Integrated Rescue System. The umbrella project and all the regional standardised projects of operation centres are currently under implementation.

The indicator No 260406 is not fulfilled by individual projects since the contribution to the decrease in the average response time cannot be attributed to any particular implemented project. This is why the indicator was not chosen in any of the projects. The IOP MA ascertained the value of this indicator reported a summary value by the FRS and PCR units. In case of the Police, the implementation of projects should lead to the decrease in the average response time to imminent or existing safety risks at least by 25 %, the implementation of projects will cut the period necessary for tracking the police patrol vehicles from the current  300 seconds to 5 seconds (the decrease in response time by approx. 98 %) and cutting the time of information transmission from databases from the current 360 seconds to 40 seconds (decrease of response time by 89 %). The FRS is able to monitor this indicator to a certain extent in certain types of equipment.

### 3.3.4 Problems and measures taken

Intervention area 3.1

The most pivotal issue is the risk of failure to absorb the allocation and to fulfil the n+3 rule. The risk is still present even though the MoLSA keeps adopting measures to minimise it. The vast majority of activities and adopted corrective measures are directed to the support of absorption of funds, support of project submission and speeding up of project administration.

In calls No 06 – 08,  the evaluation mechanism was modified and other changes were made which were to simplify the preparation of projects and their subsequent administration. In the monitored period, the volume of funds in projects with issued Decision rose by 18 % and as of 30 Sep 2012 the amount reached 32 % of the allocation for this intervention area.

Corrective measures

- The MoLSA continued to implement the system of regular reporting to the EC, which contains information on the issuance of guidance documents, an overview of absorption of funds and forecast absorption. Thus, the monitoring of progress made in the absorption of funds is ensured. Reports are also forwarded to MoLSA senior officials. For internal purposes, monitoring of individual activities (anticipated issuance of the Decision on providing a grant, ex-ante checks, notification of changes) was introduced by MoLSA in selected projects.

- On 2 Jul 2012, the comment procedure concerning the revision of the Handbook of Work Procedures of the Ministry of Labour and Social Affairs Intermediate Body, version 1.4 (hereinafter referred to as the “HWP“) was completed. The revision of HWP included for instance the modification of work procedures leading to the acceleration of project administration, issuance of single (merged) guidance documents, cutting or introducing the deadlines for individual activities (conduct of ex-ante checks, handing over the documentation between MoLSA and CRD), activities related to regular reporting, changes in project quality evaluation, etc.

- Working meetings between MoLSA and CRD have been introduced that are instrumental in faster project administration. At these meetings, current priority tasks are identified and prevailing problems in administration are highlighted and addressed.

- Monitoring of projects falling in the category of sleeping and risky projects has been introduced.  Delays in administration are identified and appropriate measures are adopted.

- An important measure in support of absorption under activities 3.1 a) and b) is the division of time consuming projects and projects with high financial requirements into smaller stages.  This division was brought to the attention of beneficiaries by letters of the Director of EU Funds Implementation Department of 14 Aug 2012 and 30 Aug 2012.

- In June, the evaluation of work procedures optimisation called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP“ was completed. On June 12, the report from this evaluation was published on http://www.strukturalni-fondy.cz/Programy-2007-2013/Tematicke-operacni-programy/Integrovany-operacni-program/Dokumenty/Dalsi-dokumenty/Evaluacni-aktivity-RO.

The evaluation of barriers mapped the procedural and system barriers to absorption in Intervention areas 3.1 and 3.3 and the reasons behind the lack of absorption and the adoption of measures to support the absorption of funds were proposed.

Based on the evaluation of barriers, an action plan comprising ninety corrective measures and deadlines for their fulfilment has been adopted.

The evaluation proposed corrective measures aimed to accelerate the administration, mainly by modifying the description of activities and deadlines in the HAB. In the revision of the Handbook of Work Procedures version 1.4 duplicate and redundant activities were removed and the checklist for eligibility checks and checks of formal requisites of CRD was modified. Following the approval of revisions of calls and Handbooks for Applicants and Beneficiaries, the MoLSA shall hold a seminar for CRD staff on the evaluation of eligibility and formal requisites. As of 30 Sep 2012, no revision of Handbooks for Applicants and Beneficiaries was approved.

Another measure proposed within the evaluation of barriers was the introduction of a more effective system of issuing guidance documentation. A step towards the meeting of this requirement was e.g. the revision of the Handbook of Work Procedures, concerning the issuance of a single (merged) document of the Registration of action and the Decision on providing a grant.

Also other issues were identified, such as extension of the deadline for ex-ante checks and high percentage of projects in which ex-ante checks are carried out.  In line with the Action Plan, measures to eliminate them were put into practice. A large number of projects subject to ex-ante checks and their lengthy conduct keep unduly protracting the administration of applications for support, postpone the implementation of projects and the absorption of assistance.

Some of the planned measures listed in the Action Plan were commenced in the monitored period, but have not been completed as yet. E.g. the revisions of calls are time consuming due to the prevailing problems in the areas in which the consensus between MoLSA, CRD and IOP MA has not been reached as yet.

Another area, in which the consensus between MoLSA, CRD and IOP MA has not been reached as yet, is the simplification of excessive requirements placed on the applicants (e.g. unclear definitions of terms, Aid Registration System forms, determination of financial and technical limits, parameters in the Decision, reporting of indicators, supporting documents for final evaluation of action).

Strengthening the absorption capacity. One of the reasons behind the failure to fulfil the n+3 rule and absorb the allocation is constituted by absorption capacity issues. These two issues are closely linked and have to be addressed simultaneously.

Corrective measures

- In order to increase the absorption capacity the revision of all the calls under Intervention area 3.1 was commenced. The revision of calls aims primarily to simplify and clarify the obligations of aid beneficiaries.

- On 28 Jul 2012, the MoLSA extended the call for activity 3.1 c). The revision of the call aimed to simplify the requirements placed on the applicants, to specify and clarify the interpretation of rules of the call. Modifications were made mainly in those parts of documentation where the applicants most frequently made mistakes while completing the application. Changes were made based on the most frequently asked questions and consultations. The conducted modifications concern particularly the specification of the reporting of monitoring indicators, interpretation of the eligibility of expenditure in case of technical improvement of fixed assets, extension of staffing and production capacity of the existing company, endorsing the social economy principles by the applicant in the foundation documents, update of instructions to complete the application in IS Benefit 7.

- Intensive consultations concerning the submitted projects and project outlines in cooperation with the National Centre for Support of the Transformation of Social Services and the Agency for Social Inclusion.

- In September 2012, the IOP Annual Conference was held on the Quality of Life – Forms of social integration supported by the EU. It was divided into three blocks focused on the process of transformation of residential social service facilities, support to members of socially excluded Roma locations/communities and support to social economy. During the conference presentations were given by MoLSA representatives on successful projects and subsequently the participants visited a successfully implemented project, namely Mléčný bar NAPROTI social enterprise.

Intervention area 3.2

Error rate in conducted DAB audits

The updated Methodology of Financial Flows defines the DAB audit findings to be a confirmed suspected irregularity. In the opinion of MoH, the findings of DAB auditors are often of subjective nature, before the new Methodology of Financial Flows came into force the findings of DAB auditors had not been confirmed by other authorities (OPC, Tax Offices).

Measure taken

Cooperation with beneficiaries in the framework of DAB audits, preparation of supporting documents for contentious proceedings between the AA and MA.

Amendment to Act on public contracts, a necessity to modify the prepared tender documentation.

Measure taken

Holding a seminar focused on the amendment to Act on public contracts, provision of information to beneficiaries via e-mail and website.

Extension of implementation of projects with respect to the Amendment to Act on public contracts (if only one bid is submitted, the tender has to be cancelled) and Anti-Corruption Strategy of MoH (splitting the contract pursuant to Section 98 of APC, higher administrative burden).

Measure taken

Continuous consultations with beneficiaries, a proposal for division of projects into more stages to enable an on-going submission of applications for payment for the tendered parts of contracts.

Repeated findings in DAB audits concerning the evidencing of work by external management

Measure taken

For all the calls a binding guideline concerning the HAB was issued which provided a binding model statement of work and bill of delivery.

Intervention area 3.3

Tenders. Time consuming preparation of tenders which causes delays in administration and absorption.

Measure taken

The General Directorate of the Labour Office of the Czech Republic conducts a central tender for the administrator of public contracts, a designer, investor's engineering supervision and occupational health and safety coordinator for projects of the Labour Office of the Czech Republic, in which these activities have not been tendered as yet (it concerns approx. 10 projects). The implementation of a central tender helps avoid mistakes which could otherwise be made in awarding the individual contracts. The tenders for investor's engineering supervision and occupational health and safety coordinator and a designer have already been closed and soon will be referred to the CRD for control.

Failure to absorb the allocation under call No 5 – in activity c) following the reallocation in May funds were earmarked to 4 planned projects, 2 projects were supported and there is a risk of failure to absorb the allocation.

Measure taken

The MoLSA will announce call No 9 for 3.3 c) in the autumn of 2012. Based on the interest expressed by potential applicants, a new call for this activity was drawn up at the working meeting with the representatives of regions (April 2012), which better reflects the existing situation and shall safeguard the absorption of allocation. Now, the MoLSA finalises the documentation for the call which will be submitted to the IOP Managing Authority for approval in November 2012.

Time consuming preparation of projects under call No 4. It concerns construction investment actions, the preparation of which is extremely time-consuming (acquisition of a building permit, planning permission procedure, acquisition of the building by the applicant, etc.). Considered risky are projects which were included in the List of Projects of the Labour Office of the CR only in 2011 and for which there is not time enough for proper preparation.

Measure taken

On-going methodological support to applicants with the aim to facilitate the submission of all the projects under activities a) and b) by the end of 2012.

Risk of failure to fulfil the N+3 rule and absorb the allocation. It concerns primarily the delay in absorption which occurred at the beginning of programme implementation. The MoLSA adopts measures to minimise this risk. Vast majority of activities and adopted corrective measures is directed at the support of absorption of funds, support of project submission and acceleration of project administration.

Measure taken

- Revision of the Handbook of Work Procedures of MoLSA IB – modification of work procedures conducive to the speeding up of project administration, e.g. issuance of single (merged) guidance documents, introduction or cutting of the deadlines for individual activities.

- In September 2012, projects were selected that are fitting for the division into stages, the applicants were sent letters requesting this division.

Intervention area 3.4

Involvement of Česká pošta in the implementation of projects under the programme “Uniform standard of information systems of operational management and modernisation of technologies for the receipt of emergency calls of basic units of the Integrated Rescue System” (IRS IS) pursuant to Government Resolution No 224/2012 and delays in the timetables of  implementation of individual projects.

Measures taken

Regular monthly meetings with the IRS units concerning the current developments and postponement in the implementation of the umbrella project (IRS NIS), individual regional standardised projects, the system of project management, etc.

Low fulfilment of forecast absorption of funds and postponements of activities to next project stages, extension of project implementation

Measures taken

The IOP MA designed the system of identification and monitoring of sleeping and risky projects and assigned the specific measures to the individual projects. The sleeping and high-risk projects are regularly monitored. A precondition for the extension of project implementation is its division into stages.

As of 1 Jul 2012, the delegated activities were transferred from MoI CR to MRD CR and CRD CR which should help accelerate the administration and absorption under the Integrated Operational Programme.

### 3.3.5 Example of a project

Intervention area: 3.1 Social integration services

Name of the project, registration number: NAPROTI Dairy Bar – setting up and stabilisation of a sustainable social enterprise Reg. No  CZ.1.06/3.1.02/01.07612

Beneficiary: NAPROTI Cooperative

Project funding:  Total budget CZK 1 105 769, of which CZK 845 912 Structural Funds contribution, CZK 149 279 state budget contribution, CZK 110 578 own resources of the applicant

In the centre of Ostrava you can visit NAPROTI Dairy Bar which is the first example of social entrepreneurship in the field of catering in Ostrava. The wheelchair accessible entrance to the bar on its own indicates that all clients are welcome here. They can choose from a broad range of meals and drinks prepared from quality raw materials supplied by local farms. The kids' corner shows that the bar is also family friendly. While the change table is important for mothers with babies, the free Wi-Fi access is appreciated mainly by students.

Apart from offering quality and fast food, NAPROTI Dairy Bar also offers a friendly setting to persons with partially-reduced work capacity. In total, eight new jobs have been created, of which three permanent jobs for persons with mental disability and psychiatric diagnosis. The applicant for support has had abundant experience with this group of citizens. He has helped disabled persons find jobs in the Czech labour market before. And this experience he decided to exploit when operating NAPROTI Dairy Bar.

Intervention area: 3.2 Public Health Services

Name of the project, registration number: Rental of compensatory aids of the Association of Persons with Disabilities in the Czech Republic, o.s, CZ.1.06/3.2.01/02.06114

Beneficiary: Association of Persons with Disabilities in the Czech Republic, o.s.

Project funding: Total budget CZK 9 266 308, of which CZK 7 876 361 SF contribution and CZK 1 389 947 SB contribution

There are approximately 550,000 persons with disabilities living in the Czech Republic who can rent any of the wide portfolio of aids offered by the rentals run by the Association of Persons with Disabilities, a non-profit organisation. Thanks to the support from IOP, the Association could purchase 489 wheel chairs, walking frames, adjustable beds and other kinds of aids which make the everyday life of handicapped citizens easier.

The project helped equip the 14 existing rentals and open additional 8 new rentals. The rentals offer compensatory aids when the persons with a permanent or temporary disability need them the most and have no access to them.

Mobility scooter					Stair climber

Anti-decubitus pad

Intervention area: 3.3 Employment services

Name of the project: Information and Education Centre of Plzeňský region, CZ.1.06/3.3.00/05.08084

Beneficiary: Regional Education Centre and Language School with accreditation of state language examinations, Plzeň, sady 5. května 42

Project funding: Total budget CZK 24 193 382, of which CZK 20 564 374 Structural Funds contribution, CZK 3 629 008 regional budget.

The consistently high unemployment rate requires the use of new tools of employment services which would  complement and extend the range of services offered by the Labour Office of the CR. There is a room for other public entities that can more flexibly respond to the current needs. Ranking among such entities will be the newly developed Information and Education Centre that shall focus on lifting certain barriers to the employment of job applicants and job seekers in the labour market.

Basic information will be available to clients in self-service information kiosks in the information hall that the visitors can use independently, or with the assistance of the receptionist. The trained consultants will be there for clients, capable of analysing their needs and giving them recommendations as to how to improve their position in the labour market. For the sake of clients development there are study rooms and computer technology available. On the second floor group consultancies will take place, within which certain types of training will be offered to a limited degree which are either completely missing in the region or are not included in the portfolio of services offered by educators and trainers as yet.

The financial support will be spent on the reconstruction of the building that shall accommodate the centre and on the purchase of technical and office equipment.

Intervention area: 3.4 Services in security, risk prevention and management

Name of the project: Increasing the operational capability of the FRS of Vysočina Region for rescue and liquidation operations during natural disasters, CZ.1.06/3.4.00/13.08172

Beneficiary: Fire Rescue Service of Vysočina Region

Project funding: Total budget CZK 16 560 000.00, of which CZK 14 076 000.00 Structural Funds contribution, CZK 2 484 000.00 state budget contribution

The main aim of the project is to increase the mobility and operational capability of the FRS CR, one of the basic units of IRS, in the territory of Vysočina region in case of emergency situations – natural disasters, especially floods, and to enhance the readiness of FRS of Vysočina Region (and FRS CR as a whole) in the framework of IRS for various emergency situations, natural disasters in particular.

The aim was achieved by acquiring special mobile rescue set that shall increase the operational capability and mobility of the FRS of Vysočina Region for rescue and liquidation operations during natural disasters, especially floods, and improve the effectiveness of these operations.

The project is a part of the operation called Increasing the operational capability of the FRS CR for rescue and liquidation operations during natural disasters. The implementation of similar projects in the territory of the other regions (except for the City of Prague) will bring about a synergic supra-regional effect of projects in the framework of the operation. The project implementation is foreseen to be completed in February 2013.

## 3.4 Priority axis 4a, 4b – National support of tourism

### 3.4.1 Focus of priority axes/intervention areas

The aim of Priority axes 4a, 4b is to support the formation of basic environment and conditions necessary for tourism development at the national level. To achieve its effective development it is necessary to manage and coordinate some tourism activities from the national level, which helps create suitable conditions for the development of business, increased competitiveness and employment in the this area.

The priority axis covers the Convergence objective (4a) and the Regional Competitiveness and Employment objective (4b).

Specific goals:

- Increase of the number of entities connected to the reservation (booking) system in tourism sector,

- To improve the quality of services provided in tourism, their uniform certification and standardisation,

- To improve the tourism statistics and information,

- To increase the number of publicity and marketing products of tourism.

Supported activities:

  - establishment of a national information and reservation (booking) system,

  - introduction and information support of national and international standards in tourism services,

  - support of nationwide marketing and creation of source databases,

  - presentation and promotion of cultural and natural wealth, culture industry and services used for tourism on the national level,

  - support of the promotion of the CR as a tourism destination.

Beneficiaries:

- government agencies and semi-budgetary organisations established by them (activities a, b, c, e),

- non-governmental non-profit organisations and interest associations of legal persons with national scope of activities in tourism (activity d).

### 3.4.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention areas 4.1a and 4.1b in the monitored period the call No 12 was opened, under which two projects were submitted increasing the volume of submitted applications by EUR 0.95 million, by 1.3% of allocation in each objective. The submitted applications have thus reached EUR 141.34 million and equal 61.8 % of the allocation.

In the monitored period the Decision on providing a grant was issued for a total of 8 projects, as against the data given at the previous MC meeting the value grew by EUR 20.90 million to EUR 47.42 million. The share of projects with issued Decision on providing a grant equals 64.8 %.

A slight progress by EUR 1.5 million was achieved in the reimbursement of funds to beneficiaries, the volume of which rose to EUR 9.8 million representing 12.7 % of the allocation. Similar situation is reported by the volume of funds included in aggregate payment claims, the volume of which increased by EUR 0.86 million to EUR 9.06 million and represents 11.7 % of the allocation.

It will be necessary to adopt measures to support the absorption of funds. The problem of evidencing the eligible expenditure encountered in the previous period continues due to the large quantity of labour and overhead costs. In this context, the CRD more often uses external experts for the assessment of 3E.

The volume of certified expenditure remained unchanged due to the suspension of certification since the previous monitored period, the funds totalling EUR 7.20 million were certified, i.e. 9.3 % of the allocation for the intervention area.

Cumulative progress at the level of Intervention area 4.1a and 4.1b (in mil. CZK/EUR)

| 4.1a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 1 769,80 | 71,26 | 75 | 3 262,77 | 184,4% | 131,25 | 23 | 1 092,99 | 61,8% | 44,03 | 224,63 | 12,7% | 9,10 | 207,61 | 11,7% | 8,41 | 164,70 | 9,3% | 6,69 |
| Previous MC | 1 764,55 | 71,26 | 74 | 3 230,27 | 183,1% | 130,37 | 19 | 610,37 | 34,6% | 24,63 | 191,09 | 10,8% | 7,71 | 187,44 | 10,6% | 7,61 | 164,70 | 9,3% | 6,69 |
| 4.1b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract17 | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 136,14 | 5,48 | 75 | 250,95 | 184,3% | 10,09 | 23 | 84,08 | 61,8% | 3,39 | 17,28 | 12,7% | 0,70 | 15,98 | 11,7% | 0,65 | 12,68 | 9,3% | 0,51 |
| Previous MC | 135,73 | 5,48 | 74 | 248,45 | 183,0% | 10,03 | 19 | 46,95 | 34,6% | 1,89 | 14,70 | 10,8% | 0,59 | 14,43 | 10,6% | 0,59 | 12,68 | 9,3% | 0,51 |

Source: Current MC – MSC2007 as of 3 Oct 2012

Previous MC – MSC2007+ as of 4 Apr 2012

CZK/EUR exchange rate: Current MC – 24.859

Previous MC (“a” column) – 24.778

Source of funding – public funds total

Overview of on-going calls

In Intervention areas 4.1a and 4.1b, one call was under way in the monitored period, announced in September 2011 as a continuous call with allocation of EUR 40.13 million. Altogether 20 project applications in the amount of EUR 44.83 million were submitted and 6 projects in the amount of EUR 19.16 million was approved.

Overview of on-going calls in the period from 1 Apr to 30 Sep 2012 in Priority axis 4a and 4b

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | IA/acti-vity | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 43. | 12 | 7.9.2011 |  | continuous | 4.1 a,c,e | 37 261 593 | 10 | 41 627 865 | 3 | 17 793 282 |
|  |  |  |  |  |  | 2 866 276 | 10 | 3 202 143 | 3 | 1 368 714 |
|  |  |  |  | Call total | 40 127 870 | 20 | 44 830 008 | 6 | 19 161 996 |
| CONV total | 37 261 593 | 10 | 41 627 865 | 3 | 17 793 282 |
| RCE total | 2 866 276 | 10 | 3 202 143 | 3 | 1 368 714 |
| PA 4 total | 40 127 870 | 20 | 44 830 008 | 6 | 19 161 996 |

Source: IS Monit7+ as of 2 Oct 2012

CZK/EUR exchange rate: 24.859

Source of funding –public funds total

### 3.4.3 Fulfilment of indicators

Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value CONV | Target value RCE | Commitment of approved projects CONV | Commitment of approved projects RCE | Achieved value as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 410100 Core 34 | Number of projects focused on tourism development | Number | 0 | 44 | 23 | 23 | 23 | 12 |
| 413305 | Number of information portals | Number | 0 | 1 | 1 | 0 | 0 | 0 |
| 413315 | Number of introduced standards in tourism services | Number | 0 | 5 | 5 | 4,64 | 0,36 | 0 |
| 410304 | Number of marketing and statistical surveys | Number | 0 | 6 | 6 | 9,29 | 0,71 | 1 |
| 410303 | Number of publicity campaigns promoting tourism products | Number | 0 | 32 | 11 | 34,37 | 2,63 | 10 |

Source: MSC2007 as of 30 Sep 2012

Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value CONV | Target value RCE | Commitment of approved projects CONV | Commitment of approved projects RCE | Achieved value as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 413311 | Share of entities operating in tourism in the CR, which will be connected to the information portal | % | 0 | 50 | 50 | 0 | 0 | 0 |
| 413320 | Number of newly classified and certified entities operating in tourism | Number | 0 | 1720 | 280 | 2000 | 280 | 0 |
| 413321 | Number of created source databases | Number | 0 | 6 | 6 | 3,72 | 0,28 | 0 |
| 410302 | Number of created publicity or marketing products for tourism | Number | 0 | 10 | 10 | 25,09 | 1,91 | 11 |

Source: MSC2007as of 30 Sep 2012

Comparison of physical and financial progress

Source: IS Monit7+as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

Progress in the fulfilment of monitoring indicators in Intervention area 4.1 is very low because the majority of indicators is being fulfilled only after the completion of project implementation. As of  30 Sep 2012, the implementation of four projects in activity d) and two projects in activity e) was completed, which was manifested by the increase in the achieved values of indicator No 410302 Number of created publicity or marketing products for tourism  and No 410303 Number of publicity campaigns promoting tourism products.

For the fulfilment of MI in activity a) Establishment of the national information system - (indicators No 413311, 413305), projects were submitted at the beginning of 2012. The administration of projects was extended due to the identification of deficiencies during the evaluation of quality confirmed by risk analyses and ex-ante checks. There was an imminent risk of ineligible expenditure (non-compliance with the criteria of economy, efficiency and effectiveness of expenditure, insufficient analyses, unclear activities). The project approval is anticipated by the end of November 2012.

The commitment to fulfil the monitoring indicator No 413315 in activity b) Introduction and information support of national and international standards in tourism services (including especially certification, manuals, methodologies, systems, controls) of approved projects corresponds with the forecast target values.

When the programme was drafted and the indicative target values for both the objectives were set, no account was taken of the fact that the indicator No 410302 will be fulfilled in all the projects focused on publicity in tourism. Since this indicator is opted for by majority of applicants for support, the planned target value of the monitoring indicators exceeded. Currently, the indicator reports the value of 11, which is by one point (product) more than the originally planned target value of the indicator.

The excessive value of indicator No 410304 is caused by the need to implement more separate statistical surveys than planned.

### 3.4.4 Problems and measures taken

A challenging control of economy, efficiency and effectiveness of spent funds

Measures taken: Cooperation with external experts in the assessment of economy, efficiency and effectiveness of spent funds at the stage of ex-ante checks of projects

Failure to meet the timetables of project implementation, slow progress in project implementation. Apart from insufficient activities of aid beneficiaries in project implementation, the IOP MA analyses also other barriers to fast implementation and administration of projects. In some procedures (approval of applications for payment, evaluation of eligibility and formal requisites, etc.) delays in project administration were detected which subsequently result in the extension of deadlines for approval of projects, delays in the announcement of tenders and in the approval of applications for payment.

Measures taken

- Introduction of meetings of the directors of the IOP Managing Authority, Centre for Regional Development of the CR, Tourism Department of MRD and CzechTourism with the 1st Deputy Minister for Regional Development (approx. every two months).

- Introduction of quarterly reporting on the progress made in the implementation of projects to senior officials of the ministry.

- Bilateral meetings between IOP MA and individual beneficiaries.

- Participation of IOP MA in working meetings with beneficiaries.

- Setting out priorities for CRD activities in project administration.

Inadequate description of project activities, inconsistency of activities with project budget

Measures taken: Consultations at CRD branches and use of expert opinions provided by consultants.

### 3.4.5 Example of a project

Intervention area: 4.1 National support of tourism

Name of the project, registration number: Monitoring of foreign visitors to the Czech Republic, CZ.1.06/4.1.00/04.05985

Beneficiary: Czech Headquarters of Tourism - CzechTourism

Project funding: Total budget CZK 73 102 000,-, of which CZK 62 136 700,- Structural Funds contribution, CZK 10 965 300,- state budget contribution

The aim of the project is to define the profiles of foreign visitors to the Czech Republic. The results of the survey are used primarily for planning the strategy of marketing activities of CzechTourism agency, but they also serve as a starting point for planning activities in regions of the Czech Republic, tourist regions and tourist destinations.

The project is composed of the following activities:

- Monitoring of foreign tourists with respect to tourist products broken down by geographical location - Europe

- Monitoring of foreign tourists with respect to geographical location - Russia, Ukraine and the Baltics

- Monitoring of foreign tourists with respect to geographical location - overseas

- Profile of foreign tourists as a measure of effectiveness of targeted campaigns to support the incoming tourism

The first three processes focus on the collection of data on potential foreign visitors to the Czech Republic and their analysis. The fourth process aims to measure the effectiveness of promotion campaigns conducted by the CzechTourism agency.

Motives of products that best capture the spirit of the CR

Source: The final report from the project called Profile of foreign visitors as a measure of effectiveness of targeted campaigns to support incoming tourism – Europe, January 2011, elaborated by  STEM/MARK, a. s. (http://www.czechtourism.cz/vyzkum/monitoring-zahranicnich-navstevniku-cr-iop/)

## 3.5 Priority axis 5 – National support of territorial development

### 3.5.1 Focus of priority axes/intervention areas

The interventions aim to create the basic environment that will be complemented by interventions from Regional Operational Programmes. The intervention areas are:

- 5.1 – National support for utilising the cultural heritage potential

- 5.2 – Improving the environment in problematic housing estates

- 5.3    Modernisation and development of systems for creating territorial policies

Specific goals:

- Improvement of services for owners of the monuments in the field of care of the  cultural heritage, more intensive use of cultural heritage in the CR and presentation of culture to the public

- Enhancing the quality of life and environment for inhabitants of problematic housing estates in large towns over 20 000 inhabitants by means of revitalisation of the environment of these estates and regeneration of residential buildings in the housing estates, including energy savings.

- Enforcing the management of sustainable development of the territory with the use of territorial plans of municipalities and better analytical planning materials to reduce regional disparities.

Beneficiaries:

- Government agencies and semi-budgetary organisations established by them,

- Municipalities and organisations established by them, unions of municipalities,

- Non-governmental non-profit organisations and interest associations of legal persons

- Owners of residential, or non-residential premises,

- Regions.

### 3.5.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention area 5.1 no call was under way in the monitored period. The total of 51 project applications submitted since the beginning of the programming period thus reach EUR 636.19 million and account for 234.6 % of the allocation. Two projects from the third call were approved and the volume of projects with issued Decision on providing a grant thus increased from EUR 226.60 million to EUR 240.38 million, which represents 88.7 % of the allocation. The beneficiaries were paid a total of EUR 55.98 million, which is 20.7 % of the allocation, the aggregate payment claims accounted for by the PCA total EUR 55.67 million (20.6 % of the allocation).

The slow reimbursement of funds is caused by complicated and time consuming implementation of public procurement procedures, protractions in public procurement procedures brought about by the provision of additional information to parties interested, problematic assessment and evaluation of received bids or lodging appeals by unsuccessful applicants with the OPC.

Throughout the whole process of public procurement/tender procedures the controls are conducted by the Ministry of Culture and the National Heritage Institute as an external expert, thanks to which the referred to risks are reduced to minimum. The Ministry of Culture provides consultations to beneficiaries, holds training courses and seminars, intensively communicates with beneficiaries, and takes part in Selection Committee meetings as an observer.

Another reason behind the slow absorption of funds is unpredictable factors emerging during construction activities, such as archaeological finds or requirements of the conservation of monuments.

In the monitored period (especially towards its end) the beneficiaries concluded 7 contracts for the delivery of construction works. The commencement of construction works has, however, no impact on the progress in financial terms. The concluded contracts for the delivery of construction works were thus not reflected in the financial data of the monitored period. The actual rate of absorption therefore mirrors the progress in implementation of projects, in which the contracts for construction works were concluded in the previous period.

Cumulative progress at the level of Intervention area 5.1 (in mil. CZK/EUR)

| 5.1 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 6 741,52 | 270,95 | 51 | 15 815,05 | 234,6% | 636,19 | 19 | 5 981,77 | 88,7% | 240,38 | 1 397,57 | 20,7% | 55,98 | 1 390,03 | 20,6% | 55,67 | 489,84 | 7,3% | 20,02 |
| Previous MC | 6 707,95 | 270,95 | 51 | 15 815,05 | 235,8% | 638,27 | 17 | 5 614,77 | 83,7% | 226,60 | 1 013,28 | 15,1% | 40,89 | 894,06 | 13,3% | 36,01 | 510,78 | 7,6% | 20,84 |

In Intervention area 5.2 the projects have been submitted, approved and funds have been reimbursed throughout all the years of the programming period. As of 30 Sep 2012, a total of 959 project applications in the amount of EUR 197.80 million (78.9 % of the allocation) were submitted, of which 868 projects  amounting to EUR 144.64 million (57.6 % of the allocation) were approved. The beneficiaries were paid the amount of EUR 89.92 million, which represents 35.7 %, and the aggregate payment claims accounted for by the PCA amounted to EUR 89.58 million (35 % of the allocation).

Cumulative progress at the level of Intervention area 5.2 (in mil. CZK/EUR)

| 5.2 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract18 | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 6 233,50 | 251,03 | 959 | 4 917,01 | 78,9% | 197,80 | 868 | 3 588,58 | 57,6% | 144,64 | 2 228,30 | 35,7% | 89,92 | 2 219,85 | 35,6% | 89,58 | 1 152,41 | 18,5% | 47,02 |
| Previous MC | 6 207,49 | 251,03 | 895 | 3 943,46 | 63,5% | 159,15 | 791 | 3 091,52 | 49,8% | 124,77 | 1 931,36 | 31,1% | 77,95 | 1 669,98 | 26,9% | 67,54 | 1 152,69 | 18,6% | 47,03 |

In Intervention area 5.3 no new project applications were received in the monitored period, their volume remains to be EUR 10.28 million, which represents 107.4 % of the allocation. 509 projects in the volume of EUR 16.76 million (91.9 % of the allocation) were approved. The reimbursement of funds to beneficiaries was smooth, the share of funds paid to beneficiaries increased by 7.5 % (by EUR 0.89 million) to EUR 16.26 million.

Cumulative progress at the level of Intervention area 5.3 (in mil. CZK/EUR)

| 5.3 | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 466,94 | 18,27 | 579 | 501,63 | 107,4% | 20,18 | 509 | 429,31 | 91,9% | 16,76 | 417,02 | 89,3% | 16,26 | 414,86 | 88,8% | 16,18 | 327,73 | 70,2% | 12,70 |
| Previous MC | 465,75 | 18,27 | 579 | 501,63 | 107,7% | 20,24 | 510 | 433,31 | 93,0% | 17,49 | 380,75 | 81,8% | 15,37 | 364,74 | 78,3% | 14,18 | 327,73 | 70,4% | 12,70 |

The following is applicable to all the tables above:

Source: Current MC – MSC2007 as of 2 Oct 2012

Previous MC – MSC2007+ as of 4 Apr 2012

CZK/EUR exchange rate: Current MC – 24.859

Previous MC (“a” column) – 24.778

Source of funding – public funds total

Overview of on-going calls

In Priority axis 5 one call was under way for the submission of project applications under Intervention area 5.2,  announced in May 2009 as a continuous call. The project applications have been submitted on a continuous basis. As of 30 Sep 2012, altogether 958 applications in the amount of EUR 175.17 million were submitted and 881 projects in the amount of EUR 149.18 million were approved.

Overview of on-going calls in the period from 1 Apr to 30 Sep 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | IA/acti-vity | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 15. | 07 | 22.5.2009 |  | Continuous | 5.2 a,b,c | 167 222 155 | 958 | 175 165 152 | 881 | 149 183 688 |
| IA 5.1 total | 0 | 0 | 0 | 0 | 0 |
| IA 5.2 total | 167 222 155 | 958 | 175 165 152 | 881 | 149 183 688 |
| IA 5.3 total | 0 | 0 | 0 | 0 | 0 |
| PA 5 total | 167 222 155 | 958 | 175 165 152 | 881 | 149 183 688 |

Source: IS Monit7+ as of 2 Oct 2012

CZK/EUR exchange rate: 24.859

Source of funding – public funds total

IUDP implementation

Status of IUDP implementation

The Integrated Urban Development Plans of IOP have been implemented in 41 towns (municipalities). Until 30 Sep 2012, a total of 193 calls were announced in all the towns, of which 131 calls were closed and the remaining 60 calls, mostly continuous, are still under way.

Number of calls announced for IUDP

| Activity 5. 2. | Number of calls announced before 30 Sep 2012 |
| --- | --- |
|  | Number of calls total | Of which closed calls | Of which open calls |
| a) revitalisation of public spaces | 48 | 7 | 40 |
| b) regeneration of residential buildings | 126 | 112 | 14 |
| c) pilot projects | 9 | 5 | 4 |
| Combined calls for a) + b) | 8 | 8 | 0 |
| Combined calls for a) + b) + c) | 2 | 0 | 2 |
| Total | 193 | 133 | 60 |

Source: IOP MA as of 30 Sep 2012

The MA monitored primarily the compliance with the requirement for absorption of at least 40 % of total eligible expenditure of IUDP by the end of 2012. Based on the ex-ante evaluation, the MA decided to issue in the course of October 2012 a Decision on postponing the deadline for the submission of applications for payment which will be included in the absorption of allocation in 2012 to 31 Dec 2012. The requirement to absorb the total eligible expenditure in 2012 was successfully met almost by all the IUDP towns. The IOP MA anticipates the meeting of this requirement in 39 of 41 towns. Only two towns – Most and Děčín – will fail to meet the required 40% absorption in 2012. In these towns the MA shall cut the funds allocated to IUDP. These funds will be reallocated to towns, whose IUDPs are successfully implemented and exhibit absorption capacity. The precise methodology governing the reallocation of funds by IOP MA will be specified by the end of 2012.

Information on IUDP allocation for Intervention area 5.2

| Name of the applicant | Approved assistance from IOP (from ERDF) | Submitted projects (ERDF) | Forecast absorption 2010 | Forecast absorption 2011 | Forecast absorption as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- |
|  | EUR | EUR | (%) | (%) | (%) |
| Bohumín | 2 581 191 | 1 740 704 | 13,44 | 41,02 | 54,43 |
| Brno | 5 258 220 | 3 023 386 | 7,41 | 23,45 | 40,04 |
| Břeclav | 2 090 289 | 402 615 | 10,32 | 31,34 | 67,04 |
| České Budějovice | 6 849 922 | 2 492 253 | 15,45 | 59,38 | 57,57 |
| Český Těšín | 4 078 349 | 2 723 352 | 5,04 | 40,93 | 69,38 |
| Děčín | 4 235 187 | 134 397 | 4,49 | 15,29 | 15,25 |
| Frýdek-Místek | 5 237 029 | 1 362 823 | 3,60 | 27,54 | 44,27 |
| Havířov | 6 835 603 | 4 006 079 | 0,00 | 35,68 | 46,33 |
| Hodonín | 3 099 232 | 1 557 486 | 13,31 | 45,99 | 60,39 |
| Hradec Králové | 6 633 156 | 1 835 666 | 2,95 | 21,11 | 42,54 |
| Cheb | 3 729 669 | 1 416 619 | 21,24 | 17,96 | 65,48 |
| Chomutov | 6 489 612 | 1 921 628 | 26,83 | 34,16 | 41,75 |
| Chrudim | 3 217 388 | 3 001 087 | 15,29 | 75,21 | 63,24 |
| Jablonec nad Nisou | 4 393 360 | 2 837 248 | 18,38 | 44,62 | 40,03 |
| Jirkov | 4 006 329 | 2 024 318 | 42,04 | 65,25 | 86,32 |
| Karlovy Vary | 3 243 289 | 866 475 | 7,26 | 34,56 | 54,82 |
| Karviná | 5 750 823 | 2 452 936 | 13,69 | 36,19 | 82,26 |
| Kladno | 6 213 506 | 6 261 153 | 17,45 | 54,93 | 83,55 |
| Kopřivnice | 3 799 948 | 2 445 472 | 12,35 | 27,52 | 52,33 |
| Kroměříž | 3 816 513 | 2 112 624 | 24,50 | 53,02 | 69,93 |
| Liberec | 6 020 554 | 556 575 | 0,59 | 21,83 | 47,39 |
| Litvínov | 3 336 657 | 2 097 381 | 16,24 | 25,89 | 48,20 |
| Mladá Boleslav | 3 836 636 | 3 972 392 | 11,97 | 77,99 | 79,20 |
| Most | 6 502 569 | 276 760 | 2,88 | 2,19 | 24,44 |
| Náchod | 4 233 175 | 1 493 799 | 12,09 | 35,23 | 59,12 |
| Nový Jičín | 3 666 244 | 2 065 528 | 27,88 | 45,33 | 69,58 |
| Olomouc | 7 179 511 | 3 742 517 | 35,38 | 27,06 | 31,91 |
| Opava | 6 440 187 | 3 050 034 | 1,54 | 37,35 | 69,18 |
| Orlová | 3 197 484 | 711 763 | 17,44 | 26,97 | 66,92 |
| Ostrava | 6 943 367 | 1 060 101 | 0,00 | 12,67 | 24,56 |
| Pardubice | 6 237 014 | 4 152 886 | 16,90 | 40,72 | 52,81 |
| Písek | 3 938 336 | 1 166 549 | 16,32 | 36,40 | 41,24 |
| Přerov | 3 479 083 | 861 790 | 6,87 | 33,78 | 46,51 |
| Příbram | 5 099 733 | 4 327 804 | 20,68 | 42,86 | 51,76 |
| Strakonice | 4 776 436 | 2 951 855 | 35,40 | 34,19 | 66,45 |
| Tábor | 4 161 657 | 1 963 895 | 11,37 | 78,66 | 70,21 |
| Třebíč | 3 902 239 | 1 770 263 | 24,52 | 28,80 | 51,39 |
| Uherské Hradiště | 3 553 928 | 1 823695 | 40,01 | 33,21 | 60,81 |
| Ústí nad Labem | 6 769 518 | 3 285 486 | 0,00 | 26,64 | 46,13 |
| Vsetín | 3 903 030 | 2 699 363 | 4,08 | 51,80 | 54,37 |
| Znojmo | 3 837 349 | 1 456 110 | 6,69 | 37,29 | 32,83 |
| Total | 192 573 322 | 26 094 467 | 15,12 | 36,49 | 53,73 |

Source: IS Monit7+ as of 30 Sep 2012

CZK/EUR exchange rate: 24.859

Status of implementation of projects under activity 5.2

In the monitored period the number of submitted applications in Intervention area 5.2 increased to the total of 919 projects as against 31 Mar 2012. The towns in their strategy of IUDP implementation focused at first on the support for regeneration of residential buildings. More demanding projects and projects of long-term nature implemented by towns in the field of revitalisation of public spaces were mostly left by IUDP towns until later. Since the projects on regeneration of residential buildings were already implemented in majority of towns, the towns launch the implementation of larger projects focused on the revitalisation of public spaces.

Status of implementation of pilot projects

Calls for the submission of projects are currently announced in all the six towns. As of 30 Sep 2012, a total of 55 submitted projects are registered under activity 5.2c). The investment projects supplement the projects on social inclusion financed mostly from OP HRE, Intervention areas 3.2 Support for social integration of members of Roma communities, 5.1 International cooperation (exchange of experience with social inclusion) and Intervention area 3.1b of IOP. Moreover, implemented within the pilot projects are also the projects from the Operational Programme Education for Competitiveness, which fall under Intervention area 1.2 Equal opportunities for children and pupils. The IOP MA in cooperation with OP HRE endeavours to ensure the maximum possible consistency in the administration of pilot projects and OP HRE projects.

An essential activity in support of pilot projects was the 10th meeting of the Working Group Pilot held on 4 Sep 2012 (for more information see Chapter 4.4.3). In the monitored period the IOP MA paid a monitoring visit to five of six towns with IUDP, implementing the pilot projects. In all the towns the implementation of pilot projects was considered successful. The monitoring visit to the last pilot town (Přerov) is scheduled before the end of 2012. The pilot projects as a support tool for socially excluded locations were presented also on the occasion of the IOP Annual Conference in Ostrava on 19 -20 September 2012.

### 3.5.3 Fulfilment of indicators

Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 410401 | Number of regenerated immovable cultural monuments | Number | 0 | 70 | 76 | 5 |
| 410402 | Number of newly built or modernised cultural facilities | Number | 0 | 5 | 4 | 0 |
| 330100 Core 39 | Number of projects improving the attractiveness of towns | Number | 0 | 1000 | 868 | 756 |
| 331000 | Number of established Urban Development Funds | Number | 0 | 1 | 0 | 0 |
| 330103 | Number of projects improving the attractiveness of housing in the territory | Number | 0 | 41 | 101 | 101 |
| 330101 | Number of projects improving the conditions of rental houses (residential buildings) | Number | 0 | 950 | 628 | 628 |
| 330102 | Number of pilot projects – support for selected Roma localities | Number | 0 | 7 | 6 | 6 |
| 330400 | Number of projects on creating planning analytical materials of regions | Number | 0 | 10 | 9 | 9 |
| 330401 | Number of assisted projects on creating planning analytical materials of municipalities | Number | 0 | 140 | 170 | 170 |
| 330411 | Number of assisted projects on creating new or updating the existing territorial plans | Number | 0 | 60 | 330 | 330 |
| 330415 | Area of municipalities covered by the planning analytical materials of municipalities | km2 | 0 | 34 800 | 63 398 | 63 398 |
| 330416 | Area of municipalities covered by the new territorial plan | km2 | 0 | 140 | 8361 | 8361 |

Source: MSC2007 as of 30 Sep 2012

Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 410404 | Number of created methodologies in the cultural heritage area | Number | 0 | 20 | 13 | 0 |
| 410411 | Increase in the number of visitors to monuments and cultural facilities | % | 100 | 125 | 189 | 100 |
| 331200 | Number of renovated apartments | Number | 0 | 24 500 | 38 055 | 32 218 |
| 331300 | Area of revitalised territory | m2 | 0 | 4 108 000 | 2 347 140 | 1 517 353 |
| 331500 | Energy savings in rental houses (residential buildings) | % | 0 | 20 | 31,83 | 32,76 |
| 330418 | Increase in the area of development areas, development axes and specific areas covered by new territorial plans | % | 0 | 0,18 | N/A | 20,05 |
| 330417 | Increase in the area of the CR which will be covered by planning analytical materials of municipalities | % | 0 | 18,5 | 80,3 | 80,3 |

Source: MSC2007 as of 30 Sep 2012

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

In Intervention area 5.1 four indicators are monitored – two output and two result indicators. In the period from 1 Apr 2012 to 30 Sep 2012, two new Decisions on providing a grant were issued, which represents an increase in the commitment by 6.5 %. The commitment of approved projects increased in indicator No 410401 – Number of regenerated immovable cultural monuments by two monuments, which represents an increase by 2.7 %.

In the monitored period the achieved value of indicator No 410401 – Number of regenerated immovable cultural monuments rose by one monument. The Vila Tugendhat project, whose beneficiary is the Statutory Town of Brno, was completed on 31 May 2012. Cumulatively, as of 30 Sep 2012, the regeneration of 5 immovable cultural monuments was implemented, which represents 6.6 % of the total value of indicator.

The values achieved in indicator No 410411 – Increase in the number of visitors to monuments and cultural facilities equal the baseline value. It is caused by the fact that the fulfilment of this indicator is reported one year after the completion of project implementation.

In indicators 410402 – Number of newly built or modernised cultural facilities and 410404 – Number of created methodologies in the cultural heritage area no changes occurred in the monitored period, the achieved value is zero. It is due to the fact that no project under activities 5.1a and 5.1c was completed.

Comparison of physical and financial progress

Source: IS Monit7+as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

The fulfilment of MI in Intervention area 5.2 corresponds with the progress achieved in the implementation of this intervention area. Of the total allocation amounting to CZK 5.340 billion, CZK 2.258 billion was earmarked for the area of residential buildings. As at the end of the monitored period the Decision on providing a grant was issued in IA 5.2 b) in the amount of CZK 1.299 billion, i.e. 66% of the total allocation. The reason why the value of MI 331200 in IA 5.2 b) from committed projects exceeds 100 % of the target MI value for this activity is the prevailing trend of towns with IUDP to implement more projects in the area of regeneration of residential buildings than originally planned. Moreover, in some projects duplicate reporting of the number of regenerated buildings happened due to the implementation of more projects in a single residential building. The IOP MA will correct these duplicate values during the completion and evaluation of IUDP implementation.

The fulfilment of the MI 331300 Area of revitalised territory was also affected by the fact that due to the financial crisis the towns in later years of IUDP implementation did not avail of sufficient volume of funds to co-finance the projects with high financial requirements. The IOP MA intends to adopt a measure at the beginning of 2013 promoting the implementation of projects on the revitalisation of public spaces. It plans to reallocate the IUDP allocation to towns with absorption capacity for Intervention area 5.2a). The IOP MA will obtain these funds by gradual releasing of the exchange rate reserve and also from the allocation of those towns which do not meet the requirement of absorption and where the IOP MA will cut the ERDF funds allocated to the implementation of IUDP. The additional funds over and above the allocation will be granted to towns which prove the absorption capacity for projects on the revitalisation of public spaces and also do not report any problems with the absorption of the existing allocation.

The MI No 330103 Number of projects improving the attractiveness of housing in the territory is exceeded since when drawing up the Programme Document the IOP MA assumed that individual projects on the revitalisation of public spaces will be implemented in the framework of a single project at the level of the whole IUDP. Nonetheless, the towns implement individual projects separately, thanks to which the number of projects is higher than the target value of the indicator. The number of the umbrella projects at the level of IUDP equals the target value of the indicator.

The MI No 331000 is related to the implementation of JESSICA FI. The IOP MA foresees the fulfilment of the target value of indicator – creation of a single Urban Development Fund (UDF) in the 2nd quarter of 2013.

Comparison of physical and financial progress

Source: IS Monit7+ as of 30 Sep 2012

The notes explaining the chart Comparison of physical and financial progress are included at the beginning of Chapter 3 Progress at the level of priority axis.

In case of indicators in Intervention area 5.3 in activity a) the commitment of approved projects equals the target value. The target value of indicator No 330400, related to projects of regions, has almost been achieved. The anticipated target value of the number of projects on creating planning analytical materials of regions has been covered by the submitted project applications, one project was rejected during the administration. In case of projects on creating planning analytical materials of municipalities with extended powers, the target values of indicators (No 330401 and 330415) were exceeded. Since there was a total of 204 eligible applicants, the IOP MA expected to grant the support to 140 applicants, whereas in reality 170 applications submitted by municipalities were supported. The setting of the target value of the indicator 330415 was based on the anticipated value of indicator No 330401. The area was calculated as the area of 140 smallest municipalities with extended powers.

All the achieved values of indicators for activity b) as at 30 Sep 2012 exceeded the target values. When setting the indicator No 330411, the calculations were made based on the price of territorial plans that was several times higher, i.e. the price valid at the time of preparation of the Programming Document. The calculations considered the maximum price of CZK 4 million per 1 territorial plan and expert opinions, but the average application for support claims CZK 800 thousand only. When the target value of indicator No 330416 was set out, the calculations were made based on the anticipated value of indicator No 330411. The area was calculated as the area of 60 smallest municipalities with more than 500 inhabitants, which complied with the conditions of the prepared calls for 5.3b).

In indicator No 330418, it is not the commitment of approved projects which is reported, but the achieved value as of 30 Sep 2012. The value of indicator is ascertained by the semi-budgetary organisation of MRD, the Institute for the Territorial Development. The achieved value of the indicator many times exceeds the target value due to the reasons stated in indicators No 330411 and 330416, on which it is based.

### 3.5.4  Problems and measures taken

Intervention area 5.1

Low absorption of funds and extension of project implementation caused by conditions of the call, according to which the beneficiaries were obliged to produce a building permit for major part of the project no later than 1 year following the approval of the Decision on providing a grant. In projects qualified as high-risk projects the building works contractor has not been selected as yet. As soon as the contract for work done is signed, the absorption of funds will considerably grow.

Measures taken

The MoC IB carried out a screening of the status of implementation of all the projects under Intervention area 5.1. In projects that exhibit low absorption of funds and delays in implementation the MoC IB decided to conduct more intensive and continuous supervision over the fulfilment of the timetable of project implementation with the view to minimise the delay between individual steps (to ensure smooth continuity – signing the contract, handing over of the building site, commencement of implementation, etc.). These measures are implemented continuously and regularly through monitoring reports, controls of public procurement procedures/tenders, notification of a change in the project, etc. Discussions with beneficiaries on the progress achieved in project implementation are held on a continuous basis.

The projects, in which 12 months following the issuance of the legal act no funds or funds lower than 5 % of the budget are absorbed, are put on the list of “sleeping” or “high-risk” projects. Falling under this category are also the projects, in which upon request the implementation was extended by more than 1 year. This situation is addressed by monthly reporting of the beneficiary to the MoC and subsequently by the MoC to the IOP MA, by the adoption of a crisis timetable of project implementation and absorption of funds approved by beneficiaries, trilateral meetings between beneficiaries, MoC and IOP MA.

In the update of Handbooks for Applicants and Beneficiaries of 20 Aug 2012, the obligation to merge the quarterly stages was removed in case the amount of eligible expenditure fails to reach the ceiling of CZK 10 million. The notifications of a change, through which the beneficiary applies for the extension of project implementation by more than 3 months, will be subject to approval by IOP MA.

By letter (Ref No 30235/2012-26) of 27 Aug 2012 the IOP MA requested the MoC IB to cut the salaries of project team members in projects which repeatedly apply for the extension of implementation and do not meet the timetable of activities.

Several times already the MoC IB brought to the attention of beneficiaries the possibility of cutting the eligible expenditure on the project implementation team provided the outputs achieved by this team are not optimal. Since in some beneficiaries the unsatisfactory situation in project administration still prevails, the MoC IB shall impose the referred to sanction, namely upon the next submission of expenditure on salaries of staff employed by aid beneficiary, or upon the submission of invoices by service supplier.

State aid – Intervention area 5.1 faces the risk of provision of unauthorised state aid.

Measures taken

The Handbooks for Applicants and Beneficiaries require that the applicant elaborates on all the four features of state aid, or states the procedure or measure to eliminate the risk of unauthorised state aid. The risk of unauthorised state aid is subject to all the risk analyses. The compliance with state aid rules is verified during the project eligibility assessment. The MoC IB always requests an opinion of an external expert.

The Ministry of Culture commissioned the PBA Group company to elaborate a study on assessing the state aid in all the projects. At the time being, one-to-one consultations between individual aid beneficiaries and PBA company are under way. The goal is to modify the project so as to minimise the risk of unauthorised state aid.

Award of public contracts – demanding public procurement procedures or tenders, delays in implementation of public procurement procedures/tenders, appeals of unsuccessful applicants to the OPC, major difference in bids (up to 60 %).

Measures taken

Throughout the process of public procurement procedure/tender, the MoC IB and, where necessary, also an external expert, conduct controls conducive to the minimisation of the above mentioned risks. The MoC IB offers consultations to beneficiaries, holds training courses and seminars, intensively communicates with beneficiaries, as an observer participates in meetings of the Selection Committee.

Intervention area 5.2

In the monitored period the IOP MA identified problems in some municipalities with IUDP to meet the absorption up to the required 40 % of the total allocation. It concerns especially the municipalities of Most and Děčín.

Measures taken

The IOP MA responded to this threat via consultations with the respective municipalities. Even though they sought to meet the requirement of absorption of financial allocations in individual years, there is a risk of failure to meet this requirement by Most and Děčín in 2012. In such a case the IOP MA would again cut the ERDF financial allocation and consider the reallocation of funds to IUDP municipalities which successfully absorb the allocation and still avail of absorption capacity.

Based on the valid regional map of state aid for 2007 – 2013 period, the Decision on providing a grant can be issued for the area of regeneration of residential buildings only until the end of 2013.

Measures taken

Although the majority of municipalities (towns) has already implemented most of the projects on regeneration of residential buildings, the IOP MA informs about this situation all the municipalities involved in IUDP implementation in order to eliminate the risk of failure to implement all the planned projects for the area of regeneration of residential buildings in individual towns with IUDP. Potential failure to implement all the projects on regeneration of residential buildings will not have any effect on the fulfilment of MI at the level of intervention area, since it has already been fulfilled. An opposite situation is seen in the MI Revitalisation of public spaces. The original value of MI in m² now seems overrated. The same is true at the level of fulfilment of MI of IUDP towns. The towns often set the MI value of the revitalisation for the whole IUDP zone. One of the measures taken by IOP MA to address this situation is the support of projects on revitalisation of public spaces with the reallocation of funds obtained by IOP MA by cutting the ERDF allocation to towns which fail to meet the obligation to absorb the total eligible expenditure in individual years of IUDP implementation. The IOP MA reckons that primarily supported will be new projects in the area of revitalisation of public spaces.

Intervention area 5.3

In this intervention area no serious problems occurred, no calls were announced and no new projects were received in the monitored period. The approved projects account for 92 % of the total allocation to this intervention area and the aggregate payment claims accounted for by the PCA cover 89 % of the total allocation. The implementation of projects from the last announced call No 08 was completed as of 30 Jun 2012 and the funds are smoothly paid to beneficiaries. Once the exchange rate reserve is calculated, the MA intends to announce a call in November 2012 for the rest of the allocation in the amount of roughly CZK 30 million (EUR 1.2 mil.).

### 3.5.5 Example of a project

Intervention area: 5.1 – National support for utilising the cultural heritage potential

Name of the project, registration number: National Centre of Garden Culture in Kroměříž, CZ.1.06/5.1.00/01.06138

Beneficiary: National Heritage Institute, local office in Kroměříž

Project funding: Total budget CZK 336 467 204, of which CZK 285 997 123.40 the Structural Funds contribution, CZK 50 470 080.60 the state budget contribution

The Flower Garden (Květná zahrada), the main part of which was built between 1665 and 1675, represents a turning point in the development of the European garden art. On the one hand it still evokes the late renaissance Italian and Transalpine gardens, while on the other hand it opens the way to French baroque-classicism type of gardens. The uniqueness of the garden consists in it being today practically the only example of similarly constructed complex in Europe.

By implementation of the National Centre of Garden Culture in Kroměříž project, a centre unique in the Central European space will be created, which will on the one hand address and also guarantee highly professional methodological aspects of the restoration of historical gardens and parks and on the other hand it will present and communicate these findings to the broadest possible audience and thus increase the awareness and knowledge of this topic. The main aim remains to be the development of methodologies for restoration and subsequent care of historical gardens and parks in the CR and their presentation to all those interested.

Project outputs:

- A display on Kroměříž chateau gardens, short-term exhibitions devoted to garden culture,

- A methodology centre which shall create professional methodologies for restoration and care of historical gardens and parks,

- A centre of lifelong learning which shall ensure and enhance the awareness of garden culture among the experts as well as the general public,

- A professional library and research facilities which provide access to unique archival documents in the field of historical garden culture,

- Restored parts of the Flower and Chateau gardens.

Before the project implementation		        After the project implementation

Intervention area: 5.2 Improving the environment in problematic housing estates

Name of the project, registration number:   Reconstruction of block 2 in Chanov  CZ.1.06/5.2.00/07.07708

Beneficiary: Statutory Town of Most

Project funding: Total budget CZK 6 341 303,-, of which CZK 2 156 043,- the SF contribution and CZK 380 478,-  the SB contribution

The project focuses on overall regeneration of a residential building in a socially excluded housing estate of Chanov. The building was fitted with a thermal protection of the building envelope and the ceiling above the ground floor, new windows and doors, thermal protection of roof cladding, modernisation of common spaces, reconstruction and adding of new wiring and piping in rising pipes and in cellars, reconstruction of balcony and main entries handrails.  Newly, also the outer steps as well as all tinsmithing and balconies will be reconstructed.

Intervention area: 5.3 – Modernisation and development of systems for creating territorial policies

Name of the project, registration number: Elaboration of a territorial plan for the municipality of Čeladná, CZ.1.06/5.3.00/08.07466

Beneficiary: Municipality of Čeladná

Project funding: Total budget CZK1 956 000,-, of which CZK 1 662 600,- the Structural Funds contribution, CZK 293 400,-  state budget contribution

The new territorial plan shall respond to the requirements of natural and legal persons and various stakeholders, neighbouring municipalities. It shall be linked to the previous land related activities and requirements of the owners of plots in the territory of the municipality, it shall address in a comprehensive manner the functional use of the territory, coordinate the new development, and it shall respect the superior territorial planning documentation and various restrictions.

The project involves an elaboration of the assessment of the territorial plan effects on sustainable development of the territory, the strategic environmental assessment, including an evaluation of implications on NATURA 2000 system, and an elaboration of a draft territorial plan.

The project expenditure has already been certified.

An indicative section of the main drawing  – urban design

## 3.6 Priority axis 6a, 6b – Technical assistance

### 3.6.1 Focus of priority axes/intervention areas

### 3.6.1 Focus of priority axes/intervention areas

The priority axes comprise activities which are inseparable as to their geographical scope and which have an impact on the whole territory of the CR. Their content is therefore identical, regardless their classification by objective. Priority axes 6a and 6b focus on the support of effective management of the Integrated Operational Programme throughout the programming period 2007 – 2013.

The Priority axis covers the Convergence objective (6a) and the Regional Competitiveness and Employment objective (6b).

Specific goals:

- Reinforcing administrative capacities involved in programme implementation at the level of the Managing Authority and Intermediate Bodies,

- Ensuring effective management, monitoring, evaluation, controls and absorption capacity in implementing the operational programme at the level of the Managing Authority and Intermediate Bodies.

Beneficiaries:

- Managing Authority,

- Intermediate Bodies.

### 3.6.2 Progress achieved in implementation of priority axes/intervention areas

In Intervention areas 6.1a and 6.1b as of 30 Sep 2012 a total of 36 project applications in the amount of EUR 42.42 million were received (130.1 % of the allocation), of which 5 applications in the volume of EUR 1.37 million were submitted in the period from April to September 2012. The volume of approved projects rose by EUR 1.04 million, three projects were approved. In total, 33 projects in the amount of EUR 30.86 million (94.8 %) were approved. The beneficiaries were paid a total of EUR 13.63 million, representing 41.9 % of the allocation. The amount of EUR 13.24 million (40.8 % of the allocation) was accounted for by the PCA in aggregate payment claims. Since the applications for payment with a suspected irregularity under investigation were excluded from certification, the amount of certified expenditure dropped from EUR 11.23 million to EUR 11.04 million.

Cumulative progress at the level of Intervention area 6.1a and 6.1b (in mil. CZK/EUR)

| 6.1a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 796,08 | 31,97 | 36 | 1 035,39 | 130,1% | 41,65 | 33 | 754,54 | 94,8% | 30,30 | 333,91 | 41,9% | 13,38 | 324,54 | 40,8% | 13,00 | 270,08 | 33,9% | 10,84 |
| Previous MC | 793,88 | 31,97 | 31 | 998,79 | 125,8% | 40,31 | 30 | 725,51 | 91,4% | 29,28 | 308,61 | 38,9% | 12,45 | 292,28 | 36,8% | 11,71 | 274,96 | 34,6% | 11,03 |
| 6.1b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract22 | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC23 |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 14,63 | 0,59 | 0 | 19,04 | 130,1% | 0,77 | 0 | 13,87 | 94,8% | 0,56 | 6,14 | 42,0% | 0,25 | 5,97 | 40,8% | 0,24 | 4,97 | 33,9% | 0,20 |
| Previous MC | 14,59 | 0,59 | 0 | 18,36 | 125,8% | 0,74 | 0 | 13,34 | 91,4% | 0,54 | 5,68 | 38,9% | 0,23 | 5,38 | 36,8% | 0,22 | 5,06 | 34,7% | 0,20 |

In Intervention area 6.2a and 6.2b 8 project applications were submitted in the monitored period, thus the volume increased by EUR 0.52 million to the total volume of EUR 15.69 million, which represents 73.3 % of the allocation. Altogether 8 projects were approved and the volume of projects with issued Decision on providing a grant rose from EUR 8.26 million to EUR 8.55 million, representing 40.1 % of the allocation. Beneficiaries were paid EUR 3.16 million (14.9 % of the allocation) and all these funds were included in the aggregate payment claims accounted for by the PCA. Since no certification of expenditure took place in the monitored period, the volume of certified expenditure remained at the same level of 12.9 % of the allocation, i.e. EUR 2.75 million.

Cumulative progress at the level of Intervention area 6.2a a 6.2b (in mil. CZK/EUR) 5

| 6.2a | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
| --- | --- | --- | --- | --- | --- | --- |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 522,89 | 21,01 | 59 | 383,15 | 73,3% | 15,41 | 54 | 209,45 | 40,1% | 8,40 | 77,67 | 14,9% | 3,10 | 77,67 | 14,9% | 3,10 | 67,69 | 12,9% | 2,70 |
| Previous MC | 521,37 | 21,01 | 51 | 369,31 | 70,8% | 14,90 | 46 | 200,98 | 38,5% | 8,11 | 72,65 | 13,9% | 2,93 | 68,55 | 13,1% | 2,74 | 67,69 | 13,0% | 2,70 |
| 6.2b | 2007-2013 allocation | Submitted applications | Projects with issued Decision/signed Contract24 | Funds paid to beneficiaries | Funds included in aggregate payment claims accounted for by the PCA | Certified expenditure submitted to the EC |
|  | CZK (a) | EUR | Num-ber | CZK (b) | % (b/a) | EUR | Num-ber | CZK (c) | % (c/a) | EUR | CZK (d) | % (d/a) | EUR | CZK (e) | % (e/a) | EUR | CZK (f) | % (f/a) | EUR |
| Current MC | 9,61 | 0,39 | 0 | 7,04 | 73,3% | 0,28 | 0 | 3,85 | 40,1% | 0,15 | 1,43 | 14,9% | 0,06 | 1,43 | 14,9% | 0,06 | 1,25 | 13,0% | 0,05 |
| Previous MC | 9,59 | 0,39 | 0 | 6,79 | 70,8% | 0,27 | 0 | 3,69 | 38,5% | 0,15 | 1,34 | 13,9% | 0,05 | 1,26 | 13,2% | 0,05 | 1,25 | 13,0% | 0,05 |

The following is applicable to all the tables above:

Source: Current MC – MSC2007 as of 3 Oct 2012

Previous MC – MSC2007+ as of 4 Apr 2012

CZK/EUR exchange rate: Current MC – 24.859

Previous MC (“a” column) – 24.778

Source of funding – public funds total

Overview of on-going calls

In priority axes 6a and 6b two calls were under way in the monitored period.  A total of 71 project applications in the amount of EUR 48.57 million were submitted. A total of 67 projects in the volume of EUR 46.08 million were approved.

In Intervention areas 6.1a and 6.1b one continuous call has been under way since 5 Jun 2008.  A total of 36 project applications in the amount of EUR 42.88 million were submitted, of which 34 projects in the amount of EUR 41.23 million were approved.

In Intervention areas 6.2a and 6.2b one continuous call was under way which was announced in September 2010. A total of 35 project applications in the volume of EUR 5.69 million were submitted, of which 33 projects in the amount of EUR 4.84 million were approved.

Overview of on-going calls in the period from 1 Apr to 30 Sep 2012

| Order of the call | Num-ber of the call | Submission of project applications | Type of the call | IA/acti-vity | Allocation for the call | Submitted applications for support | Projects with issued Decision/ signed Contract |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | Opening date of the call | Closing date of the call |  |  | in EUR | Num-ber | in EUR | Num-ber | in EUR |
| 2. | 01 | 5.6.2008 | 30.9.2015 | continuous | 6.1 a-e | 32 586 086 | 36 | 42 107 793 | 34 | 40 486 340 |
|  |  |  |  |  |  | 599 155 |  | 774 229 |  | 744 416 |
|  |  |  |  | Call total | 33 185 241 | 36 | 42 882 022 | 34 | 41 230 755 |
| 36. | 10 | 27.9.2010 |  | continuous | 6.2 a-g | 12 778 984 | 35 | 5 585 935 | 33 | 4 757 022 |
|  |  |  |  |  |  | 234 965 |  | 102 708 |  | 87 467 |
|  |  |  |  | Call total | 13 013 949 | 35 | 5 688 643 | 33 | 4 844 489 |
| IA 6.1 total | 33 185 241 | 36 | 42 882 022 | 34 | 41 230 755 |
| IA 6.2 total | 13 013 949 | 35 | 5 688 643 | 33 | 4 844 489 |
| CONV total | 45 365 070 | 71 | 47 693 728 | 67 | 45 243 361 |
| RCE total | 834 120 | 0 | 876 937 | 0 | 831 882 |
| PA 6 total | 46 199 190 | 71 | 48 570 664 | 67 | 46 075 244 |

Source: IS Monit7+ as of 2 Oct 2012

CZK/EUR exchange rate: 24,859

Source of funding – public funds total

### 3.6.3 Fulfilment of indicators

The achieved value as of 30 Sep 2012 and the commitments of approved projects in Intervention areas 6.1 and 6.2 correspond with the rate of absorbed funds of IOP TA projects.  They cannot be compared with the target values since the target values were set based on the original methodology of IOP TA indicators and the commitments of approved projects in IOP TA were set (and changed in the already implemented projects) in line with the revised methodological sheets of IOP TA indicators of 2009.

- Output indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 480500 | Number of elaborated studies and reports (incl. evaluation ones) | Number | 0 | 14 | 1390 | 934 |
| 480700 | Number of developed methodological and technical and information materials | Number | 0 | 84 | 257 | 121 |
| 481100 | Number of held training courses, seminars, workshops, conferences | Number | 0 | 70 | 310 | 165 |
| 481600 | Number of persons who attended the educational courses - total | Number | 0 | 1400 | 9976 | 5835 |
| 480800 | Implemented cooperation with mass media and communication with the general public | Number | 0 | 30 | 99 | 81 |
| 480900 | Number of organised information and publicity activities | Number | 0 | 32 | 180 | 79 |
| 483100 | Number of full-time employees of the implementation structure | Number | 0 | 90 | 432,87 | 329,14 |

Source: MSC2007 as of 30 Sep 2012

Result indicators

| Code | Name of the indicator | Unit of measure | Baseline value (2005) | Target value | Commitment of approved projects | Value achieved as of 30 Sep 2012 |
| --- | --- | --- | --- | --- | --- | --- |
| 481900 | Number of trained persons – total | Number | 0 | 1 100 | 3796 | 2123 |
| 480300 | Number of meetings of (monitoring, advisory and management) committees | Number | 0 | 14 | 15 | 10 |
| 482500 | Number of performed controls | Number | 0 | 1 350 | 8144 | 7420 |

Source: MSC2007as of 30 Sep 2012

### 3.6.4 Problems and measures taken

Risk of ineligible activities and expenditure. The IOP Managing Authority continued to monitor the use of Technical assistance funds in order to safeguard the maximum level of eligible expenditure in terms of economy, effectiveness and efficiency.

Measures taken

The IOP MA in the previous period already decided on stricter steps to be taken prior to the submission of project applications to the Selection Committee for IOP TA projects (IOP TA SC) and when applying for the approval of new activities in IOP TA projects. The submitted project applications consistently did not meet the rules for edibility of expenditure. They were subject to several rounds of comments before the IOP MA agreed that they could be submitted to the IOP TA SC for approval. In the monitored period, the IOP TA SC meeting was held on 24 May 2012, 10 project applications were approved (1 project application of MRD CR, 3 project applications of CRD CR and 6 project applications of MoI CR).

Problems still arise with respect to the submitted project applications. The IOP MA intensified consultations with responsible staff of IOP IBs.

As of 1 Aug 2012 the IOP MA revised the Handbook for Applicants and Beneficiaries for Priority axes 6A and 6B Technical assistance, which in its part called “Eligible expenditure” specified and extended the list of eligible expenditure in response to:

- Revision of methodological guideline for eligible expenditure for programmes co-financed from the Structural Funds and the Cohesion Fund for 2007-2013 programming period;

- Resolution of the Government of the CR of 2 May 2012 No 313, by which the methodology governing the selection of employees implementing the EU funds in 2007-2013 programming period and in 2014+ programming period;

- Issuance of the methodological guideline for the use of external services within the implementation structure of the National Strategic Reference Framework;

- Issuance of the Methodological Guideline No 30 – Procedure for the payment of bonuses for absorption of allocation.

Based on the task C/17 assigned by the 9th meeting of the IOP Monitoring Committee – Risky Operational Programmes and in line with the Resolution of the Government of the CR No 1332 of 26 October 2009 on the Methodology of financial remuneration of employees implementing the National Strategic Reference Framework in 2007-2013 programming period, the IOP MA drew up a proposal for cutting the incentive bonuses of IOP IB staff in dependence on the fulfilment of the forecast absorption of allocations.

The IOP MA shall discuss the proposal with IBs and issue it as its binding opinion.

Problems with administration of IOP TA projects. In the monitored period, the most pressing issue in the administration of IOP TA projects was a large quantity of public contracts common for more projects, evidencing the expenditure, mostly labour costs, matching the expenditure with the adequate contract, or project.

Measure taken

Consultations at a CRD CR branch and with IOP MA staff.

# 4 ADMINISTRATION OF THE PROGRAMME

## 4.1 Information on the Conduct and Results of Audits and Financial Controls

Audit of the European Commission

Audit of the European Commission carried out at the Audit Authority

In the Report on Implementation of IOP for the period from 1 Oct 2011 to 31 Mar 2012, the IOP MA informed about the preliminary findings of audit No 2011/CZ/REGIO/J4/870/8, carried out by the Directorate General for Regional Policy of the European Commission at the Audit Authority. Considered by the auditors to be the main preliminary findings concerning the IOP MA are the system of reporting and addressing irregularities and the set out system of waiver of penalties for the breach of budgetary discipline. They also point at the fact that in 7 of 8 projects selected in the sample by the audit mission a finding with an impact on eligibility of expenditure was identified by the Delegated Audit Body.

The Audit Authority raised objections to the draft report and the IOP MA submitted its opinion on findings identified in individual projects. The IOP MA also stresses that even though during the audit the IOP MA was neither an auditee, nor was it explicitly referred to under the subject of the audit, the findings and subsequent recommendations and conclusions concern the IOP MA. The IOP MA also disagrees with the audit conclusions. In projects concerned, the MA shall apply financial corrections based on the findings given in the report. The findings listed in the report, however, are only very general and insufficiently justified.

The final report of the conducted audit was not available as of 30 Sep 2012.

Audits conducted by the Paying and Certifying Authority

In the monitored period there were no audits of IOP conducted by the PCA.

Audits conducted by the Supreme Audit Office

SAO audit at the Ministry of Health

In December 2011, the SAO audit No 11/34 was launched at the Ministry of Health of the CR. The audit focused on spending funds to cover the costs of activities performed by the Ministry and it also concentrated on the selected projects implemented by the MoH under the IOP Technical assistance. The audit revealed that the Ministry had failed to comply with provisions of Section  82 para 2 of Act No 137/2006 Coll. by concluding a contract on service provision with the KPMG Česká republika Audit, s.r.o. company, which was awarded an above-the-threshold public contract called “Audit of the implementation of projects from the 1st call for IA 3.2 of IOP“ 42 days following the statutory deadline. According to the SAO, the Ministry violated the provisions of Section 83 para 1 of Act No 137/2006 Coll. by sending the notification of the result of the public procurement procedure 25 days after the statutory deadline. The IOP MA considers this to be a violation of a formal nature with no effect on the selection of the most suitable bid or a group of candidates.

SAO audit at the Ministry for Regional Development of the CR and the Ministry of Culture of the CR

On 31 Jan 2012, the audit No 12/02 of the Supreme Audit Authority was commenced at the Ministry for Regional Development of the CR focusing on the verification of the absorption of the European Union and state budget funds earmarked for the implementation of the Integrated Operational Programme under Intervention area 5.1. On 7 Mar 2011, the audit was also commenced at the Ministry of Culture of the CR. On 10 Aug 2012, the MRD CR received a protocol from the audit, to which it raised objections by the due date. The objections were settled by the SAO by Decision on objections of 3 Sep 2012. The MoC CR received the audit protocol on 8 Aug 2012 and following the submission of its objections by the due date it received the Decision on objections on 27 Aug 2012. On 18 Sep 2012, the IOP MA lodged an appeal to the SAO Board against the Decision on objections with respect to the finding concerning the design of a specific eligibility criterion.

The main audit findings concern the design of the system of monitoring indicators in IA 5.1, the risk of unauthorised state aid in projects implemented under IA 5.1, and the design of the specific eligibility criterion in IA 5.1. The SAO auditors believe that the result and output monitoring indicators provide only minimum information necessary for the assessment of economy, effectiveness and efficiency of spent funds and that based on the indicators defined in such a way it is difficult to monitor the level of fulfilment of objectives under IA 5.1.

The IOP MA disagrees with the finding. Economy, efficiency and effectiveness under IA 5.1 of IOP are assessed also by other means than the monitoring indicators, the administrative procedures include processes which reinforce these principles. E.g. the 3E principles are taken into account in the criteria for project quality evaluation, the forecast expenditure is assessed during the eligibility and ex-ante checks, the expenditure incurred is assessed in terms of the fulfilment of 3E principles during the documentary check prior to the reimbursement of expenditure.

The audit also revealed that the IOP MA and MoC CR, as grant providers, had not notified the planned state aid or the change in the existing support for Intervention area 5.1. According to the SAO, the risk of unauthorised state aid under IA 5.1. cannot be ruled out. The IOP MA disagrees with the SAO finding. Since the beginning of preparation of Intervention area 5.1 the IOP MA and the MoC CR have been aware of the risks faced in this area with respect to the potential provision of unauthorised state aid. Nonetheless, it is a risk which does not necessarily have to occur and, as shown by studies related to individual projects, there are also projects with zero risk of unauthorised state aid. Being aware of this risk and the possibility of its elimination by project modifications, the IOP MA in cooperation with the MoC CR adopted numerous measures and procedures – also during the implementation of projects as such, not only during the first approval of projects for implementation – so that it is possible to avoid the unauthorised state aid. In the framework of preventive measures with the view to remove the risk of unauthorised state aid, the MoC CR had an expert opinion issued for each of the submitted applications describing the relation between the project and the state aid. In the first call, the evaluation opinion was submitted for project risk analysis, whereas in the subsequent calls the assessment of compliance with the state aid rules was a component part of the eligibility check. This criterion related to the state aid was also the reason for rejection of some projects during the eligibility check. In order to assess the potential risk of unauthorised state aid, in January 2012 the PBA company was addressed  and tasked to conduct an analysis of unauthorised state aid in all the projects under implementation and at the same time to assess the risk of unauthorised state aid in applications under the 3rd call. The beneficiaries ad well as applicants were repeatedly alerted to the imminent risk (especially during the discussions prior to the submission of their application) and they were recommended to consult the project applications first with a state aid expert.  Currently, one-to-one consultations between individual aid beneficiaries and the PBA company are held. The aim is to modify the projects with the view to minimise the risk of unauthorised state aid and to recommend potential modifications to project activities. Bearing in mind the above adopted measures, the IOP MA will not proceed to the notification in IA 5.1 of IOP at the current stage of programme implementation.

Other NSO findings concerned the design of a specific eligibility criterion for cultural monuments. According to the SAO, there was a discrepancy between the Binding interpretation of eligibility criteria issued by the Ministry of Culture and the IOP Programming Document stating that the support for Intervention area 5.1 of IOP can be provided for the regeneration of cultural monuments or sets inscribed on the UNESCO World Heritage List, on the List of candidates for inscription on this list, or on the Central List of Cultural Monuments as the national cultural monument (NCM). According to the Binding interpretation of eligibility criteria, however, the IOP funds can also be used for property located within the conservation area, conservation zone or the buffer zone of an intangible cultural monument in case they are necessary for the attainment of the project objective and are directly associated with activities described in the IOP Programming Document. The IOP MA disagrees with this SAO finding. The IOP MA believes the Binding interpretation merely specified in detail what was stated in the IOP Programming Document and did not extend it. The Binding interpretation allowed for the use of IOP funds also for the regeneration of monuments that are not a part of the NCM or UNESCO heritage, but provide necessary technological infrastructure or host the project activities necessary for the accomplishment of the project objectives.

Audit conducted by the Audit Authority

On 5 Sep 2012, an audit of the Audit Authority was launched at the IOP MA focused on the observance of methodological guidelines related to the selection of new employees implementing the EU Structural Funds since 2009. The final report of the conducted audit was not available as of 30 Sep 2012.

System audit conducted by the Delegated Audit Body

Audit of the system of implementation for the Integrated Operational Programme No 28/2011/DAB

In the Report on Implementation of IOP for the period from 1 Oct 2011 to 31 Mar 2012 the IOP MA informed  about the results of the system audit conducted by the Delegated Audit Body at the IOP MA and Intermediate Bodies launched in September 2011 and completed in January 2012. The Delegated Audit Body keeps the IOP MA posted about the adopted corrective measures ensuing from this system audit and about measures arising from the previous system audits.

Based on the auditors' finding concerning the insufficient separation of incompatible functions in the conduct of ex-ante checks in projects under Priority axis 6 – Technical assistance, the failure to assure the prevention of the conflict of interest, insufficient provision of ex-ante checks of IOP TA projects, the Operational Manual of the IOP Managing Authority was revised. The revision helped clearly define the responsibilities of the IOP MA Unit.

With respect to the findings concerning the effectiveness of the performance of tasks delegated by the IOP Managing Authority to the Intermediate Bodies of the Ministry of Labour and Social Affairs and the Centre for Regional Development of the CR, the Handbook of Work Procedures for Intervention areas 3.1 and 3.3 was revised with setting out the individual procedural steps in the administration of projects in these intervention areas. An obligation was imposed to regularly inform the IOP MA on meeting the deadlines in project administration. Some reports to the MoLSA are sent by the IOP MA to the EC representatives and the problem areas are discussed at meetings with Intermediate Bodies. The revised procedures in the Handbook of Work Procedures will be reflected by the CRD in the Methodological Guideline No 18 EU-IOP programmes for Intervention areas 3.1 and 3.3.

At the MoLSA Intermediate Body, a finding of medium materiality was detected concerning the extremely long time between the receipt of the application and the issuance of the Decision on providing a grant. The auditors recommended the MoLSA to analyse the reasons behind the delays with the stress put on ex-ante checks and to modify the duration of administration. The MoLSA undertook to analyse the reasons of delays in project administration.

The IOP MA responded to the recommendations and findings of DAB audit and as of 18 May 2012 in cooperation with MoLSA and CRD  elaborated an analysis of barriers to absorption in Intervention areas 3.1 and 3.3 of IOP, the aim of which is to propose measures to remove these barriers or to reduce their impacts. In the field of ex-ante checks it was found out that there was a high number of projects in IA 3.1 that were included in ex-ante checks based on ex-ante risk analysis, namely on the grounds of inappropriately set scale of risk analysis. It was also ascertained by the analysis that the MoLSA checks are very thorough and thus there is a risk of duplicity of checks within the remit of other state institutions. The MoLSA also requests that within ex-ante checks the beneficiaries supply information beyond the scope of obligations set by the call and HAB. Moreover, it was revealed that in the revision No 3 of the Handbook of Work Procedures of MoLSA there is no deadline set for the completion of ex-ante checks (the deadline for the conduct of ex-ante checks was set in the new revision of the Handbook of Work Procedures No 4). The analysis also reveals that the MoLSA fails to observe the procedures for entering data in IS Monit 7+ and exploits the possibility to extend the deadline for the duration of ex-ante checks. The analysis also detected that at the stage of ex-ante checks there is a high proportion of rejected/withdrawn projects in activity 3.1b). The withdrawal of applications is mainly caused by the quantification of ineligible expenditure in the course of ex-ante checks, in some cases it is revealed that the selected premises are unsuitable and the technical and financial limits could be met only at the expense of high ineligible expenditure. With respect to the findings arising from the analysis, the MoLSA was given specific recommendations explaining how to eliminate the negative findings. At the time being, the IOP MA conducts a check of delegated activities at MoLSA with the view to verify the administrative procedures, the deadlines for ex-ante risk analysis and ex-ante checks.

Audit on operations conducted by the Delegated Audit Body

Audit on IOP operations No 31/2012/DAB

As of 30 Sep 2012, the audit on operations No 31/2012/DAB was conducted in 57 projects in Intervention areas 1.1, 2.1, 3.2, 3.4, 4.1, 5.1, 5.2, 5.3 and 6.1. In total, the IOP MA received 55 final reports and 2 audits are currently at the stage of drafting the report. Of the total number of 57 audits, 23 audits, i.e. almost a half of them, were completed with no finding. Right now the contentious proceedings between the AA and IOP MA is under way concerning the final reports from audits on operations conducted by DAB completed following 30 Jun 2012, the purpose of which is to explain all the irregularities identified by the DAB audits on operations and potential confirmation/disproval of the irregularities concerned.

Main findings repeatedly identified in DAB audit No 31/2012

The most frequent findings identified by the conducted audit on operations No 31/2012, regardless the intervention area, were the following findings with an impact on eligibility:

- public procurement procedures,

- discriminatory design of qualification requirements.

In Intervention area 1.1 of IOP, the number one problem was the award of public contracts, namely the non-compliance of the award of public contracts with Section 6 of Act No 137/2006 Coll., on public contracts. The qualification and technical requirements were found discriminatory by the DAB, the definition of the subject matter of the design contest and the subject matter of the related public contract were discriminatory. In several audited projects improperly kept separate accounts were detected.

In Intervention area 2.1 of IOP, the DAB audit was conducted in 2 CzechPOINT type projects, one of which had an impact on eligibility of expenditure. The main problem was the breach of equal treatment principle in the award of a public contract for the supply of computer technology.

In Intervention area 3.2 of IOP, 13 projects were audited. The audit most frequently revealed low transparency of the award of small-scale public contracts (the requirement to include information on the ISO quality system was unspecific, lacking in transparency).

In several projects the DAB auditors identified the unauthorised use of a direct purchase within the public contract. They also detected insufficiently evidenced correspondence of activities reported in tender in terms of time and content with respect to project management and monitoring – as ascertained the declared activities, except for a few, are not accompanied by relevant outputs based on which they could be identified and proven and based on which the necessity for project implementation, its economy, effectiveness and efficiency could be verified. In several cases, the qualification and technical requirements were found discriminatory by DAB auditors. The DAB auditors in some cases identified deficiencies in the application of Section 98 of Act on public contracts – a discriminatory approach in the award of a public contract for the supply of medical devices, when the contracting authority awarded the public contract as a whole and thus according to the DAB auditors discriminated those suppliers who could supply individual parts only.

In Intervention area 3.4 of IOP, only 1 project was audited with no impact on eligibility of expenditure.

In Intervention area 4.1 of IOP, a total of 2 projects were audited. The main problem encountered was the non-compliance of the requirement for proving the qualification and the process of assessment of contracts with Act No 137/2006 Coll., on public contracts, according to the auditors the subject matter of the public contract was not defined in line with Section 45 of APC, the evaluation criteria were defined in a non-transparent and biased way; the way of assessing the bids was also non-transparent. Moreover, the DAB audit states a malpractice in the award of a small-scale public contract for making a commercial spot.

In Intervention area 5.1 of IOP, the DAB audit was conducted in 6 projects, of which 2 had an impact on eligibility of expenditure. The main problem was the non-compliance with the procedure laid down in the provisions of Section 44 of APC (the tender documentation did not contain the method of assessing the bids against the evaluation criteria) and in the provisions of Section 78 of APC (the contracting authority violated the criteria given in the tender documentation).

In Intervention area 5.2 of IOP, the largest number of projects was audited and the DAB auditors identified particularly deficiencies in the area of determination and evidencing the basic qualification requirements, they underline the fact that these requirements were in conflict with the HAB. Another problem is incorrect accounting for of the short-term contingent claims in relation to EU funds.

In Intervention area 5.3 of IOP, 1 project was audited with an impact on eligibility of expenditure. The problem was the non-compliance of the keeping of accounts with Decree No 410/2009 Coll., implementing some provisions of Act No 563/1991 Coll., on accounting, and the non-compliance of the procedures in the implementation of a small-scale public contract with the rules of the call (Handbook for Applicants). The IOP MA disapproves with the “high” level of materiality of the finding and with the financial correction.

In Intervention area 6.1 of IOP, the main problem identified was insufficient proof of eligibility of expenditure in the field of personal costs, namely the breach of the obligation arising from the provisions of Section 25 para 2 (c) of Act on financial control (AFC) (statement of all the operations and controls), provisions of Section 25 para 2 (e) of AFC (economic, efficient and effective use of public funds in keeping with the principles of reliable management), Section 13 para 1 of AFC and the Decree No 416/2004 Coll., Section 8 para 1 of Act on accounting (the accounting units are obliged to keep correct, complete, conclusive, comprehensible, clear accounts in a manner safeguarding the permanent nature of accounting records).

The IOP MA disagrees with some findings of the DAB audit, the confirmation of which will be subject to the contentious proceedings.

Checks conducted by the Managing Authority

Checks of delegated activities

In the monitored period, checks of delegated activities were under way, commenced in the previous period, with focus on the verification of compliance of activities performed by the IBs with procedures set out in the IOP Operational Manual, IB manuals and Handbooks for Applicants and Beneficiaries, namely during the control of eligibility, control of formal requisites, evaluation of projects, ex-ante risk analysis and ex-ante control of projects and administration of applications for payment. The IOP MA verifies also the observance of procedures for entering data in IS Monit7+.  Majority of the controls are administrative checks or monitoring visits, which constitute a more flexible tool for early imposition of corrective measures. The IOP MA also carries out time-consuming on-the-spot public administration checks.

In the period from 1 Apr 2012 to 30 Sep 2012, the IOP MA commenced 21 controls of delegated activities at the CRD, MoI, MoLSA, MoC and MoH. An overview of all the checks, their status and results is given in the attached table. In the monitored period 6 check were incorporated in the plan, 12 check were commenced and 3 were completed.  Of the completed checks, 1 was concluded with a finding related to ineligible expenditure,  non-compliance with legislation governing the field of public contracts and ineligibility of labour costs. Moreover, in the monitored period 3 checks of delegated activities, commenced in the course of 2011, were completed, of which 2 checks with no finding and  1 check which imposed a number of corrective measures. The checks did not detect any serious system deficiencies. In the event corrective measures are proposed, the IOP MA continuously monitors their fulfilment.

With respect to the error rate identified during the checks performed by the IOP MA and other control authorities, the IOP MA identified the risk of inadequate number of checks of delegated activities, which especially in the past was brought about by the IOP MA understaffing. As a corrective measure the IOP MA implemented a public procurement procedure for the selection of an external supplier, who will expand the control teams of IOP MA and thus the number of checks will be increased. It will support the conduct of control and certainly not substitute the control conducted by IOP MA. Simultaneously, the plan of IOP MA controls for 2012 comprised an increased number of checks of delegated activities and it specifies the risks at each IB, on which the checks of delegated activities shall focus in 2012.

Summary of checks of delegated activities at IBs conducted in the period from 1 Apr 2012    to 30 Sep 2012.

| No | Date of commencement | Type of the check | Number of the check | Name of the check | Description of findings | Status |
| --- | --- | --- | --- | --- | --- | --- |
| 1. | 10.4.2012 | Administrative check | 38/2012/I | Administrative check of IUDP Cheb |  | Included in the plan |
| 2. | 11.4.2012 | Administrative check | 16/2012/I. | Administrative check of IUDP Písek |  | Included in the plan |
| 3. | 12.4.2012 | On-the-spot check | 12/2012/I | Check of delegated activities at MoLSA |  | Commenced |
| 4. | 19.4.2012 | On-the-spot check | 10/2012/I | Check of CRD procedures in the field of public procurement and tender controls |  | Commenced |
| 5. | 20.4.2012 | Ex-ante administrative public administration check | 18/2012/I | Check of CRD procedure |  | Commenced |
| 6. | 24.4.2012 | On-the-spot check | 24/2012/I | Check of the completeness of project files – MoI |  | Included in the plan |
| 7. | 27.4.2012 | Administrative check | 15/2012/I | Check of IUDP Jirkov – evaluation of projects by the municipality |  | Included in the plan |
| 8. | 2.5.2012 | Administrative check | 2/2012/I | Verification of CRD procedure in the administration of project %7693 | The check revealed that in the conduct of interim risk analysis the checked person failed to meet the deadline of 20 working days from the approval of the monitoring report to the approval of interim risk analysis as laid down in the Methodological Guideline No 18 of CRD. | Completed – negative (with finding) |
| 9. | 11.6.2012 | On-the-spot check | 26/2012/I | Assessment of the justification of requirements for redrafting project documentation - %6731, %6528 |  | Commenced |
| 10. | 18.7.2012 | Ex-post administrative check | 34/2012/I | Administrative check of delegated activities | The Ex-post monitoring visit by the MoH – European Funds Department ascertained that other types of monitors for computer processing of digital documentation were delivered than that stated in the contract and that no addendum to the contract was concluded which would explain this fact. The beneficiary made a mistake by not concluding an addendum specifying the actually delivered goods. This fact cannot be verified based on the invoices. This deficiency can be removed by concluding an addendum with the reasoning, which would define the subject matter of the delivery with exact specification of delivered goods - monitors, also with reference to the invoice based on which the delivery was made. By delivering different goods the project objective was not endangered or effected. In spite of that the beneficiary should have at least informed the grant provider about this fact. Recommendation: The MoH IB shall recommend the aid beneficiary to conclude an addendum to the contract with a reasoning and a clear definition of the subject matter of the contract, or the delivery with the accurate specification of the delivered goods – monitors, also with reference to the invoice based on which the delivery was supplied. Conclusion: The procedure taken by the contracting authority favoured the winner of the tender. The delivery of different than originally offered in the subject matter of the contract had an impact on the transparency and equal treatment principles defined in the provisions of Section 6 of Act No 137/2006 Coll., on public contracts, as amended. | Completed - positive (no finding) |
| 11. | 20.7.2012 | Administrative check | 20/2012/I | Check of the observance of administrative deadlines |  | Commenced |
| 12. | 20.7.2012 | Administrative check | 39/2012/I | Assessment of technical and financial limits for social service constructions and facilities |  | Commenced |
| 13. | 30.7.2012 | Ex-ante administrative public administration check | 33/2012/I | Verification of the control procedure of CRD upon request of the applicant |  | Completed - positive (no finding) |
| 14. | 7.8.2012 | Ex-post administrative public administration check | 23/2012/I | Check of the method of selection and evaluation of project applications |  | Included in the plan |
| 15. | 15.8.2012 | Interim administrative public administration check | 36/2012/I | Revision of conclusions of the check of CRD CR |  | Commenced |
| 16. | 29.8.2012 | Administrative check | 47/2012/I | Check of delegated activities at MoH – administration of applications for payment |  | Commenced |
| 17. | 30.8.2012 | Administrative check | 48/2012/I | Check of delegated activities at MoC – administration of applications for payment |  | Included in the plan |
| 18. | 5.9.2012 | Administrative check | 49/2012/I | Check of administration of applications for payment by MoI |  | Commenced |
| 19. | 10.9.2012 | Interim administrative public administration check | 37/2012/I | Revision of conclusions of the check of CRD CR |  | Commenced |
| 20. | 11.9.2012 | Interim public administration on-the-spot check | 46/2012/I | Verification of the correctness of IB procedure in project selection, 3E – MoC |  | Commenced |
| 201 | 20.9.2012 | Interim administrative public administration check | 52/2012/I | Check of delegated activities at MoH |  | Commenced |

Checks (verifications) of projects of individual Intermediate Bodies

Checks on projects are the responsibility of the MA who delegates the conduct of checks, with the exception of a part of Technical Assistance projects, to the individual Intermediate Bodies, see the table called Overview of entities conducting the checks on projects. The IOP MA is entitled to carry out its own checks on any of the projects during all stages of project administration. The IOP MA also uses the assistance of experts during the checks of physical implementation of projects under the NCA project for support of the conduct of controls.

In accordance with Article 13 of Commission Regulation (EC) No 1828/2006 the verifications shall cover administrative, financial, technical and physical aspects of operations, as appropriate. The IOP Operational Manual lays down the minimum requirements for all the Intermediate Bodies concerning the procedures during the checks on projects and the minimum scope of the sample for checks pursuant to Article 13 of Commission Regulation (EC) No 1828/2006. The Intermediate Bodies in line with the IOP Operational Manual have elaborated their own detailed procedures for the conduct of checks, including the set methodology for selection of a sample of projects for on-the-spot checks, in case the on-the-spot check is not conducted in 100 % of projects.

Overview of entities conducting checks of projects

| Intervention area | Ex-ante check | Interim check | Ex-post check |
| --- | --- | --- | --- |
|  | administrative | on-the-spot | administrative | on-the-spot | administrative | on-the-spot |
| 1.1 | MoI | MoI | MoI | MoI | MoI | MoI |
| 2.1* | CRD, MoI | MoI | CRD | CRD, MoI | CRD | CRD, MoI |
| 3.1 | CRD, MoLSA | MoLSA | CRD | CRD, MoLSA | CRD | CRD, MoLSA |
| 3.2 | MoH | MoH | MoH | MoH | MoH | MoH |
| 3.3 | CRD, MoLSA | MoLSA | CRD | CRD, MoLSA | CRD | CRD, MoLSA |
| 3.4* | CRD, MoI | MoI | CRD | CRD, MoI | CRD | CRD, MoI |
| 4.1 | CRD, MA | CRD, MA | CRD | CRD, MA | CRD | CRD, MA |
| 5.1 | MoC | MoC | MoC | MoC | MoC | MoC |
| 5.2 | CRD, MA | CRD, MA | CRD | CRD, MA | CRD | CRD, MA |
| 5.3 | CRD, MA | CRD, MA | CRD | CRD, MA | CRD | CRD, MA |
| 6.1 | CRD, MA | - | CRD, MA | MA | CRD, MA | MA |
| 6.2 | CRD, MA | - | CRD, MA | MA | CRD, MA | MA |

Source: MA as of 30 Sep 2012

* since 1 Jul 2012 the CRD has conducted all the checks

The MA carries out its own checks of projects, particularly upon the initiatives of IBs, beneficiaries and other entities and based on risk analyses of individual IBs. In the period from 1 Apr 2012 to 30 Sep 2012, the MA commenced 21 checks of projects directed at the award of public contracts, checks of eligibility of expenditure, observance of deadlines, verification of the feasibility of the fulfilment of project implementation timetables. The IOP MA also completed 3 checks focused on the procedures followed by the contracting authority in the award of public contracts that had been commenced in 2011.

In the period from 1 Apr 2012 to 30 Sep 2012, the Intermediate Bodies commenced 230 checks at applicants and beneficiaries. A more detailed breakdown of checks by the form and stage of their conduct is given in the tables below.

Overview of checks conducted in the period from 1 Apr 2012 to 30 Sep 2012 in the breakdown by intervention area

| Row heading | Ex-ante admin. check | Interim admin. check | Ex-post admin. check | Ex-ante physical on-the-spot check | Interim physical on-the-spot check | Interim physical check with reimbursement | Ex-post physical on-the-spot check | Sum total |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1- MoI | 0 | 0 | 0 | 0 | 2 | 0 | 1 | 3 |
| 2.1-MoI | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 |
| 2.1-CRD | 0 | 31 | 0 | 0 | 7 | 13 | 37 | 88 |
| 3.1 MoLSA | 39 | 6 | 1 | 2 | 1 | 0 | 0 | 49 |
| 3.1-CRD | 1 | 9 | 0 | 0 | 1 | 5 | 0 | 16 |
| 3.2-MoH | 0 | 0 | 0 | 0 | 13 | 0 | 4 | 17 |
| 3.3 MoLSA | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 3 |
| 3.3-CRD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 |
| 3.4-MoI | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3.4-CRD | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 2 |
| 4.1-CRD | 2 | 16 | 0 | 0 | 5 | 2 | 0 | 25 |
| 5.1-MoC | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 |
| 5.2-CRD | 0 | 0 | 0 | 0 | 18 | 0 | 0 | 18 |
| 5.3-CRD | 0 | 0 | 0 | 0 | 3 | 0 | 0 | 3 |
| 6.1-CRD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 6.2-CRD | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |

Source: IS Monit7+IOP as of 30 Sep 2012

Of the total number of checks conducted in the monitored period, 98 were on-the-spot checks.

According to the following overview, of the total of 230 checks 15 checks were completed with a negative result (with finding), 166 checks with a positive result (no finding), and in no check resulted in the imposition of a corrective measure. The most frequent deficiency consisted in the non-compliance with public procurement legislation, ineligible activities and expenditure such as implementation of activities not planned in the project, implementation of activities beyond the planned scope, temporal discrepancy of eligibility of expenditure. In multiple checks deficiencies in the archiving of documents and deficiencies concerning the late submission of applications for payment or violation of conditions of support were identified.

Overview of checks conducted in the period from 1 Apr 2012 to 30 Sep 2012 in the breakdown by check status

| Row heading | Check was cancelled | Completed - negative (with finding) | Completed - positive (no finding) | Corrective measure imposed | Commenced | Scheduled | Sum total |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1.1- MoI | 0 | 0 | 3 | 0 | 0 | 0 | 3 |
| 2.1-MoI | 0 | 0 | 1 | 0 | 0 | 0 | 1 |
| 2.1-CRD | 0 | 11 | 59 | 0 | 12 | 6 | 88 |
| 3.1MoLSA | 0 | 0 | 33 | 0 | 13 | 3 | 49 |
| 3.1-CRD | 1 | 1 | 11 | 0 | 2 | 1 | 16 |
| 3.2-MoH | 0 | 0 | 17 | 0 | 0 | 0 | 17 |
| 3.3MoLSA | 0 | 0 | 2 | 0 | 1 | 0 | 3 |
| 3.3-CRD | 0 | 1 | 1 | 0 | 0 | 0 | 2 |
| 3.4-MoI | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 3.4-CRD | 0 | 0 | 0 | 0 | 2 | 0 | 2 |
| 4.1-CRD | 0 | 2 | 17 | 0 | 6 | 0 | 25 |
| 5.1-MoC | 0 | 0 | 3 | 0 | 0 | 0 | 3 |
| 5.2-CRD | 0 | 0 | 16 | 0 | 0 | 2 | 18 |
| 5.3-CRD | 0 | 0 | 3 | 0 | 0 | 0 | 3 |
| 6.1-CRD | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| 6.2-CRD | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Sum total | 1 | 15 | 166 | 0 | 36 | 12 | 230 |

Source: IS Monit7+IOP as of 30 Sep 2012

The breakdown by the number of checks conducted by individual Intermediate Bodies under the respective intervention areas is presented in the following table.

Overview of checks conducted in the period from 1 Apr 2012 to 30 Sep 2012 in the breakdown by number of checks per IB

| Control authority | Intervention area | Sum total |
| --- | --- | --- |
|  | 1.1 | 2.1 | 3.1 | 3.2 | 3.3 | 3.4 | 4.1 | 5.1 | 5.2 | 5.3 | 6.1 | 6.2 |  |
| CRD CR | - | 88 | 16 | - | 2 | 2 | 25 | - | 18 | 3 | 0 | 0 | 154 |
| Ministry of Culture CR | - | - | - | - | - | - | - | 3 | - | - | - | - | 3 |
| Ministry of Labour and Social Affairs | - | - | 49 | - | 3 | - | - | - | - | - | - | - | 52 |
| Ministry of Interior CR | 3 | 1 | - | - | - | 0 | - | - | - | - | - | - | 4 |
| Ministry of Health CR | - | - | - | 17 | - | - | - | - | - | - | - | - | 17 |
| Sum total | 3 | 89 | 65 | 17 | 5 | 2 | 25 | 3 | 18 | 3 | 0 | 0 | 230 |

Source: IS Monit7+ IOP as of 30 Sep 2012

Other checks by IOP MA – Priority axis 6

In the monitored period from 1 Apr 2012 to 30 Sep 2012, the Managing Authority commenced 5 checks in Intervention area 6.1. Three checks were carried out by the Budget Department, all completed with no finding. The checks focused on the 1st and 2nd stage of the Labour costs project of IOP IB at CRD CR 2012 – 2013 and the 1st stage of the project called Provision of administrative support. One check was commenced by the IOP MA of the project called Provision of capacities at IOP MA, and another check verifying the labour and related expenditure of MoI IB was completed and corrective measures were imposed. In Intervention area 6.2, no check was commenced in the monitored period.

## 4.2 Implementation of the Communication Plan and Activities in the Field of Publicity

In the given period the key IOP publicity activity of 2012 took place – the Annual Conference.

In the monitored period, one of the pivotal communication activities was held, namely the Annual Conference of IOP. The conference, intended for both the professional and general public, was held in the New Townhall of the Municipal Authority of the City of Ostrava on 19 - 20 September, 2012. It was co-organised by the Ministry for Regional Development, the Ministry of Labour and Social Affairs and the Municipal Authority of the City of Ostrava.

Individual speakers concentrated on social integration aspects such as transformation of shelters, support of social entrepreneurship or inclusion of socially excluded groups, Romas in particular, in the society. The speakers oat the conference were recruited from among the outstanding Czech as well as foreign experts. In total more than 120 persons participated in the conference.

The accompanying programme of the conference included a field trip to the former mining area of  Dolní Vítkovice, or NAPROTI Dairy bar social enterprise. In the foyer of the conference hall, an NGO market took place, where the participants had the opportunity to purchase products made in sheltered workshops. The feedback given in the evaluation questionnaires proved that the participants considered the conference to be most useful and interesting.

IOP pod lupou (Under the Magnifying Glass) Newsletter

In the period concerned, a new issue of IOP pod lupou quarterly was published, namely Issue No 14, devoted to the Northwest region. This issue ushered a few changes. The IOP pod lupou Newsletter is now published mainly as an e-version periodical, with only several hundred printed copies distributed. Also the graphic design of the Newsletter was aligned to the new Quality of Life concept.

The latest issue comprises information about the reconstruction of the shelter in Cheb, reconstruction of the Terezín fortress and the newly reconstructed residential buildings at the housing estate in Chanov near Most.

Quality of Life microsites

The IOP MA continuously updates the www.kvalitazivota.eu microsites which offer information on projects implemented with IOP support. At present, you can find around seventy projects with pictures and detailed information on the microsites. More projects are to be added in due course.

Photographs taken from projects posted on the Quality of Life microsites

Restoration of Kuks château

Development of contact coordination centres	New rehabilitation equipment in Hradec Králové  Hospital

A detailed list of all the implemented activities, including seminars for beneficiaries and applicants, is given in the annex.

The list of aid beneficiaries under IOP is published and monthly updated on:

http://www.strukturalni-fondy.cz/Programy-2007-2013/Tematicke-operacni-programy/Integrovany-operacni-program/Projekty/Podporene-projekty

## 4.3 Conducted Evaluations and Studies

In the period from April to September 2012, 1 internal evaluation conducted by the MA included in the Evaluation Plan for 2012 was completed and 1 evaluation was commenced.

In 2012, corrective measures from the Action Plans from evaluations completed in 2011 continue to be acted upon. A summary of corrective measures is given in Annex No 2. Evaluation outputs are available at www.strukturalni-fondy.cz/iop in the section of Documents/Other documents.

### 4.3.1 Evaluations conducted by the Managing Authority

Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP

Its conduct ensues from the Evaluation Plan of IOP approved at the 8th meeting of the Monitoring Committee on 24 Nov 2011.

The main aim of this evaluation was to identify and evaluate the procedural and systemic barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP and to propose measures to eliminate them or to reduce their impacts. The key methodological tools were the analysis of data from IS Monit7+, analysis of documentation, one-to-one interviews, a questionnaire survey targeted at applicants and beneficiaries, and a focus group composed of the implementation structure representatives.

Implementation period: January – March 2012

Type of evaluation: internal

Evaluator: IOP MA in cooperation with CRD and MoLSA

Brief summary of conclusions:

The major bottleneck in project implementation is an excessively long period necessary for the administration of project applications, caused by exceeding and extending the deadlines at individual stages of administration. This is closely connected to a large quantity of changes in projects. In many projects the project completion date is being postponed and it is frequently due to delays in the conduct of activities by implementation entities.

Recommendations aimed to accelerate the administration at individual stages:

- accurate description of activities and deadlines in HAB,

- removal of duplicate and redundant activities,

- observance of deadlines set out in IOP OM.

Another major bottleneck consists in inadequate and unclear requirements for applicants and beneficiaries. One of the consequences thereof are delays at the stage of eligibility and formal requisite evaluation under all the calls. Another consequence are frequent changes in projects brought about by high level of detail of parameters, required by MoLSA and stated in the Decision on providing a grant/Statement of expenditure. Each minor change results in the issuance of new guidance documentation and demanding administration. The checks are ever more complicated and there is an ever higher risk of violation of the Conditions, suspected breach of budgetary discipline and return of support.

The following recommendations are proposed:

- The MoLSA shall specify the checklists for checking the eligibility and formal requisites for CRD (incl. sub-criteria),

- The MoLSA shall hold a seminar for CRD staff on the evaluation of eligibility and formal requisites,

- The MoLSA and CRD staff shall regularly meet at least once a month in order to discuss the topical problems,

- The MoLSA shall explain and simplify the requirements for applicants and beneficiaries.

Bottlenecks were identified at the stage of ex-ante checks, where the MoLSA considerably extends the deadlines, a high percentage of projects is subject to ex-ante checks, there is a high share of rejected projects in activity 3.1b) often on the grounds of a failure to meet the financial and technical limits or they are met at the cost of a large amount of ineligible expenditure. During the ex-ante checks, the MoLSA requests that the applicants produce documents and annexes beyond the scope stipulated by the call and the Handbook for Applicants and Beneficiaries and because of the broad scope of ex-ante checks there is a risk of duplicity with checks conducted by other institutions.

The evaluators propose a number of recommendations starting with the observance of procedures, more specific definition of the content and deadlines of checks, and verification of the scale of risk analysis.

A bottleneck that may cause several months delays in the implementation of individual projects is the external elaboration of an opinion on project documentation. The approval of project documentation is a precondition for the announcement of a tender for the main construction part of the project. The evaluation of project documentation in terms of its completeness is partly duplicated as it is done during the control conducted by the Building Authority before the issuance of the zoning permit or the building permit. Comparing the itemised budget against the prices listed in the pricelist of the Institute of Rationalisation in the Construction Industry (IRCI) and potential cuts in eligible expenditure are redundant at this stage. The final price arising from the tender is on average by 15 % lower than the price adjusted in line with the IRCI opinion.

It is recommended to set a shorter deadline for the elaboration of an opinion and to increase the threshold for the value of the construction part of the project which necessitates an external assessment.

The administration of the system of issuing the Decision on providing a grant/Statement of expenditure is despite some minor improvements still demanding and prolongs the project implementation by 1-2 months. Every single winning bid requires the issuance of a new Decision on providing a grant/Statement of expenditure, prior to which the tender has to be checked (delays occur during the checks at CRD) and the beneficiaries are requested to submit a huge amount of supporting documents before the guidance documents are issued.

The recommendation aims to introduce a more effective system of issuance of guidance documentation in keeping with the IOP Operational Manual (just as in the other IA) or to speed up the process in the existing system.

The demanding and lengthy preparation of projects is a challenge for applicants and beneficiaries. Numerous and difficult to understand requirements are despite a high number of consultations prior to the submission of applications conducive to errors and deficiencies in project applications. The most serious problems faced by applicants are caused by a large number of technical and financial limits (or transformation criteria for 3.1a), particularly in case of reconstructions.

The evaluators recommend to simplify the requirements for submission of applications and setting the conditions.

The MoLSA suggests to examine the wording and definition of technical and financial limits. It recommends to make their list and definitions clearer for applicants.

The Action Plan arising from the Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3 of IOP contains roughly 90 recommendations. One fifth of the recommendations was drawn up by the MoLSA IB and incorporated in the revised Handbook of Work Procedures (version 1.4 approved on 2 Jul 2012). Approximately 15 % of recommendations is accomplished by MoLSA through the revisions of rules for the announced calls. Not a single revision was completed by 30 Sep 2012. The MoLSA incorporates the most essential comments raised by IOP MA.

About 15 % of the evaluator's recommendations are accomplished by MoLSA thanks to more intensive collaboration with CRD. The evaluator's recommendations were also partly fulfilled by regular reporting or through seminars and consultations. Some recommendations were not accepted by MoLSA or are still subject to discussions with IOP MA, e.g. the request for ARS/ASOA forms, documents for final evaluation of action, setting the financial and technical limits.

Full version of the Action Plan, including its fulfilment as of 30 Sep 2012, is attached in Annex No 2.

Analysis of administrative capacities and outsourcing in IOP implementation structure

To elaborate the Analysis of administrative capacities and outsourcing of Intermediate Bodies in 2011 was one of the tasks assigned to the IOP Managing Authority (IOP MA) at the 7th meeting of the Monitoring Committee (IOP MC). The Monitoring Committee was acquainted with the results at its 8th meeting held on 24 Nov 2011 and a task was assigned to the IOP Managing Authority to examine the structure of expenditure spent on outsourced activities at IOP MA and IOP IBs and to share the information with the MC at its next meeting. At the 9th MC meeting the IOP MA presented brief information on the structure of expenditure of IBs and MA on outsourced activities. In the Evaluation Plan of IOP for 2012, the IOP MA undertook to carry out a more detailed analysis of administrative capacities and outsourcing of Intermediate Bodies and IOP MA. The aim was to quantify the funds actually spent by individual Intermediate Bodies on the administration of delegated activities and also the MA costs of programme management. Based on the comparison of costs incurred at individual Intermediate Bodies it also sought to identify the risks and to propose recommendations leading to improved efficiency and economy.

Implementation period: July – September 2012

Type of evaluation: internal

Evaluator: IOP MA in cooperation with IBs

Brief summary of conclusions:

As of 30 Sep 2012, a draft final report was compiled which is currently being commented upon, and the results will be presented to the MC at its 10th meeting.

### 4.3.2 Evaluation and studies carried out by the Intermediate Bodies

The Intermediate Bodies did not conduct any evaluation in the monitored period.

## 4.4 Other Activities of the Managing Authority and the Monitoring Committee

### 4.4.1 Activities of the Managing Authority

4.4.1.1 Reinforced risk management of NCA

Considered essential in the monitored period can be the drawing up of the document called “Risky Operational Programmes – Proposed Measures Promoting the Accomplishment of Objectives of the National Strategic Reference Framework“, submitted by the National Coordination Authority and discussed by the Government of the CR. The document was approved by the Government of the CR on 4 July 2012 by Resolution No 498.

The aim of this document was to inform the Government of the CR on operational programmes considered risky by the MRD-NCA as at the date of elaboration of this document (i.e. OP Transport, OP Environment, OP Research and Development for Innovations, OP Education for Competitiveness, Integrated OP and ROP Northwest). Each risky OP was subject to overall evaluation in terms of physical fulfilment of objectives, financial aspects and OP management. The document also comprised the action plans for individual operational programmes. The action plan for IOP contained ten risks in five risky areas. The Action Plan itself and the status of fulfilment of measures as at the end of September 2012 are attached to this Report as Annex No 5.

In the months of August and September, the MRD-NCA conducted a control of accomplishment of these measures which replaced the meetings concerning the reinforced risk management that had been convened until then.

4.4.1.2 Reinforced risk management of IOP MA

In the monitored period, the Managing Authority carried out two essential crisis management activities. They consisted primarily in the transfer of the agenda under Intervention areas 2.1 and 3.4 from MoI CR to MRD and CRD CR as well as in the identification of sleeping projects and the proposals for their solution. Details of both these activities are given below. Apart from these activities, all the previous measures mentioned in previous Reports on Implementation of IOP have continued to be performed.

4.4.1.3 Meetings of Deputy Ministers of ministries implementing the IOP

With regard to the status of implementation of the programme and addressed problems, which many times went beyond the competence of IOP IB directors, the top officials of MRD continued to convene the meetings of the Interministerial Commission of Deputy Ministers implementing the IOP.

In the monitored period, one meeting was held with the view to speed up the implementation of the Integrated Operational Programme in 2012, to fulfil the N+3 rule in 2012 and N+3 and N+2 rules in 2013, to solve the issue of sleeping projects, to specify and fulfil forecast absorption. The IOP MA informed on the results of control and audit activities in individual intervention areas and on specific problems and risks faced by individual intervention areas.

Main conclusions of the meeting of Interministerial Commission of Deputy Ministers implementing IOP

Ministry of Interior

- To guarantee the observance of timetables, stages and forecast absorption of funds in IA 1.1.

- To safeguard crisis management of projects in IA 1.1.

- To propose crisis timetables for sleeping projects in IA 1.1.

- To ensure the handing over of all the relevant documents associated with the transfer of IA 2.1 and 3.4.

Ministry of Labour and Social Affairs

- Prevailing lengthy administration period and unclear procedures of CRD and MOLSA, insufficient absorption of funds, excessive burden on applicants and beneficiaries (e.g. inadequate flexibility of setting the financial and technical limits, supporting documents for final evaluation of action, ARS forms, unclear definition of terms), extension of administrative deadlines or lacking methodology and the associated problem of protracted process of approval of handbooks and manuals.

- Necessity to issue legal acts in line with the task assigned at IOP MC in the amount of 50 % of allocation for Intervention areas 3.1 and 3.3. The MoLSA anticipates the fulfilment in IA 3.3, while in IA 3.1 it expects the issuance of legal acts in the amount of 46–53 % of the allocation.

Ministry of Culture

- Slow implementation of projects, low rate of absorption of funds, necessary acceleration of project implementation and monitoring of detailed timetables of project implementation.

- To issue legal acts for projects under the 3rd call.

Ministry of Health

- Request for the IOP MA opinion on the change in legal form of hospitals

4.4.1.4   Bilateral meetings between IOP MA and IOP IBs

In the period from 1 Apr 2011 to 30 Sep 2012, several bilateral meetings with the Ministry of Culture and the Ministry of Health took place, at which the following topical issues were dealt with:

- To accelerate the issuance of RA and Decision, to update the status in Monit7+,

- In the prepared update of HAB for all the calls to eliminate the obligation to merge the quarterly stages in case the amount of eligible expenditure is lower than the financial limit of CZK 10 million,

- Extension of project implementation by more than 3 months will have to be approved by IOP MA,

- In Intervention area 5.1, ex-post notification is not possible, the risk of state aid shall be eliminated when assessing project applications through changes in problem activities and checks of projects,

- Sleeping, or high-risk projects – the MoC shall invite the IOP MA representatives to meetings with beneficiaries in Veltrusy, Plasy, Valtice and Krumlov projects,

- The IOP MA shall send the MoC the amount of available funds following the calculation of the exchange rate reserve,

- In order to eliminate the risk of extra works in projects the MoC IB hired construction experts who are authorised to assess the extra works,

- Cancellation of tenders due to the submission of only one or no bid – the MoH shall consider the possibility to divide these projects into stages,

- Setting of priorities in planning the calls,

- Nový Jičín – the MoH shall inform the MA before 24 August and send the protocol from public administration checks with corrective measures.

4.4.1.3 Education and training

Overview of conducted education and training activities

| Evaluation of education plans / Activity | Role of the MA | Comments |
| --- | --- | --- |
| Education and training organised by the Managing Authority for Intermediate Bodies | Organisation of education and training activities which reflect topical issues in IOP implementation and the topics of which are not covered by external training courses offered in the market. | In the period from 1 April 2012 to 30 September 2012, the MA held a total of 8 education and training events during which 68 persons (IB) were trained. The thematic areas covered by the education and training events focused on publicity and promotion of the programme, monitoring and evaluation, financial management, preparation and management of projects, and controls. |
| Education and training at the MA | Organisation of education and training activities based on the individual education plans of MA staff, or the IOP annual plan. | From 1 April 2012 to 30 September 2012, a total of 260 members of IOP MA staff were trained during 50 education and training events. The largest number of staff was trained in multiple thematic areas, they also took part in initial training courses of IOP MA, courses focused on computer skills, state aid, public procurement, IOP legislation, financial and management control, monitoring and evaluation. The smallest number of persons was trained in thematic areas focused on IOP information systems, financial management and experience from other OPs. |

### 4.4.2 Activities of the Monitoring Committee

In the period from April 2012 to September 2012, the 9th regular meeting of the IOP Monitoring Committee was held at Barceló hotel, Na Strži 32, Prague 4, on 31 May 2012.

At the 9th meeting of IOP MC the Annual Report for 2011 was submitted for approval.

The IOP MC members took note of the following:

- Report on acting upon the conclusions of the 8th meeting of the IOP Monitoring Committee;

- Report on Implementation of IOP as of 31 Mar 2012;

- Information on the examination of the structure of expenditure on outsourced activities in the IOP implementation structure;

- Information on the evaluation of activities performed by working groups set up by the IOP Monitoring Committee and a proposal for their dissolution.

A number of recommendations and tasks for the MA and individual IBs (for more details see Annex No 6) has arisen from the meeting.

### 4.4.3 Activities of Working Groups

Working groups represent a tool for communication on topical themes or problems. The respective working groups meet usually 4x a year, the minutes are taken from their meetings and the WGs are subject to evaluation by the MA. In collaboration with WG members, the evaluation considers the frequency of meetings in the year concerned, the attendance, the fulfilment of tasks assigned at the working group meetings, the involvement and activity of members, the satisfaction of members with the organisation of WG and the benefits of the respective working group.

Working groups can respond in a flexible fashion to the emerging problems in IOP implementation. To a great degree they are also used as an education and training tool.

Working Groups of IOP MC

Pursuant to its Statute (Article 6, para 1 – 4), the IOP MC Chairperson at the Technical Meeting of IOP MC held on 27 Jun 2008 established working groups for addressing specific issues. In compliance with the Statute (Article 6, para 5) the working groups were established to discuss the issues of coordination and cooperation between IOP and OP and their meetings were within the remit of  the relevant ministries responsible for the given intervention area.

The IOP MC Chairperson, upon the proposal of IOP MC members, has established the following working groups:

- WG for Intervention area 3.1, 3.2 and 3.4 – this working group has never met, its activity is addressed at meetings between MoLSA and MoI CR

- WG for Intervention area 4.1 – activities in tourism are twice a year discussed at the Meeting of regional representatives for tourism, regional coordinators and representatives of the Czech headquarters of tourism – CzechTourism.

- WG for Intervention area 5.1 – activity of this working group was replaced by the participation of the director of the Strategy and Aid Policy Department of the MoC in the meeting of the expert working group of the Association of Regions of the CR for EU funds, at which representatives of regions and the Regional Operational Programmes meet. The Working Group for IA 5.1 met once in 2008.

- WG for Intervention area 5.3 – Intervention area 5.3 of IOP is on the agenda of WG for coordination of urban policy, which is managed by the Regional Policy Department of MRD, and IOP MA participates in its meetings just like the other representatives of operational programmes and professional associations.

Pursuant to the IOP MC Statute (Article 6, para 1), upon the proposal of IOP MC members the Chairperson can establish or dissolve a working group for addressing specific issues. Since all the IOP MC working groups have been adequately replaced by the existing working groups or working meetings at the level of ministries, these working groups were dissolved at the 9th meeting of IOP MC on 31 May 2012  in connection with the Task No C2 from the 8th meeting of IOP MC.

In the period from 1 Apr 2012 to 30 Sep 2012, meetings of the following IOP MA Working Groups were held:

- WG Pilot

- WG IS and monitoring

- WG Jessica

- WG for public contracts

- WG for reducing the risks in Smart Administration

- WG Evaluation

In the monitored period, no meetings of the following WG were convened:

- WG Financial Management – following the training course on the amendment to Act No 218/2000 Coll., on budgetary rules (held on 27 Mar 2012), the MA consulted with individual IBs the  changes in the Conditions of guidance documents for the provision of documents for granting IOP funds brought about by this amendment.

- WG for communication

- WG for IA 5.2

- WG Technical assistance

Main conclusions from meetings of the working groups

WG for communication

In the monitored period the working group met two times. The main point on agenda of the November meeting was the introduction of the new communication strategy of IOP called “Quality of My Life”, which will facilitate an effective presentation of the achieved results of IOP over the remaining years of the current programming period. It shall also serve as an easily accessible source of information on IOP projects, not only for the general public, but also for mass media. The new strategy, built around the principle that can be briefly characterised as the “integrated approach” follows from the final report of the Evaluation of communication and publicity activities of IOP, commissioned by IOP MA that was completed in April 2011.

The main point on the agenda of the March meeting was the presentation of the new “Quality of life” website offering information on successful projects in IOP.

WG Pilot

In the monitored period the working group met on 4 Sep 2012. Apart from this meeting, the IOP MA paid monitoring visits to the Pilot projects. All the monitored visits were smooth and the status of individual projects was found trouble-free.

WG for risk management

In the monitored period the working group met once – on 12 Apr 2012. The List of Risks and the Catalogue of Risks were approved at the meeting and essential changes in risk management system were discussed.

WG for evaluation

In the monitored period the working group for evaluation of IOP met twice on 24 Apr 2012 and 22 May 2012. At both the meetings training courses were held by the Czech Evaluation Company. The training courses followed from the first block of courses held at the end of 2011 and focused on the conduct of evaluation and on the application of results.

WG IS and monitoring

In the monitored period the working group met once. The working group convened on 26 Jun 2012  focused on the use of output reports from IS Monit7+IOP and MSC2007.

WG Jessica

The meeting of the working group took place on 18 Jun 2012. At the meeting of the Working Group its members arrived at the following conclusions:

- In order to act upon the conclusions of the 8th meeting of MC as concerns the sending of up-to-date information on progress in implementation at two months intervals, the next information will be sent as at 16 July 2012,

- The MA in cooperation with SHDF shall ensure the fulfilment of the task assigned at the 9th meeting of MC with regard to the maximum effectiveness of JESSICA FI implementation in IOP in order to maximise the amount allocated to loans,

- The SHDF in cooperation with IOP MA shall draft criteria for the selection of Urban Development Fund (UDF) administrator so that the criteria can be submitted for approval at the 10th meeting of the IOP Monitoring Committee,

- The eligible expenditure at the level of UDF and final recipients shall be evidenced and implemented no later than on 31 December 2015,

- On 21 and 25 Jun 2012, the municipalities shall be introduced to JESSICA FI with regard to the new IUDP methodology,

- The IOP MA will continue to cooperate with the OPC on preparing the approval of the Addendum to the Decision of the Commission on state aid,

- The IOP MA shall continue to prepare the conditions for the Decision on providing a grant which shall be forwarded to the PCA for comments,

- The SHDF shall continue to prepare the tender documents for a tender for EDF administrator. Based on the DG REGIO requirement, the tender documents will be sent to the Commission for examination.

- The IOP MA shall continue to draft the  “Manual for the implementation of JESSICA FI“,

- The SHDF shall continue to elaborate the annexes to the application for support through IS BENEFIT,

- The SHDF shared information on progress in the approval process due to the amendment to Act on the SHDF.

WG for public contracts

In the monitored period the working group met once on 3 May 2012. At this meeting the WG addressed problems arising in connection with the amendment to Act No 137/2006 Coll., on public contracts, which took effect on 1 Apr 2012.

WG for risk reduction in Smart Administration

The working group was set up in January 2012 as one of the IOP MA measures to improve and accelerate the absorption at MoI CR. It is a working group composed of directors and heads of units of IOP MA, Structural Fund department, Programme Management Department and CRD. The aim of the working group is not only to address the topical issues of project implementation and absorption of funds, but also to ensure smooth transfer of delegated activities in Intervention areas 2.1 and 3.4 from MoI CR to MRD CR. The working group meets at an interval of two weeks and addresses the tasks within the deadlines.

Since July 2012, when the transfer of delegated activities in Intervention areas 2.1 and 3.4 was made, the working group meetings have been devoted explicitly to Intervention area 1.1. The working group convenes monthly without the Centre for Regional Development of the CR.

## 4.5 Administrative Capacity of Implementation Structure Entities of the Programme

The MA monitors and registers the administrative capacity of entities involved in the IOP implementation. The following two tables of administrative capacity were elaborated pursuant to the NCA guideline for drafting the report on implementation.

The table includes all the units and their employees involved in IOP implementation, expressed in full time equivalent. Apart from the Managing Authority and Intermediate Bodies staff, it also comprises those MRD technical sections that cooperate with the Managing Authority in the field of tourism, territorial (spatial) planning and housing support, Financial Section of MRD and the section of the Delegated Audit Body.

The table presents the structure of entities involved in IOP implementation. The “Number of employees” column gives the number of employees involved in IOP implementation expressed in full time equivalent (FTE). An employee with a full-time position (who spends 100 % of his working time on IOP implementation) is assigned the value of 1.0 FTE, while an employee with a quarter-time position who spends 25 % of his time on IOP implementation is assigned the value of 0.25 FTE.

Status of administrative capacity of IOP implementation structure

| Authority | Department | Unit | Number of employees (FTE) | Total for the authority (FTE) |
| --- | --- | --- | --- | --- |
| Managing Authority | Operational Programmes Management Department | Director of the Department and the Secretariat to the Department | 2,00 | 53,45 |
|  |  | Management Unit | 12,70 |  |
|  |  | Methodology Unit | 9,90 |  |
|  |  | Monitoring Unit | 5,00 |  |
|  |  | Control Unit | 9,87 |  |
|  | Budget Department | EU Programmes Administration Unit | 9,98 |  |
| Persons responsible in the Technical sections of the Ministry for Regional Development CR | Housing Policy Department | National Programme Administration and IOP Unit | 2,00 |  |
|  | Tourism Department | Integration and Tourism Competitiveness Unit | 1,00 |  |
|  | Spatial Planning Department | Spatial Development Unit | 1,00 |  |
| Financial Section | Accounting and Financial Services Department | European Funds Accounting Unit and Budgetary Chapter Accounting Unit | 3,20 | 3,20 |
| Ministry of Culture CR | Strategy and Aid Policy Department | Project Implementation Unit | 7,00 | 13,75 |
|  |  | Financial Management Unit | 2,75 |  |
|  |  | Strategy and Methodological Support Unit | 4,00 |  |
| Ministry of Health CR | European Funds Department | Methodology Unit | 5,00 | 23,00 |
|  |  | Project Management Unit | 4,00 |  |
|  |  | Project Financing Unit | 5,00 |  |
|  |  | Monitoring, Control and Technical Assistance Unit | 6,00 |  |
|  |  | Director, assistant, administrative officers | 3,00 |  |
| Ministry of Interior CR | Structural Funds Department | Organisational and TA Unit | 8,22 | 32,82 |
|  |  | Methodology and Monitoring Unit | 4,89 |  |
|  |  | IOP Implementation Unit | 8,00 |  |
|  |  | Control, Monitoring and Publicity Unit | 6,93 |  |
|  |  | Publicity and Absorption Capacity Unit | 1,65 |  |
|  | Financial Department of MOI CR | Financial Management of Payments Unit | 3,13 |  |
| Ministry of Labour and Social Affairs CR | EU Funds Implementation Department | Programme Implementation Unit - employment | 2,30 | 21,14 |
|  |  | Programme Implementation Unit – social integration and services | 7,60 |  |
|  | Programme Financing Department | Financial Management of Assistance and IOP Unit | 9,79 |  |
|  |  | Other MoLSA units involved in IOP implementation | 1,45 |  |
| Centre for Regional Development of the CR |  | SF Management for Objective 1 and Objective 2 Section | 5,50 | 41,95 |
|  |  | Financial Management Section | 5,00 |  |
|  |  | Regional Branches Section | 31,45 |  |
| DAB | Internal Audit and Delegated Audit Body Department | Internal Audit Unit | 0,00 | 9,00 |
|  |  | Delegated Audit Body Unit | 9,00 |  |
| Total |  |  | 198,31 | 198,31 |

Source: MA and IBs as of 30 Sep 2012

The following table contains comparisons of the current status of IOP administrative capacity and the status as of 31 Mar 2012. It also includes the target number of employees until the end of 2013.

Monitoring the status of administrative capacity in 2007 – 2013 programming period

| Number of employees of IOP implementation structure expressed in FTE (target number of employees until the end of 2013) |
| --- |
|  | FTE as of 31 Mar 2012 | FTE – as of 30 Sep 2012 | Target FTE for 2012 | Target FTE for 2013 | Target FTE for 2014 |
| Managing Authority | 43,85 | 49,45 | 50,00 | 50,00 | 50,00 |
| Persons responsible in technical sections of MRD CR | 4,00 | 4,00 | 4,00 | 4,00 | 4,00 |
| Financial Section | 3,20 | 3,20 | 3,20 | 3,20 | 3,20 |
| Ministry of Culture CR | 17,00 | 13,75 | 17,00 | 17,00 | 17,00 |
| Ministry of Health CR | 20,50 | 23,00 | 25,00 | 25,00 | 25,00 |
| Ministry of Interior CR | 39,01 | 32,82 | 33,00 | 33,00 | 33,00 |
| Ministry of Labour and Social Affairs CR | 21,30 | 21,14 | 23,30 | 23,30 | 23,30 |
| Centre for Regional Development CR | 38,45 | 41,95 | 42,95 | 46,00 | 46,00 |
| DAB | 9,00 | 9,00 | 10,00 | 10,00 | 10,00 |
| Total | 196,31 | 198,31 | 208,45 | 211,5 | 211,5 |

Source: MA and IBs as of 30 Sep 2012

Comments on administrative capacity of individual IOP entities are presented in the following table.

| Managing Authority | The number of IOP MA staff was increased by five officers following the signature of the Addendum No 2 to the Agreement on delegating tasks of the Managing Authority of the Integrated Operational Programme to the Ministry of Interior as the Intermediate Body in the framework of implementation of the Integrated Operational Programme for 2007 – 2013 period, by which the administration of Intervention areas 2.1 and 3.4 was transferred to IOP MA and CRD CR. The number of staff of IOP MA as at 30 Sep 2012 includes 8 officers working based on the Agreement on work activities (FTE – 4). |
| --- | --- |
| Centre for Regional Development of the CR | The number of staff of IB – CRD CR expressed in FTE equals the number of staff covered from IOP TA set and non-budgeted by the MRD CR founder. Until June 2012, the maximum administrative capacity was 39 FTE which has been always observed – 38.45 (FTE as of 30 Jun 2012). Since 1 July 2012, the MRD CR became the grant provider in IA 2.1 and 3.4, which is accompanied by the changed number of FTE for IOP at CRD, which is gradually increased by 7 FTE. By the end of the monitored period the number of FTE was increased by 3.5 FTE. No marked turnover has been reported. |
| Ministry of Interior of the CR | At the MoI CR IB – Structural Funds Department the administrative capacity dropped due the new pro-rata formula, based on which the labour costs of MoI CR IB staff involved in IOP and OP HRE implementation are calculated. Before 1 Jul 2012, it was 77.61 % for IOP and 22.39 % for OP HRE, starting with 1 Jul 2012 it is 63 % for IOP and 37 % for OP HRE. This change occurred in connection with the transfer of administration of projects under IA 2.1. and 3.4 from MoI CR to CRD CR and MRD CR. At the MoI CR since 1 Oct 2011 the effectiveness of administrative capacity has been improving. The Project Control Unit and the Publicity and Absorption Capacity Unit merged as well as the Project Evaluation Unit and the Project Methodology and Monitoring Unit. |
| Ministry of Culture of the CR | At the MoC CR IB there were rather significant changes in staffing. 2 lawyers left the Project Implementation Unit as of 31 Jul 2012 and 15 Aug 2012, respectively. As of 1 Aug 2012, the head of the Financial Management Unit was entrusted with the management of the department. One of the employees of the Financial Management Unit was appointed the head of the unit as of 1 Sep 2012. |
| Ministry of Labour and Social Affairs of the CR | In the monitored period, the overall staffing capacity of the implementation structure at MoLSA CR IB dropped due to the migration of staff. |
| Ministry of Health of the CR | In the monitored period, especially the Methodology Unit was reinforced by hiring 3 new members of staff (of which one as a substitute for an officer on maternity leave), i.e. the number of officers of the Methodology Unit grew from 3 to 5. Of major importance was the hiring of an officer with legal background. In addition, also one part-time (0.5 FTE) temporary worker was hired in the monitored period. |
| DAB | The capacities were continuously achieved pursuant to the Government Resolution No 884/2007 and in line with the project Ensuring staffing capacities of MRD DAB and work in the group of auditors. |

The following table monitors the turnover rate of staff by individual type position as of 30 Sep2012.

Monitoring of turnover rate by type position and implementation entity

| Turnover of employees of OP implementation structure by type position | Number of employees at the given position by share of their involvement in implementation as of 31 Mar 2012 | Number of employees at the given position by share of their involvement in implementation as of 30 Sep 2012 | Number of terminated/changed employment contracts at the given type position by the share* of their involvement in OP implementation | Number of terminated/changed employment contracts at the given type position by the share* of their involvement in OP implementation (only maternal leave, retirement, death etc. | Number of commenced employment contracts at the given type position by the share* of their involvement in OP implementation |
| --- | --- | --- | --- | --- | --- |
|  | MA + DAB | IB | MA + DAB | IB | MA + DAB | IB | MA + DAB | IB | MA + DAB | IB |
| Administrator of the monitoring system | 4,00 | 0,00 | 4,00 |  |  |  | 1,00 |  | 1,00 |  |
| Administrative officer | 4,00 | 8,94 | 5,00 | 7,97 |  |  |  | 0,39 |  | 1,08 |
| OP analyst |  | 0,40 |  | 0,32 |  |  |  | 0,40 |  |  |
| DAB auditor for OP | 9,00 | 0,00 | 9,00 |  |  |  | 1,00 |  | 1,00 |  |
| Financial manager | 12,75 | 32,06 | 11,18 | 31,23 |  |  |  | 2,74 | 1,00 | 6,18 |
| Communication officer | 0,60 | 2,74 | 1,40 | 2,85 |  |  |  |  | 0,80 | 0,63 |
| Controller | 9,00 | 6,17 | 7,87 | 6,07 |  |  |  | 1,02 | 2,00 | 0,32 |
| Coordinator of evaluation | 0,95 | 1,28 | 0,80 | 1,75 |  |  |  |  |  |  |
| Coordinator of controls and irregularities |  | 2,05 |  | 0,99 |  |  |  |  |  |  |
| Coordinator of technical assistance | 2,00 | 3,55 | 2,00 | 4,11 |  |  |  |  |  |  |
| Coordinator of education and training | 1,00 | 0,39 | 1,00 |  |  |  |  |  |  |  |
| Methodologist of OP management | 8,75 | 5,79 | 8,40 | 7,78 | 0,88 | 0,50 |  | 1,00 | 2,00 | 1,50 |
| Lawyer | 0,00 | 5,34 |  | 4,46 |  |  |  | 1,13 |  | 1,39 |
| Project manager | 0,00 | 46,86 |  | 46,68 |  |  |  | 2,66 |  | 4,33 |
| Senior officer | 6,00 | 20,69 | 6,00 | 18,45 |  | 1,00 |  | 2,51 |  | 2,26 |
| Other positions | 6,00 | 0,00 | 9,00 |  |  |  | 1,00 |  | 2,20 |  |
| Total number of employees | 64,05 | 136,26 | 65,65 | 132,66 | 0,88 | 1,50 | 3,00 | 11,85 | 10,00 | 17,69 |

Source: MA and other implementation entities as of 30 Sep 2012

Note: *In case the employee devoted less than 100 % of his time to work activities related to programme implementation, share of his work devoted to the programme is given

Note: starting with 1 Jan 2013 the DAB will not be a part of the implementation structure

# 5 MAIN CONCLUSIONS

In the period from 1 Apr 2012 to 30 Sep 2012, a total of 1 294 project applications in the amount of EUR 450.42 million were submitted in fifteen calls. As of 30 Sep 2012, a total of 8 424 project applications amounting to EUR 2 486.85 million were submitted, which represents 130 % of the programme allocation. 7 374 projects in the amount of EUR 1 485.56 million, i.e. 78 % of the allocation,  were approved. The beneficiaries were paid EUR 514.09 million, representing 27 % of the programme allocation. The aggregate payment claims accounted for by the PCA totalled  EUR 495.16 million. Expenditure in the amount of EUR 217.99 million, i.e. 11 % of the programme allocation was certified. Above mentioned amounts include total public funds.

MA IOP has finished the completion of analysis of the optimisation of work procedures called “Identification of barriers to the absorption of funds in Intervention areas 3.1 and 3.3“. The measures defined in the Action Plan are being implemented, following the completion of their implementation the IOP MA in cooperation with the MoLSA IB will evaluate their effectiveness.

MA IOP in cooperation with CRD has transferred the delegated activities in Intervention areas 2.1 and 3.4 were transferred from the MoI CR to the MRD CR and the CRD CR due to unsatisfactory status of implementation in intervention areas under the responsibility of the MoI CR. It aimed to improve the quality, decrease the error rate and accelerate the administration. By relieving of MoI CR agenda in this area capacities will be released to reinforce the administration and control of projects in Intervention area 1.1.

State administration registres were launched into full operation mode. In July was approved a new status of the Government Council for Competitiveness and Information Society.

The IOP MA agreed with the Audit authority to decrease the error rate identified by the Annual Control Report for 2011. Subsequently the Audit authority sent to the EC a detailed reasoning of the decreasing of error rate.

The volume of funds included in aggregate payment claims reached the level sufficient for the achievement of n+3 target in 2012 with the use of the advance payments under both the objectives. An essential precondition for achieving the n+3 target is the relaunch of certification by the end of 2012.

The IOP MA introduced the system of monitoring and management of sleeping and risky projects as a tool to optimization of drawing predictions.  The aim is to reduce non-compliance schedules and moving activities into the following stages of the projects.

The planned volume of certified expenditure by the end of 2013 is sufficient for the fulfilment of n+3 and n+2 rule in 2013. Taking into account the risk of failure to fulfil the absorption forecasts due to the postponements in project timetables, the IOP MA prepares measures which should prevent it. These measures include e.g. the limited approval of changes in timetables of stages, extraordinary division of projects into stages with the view to increase the funds certified by the end of 2013, discussions with OPC concerning the closing of investigations which are the reason for suspension of administration of applications for payment, continuous consultations on applications for payment with beneficiaries.

MA IOP has announced a call for promoters IUDP which responds to the possible use of soft loans from the JESSICA financial instrument. It has launched preliminary notification to be followed by notification of expenditures  in the intervention area 5.2 in order to enable providing the support in the form of soft loans. By the end of 2012 an announcement of the tender for the administrator of UDF is expected.

# LIST OF ABBREVIATIONS

| AA | Audit Authority |
| --- | --- |
| ACR | Annual Control Report |
| AIS | Agenda Information Systems |
| AP | Action Plan |
| ARS | Aid Registration System |
| ASOA | Administration of State-Owned Assets |
| AWA | Agreement on work activities |
| AWP | Agreement on work performance |
| Conv. | Convergence objective |
| CoP | Communication Plan |
| CRD | Centre for Regional Development |
| CRD BRA | CRD Branches |
| CZK | Czech Crown – currency |
| DAB | Delegated Audit Body |
| DOZP/HPD | Home for people with disabilities |
| DPG | Decision on providing a grant |
| DSS/SCH | Social care home |
| EC | European Commission |
| ERDF | European Regional Development Fund |
| ESF | European Social Fund |
| EU | European Union |
| EUR | Euro – currency |
| FEA | Final evaluation of the action |
| FI | Financial Instrument |
| GA | Government Agency |
| GD FRS HZS | General Directorate of the Fire Rescue Service |
| GFD | General Financial Directorate |
| HAB | Handbook for Applicants and Beneficiaries |
| HF | Holding Fund |
| HQ | Headquarters |
| HWP | Handbook of Work Procedures |
| IB | Intermediate Body |
| ICT | Information and communication technologies |
| ImS | Implementation system |
| IOP | Integrated Operational Programme |
| IOP MC | IOP Monitoring Committee |
| IOP OM | IOP Operational manual |
| IRS | Integrated Rescue System |
| IUDP | Integrated Urban Development Plan |
| LTO | Local tax Office |
| MA | Managing Authority |
| MIP | Manual of Internal Procedures |
| MMR | Monthly Monitoring Report |
| MoC | Ministry of Culture |
| MoH | Ministry of Health |
| MoI | Ministry of Interior |
| MoI PMD | Programme Management Department of the Ministry of Interior |
| MoLSA | Ministry of Labour and Social Affairs |
| MR | Monitoring Report |
| MRD | Ministry for Regional Development |
| NCT | National Centre for Support of the Transformation of Social Services |
| NoCP | Notification of a change in the project |
| NSRF | National Strategic Reference Framework |
| NVA | National Coordination Authority |
| OP | Operational Programme |
| OP HRE | Operational Programme Human Resources and Employment |
| OPC | Office for the Protection of Competition |
| OPTA | Operational Programme Technical Assistance |
| PA | Priority axis / priority area |
| PC | Payment Classification |
| PCA | Paying and Certifying Authority - National Fund |
| RA | Registration of the action |
| RAC | Regional Administrative Court |
| RCE | Regional Competitiveness and Employment objective |
| ROP | Regional Operational Programme |
| RVKIS | Government Council for Information Society |
| SA | Smart Administration |
| SAC | Supreme Administrative Court |
| SAO | Supreme Audit Office |
| SAPD | Strategy and Aid Policy Department of the Ministry of Culture |
| SB | State budget |
| SCC | Social Care Centre |
| SE | Statement of expenditure on financing the GA action |
| SF | Structural Funds |
| SFD | Structural Funds Department |
| SHDF | State Housing Development Fund |
| SMR | Stage Monitoring Report |
| T | Tourism |
| T | Tender |
| TA | Technical assistance |
| TD | Tender documentation |
| TO | Tax Office |
| UDF | Urban Development Fund |
| WG | Working Group |

# ANNEXES

Annex No 1 – Publicity activities in the period from 1 Apr 2012 to 30 Sep2012

Annex No 2 – Action Plans

Annex No 3 – System of monitoring of sleeping ad risky projects

Annex No 4 – List of sleeping projects

Annex No 5 – Action Plan of the NCA on IOP

Annex No 6 – Summary of measures taken with respect to the conclusions of the previous meeting of IOP MC

## Annex No 1 – Publicity activities in the period from 1 Apr 2012 to 30 Sep 2012

| MA/IB | Name | Topic | Target group | Funds from IOP TA (EUR) | More information |
| --- | --- | --- | --- | --- | --- |
| MA | www.strukturalni-fondy.cz/iop website | On-going publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | Website is being updated continuously throughout the year. Updated information is supplied in the following sections: news, calls, for applicants, list of beneficiaries, tenders. |
| MA | Number of replies to enquiries through iop@mmr.cz | Enquiries concerning IOP | Applicants General public | 0 | 4/2012-9/2012- 28 enquiries |
| MA | Seminars for beneficiaries under Intervention area 4.1 | Information for applicants under IA 4.1 | Beneficiaries | 201 | 20. 6. 2012 Prague. Number of participants: 40 |
| MA | 2 seminars for applicants under Intervention area 5.3 | Information for applicants under IA 5.3 | Applicants | 241 | 25. 6. 2012 Prague. Number of participants: 10 21. 6. 2012 Prague. Number of participants: 40 |
| MA | Seminar for beneficiaries under Intervention area 2.1 | Training of beneficiaries under Intervention area 2.1 – a change in grant provider | Beneficiaries | 1 232 | 10. 7. 2012 Prague. Number of participants: 155 |
| MA | Seminars on 3.4 | Training of beneficiaries under Intervention area 3.4 – a change in grant provider, 15th call | Applicants Beneficiaries | 0 | 10. 7. and 29. 8. 2012 Prague. Number of participants: 155 + 21 |
| MA | IOP Annual Conference | Forms of social integration supported from EU | Professional and general public, mass media | 4 904 | 19–20 September 2011, Ostrava. Number of participants – approx. 120 persons |
| MA | “IOP pod lupou” (IOP under the Magnifying Glass) Newsletter | Topical information on IOP Successful projects Calls FAQ, etc. | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | Invoice has not been sent as yet | Conduct of a tender for a new company and the publishing of one issue (September 2012). Circulation of 500 copies, 5,000 copies in electronic form. It contains articles by MA and IBs, information on current calls and activities of IOP, etc. |
| MA | Webhosting and update of kvalitazivota.eu microsites | Information on successful projects | Applicants and beneficiaries General public Mass media | 454 | Information on successful IOP projects |
| CRD | Seminars on 2.1 | Training of beneficiaries under Intervention area 2.1 – a change in grant provider | Beneficiaries | 0 | 10. 7. 2012 Prague. Number of participants: 155 (the seminar was held by the MRD) |
| CRD | Seminars on 3.1 | Training of beneficiaries under Intervention area 3.1 – public contracts, monitoring reports, Benefit, eligible expenditure | Applicants Beneficiaries | 0 | 15. 5. (Prague - 3.1a) and 6. 9. (Prague – 3.1b, 3.1c) 2012. Number of participants: 35 + 50 (held in cooperation with MoLSA) |
| CRD | Seminars on 3.4 | Training of beneficiaries under Intervention area 3.4 – a change in grant provider, 15th Call | Applicants Beneficiaries | 0 | 10. 7. (Prague) and 29. 8 (Prague) 2012. Number of participants: 155 + 21 (seminars were held by MRD) |
| CRD | Seminars on 4.1 | Training of beneficiaries under Intervention area 4.1 – public contracts, administration of projects, project sustainability | Applicants Beneficiaries | 0 | 20. 6. 2012 Prague. Number of participants: 20 |
| CRD | Seminars on 5.2 | Training of beneficiaries under Intervention area 5.2 - Improving the environment in problematic housing estates | Applicants Beneficiaries | 0 | 23. 4. 2012 Jablonec n. Nisou. Number of participants: 7 |
| CRD | Workshop at the IOP Annual Conference | Development of project applications – How to develop a project | Applicants, beneficiaries | 0 | 19. 9. 2012 Ostrava. Number of participants: approx. 20 (held by IOP MA) |
| CRD | An article in professional journals | Introduction to the situation in Intervention area 5.2- Improving the environment in problematic housing estates | Applicants, beneficiaries, professional public, general public | 0 | A specialised article “European assistance helps improve the environment of Czech housing estates“ – IUDP topic. Focus on towns in Central Bohemia (Kladno, Mladá Boleslav), Panelák journal issue No 38 and 39, published also on www.panelovydum.cz server |
| CRD | Article in professional journals | Introduction to the situation in Intervention area 5.2- Improving the environment in problematic housing estates | Applicants, beneficiaries, professional public, general public | 0 | A specialised article “Regeneration of residential buildings funded from the European Structural Funds“ – IUDP topic, Bydlet v panelu journal, May 2012 |
| CRD | “IUDP” video series | Presentation of IUDP implementation through short videos based on comparative photo documentation of projects before and after, accompanied by commentary on individual IUDPs and facts | Professional public, general public | 2 143 | A total of 12 episodes of approx. 90 sec. each, posted on CRD website, EU programmes > Projects section |
| CRD | Internet in state administration and self-government conference | Presentation of CRD CR activities, including consultations, intermediary and control activities of CRD in selected EU programmes | Representatives of self-governments | 0 | 2. – 3. 4. 2012 (Hradec Králové) – a total of 2,387 participants |
| CRD | www.risy.cz website | On-going publishing and updating of information | Applicants and beneficiaries, general public, professional public | 0 | Website is updated throughout the year |
| CRD | www.crr.cz website | On-going publishing and updating of information | Applicants and beneficiaries, general public, professional public | 0 | Website is updated throughout the year |
| CRD | Number of replies to enquiries | IOP enquiries | Applicants and beneficiaries | 0 | 4/2012-9/2012: a total of 24 registered e-mail enquiries; 1,000 unregistered e-mail enquiries (estimate); 1 800 telephone enquiries (estimate) |
| MoC | Seminar - amendment to Act on public contracts | Workshop for aid beneficiaries under IOP IA 5.1a, b,c Changes in the field of public arising from the amendment to Act No 137/2006 Coll. | Beneficiaries | 1 030 | 17.4.2012; Prague; 48 participants |
| MoC | How to develop a project - methodology, financial flows, accounting, MR, application for payment, notification of the change of beneficiary, public procurement procedures, project revenues… | “How to administer a project” seminar for beneficiaries under IOP IA 5.1. – 3rd call | Beneficiaries | 0 | 15.08.2012; Prague; 10 participants |
| MoC | Consultations on projects | Consultations with project and financial managers | Beneficiaries | 0 | 13 consultations, a total of 56 participants |
| MoC | Number of replies to enquiries sent via www.kultura-evropa.eu iop@mkcr.cz | Enquiries concerning IOP 5.1 a,b,c | Applicants and beneficiaries General public | 0 | 4/2012-9/2012: a total of 4 enquiries |
| MoC | Photo documentation of projects | For the purpose of creating printed materials, website | General public | 1 979 | A total of 5 projects |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – drawing and colouring books | General public | 3 596 | Drawing and colouring book |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – Pairs (game) | General public | 1711 | Pairs (game) |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – Stickers featuring characters | General public | 389 | Stickers featuring characters |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – PF 2013 | General public | 700 | PF 2013 |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – fold | General public | 2 380 | Fold |
| MoC | Graphic services | Graphic design of printed materials for publicity of IA 5.1 of IOP – A6 notepads | General public | 188 | A6 notepads |
| MoC | Printed materials | Stickers to label the objects purchased thanks to the assistance | Applicants and beneficiaries+general public | 212 | Stickers 90x20 mm |
| MoLSA | www.mpsv.cz website | On-going publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | Website is updated throughout the year. Updated information concerns particularly the following sections: news, calls, tenders, replies to the most frequently asked questions, events, list of beneficiaries, tenders, contacts, dates of Selection Committee meetings. |
| MoLSA | Information on website | Information on the 8th call (activity 3.1c) | Applicants | 0 | On the website with information on support: http://www.edotace.cz/dotacni-deni/prodlouzeni-vyzvy-c-8/ On the website of the Association of Small and Medium-sized Enterprises and Crafts: http://www.amsp.cz/investicni-podpora-socialni-ekonomiky On the website of the Czech Chamber of Commerce http://www.komora.cz/zpravodajstvi-a-media/aktuality-4/firmy-a-podnikatele/mpsv-prodlouzilo-lhutu-pro-podavani-projektovych-zadosti.aspx |
| MoLSA | Number of replies to enquiries related to Intervention areas 3.1 and 3.3 | Enquiries related to IOP | Applicants General public | 0 | 4/2012-9/2012: For Intervention area 3.1, a total of 255 e-mail enquiries, 56 one-to-one consultations For Intervention area 3.3, a total of8celkem 1va.maderova@mpsv.cz. ncíh ozvučení je potřeba 154 e-mail enquiries, 168 telephone enquiries, 30 one-to-one consultations |
| MoLSA | Seminars and training courses for applicants and potential beneficiaries | Continuous call No 4, IA 3.3 Scheduled continuous call No 9, IA 3.3 | Applicants and beneficiaries | 95 | 3.4.2012 Prague, 21 participants 23.4.2012, Prague,16 participants |
| MoLSA | Seminars and training courses for applicants and beneficiaries | Continuous calls No 6, 7, 8 IA 3.1 | Applicants and beneficiaries | 155 | Prague 7x: A total of 7 seminars for activities a),b),c); a total of 73 persons |
| MoLSA | Articles in press | IA 3.1 | General public | 4 393 | Information on call for 3.1c published in a journal |
| MoLSA | Articles in press | IA 3.1 | General public | 0 | Information on the absorption of funds in Intervention area 3.1a) call No 7 of IOP will be published in the May issue of the Newsletter of the National Centre |
| MoLSA | Conferences and other specialised seminars and a public hearing for the sake of publicity of activities under IA 3.1 | IA 3.1 | General public Professional public | 232 | On 25. – 26. 4. 2012 the participation of MoLSA as a lecturer in the conference held in cooperation with the National Centre for Support of the Transformation of Social Services called “Role of municipalities in the transformation of social services“. The MoLSA took part in the conference called “Trends of social entrepreneurship in the CR and in Europe” held on 12. 9. 2012 On 19. – 20. 9. 2012 MoLSA was a co-organiser of the IOP Annual Conference – Quality of life in Ostrava together with MRD CR and the Municipal Authority of Ostrava. Number of participants was approx. 120 persons. |
| MoLSA | Promotional merchandise | Promotional merchandise with IOP logos | Applicants and beneficiaries General public Evaluators Implementation entities |  | A total of 16 types of promotional merchandise (such as notepads, spiral notebooks, paper folders, pens) |
| MoI | www.osf-mvcr.cz website | On-going publishing of information and updating of the website | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 2 934 | Website is updated throughout the year. Website traffic 4/2012-9/2012 – 52,723 visits |
| MoI | projekty.osf-mvcr.cz website | Presentation of successful projects of IOP and OP HRE | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 (paid already in the previous period) | Website is updated throughout the year. Website traffic 5/2012-9/2012 – 744 visits |
| MoI | Number of replies to enquiries related to IA 1.1 | Enquiries regarding the IOP | Applicants and beneficiaries General public | 0 | 4/2012-9/2012: a total of approx. 4,000 enquiries (e-mail, telephone and one-to-one consultations; online advisory centre on www.osf-mvcr.cz ) |
| MoI | Seminar for public administration | Beneficiaries under IA 1.1 | Beneficiaries from among public administration | 1 352 | 25. 6. 2012 in Prague, 27 participants |
| MoI | PR for general and professional public | PR | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | PR articles: European money to improve the quality of addressing emergency situations (15. 5. 2012) http://www.osf-mvcr.cz/evropske-penize-zkvalitni-reseni-mimoradnych-udalosti Digitisation and computerisation enters also the archives (31. 8. 2012) http://www.osf-mvcr.cz/digitalizace-a-elektronizace-vstupuje-take-do-archivu Computerisation makes the administrative procedure more effective and fast (26. 9. 2012) http://www.osf-mvcr.cz/elektronizace-zrychluje-a-zefektivnuje-spravni-rizeni Series of interviews with beneficiaries: Structural Funds contribute to permanent and safe storage of electronic documents http://www.osf-mvcr.cz/rozhovor-1 Twitter: account management, regular updates |
| MoI | Advertisements in eGovernment publication (Objectives, trends and approaches to its evaluation) | Computerisation of public administration | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 1 386 | Together with OP HRE |
| MoI | Advertisements in Hospodářské noviny daily (Podnikání) | European money helps modernise public administration | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 1 331 | 10. 9. 2012 |
| MoI | Advertisements in Ekonom periodical | European money helps modernise public administration | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 1 999 | 13. 9. 2012 together with OP HRE |
| MoI | Advertisements in Respekt periodical | European money helps modernise public administration | Applicants and beneficiaries General public Professional public Evaluators Implementation entities Mass media | 0 (included in the price above) | 10. 9. 2012 together with OP HRE |
| MoH | www.mzcr.cz website | Updating of information for the general public | Applicants and beneficiaries General public Evaluators Implementation entities Mass media | 0 | Continuous publishing of information and updates of information on www.mzcr.cz website, especially in the field of calls, project implementation, publicity, etc. It is done throughout the year. |
| MoH | One-to-one, written, telephone and e-mail communication | Consultancy | Applicants and beneficiaries General public | 0 | Information for potential applicants/beneficiaries. From 1.4. 2011 to 30.9.2012 a total of 63 one-to-one consultations was registered. |
| MoH | Training course on the amendment to Act on public contracts which took effect on 1 Apr 2012 | Introduction to the amendment to Act on public contracts | Beneficiaries and applicants Implementation entities | 1 486 | On 3.4.2012 beneficiaries and EF staff were introduced to the amendment to Act on public contracts. Topical information was provided to beneficiaries under the 8th call. |
| MoH | Printing and framing of photographs of “good practice examples” | Examples of good practice | General public | 172 | Collages of photographs of successful projects, taken in 2011 (8 pieces). They were placed in the corridors in the part of the building where the EF Department is located for the sake of presenting IOP. |
| MoH | www.kvalitazivota.cz website | Examples of good practice in IOP | General public | 0 | On-going posting of information on successful projects from Intervention area 3.2. |
| MoH | A seminar for applicants | A training course for applicants under the 11th and 12th call for IA 3.2 of IOP | Applicants under the 11th and 12th call | 192 | On 6.9.2012 a seminar for applicants was held in Prague (under the 11th and 12th call) attended by 12 participants. |
| MoH | A seminar for beneficiaries | A training course for beneficiaries under the 9th and 10th call for IA 3.2 of IOP | Beneficiaries under the 9th and 10th call | 240 | On 19.9.2012 a seminar for beneficiaries was held in Prague (under the 9th and 10th call) attended by 19 participants. |
| MoH | A workshop with the representatives of the MoH of the Slovak Republic | Exchange of experience with abroad | EF | 1 278 | The workshop was held in Brno on 3. – 4. 9. 2012, it was attended by representatives of the MoH of the Czech and Slovak Republics. A total of 23 participants. The main topics were sharing experience in the field of project checks, checks by external entities, etc. |

## Annex No 2 – Action Plans

Action Plan from the Evaluation of Communication and Publicity Activities of IOP

| Recommendation of the evaluator | IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOM-PLISHED | CORRECTIVE MEASURE | DEAD-LINE | ACCOM-PLISHED |
| To direct the regular meetings of publicity staff of individual Intermediate Bodies toward the creation of uniform concept of IOP publicity. | Meetings of Working Group for communication of IOP | The next meeting in 07/2011, then on a continuous basis | 14. 7. 2011, 3. 11. 2011, 17. 1. 2012 | Participation in meetings of the Working Group for communication of IOP | Next meeting in 07/2011 | 14. 7. 2011, 3. 11. 2011, 17. 1. 2012 |
| To create a concept which should focus on the provision of information to the public on how and by what the individual areas supported from IOP improve and enhance the quality of life. For the sake of setting the concept “Quality of My life” to motion and for the sake of successful implementation of communication activities it is useful to have the whole process supervised by an expert, who has experience with marketing communication and introduction of similar changes in communication. | To translate the theoretical concept to specific tools of communication and publicity. To prepare a tender and to hire a creative supervisor, who will be tasked to compile a “cookbook” for the application of the concept primarily with the use of the following three tools: 1. Internet (microsites), 2. printed matters, 3. Events | 06-09/2011 | On 14.8.2011 the services of a creative supervisor were ordered, in November 2011 the manual of the “Quality of My Life” concept was introduced | One representative of each IB shall participate in the communication with the creative supervisor and will thus help fine-tune the concept. | 06-09 2011 | 30.8.2011 meeting of the WG for communication of IOP with the creative supervisor |
| To use the topical themes to promote the IOP benefits – e.g. in the light of health care crisis to provide for media coverage of the benefits of Priority axis 3, to which the largest volume of funds of the whole programme is allocated, the interest of media in this priority axis, however, was inadequate bearing in mind the amount of allocation. | Creation of microsites in the spirit of the “Quality of My Life” concept, which will in a visually-attractive and user-friendly form present the IOP successful projects. Publishing of information on successful projects on the Structural Funds website, in IOP newsletter, elaboration of a publication with successful projects, etc. | Continuously | On 4. 1. 2012 an invitation to tender was published for the creation of the IOP information portal (microsites), 3/2012 creation of kvalitazivota.eu microsites |  |  |  |
| In order to increase the impact of IOP communication and publicity activities on the general public, it is suitable to exploit especially the TV and Internet campaigns that would concentrate on the presentation of implemented projects and their benefits for the general public. | TV – since it is very costly, this tool will be exploited only exceptionally Internet – once the simple information interface (microsites) is created, to launch a web campaign for this interface, where the information, pictures, video recordings etc. on successful IOP projects will be posted. | 11/2011 – 1/2012 | On 16 May 2012 the IOP Facebook profile was launched | WG for communication participates on an on-going basis | 11/2011 – 1/2012 |  |
| For the professional public, a suitable tool seems to be the Internet in general (Internet campaign) and the IOP website. | Internet - once the simple information interface (microsites) is created, to launch a web campaign for this interface, where the information, pictures, video recordings etc. on successful IOP projects will be posted. | 12/2011 - 2/2012 | 3/2012 creation of microsites. On 16 May 2012 the IOP Facebook profile was launched | WG for communication participates on an on-going basis | 12/2011 – 2/2012 |  |
| It is necessary to add the strategic background to the individual annual CoPs, which means to evaluate the progress in the fulfilment of CoP objectives to get a complete picture of key tasks in the long run and then to decide about the priorities for the given year. | To conduct annual external evaluations of communication activities and based on these evaluations to create a “strategic background“, which will partly be evaluated internally and partly externally in the framework of annual evaluations (always in the following year). In 2011, the main aim is to develop the referred to concept, the partial evaluation of which will be an integral part of the annual evaluation. | 1st Q 2012, 1st Q 2013 etc. | Conduct of external evaluation was postponed to 2013. It has been concluded that there is no reason for conducting evaluations every year and it is more fitting and cost -effective to conduct an external evaluation every two years. |  |  |  |
| The annual CoPs should specify and quantify the communication objectives. It is then possible to evaluate the level of fulfilment of these objectives in individual years. The level of fulfilment of objectives of the framework CoP can be evaluated in relation to the defined target values of impact indicators. | To set out impact indicators on the basis of annual evaluations and to reflect them in individual annual communication plans. | 1st Q 2012, 1st Q 2013 etc. | Communication objectives for 2012 were set out based on the evaluation of communication plans for 2011 and also monitored are communication objectives defined by the external evaluation in the first half of 2011. | To set out impact indicators on the basis of annual evaluations and to reflect them in individual annual communication plans. |  | Communica-tion objectives for 2012 were set out based on the evaluation of communication plans for 2011 and also monitored are communication objectives defined by the external evaluation in the first half of 2011. |

Action Plan from the Evaluation of the Progress of Implementation of IOP Priority axis 4 (National support of tourism) with respect to the achievement of the set out programme objectives

| Recommendation of the evaluator | IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOMPLISHED | CORRECTIVE MEASURE | DEAD-LINE | ACCOM-PLISHED |
| Recommended prices common at the given time and place (page 4) | a) To conduct an analysis of evaluation of economy, efficiency and effectiveness of project costs b) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria c) To modify the structure of the Supporting documents for quality evaluation – to modify the structure of detailed itemised budget; to detail the content of the baseline analysis – to add the requirement for calculation of costs, preliminary market research to ascertain the prices, to insist on the specification of project activities d) To modify the list of eligible expenditure – only such expenditure will be eligible that has a direct link to project activities (to exclude labour costs and expenditure beyond the mandatory publicity from eligible expenditure) e) To train the evaluators – when evaluating the prices the evaluator shall give justification with a reference to the source used | a) 2nd Q 2012 b) 31. 5. 2011 c) 5. 9. 2011 d) 5.9.2011 e) 4., 6. 10.2011 | a) Accomplished to a certain degree – in January 2012 Mr Vaníček conducted an evaluation of economy and efficiency of CzechTourism projects based on project applications. The IOP MA commissioned the conduct of analysis of tools for 3E control across IOP. At the 9th MC meeting the MA submitted the information on the status of accomplishment, at the autumn meeting it will present the final analysis and its application. The IOP MA also commissioned the elaboration of external opinions focused on 3E in selected projects with Ernst & Young experts. b) Yes c) Yes d) Yes e) Yes |  |  |  |
| To modify the system of evaluation (page 4, 30, 48,33,35) | a) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria b) To issue a methodological guideline introducing new evaluation criteria c) To issue a methodological guideline - to modify the procedure for evaluation of project quality d) To train the evaluators | a) 31. 5. 2011 b) 13. 7. 2011 c) 31. 8. 2011 d) 9/2011 | a) Yes b) Yes c) Yes – from 5.9.2011 d) Yes - 4., 6. 10.2011 |  |  |  |
| To push stronger for the submission of quality projects (page 24, 27, 29, 68) | a) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria b) To modify the structure of the Supporting documents for quality evaluation – to modify the structure of detailed itemised budget; to detail the content of the baseline analysis – to add the requirement for calculation of costs, preliminary market research to ascertain the prices, to insist on the specification of project activities c) To train the CRD for eligibility checks – to return the project application for completion in the event the project activities are not specifically described and a detailed project budget is not included | a) 31. 5. 2011 b) for the next call c) for the next call | a) Yes b) Yes – from 5.9.2011 c) Yes – from 13. 9. 2011 |  |  |  |
| To ensure the adherence to set out project timetables (page 35) | a) To consistently see to the adherence to procedures of administration of changes in projects | a) Continu-ously | a) Continuously | a) The CRD shall consistently see to the adherence to the procedure of administration of changes in projects – imposition of sanctions in case of late submission of the Notification of changes in the project (once a delay occurs in the timetable of implementation) b) Recommendation to Tourism Dept. and CzT beneficiaries to optimize the timetables of project implementation | a) Continuou-sly b) 31. 8. 2011 | a) Continuou-sly b) Accomplished – Tourism Department made changes in its projects, CzT cut the project budgets, where savings were achieved based on tenders. |
| To ensure maximum economy and effectiveness of expenditure (page 35 - points 2 and 4) | a) To conduct an analysis of evaluation of economy, efficiency and effectiveness of project costs; to conduct a survey in order to identify the possibilities of exploiting external experts for the 3E assessment b) To modify the list of eligible expenditure – only such expenditure will be eligible that has a direct link to project activities (to exclude labour costs and expenditure beyond the compulsory publicity from eligible expenditure) c) To supplement HAB with the information that no new activities can be added to projects d) To modify the evaluation criteria – to award higher score to criteria assessing 3E, project quality and to diminish the significance of specific criteria e) To modify the structure of the Supporting documents for quality evaluation – to modify the structure of detailed itemised budget; to detail the content of the baseline analysis – to add the requirement for calculation of costs, preliminary market research to ascertain the prices, to insist on the specification of project activities f) To train the evaluators – the evaluators can propose the cuts in eligible expenditure in the event of non-compliance with 3E; consistent justification of 3E evaluation | a) 2nd Q 2012 b) for the next calls c) for the next calls d) 31. 5. 2011 e) for the next calls f) 9/2011 | a) To a certain degree – MA exploited the NCA offer to have the checks conducted and opinions elaborated by Ernst & Young experts b) To a certain degree - reduced was only expenditure on compulsory publicity c) Yes – from 5.9.2011 d) Yes e) Yes – from 5.9.2011 f) Yes - 4. and 6. 10. | During the checks of applications for payment the CRD shall consistently adhere to the procedures for 3E control | Continu-ously |  |
| To modify the PD for reasons of non-fulfilment of the objective “To increase the number of entities connected to the reservation system“ and non-fulfilment of MI No 413305 Number of new information and reservation systems in tourism and No 413311 Number of entities operating in tourism connected to the reservation system. (page 41 and 45) | To draft a proposal for changes in PD and to send it to the EC for approval | 7/2011 | Yes – sent to SFC2007 29.7.2011 |  |  |  |
| To introduce ceilings for labour costs for individual positions in the project team (page 47) | Partly accepted – the list of eligible expenditure will be modified – labour costs will not be considered eligible in the following calls | For the following calls | No – Labour costs continue to be eligible expenditure in the amount of 9 % of total eligible expenditure of the project. The remuneration of project team members shall be with respect to the nature of beneficiaries (GA and organisations established by them) in line with Government Order No 564/2006 Coll., as amended. |  |  |  |
| To introduce fixed price ceilings in key budget items (page 49, 67) | Partly accepted – fixed price ceilings are not set, therefore they cannot be incorporated in the documentation a) To conduct an analysis of evaluation of economy, efficiency and effectiveness of project costs b) To conduct a survey in order to identify the possibilities to use external experts for 3E evaluation c) To suggest to the PCA and NCA to propose a system solution of evaluation and control of 3E | a) 2/ 2012 b) 12/2011 c) accomplished | a) Partly accomplished - IOP MA commissioned a conduct of analysis of tools for 3E control across IOP. At the 9th MC meeting the MA submitted the information on the status of accomplishment, at the autumn meeting it will present the final analysis and its application. b) MA exploited the NCA offer to have the checks conducted and opinions elaborated by Ernst & Young experts c) Yes |  |  |  |
| Introduction of the annex to the Supporting documents for evaluation of project quality – itemised budget of key project expenditure in a recommended structure (page 47) | To modify the structure of the Supporting documents for evaluation of quality – to modify the structure of a detailed itemised budget; | For the following calls | Yes – from 5.9.2011 |  |  |  |
| To launch the preparation of the State Tourism Policy Concept for 2013+ period | To write a letter to the Deputy Minister for Regional Development and Tourism with an appeal to accelerate the preparations of the State Tourism Policy Concept for 2013+ period | June 2011 | Yes – on 16.6.2011 the letters was sent |  |  |  |

Action Plan from Analysis of Administrative Capacities and Outsourcing of IOP Intermediate Bodies

| Conclusions | IOP Managing Authority | IOP Intermediate Bodies |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEAD-LINE | ACCOMPLI-SHED | CORRECTIVE MEASURE | DEAD-LINE | TO BE DONE BY | ACCOM-PLISHED |
| 1. Total financial costs of IB in relation to the administered allocation Major differences in financial costs related to the administered allocation of the programme between the group of Intermediate Bodies (MoH, CRD and MoC) with CZK 1 000 per 1 million of administered allocation and MoI, MoLSA with costs by 50 – 80 % higher. | IOP MA in cooperation with the Intermediate Bodies will conduct an in-depth analysis of the extreme values with the view to clarify this difference, or to eliminate it. | By 31.12.11 | Based on the data as of 31.12.2011 an analysis covering the whole year of 2011 will be conducted and presented at the 9th MC meeting | With regard to the extreme values, the individual IBs shall propose adequate measures to eliminate the risks arising from these results and shall inform the IOP MA about the proposed measures. | 15.11.2011 | MoI MoLSA | MoI – sent to the MA on 8.11. 2011 Settlement of comments sent to the MA on 8.12.2011 MoLSA – in the course of November and December 2011 the MoLSA held internal working meetings in order to reduce the administrative costs of minor part-time employment contracts of MoLSA staff involved in the IOP implementation. The internal meetings at MoLSA resulted in the reduced total number of MoLSA staff involved in the IOP implementation by 13 persons, i.e. from original 48 (July 2011) to 35 (December 2011). |
| 2. Total financial costs of administration of 1 project incurred by the IB Semi-annual costs per 1 approved project at the MoC and MoLSA exceed CZK 300 thousand as compared to the other IBs, where they range from 8 to 100 thousand. | IOP MA in cooperation with the Intermediate Bodies will conduct an in-depth analysis of the extreme values with the view to clarify this difference, or to eliminate it. | By 31.12.11 | Based on the data as of 31.12.2011 an analysis covering the whole year of 2011 will be conducted and presented at the 9th MC meeting | With regard to the extreme values, the individual IBs shall propose adequate measures to eliminate the risks arising from these results and shall inform the IOP MA about the proposed measures. | 15.11.2011 | MoC MoLSA | MoC – 1. 2. 2012 the reasoning of the extreme value was sent, MoLSA cooperated with IOP MA on the evaluation of barriers to absorption of funds under IA 3.1 and IA 3.3. Based on this evaluation the procedures and deadlines for the administration of projects under IA 3.1. and IA 3.3 were modified in the framework of revision of the Handbook of Work Procedures. |
| 3. Number of FTE in relation to the administered allocation Number of FTE involved in the administration of IOP at MoLSA per 1 billion of allocation is the highest of all the IBs (10.99 FTE), in the other IBs it ranges from 3.34 to 5.83 FTE per CZK 1 billion of the administered allocation. |  |  |  | MoLSA shall present reasons for the high number of part-time employees involved in IOP administration and covered from IOP TA and shall explain why the number has doubled since the end of 2010. | 15.11.2011 | MoLSA | Accomplished together with the corrective measure referred to under point 1 above. Starting with 1.12.2011 the number of part-time contracts was reduced by 3.1 FTE and by 13 persons involved |
| 4. Comparison of the structure of total financial costs of IBs High share of costs of outsourcing at MoI with respect to the high number of FTE, compared to the other IBs. | Revision of HAB in IOP TA, the IOP MA shall approve the project application and project budget prior to the project submission. Expenditure on activities, not approved in advance by the IOP MA in writing, will be considered ineligible. | 1.9.2011 | 1.9.2011 | The MoI shall submit to the IOP MA an analysis of the need for individual outsourced services and description of the management and control system of suppliers of outsourced services. | 15.11.2011 | MoI | MoI - Sent to the MA on 8.11. Settlement of comments sent to the MA on 8.12. |
| 5. Comparison of the structure of FTE Increasing share of FTE and costs of AWP/ AWA at the expense of skeleton staff at the MoI. |  |  |  | The MoI shall submit to the IOP MA an analysis of the need of AWP/AWA, which will contain: - detailed justification for the need of such a high number of FTE under AWP/AWA, - identification of activities performed by these persons, - management and control system of the work done under these agreements, - system of education and development of these employees. In case there is no system of management, control , education and development in place at the MoI, the MoI shall submit it to the MA by 31 Dec 2011. | 15.11.2011 | MoI | MoI - Sent to the MA on 8.11. Settlement of comments sent to the MA on 8.12. |
| 6. Mapping the administrative capacity | The IOP MA shall map the performance of administrative capacity at individual IBs. | Always as of 30.6. |  |  |  |  |  |
|  | The IOP MA shall extend the scope of regular reporting of administrative capacities as of 31 Dec of each calendar year and shall incorporate in this report also the obligatory description of the forecast for the following year. | By 31 January for the previous year | 31.1.2012 sent by all the IBs | The IBs will incorporate the description of the need for the following year in the Report on administrative capacities. | By 20 January for the previous year | All IBs | 31.1.2012 sent by all the IBs |
|  | The IOP MA shall prepare a form for reporting administrative capacities and shall send it to the IBs. | 31.11.2011 | 10.1.2012 the form sent to the IB |  |  |  |  |
| 7. Recommendations for controls | The IOP MA shall target the control of delegated activities on administrative capacity. | Continuous-ly | Monitoring visit No 19/2012/I was paid to the MoI |  |  |  |  |
|  | The IOP MA shall reflect the risks ensuing from this evaluation in the update of the Catalogue of IOP Risks. | 31.12.2011 | It will be reflected in the Catalogue of Risks as of 31.12.2011 |  |  |  |  |
|  | The IOP MA shall prepare the “Analysis of matters related to 3E evaluation in IOP“ with the view to identify the possibilities of 3E control in IOP projects, incl. the possibilities of 3E control in TA projects. | 2nd Q 2012 | At the 9th MC meeting the MA submitted information on the status of accomplish-ment, at the autumn meeting it will present the final analysis and its application. |  |  |  |  |
| 8. Recommendation concerning the simplification for 2014-2020 period | For the preparation of 2014-2020 period to verify the effectiveness and cost-effectiveness with the involvement of 2 IBs in the implementation of one IA in the context of elimination of a risk or anticipated effect related to the involvement of 2 IBs. | Continuous-ly |  |  |  |  |  |

Action plan from the Audit on implementation of projects under the 1st call for Intervention area 3.2 of the Integrated Operational Programme

| Recommendation of the evaluator | Intermediate Body of the Ministry of Health |
| --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOMPLISHED |
| In this context we recommend to draft binding model purchase contracts for medical devices or purchase contracts for services (management and publicity), with the beneficiary being entitled to deviate from the binding model in duly justified cases. In our opinion, the requirements for EF Department capacity would decrease since only the changes made by the beneficiary (in the change procedure) and not the whole document would have to be checked. Similar procedure could be followed in case of contract documents, or other documents, that the MoH is obliged to check and that show a certain degree of uniformity. | a) To elaborate a model structure of contract documents in individual types of contracts – devices, management and publicity, and to post it on the web. | 30.9.2011 | a) Accomplished - on 19.10.2011 the model contract documents for the purchase of devices and calls for small-scale public contracts for the purchase of management and publicity services were published on www.mzcr.cz website. On 20.3. the model contract documents for purchase of devices (below-the-threshold and above-the-threshold open procedure) were published on www.mzcr.cz website in line with amendment to APC effective from 1.4.2012. |
|  | b) To stipulate that the draft contract, including the trade terms, shall always be included in contract documents in contracts of higher value | By the announcement of the next call, otherwise as recommended | b) Partly accomplished – incorporated in HAB for the 9th and 10th call as a recommendation – recommendations from the audit of implementation of projects of the 1st call were influenced by the fact that within the projects devices and equipment were simply purchased, which is why it is not difficult to draft a contract. Since in the 9th and 10th call much more complicated projects will be implemented, it would be a great challenge for lawyers of the beneficiary to draft a binding draft contract. The binding draft contract as an integral part of the conditions of the tender will be required in case another call is announced for Intervention area 3.2a, with a simple purchase only. |
|  | c) To elaborate a model structure of a draft contract in individual types of contracts – devices, management and publicity, and to post it on the web. | 30.9.2011 new deadline set at 31.05.2012 | c) Accomplished – a binding guideline was issued concerning the HAB for all the calls of 10 July regarding the model handover protocol and the statements of work. The model contract, in which the beneficiaries would enter only the type of the device, price and the date of delivery, cannot be used since the contractual conditions always vary. For the 13th call the HAB will stipulate the requirement to include the draft contract in tender documentation. |
| Therefore we recommend to complement the existing or to draft a new checklist of documents which shall be a component part of documents included in the project file for each public procurement procedure. The existence of such a checklist would considerably reduce or eliminate the potential omission of any important document caused by human factor. This checklist would be made by the beneficiary at the commencement of works on public procurement procedure and submitted at fixed intervals to the project manager at the MoH for check, together with the documents that the beneficiary is obliged to forward to the implementing authority. In order to simplify the follow-up check, we recommend expanding the scope of documents archived by the MoH in order to have the full set of documents available at the MoH. To this end e.g. the checklist recommended in the point above can be used. | a) To propose a binding form of the structure of documents for tenders in the project file in archives. | 31.8.2011 new deadline set at 31.05.2012 | a) Accomplished – posted on the website http://www.mzcr.cz/Unie/dokumenty/dokumenty-k-verejnym-zakazkam_5276_1138_8.html |
|  | b) To include in the individual checklists for the check of individual steps of tenders and public procurement procedures the notes referring to the specific documents, pursuant to which the given question is checked, since the wording of majority of questions is pretty vague | 30.9.2011 New deadline set at 31.05.2012 | b) Accomplished – the valid checklists always refer to the relevant section governing the checked point. The type of document is stipulated in the respective section of the Act. Moreover, the checklists are newly complemented with the checklists compiled by the EC. |
|  | c) To use a list of mandatorily created and archived documents by individual type of tender/ public procurement procedure in the checks of the course of tenders and to send this list to beneficiaries, who will gradually mark in the list those documents which are already available to them in the tender and will send it together with the documents to be checked. | 30.9.2011 | c) Accomplished - On 28.7.2011 a new tab Documents to public contracts was created on www.mzcr.cz website in the European funds/IOP/Documents section. Under this tab the recommended list of documents for individual types of tenders by the foreseen value was published, which was defined in the corrective measure, posted under this tab were also e.g. model checklists for individual stages of control of public contracts by EF Department in order to inform the beneficiary about the pitfalls of the conduct of public contracts. Under this tab also other documents defined in the framework of other corrective measures will be published. Moreover, an information e-mail about the creation of the new tab, together with the List of documents for public contracts, was sent to beneficiaries. |
| We also recommend introducing a uniform system of files or directories in paper and electronic project files. This unification should consist in the development of a single structure of files (directories), creating versions of documents, rules for assigning names to files (directories) etc. We recommend arranging all the documents in the project files by their logical place in the process of public procurement procedure and not according to the date of delivery (naturally, the date of delivery has to be properly recorded). | a) To create a uniform binding structure of project files on “O” (the shared disc), which shall correspond to the structure of the paper file in the archive. | 31.8.2011 | a) Accomplished - On 18.8.2011 at the meeting of the department, the binding structure of project files on the O disc was presented. The employees received the graphic layout both in paper version and on the O disc. Gradual modification of files for individual calls will be done, which is under the responsibility of individual financial and project managers. The drafted proposal for the structure of the paper file will be used starting with projects under the 8th call. |
| We recommend to reconsider the approach to public contracts in case the contracting entity receives one bid only; if in such a case the beneficiary withdrew the public procurement and announced a new one, it would contribute to better transparency of the process of the award of public contracts and perhaps also to a lower purchase price. In case the contracting entity received again the bid from one supplier only, the public procurement procedure would take place in a standard manner. This procedure is common in some other operational programmes (e.g. OP Environment). | a) The obligation to withdraw a public contract in case of the receipt of one bid only. | Accomplished | a) Accomplished in January 2011 –through the adoption of Anti-corruption Strategy of MoH |
|  | b) To set up a system which makes it possible to continue with the public procurement procedure in case of one bid only, i.e. potential exceptions to the Order of the Minister, which is too strict and does not facilitate the possibility suggested in the recommendation – i.e. to continue in a public procurement procedure in case of repeated public contract or in other special cases. | 31.7.2011 | b) Accomplished - On 8.8.2011 the meeting of senior officials approved the Procedure for the control of the Order of Minister No 11/2011 Anti-Corruption Strategy for directly managed organisations, on this procedure was sent to beneficiaries and published on www.mzcr.cz website under the tab Documents for public contracts. Simultaneous, the IB and MA were informed about this document by the person responsible. |
| We recommend considering the practice of stating the technical qualification prerequisites in the form of a reference to the financial volume of past contracts in order to avoid excessive concentration in the sector. The qualification defined in financial terms results in the putting up of major barriers to the entry in the sector and in forming monopolistic and oligopolistic structures composed of established players. | a) To set out general rules for the application of technical qualification prerequisites – setting out of recommended limits of the volume of reference contracts and the amount of turnover with respect to the object of the contract. | 31.7.2011 | a) Accomplished - On 8.8.2011 the meeting of senior officials approved the Procedure for the control of the Order of Minister No 11/2011 Anti-Corruption Strategy for directly managed organisations, on this procedure was sent to beneficiaries and published on www.mzcr.cz website under the tab Documents for public contracts. Simultaneous, the IB and MA were informed about this document by the person responsible. |
| For the sake of better comparability and check of items, we recommend obligating the bidders in the next calls to identify the devices in line with the relevant standards of fit-out so that each item is easily identifiable and comparable in the budget, tender documents, bids and the contract. Unambiguous identification should consist in the consistent description of the item in line with the standard as well as the stated number of pieces. | a) To introduce a clear requirement that the names (of devices) of items shall be the same as the names used in the standards for fit-out. The same names shall be used in the project budget and the tender documents, draft contract, concluded contract and ideally also in the invoice. The specific type of a device with its name shall be a mandatory component of the contract, hand over protocol and invoice. | By the announcement of the next call | a) Partly accomplished – it is stated in HAB for the 9th and 10th call as a recommendation to always use the same names, these calls are not intended for activity 3.2a, where the standards of purchased devices and equipment are set out. The corrective measure will be fully implemented in the documentation for the 13th call (activity 3.2a.) |
|  | b) To consistently check the observance of this rule at individual stages of the project (e.g. at the stage of submission of the application, evaluation of the notification of changes, evaluation of tender documents etc.). | By the announcement of the next call | b) Partly accomplished – it is stated in HAB for the 9th and 10th call as a recommendation to always use the same names, these calls are not intended for activity 3.2a, where the standards of purchased devices and equipment are set out. Partly addressed by the binding guideline of 10 July. It will also be stated in HAB for the 13th call. |
| The quality of elaboration of the checked tender documents created by the beneficiaries varies a lot, mainly as concerns the details of technical parameters. In this context we recommend that the Ministry of Health develops a uniform methodology for the creation of tender documents in tenders for the purchase of medical devices. This methodology should among other things contain the principles governing the setting up of a team responsible for the creation of tender documents (the team should be composed of medical doctors, a biomedical engineer, a clinical engineer, an IT expert, an economist, an expert at trade in medical devices and a trade law expert) so that the professional aspects of the purchase as well as necessary check are guaranteed through the participation of multiple independent professions. Moreover, the principles governing the creation of tender documents should prevent the emergence of a situation in which the parameters are set in a way to fit one supplier only. Since the quality of checked bids varied a lot and the technical parameters of devices included in the bid were not always adequately described, the methodology should also include the standards for the elaboration of technical description of items included in the bid. | a) To elaborate a uniform methodology for technical specification in public procurement procedures. | 31.12.2011 New deadline set at 31.5.2012 | Ad a) and b) On 8.8.2011 the Meeting of senior officials approved the document with the summary of corrective measures, implemented by the European Funds Department within the reinforced risk management, within which provided to the Meeting of senior officials was also the summary of recommendations from KPMG audit (this Action Plan) stressing the need to address the corrective measure ensuing from this recommendation in a comprehensive manner across the MoH. The Director General in charge of the directly managed organisations was requested to consider the beneficial nature of this methodology for the health care sector. He considered this methodology beneficial. The main principles are included in the anti-corruption strategies of MoH CR which, together with model tender documentation available on the MoH CR website, are sufficiently instructive. Beyond the scope of this recommendations, on 15.8.the MoH started to conduct the Analysis of the market with medical devices and equipment based on the results of public procurement procedures published on the Public Procurement Information system since the beginning of 2008, which can be used by the MoH as one of the input sources when drafting the methodology. The analysis has already been conducted. Its output was presented at the Meeting of senior officials on 7.11.2011. |
|  | b) The elaborate recommendations for the creation of tender documents concerning the principles of their creation, namely in the form of recommendations of the MoH for directly managed organisations and through its application also for the other beneficiaries. | 31.12.2011 New deadline set at 31.5.2012 | b) Accomplished The main principles are included in the anti-corruption strategies of MoH CR which, together with model tender documentation available on the MoH CR website, are sufficiently instructive. |
| The tender documents should always state detailed information on the specific medical purpose for which the respective medical device is intended. Together with this purpose also stated should be the specific medical interventions to be performed by the device, their frequency and the resulting realistic usage of the device in the context of past and foreseen mix of activities performed by the respective workplace. The statement of the purpose will facilitate the selection of a more suitable device and also a more effective subsequent checks. Well described purpose stated in tender documents (together with the price limit that cannot be exceeded) can help prevent the purchase of devices with inadequate parameters at extortionate price. The support granted from EU Structural Funds frequently leads to the situation when the beneficiary with an approved budget states the maximum price and asks the manufacturer to offer the best device available at this price. This essentially rational conduct is conducive to the purchase of overly advanced (therefore also overly expensive) devices. | a) To stipulate that the medical purpose shall be stated in the tender documents. | Accomplished | a) January 2011 – accomplished by the adoption of Anti-Corruption Strategy of MoH |
|  | b) To perform consistent check of the statement of the medical purpose in the framework of checks of tender documents. | Continuously | b) Being accomplished on a continuous basis |
|  | c) The obligation to state the medical purpose in the technical specification annex already at the time of submission of the application for support – modification in the Handbook for applicants and beneficiaries. | By the announcement of a new call | c) Partly accomplished - incorporated during the preparation of the 9th and 10th call, nonetheless it does not concern the calls under which primarily the medical devices and equipment will be purchased, i.e. it is irrelevant for them. The corrective measure will be fully implemented in the documentation for the 13th call (activity 3.2a). |
|  | d) To conduct the check of eligibility of the medical purpose already during the check of applications for support in the framework of expert evaluation with respect to the following criteria: 2.2 Need of the project, 3.2 Technical and technological feasibility of the project, 3.4 Consistency of the project with the set out indicators and objectives – modifications in the Handbook for evaluators, presentations at the Seminars for evaluators. | By the announcement of a new call | See point c) The obligation to state the medical purpose in the technical specification annex already at the time of submission of the application for support – this obligation has already been stated in the HAB, Chapter C.2.6.2 Project documentation, point 3 |
| KPMG recommends considering the setting out of a financial limit for publicity in the future calls for IOP Intervention area 3.2 at the above referred to level. | a) To set out the financial limits for the item of publicity. | Accomplished | Starting with the 2nd call, precise limits are set out by the Handbooks for Applicants and beneficiaries |
| KPMG recommends considering the setting out of a financial limit for management services in the future calls for IOP Intervention area 3.2 at the above referred to level. | a) To set out the financial limits for the item of project management and monitoring. | Accomplished | a) Starting with the 2nd call, precise limits are set out by the Handbooks for Applicants and beneficiaries |
| KPMG clearly recommends applying the possibility of splitting the contracts pursuant to Section 98 of Act on public contracts for the purchase of medical technology in all the cases when the object of the contracts allows it. The conducted analysis indicates that in the prevailing majority of public procurement procedures implemented under the 1st call it was possible. This manner of the contract award will better contribute to the sound competition between the suppliers of medical technology and will help prevent the development of oligopolistic market structures and limit the tendency of strong players to divide the market between them by concluding cartel agreements. KPMG also recommends that in case the beneficiary in the framework of a grant project wishes to announce an above-the-threshold public contract for the purchase of medical technology without the possibility of contract splitting, this procedure is duly justified to the implementing authority. The MoH as the implementing authority should have the final say in the approval of such contracts. | a) To set the obligation of contract splitting pursuant to Section 98 in the relevant cases. | Accomplished | a) January 2011 – accomplished by the adoption of Anti-Corruption Strategy of MoH |
|  | b) To consistently check the application of Section 98 and the manner of splitting the contracts. The obligation is stipulated in the Order of the Minister No 5/2011 | Continuously | b) Starting with August 2011, the checklists for contract documents and the course of tenders started to be used, they include questions derived from the Anti-Corruption Strategy. Therefore a separate checklist is not used, which reduces the risk of omissions. |

Action Plan from the Interim Analysis of Communication Needs of the Ministry of Interior in the Field of EU Structural Funds

| Recommendation of the evaluator | Intermediate Body of the Ministry of Interior |
| --- | --- |
|  | CORRECTIVE MEASURE | DEADLINE | ACCOMPLISHED |
| SA communication |  |  |  |
| 1. SA communication should meet the objective of increased satisfaction of citizens with the public administration and better perception (image) of public administration by the general public | 1.1. Implementation of the “Quality of life” concept | 31.12.2015 |  |
| 2. SA communication should meet the objective of the increased transparency of public administration | 2.1 Direct communication with citizens - web; events | 31.12.2015 |  |
|  | 2.2 Introduction of particular persons | 31.12.2015 |  |
|  | 2.3 Presentation of particular projects in order to lift the barriers | 31.12.2015 |  |
| 3. SA communication should inform the professional public on its impacts | 3.1 Newsletter, seminars, workshops, one-to-one consultations, programming documents, methodologies, guidelines and handbooks | 31.12.2015 |  |
| COMMUNICATION STRATEGY |  |  |  |
| 4. Communication activities should focus primarily on the target group of general public | 4.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists, updates of websites, exploitation of social networks, events, promotional merchandise | 31.12.2015 |  |
| 5.To attach sufficient importance to information provided to the professional public; to introduce them to SA projects so that they are aware of its consequences and are able to further disseminate this information | 5.1 To be delivered through the newsletter, atlas of projects, workshops, one-to-one consultations | 31.12.2015 |  |
| 6. To present the SA projects in the broadest possible portfolio of media (ranging from television, through press up to social media) | 6.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists | 31.12.2015 |  |
| 7. To base the selection of suitable means of communication on the knowledge of what means are used by the respective target group | 7.1 Development of partial communication plans for 2011 – 2015 | 31.12.2015 |  |
| 8. To introduce primarily the common results of both the programmes (reduction in time spent at offices; support of investments in IT through education and training of clerks) | 8.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists, updates of websites, exploitation of social networks, events | 31.12.2015 |  |
| 9. To present the information on projects in a comprehensible manner; to give as many specific examples as possible. It is best served by the presentation of specific stories | 9.1 To be delivered through commercial supplements, media relations, press releases, meetings with journalists, atlas of projects | 31.12.2015 |  |
| 10. In SA project communication the total volume of support should always be mentioned | 10.1 To be delivered through advertisements, product placement, commercial supplements, media partnerships, media relations, press releases, meetings with journalists, events, newsletter, atlas of projects | 31.12.2015 |  |
| “QUALITY OF LIFE CONCEPT “ |  |  |  |
| 11. When developing a single concept, to proceed from the conclusion of the Evaluation of IOP communication and publicity activities – single image communication strategy, to which all the staff contribute; cooperation among all the Incom and Excom units; uniform communication | 11.1 Involvement of all the InCom and ExCom unit, development of a single concept, agreement on single communication | 31.12.2011 | Provision of information to communication staff of IB |
| 12. To exploit the “Quality of life“ concept as the fundamental unifying communication objective | 12.1 Involvement of all the InCom and ExCom unit, development of a single concept, agreement on single communication | 31.12.2011 | Communication staff of IB is familiar with the concept and applies it in communication activities |
| RECOMMENDED TOOLS |  |  |  |
| DIRECT COMMUNICATION |  |  |  |
| 13. To continue to perform the already established activities | 13.1 To be delivered through technical seminars, one-to-one consultations, newsletter | 31.12.2015 |  |
| 14. At seminars to better respond to the participants' feedback (availability, specific examples, financial aspects, supporting documents) | 14.1 To better focus the content of seminars | 31.12.2011 | Being accomplished on a continuous basis - feedback – satisfaction questionnaires at each seminar – majority of participants are satisfied with the seminars and with the content, the content is clearly defined in the invitation to the seminar |
| 15. To focus on improved provision of seminars – regional coverage, capacity, parking places, services | 15.1 To outsource the implementation of the seminar | 31.12.2011 | 10.10.2011 A contract was concluded with Valero s.r.o. based on the tender |
| PUBLICATIONS |  |  |  |
| 16. To more intensively respond to the on-going feedback concerning the Newsletter, especially with respect to its content, form of presented information and requirements | 16.1 To create a mechanism for feedback | 31.12.2011 | Due to austerity measures the tender for a supplier of the Newsletter was cancelled. Based on the revision of the Newsletter (content, form, scope) it will be created internally as a 4-page quarterly. The first issue is to be published in October 2012. |
|  | 16.2 To continuously monitor the feedback in line with the proposed mechanism | 31.12.2015 |  |
| 17. To consider the scope of texts in the Newsletter which is sometimes overabundant | 17.1 To modify the content and design of the Newsletter; updates | 30.6.2012 | A revision of the Newsletter was conducted in terms of its content, scope and form. The scope was cut to 4 pages and the content will be clearly structured, always focused on one main topic. |
| 18. To consider the publishing of a technical publication that would present selected projects implemented under the SA and supported from the European funds | 18.1 Publishing of the Atlas of projects | 31.12.2013 |  |
| MEDIA |  |  |  |
| 19. To continue to use the free of charge space in periodicals for advertisements whenever possible | 19.1 To be delivered through the establishment of relationships with journalists (media relations) | 31.12.2015 |  |
| 20. Special commercial supplement | 20.1 Creation | 30.6.2012 | Commercial advertisements were created, focusing on successful projects. They will be published in: - Hospodářské noviny (5.10., together with OP HRE) - Respekt weekly (10.9., together with OP HRE) - Ekonom weekly (13.9., together with OP HRE) - HN Podnikání supplement (10.9.) |
|  | 20.2 Creation of commercial supplements | 31.12.2013 |  |
| JOURNALISTS |  |  |  |
| 21. To consider the selection of attractive topics for press releases | 21.1 To be delivered through press releases | 31.12.2015 |  |
| ONLINE COMMUNICATION |  |  |  |
| 22. To create a special microsite for the presentation of the Quality of Life concept | 22.1 Creation of the microsite | 31.12.2012 | 3/2012 creation of kvalitazivota.eu microsites |

Action Plan from the Identification of Barriers to the Absorption of Funds under Intervention areas 3.1 and 3.3

| Recommendation of the evaluator | Intermediate Body: Ministry of Labour and Social Affairs of the CR |  |
| --- | --- | --- |
|  | CORRECTIVE MEASURE | DEAD-LINE | TO BE DONE BY | ACCOMPLISHMENT |  |
| Consultations and seminars |  |
| 1. MoLSA shall conduct a broad information campaign on open calls on the website (apart from information provided during consultations, training courses and in press) | 1.1. Information on calls/projects/selection committee meetings, etc. will be included in the news on MoLSA homepage. 1.2. Purchase/provision of database of contacts and dissemination of information on the announced calls 1.3. Participation in the IOP Annual Conference called Through social integration towards quality life 1.4. Advertisements in press (depending on available funding – MoLSA IOP TA funds) Note: Activity 3.1 a) – regular monthly presentation in the Newsletter trass (transformation of social services) (NCT) 1.5. MoLSA shall introduce a direct link from the homepage to IOP information (e.g. a hyperlink through IOP logo or through IOP link placed directly in the right toolbar) 1.6. Clearer and more consistent IOP structure on the website (IA 3.1 and 3.3) 1.7. Improving the visual features of the website ("user friendly") | ad 1), 4-6) 31.7.2012 ad 2) 3.9.2012 ad 3) 20.9.2012 ad 7) 31.8.2012 | MoLSA | 1.1. Information is continuously published in the topical information/news section of the MoLSA website see: http://www.mpsv.cz/cs/13385, also http://www.mpsv.cz/cs/13068 website was created to provide the required information, including the archive of articles (Information on IOP – in the part called What has been written on IOP and its projects). 1.2. For economy and efficiency reasons, a request on cooperation with regard to sharing the contacts to SMEs: Association of Small and Medium-sized Enterprises and Crafts of the CR (posted on the internet), CzechInvest, The Czech Chamber of Commerce. 1.3. MoLSA took part in the Quality of Life conference: It arranged for some of the lecturers and accompanying services (e.g. interpreting services) and among lecturers were also MoLSA employees. 1.4. The Profit editorial office was sent the text to be published on 27 Jul 2012, on 27 Aug 2012 the article editing was agreed upon, once the order was placed the respective article was published on 10 September 2012. On 3 Aug 2012, Hospodářské noviny daily was contacted. 1.5. A hypertext link through IOP logo on the left toolbar was created on MoLSA homepage (http://www.mpsv.cz/cs). 1.6. Structure of IA 3.1 and 3.3 was aligned. 1.7. MoLSA – IOP website was made clearer, e.g. 2 levels for IA 3.1 and 3.3 were removed, more user friendly clicks through were created, for more details see also the measures above. |  |
| 2. MoLSA shall increase the number of seminars and shall target them at practical matters (use of best practices, incl. hands on experience and potential risks faced by applicants in the past) | 2.1. Organisation of seminars beyond the scope of CoP (successful beneficiaries will be invited in case they are interested). The original 16 seminars scheduled for 2012 (i.e. until 31 Dec 2012) are organised by MoLSA by 31 Oct 2012, at least 20 seminars will have been held by the end of the year. 2.2. Modification of presentations – inclusion of best practices in presentations in which it is missing 2.3. Obligation to incorporate it in seminars and CRD presentations | ad 1) 31.10.2012, ad 2) 31.7.2012 ad 3) 31. 9. 2012 | MoLSA | 2.2. Best practise is obligatory for all the activities and seminars starting with 31 Sep 2012 (see Measure 2.3). The presentation compiled in the past and posted on MoLSA website under activity 3.1 c) already includes best practise, the presentation on 3.1 a) did not include best practise when presented and was not subsequently changed, this presentation was printed and handed over to the participants in the seminar, the content cannot be subsequently changed. In activity 3.1 b) the new presentations will include both the best and bad practise. A link to the updated presentations will be included in the Action Plan. 2.3. CRD was involved in seminars and presentations. CRD is invited to seminars |  |
| 3. MoLSA shall improve the IOP presentation on its website and make it clearer, or create a separate presentation. | 3.1. Modification and clearer design of presentations of calls on MoLSA website 3.2. Inclusion of calls on MoLSA website among the topical information 3.3. Improvement of visual features of IOP website ("user friendly") | 31.8.2012 | MoLSA | 3.1. http://www.mpsv.cz/cs/5498 and http://www.mpsv.cz/cs/7793 websites were redesigned 3.2. Information on the projects approved by the Selection Committee in the call was included among the news, a hyperlink to IOP calls through IOP logo was added to MoLSA website. 3.3. Accomplished, see point 1.7. |  |
| 4. MoLSA shall check the efficiency of consultations and include the most frequently consulted problems among FAQ. | 4.1. Verification of efficiency of consultations (both the form and content will be consulted with IOP MA) | 30.9.2012 | MoLSA | 4.1. Telephone, e-mail or one-to-one consultations are used by applicants. 3.1a Beneficiaries are determined by the call and consultations with beneficiaries on project applications are primarily offered by the National Centre for Support of Social Services Transformation. MoLSA is consulted especially with regard to building related matters with the view to minimise ineligible expenditure. 3.1b MoLSA holds regular seminars for applicants in Prague and in regions, during the seminars major stress is put on frequent mistakes in applications, best practice. MoLSA also provide consultations on individual project outlines, at the place of implementation, where necessary. Thanks to quality consultations the number of rejected projects considerably dropped, in the framework of the 6th call the share of projects rejected during quality evaluation is only 13% (2 projects), also the quality of submitted applications has improved. 3.1c The applicants send the business plan in advance before the one-to-one consultation. This helps enhance the efficiency of consultations at which various additions to the business plan with respect to project evaluation criteria and risk analysis are recommended. The attention of applicants is also brought to important parts of the application and business plan, poor elaboration of which ranks among the most frequent reasons of failure during evaluation: it is especially due to the lack of experience of the applicant (work with the target group, business, project management), necessity and benefits of project implementation for the target group and the market (stress is put on the description of a positive impact on the current situation of the target group, on the analysis of the market, demand and competition), description and reasoning of project sustainability, project timetable with respect to the process of administration and rules of the call. From May to September 2012, 16 one-to-one consultations of the business plan were held, of which 6 projects successfully passed the quality evaluation and 2 projects are now evaluated by an arbiter (successful to the degree of approx. 50% ). The most frequent enquiries from consultations concerned the eligibility of expenditure on the technical improvement of property, social entrepreneurship principles, partnerships, development of project timetable. |  |
| 5. MoLSA and CRD shall safeguard the provision of uniform information from all the stakeholders: a) observance of the division of competencies with respect to enquiries raised by applicants and beneficiaries, b) update of FAQ, c) sharing of information and enquiries in the form of common FAQ, mutual hyperlinks to websites etc. d) inclusion of the minutes from the meetings with applicants and beneficiaries in the project file, e) upon request of CRD sending the minutes from the consultations on projects prior to the submission of the application, f) meetings between the CRD and MoLSA staff over the topical problems. | MoLSA a) 5.1. An e-mail of the Director of the department pointing at the necessity to observe the division of competencies of CRD and MoLSA when replying to enquiries sent to the MoLSA staff responsible for this IOP agenda, or the Director of the Department 82 shall discuss the necessity to observe the division of competencies of CRD and MoLSA when handling the enquiries raised by applicants/beneficiaries at the coordination meeting b) 5.2. The update of MoLSA FAQ shall be performed regularly at least every three months, the evaluation will be included in the evaluation of the CoP c) 5.3. Following the update of FAQ, the information on the update will be sent, including the hyperlink to the MoLSA website, to CRD HQ d) 5.4. Immediately, if the project file is at MoLSA, otherwise to be archived by project managers of the given call. Notification of all responsible senior officers to all IOP staff - e-mail, meeting (minutes). e) 5.5. Upon request of CRD (sent directly by an e-mail to the project manager of the given call with a copy sent to soc.integraceIOP@mpsv.cz) the MoLSA will send the minutes from consultations concerning the projects f) 5.6. Each month at least 1 meeting will be held, from which the minutes will be taken CRD a) 5.7. The CRD staff will be reminded again of the division of competencies during the training course on the new MG 18 for MoLSA - deadline: immediately after the issuance of MG 18 b) 5.8. FAQ on CRD website will be updated - deadline: by 30 Jun 2012 and then continuously at least once quarterly. c) 5.9. A hyperlink of CRD and MoLSA websites in FAQ will be provided for. The CRD proposes to send the items from its FAQ to MoLSA and on CRD website to post only the link to the MoLSA website – there will be only one single FAQ – clearer for applicants/beneficiaries - deadline: upon agreement with MoLSA, estimate: by 30 Jun 2012 d) + e) 5.10. The minutes from the meeting will be included in project files on a continuous basis. The CRD staff will be notified about this during training courses focusing on the issuance of new MG 18 for MoLSA f) 5.11. Meetings of CRD and MoLSA staff is held at least once a month within the working group with the participation of IOP MA - deadline: continuously / where necessary | MoLSA ad a) No later than 14 days following the approval of the Action Plan (31.7.2012) ad b) 30.6.2012, 30.9.2012, 31.12.2012, 31.3.2013 (at least at the given intervals) ad c) continuous-ly no later than 5 working days after the date given in point b), 31. 7. 2012 ad d) 31. 7. 2012 and then continuous-ly ad e) No later than 3 working days following the request (31. 7. 2012) ad f) monthly, the first meeting no later than 14 days after the approval of the Action Plan (31. 7. 2012) CRD ad a) 15.6.2012 ad b) 30.6.2012 ad c) 30.6.2012 ad d+e) immediate-ly after the issuance of MG 18, then continuous-ly (31.7.2012) ad f) monthly (31.7.2012) | MoLSA CRD | MoLSA 5.1. The e-mail was sent on 3 Aug 2012 5.2. FAQ were updated on: IA 3.1a - 3.9.2012 (http://www.mpsv.cz/files/clanky/11712/faq_3-1a_040912.pdf) IA 3.1b – the last update of FAQ was done on 31 Jul 2012 (Due to the large quantity of frequently asked questions included already, there was no update done after that date (http://www.mpsv.cz/files/clanky/11910/faq_3-1b_060812.pdf) IA 3.1c - 27.9.2012 IA 3.3 a)b), OI 3.3 c) - 21.6.2012 (http://www.mpsv.cz/files/clanky/8368/Faq_3-3ab_210612.pdf). The name was aligned with IA 3.1 5.3. FAQ was updated, CRD was informed 5.4. E-mail was sent on 3 Aug 2012 5.5. E-mail was sent on 3 Aug 2012 5.6. The first meeting with CRD following the approval of AP was held on 17 Aug 2012 5.8. and 5.9. CRD sent the information on the hyperlink to MoLSA FAQ CRD 5.7. Accomplished continuously. The training course on MG18 of MoLSA has not been held as yet. The information is disseminated to CRD branches continuously – in the form of consultations with CRD HQ, at regular meetings with the heads of CRD branches And CRD HQ or through the guidelines of CRD HQ. It is also verified by the management control by CRD HQ 5.8. Accomplished. FAQ on CRD website was last updated on 2 Aug 2012 5.9. Accomplished. The hyperlink at CRD provided on 2 Aug 2012 and at MoLSA on 3 Aug 2012 5.10. Being fulfilled continuously 5.11. Accomplished + being fulfilled continuously. The last meeting of CRD and MoLSA staff took place on 17 Aug 2012 and 18 Sep 2012. |  |
| 6.More intensive provision of information on the division of competencies between CRD and MoLSA through websites (schemes), seminars and consultations | MoLSA 6.1. Clearer division of competencies on the website will included in the update of MoLSA website, see measure No 3 CRD 6.2. Information on the division of competencies will be posted on CRD website | MoLSA 31.8.2012 then continuous-ly CRD 31.7.2012 then continuous-ly | MoLSA CRD | 6.1. Posted on the website: http://www.mpsv.cz/cs/5485 The division of competencies between MoLSA and CRD was posted on the MoLSA website. 6.2. Division of competencies has not been approved by IOP MA (due to the still unclear procedure concerning the final evaluation of the action. At the last meeting with MoLSA it was agreed that the division of competencies will be posted on CRD and MoLSA websites regardless this situation (irrelevant for beneficiaries). It will be accomplished no later than on 8 Oct 2012 |  |
| Demandingness of the preparation |  |
| 7. MoLSA in cooperation with CRD shall include practical tips for the completion of the application in Benefit in the agenda of training courses for applicants. | 7.1. MoLSA will include CRD presentations in each training course for applicants submitting projects under IA 3.1. 7.2. CRD will supply MoLSA with the supporting documents on most frequent errors made/enquiries raised by applicants during the completion of project applications in IS Benefit 7.3. CRD will participate in seminars for applicants and beneficiaries | MoLSA 31.7.2012 and then continuous-ly CRD 31. 7. 2012 and then continuous-ly | MoLSA CRD | MoLSA: 7.1. The first joint presentation of MoLSA and CRD took place on 15 May 2012 (3.1 a), MoLSA accepts the recommendations and the relevant CRD presentations will be included in the next training course for applicants. 7.2. On 2 Aug 2012 the CRD sent the supporting documents concerning errors and enquiries 7.3. Training course for beneficiaries was held on 30 Aug 2012, MoLSA asked CRD to take part in the seminar for applicants, CRD refused to participate therein on the grounds of understaffing CRD: 7.2. Accomplished. Supporting documents were sent to MoLSA on 2 Aug 2012 7.3. Accomplished + It will be fulfilled continuously. CRD took part in 2 seminars for beneficiaries under 3.1b) and 3.1c) on 6 Sep 2012 |  |
| 8. MoLSA shall simplify and make clearer the requirements for submission of application. | 8.1. Revision of call for 3.1 and 3.3, e.g. clearer reporting of indicators and conditions governing the eligible expenditure in call No 8 IA 3.1. MoLSA shall modify the calls for IA 3.1 and 3.3 in order to harmonise as much as possible the procedures, requirements and their interpretation for applicants and beneficiaries. | To send to IOP MA for all the calls by 31 Aug 2012 | MoLSA | 8.1. Revisions of the calls were sent by MoLSA to IOP MA by the deadline: Call for 3.1 c) sent on 25 Jul 2012 Call for 3.1 a) sent on 31 Jul 2012 In call for 3.1b) the revision was drafted in August 2012, based on the requirement of IOP MA (MoLSA is the person responsible) it will be sent to IOP MA after the approval of the revision of 3.1c) In calls for projects under IA 3.3 a) b), 3.3 c) the revisions were also prepared in August 2012, based on the requirement of IOP MA (MoLSA is the person responsible) the revision of the calls will be sent only after the approval of the revisions of calls for 3.1. |  |
| 9. A single approach to social entrepreneurship (implementation structure, evaluators, selection committee) so that all the applications at all the stages are approached in the same and consistent manner: a) observance of the single interpretation of call No 8 for IA 3.1 (implementation structure, evaluators, selection committee), b) more intensive training of evaluators. | a) 9.1. MoLSA will set up a discussion group of all the stakeholders on the topic of social economy/entrepreneurship b) 9.2. MoLSA will again train all potential evaluators. With major stress on the interpretation of individual criteria and consistency between scoring and verbal comments. The content of the training will be discussed with MA. MoLSA will regularly invite MA to these training courses. | ad a) 31.8.2012, ad b) 30. 9. 2012 | MoLSA | a) 9.1. MoLSA set up the discussion group on the topic of social economy, support to newly created social enterprise and its concept, the first meeting with TESSEA and the Union of Czech Production Co-operatives representatives concerning project design and other potential cooperation was held on 1 Aug 2012. b) 9.2. - 3.1 a – a training for evaluators was held on 24 Sep 2012 b) 9.2. - 3.1 b – on 30 Aug a training for evaluators of 3.1b was held. b) 9.2. - 3.1 c – a seminar for the existing evaluators is scheduled in order to increase the success rate of projects during quality evaluation. Since it is necessary to pay due attention to the preparation of its content, it will be held in the course of November 2012. |  |
| 10. MoLSA shall consider the need and frequency of revisions of calls. | 10.1. MoLSA accepts the MA requirement to decrease the number of guidelines regulating the calls and the changes will be made in the form of revisions (see recommendation No 11). Revisions given in point No 8 are necessary (they were requested in 2011), the revisions will incorporate the maximum possible number of modifications which will, however, not disfavour certain applicants/beneficiaries. | See measure No 8 | MoLSA | 10.1. Accepted, see measure 8.1 |  |
| 11. MoLSA shall not change the single items one by one in the form of a guideline, but rather multiple changes simultaneously through the revision of the Handbook for Applicants and Beneficiaries. | 11.1. See measure No 10 above | Continuous-ly | MoLSA | 11.1. Accepted, see measure 8.1 |  |
| 12. MoLSA shall check the wording and definition of technical and financial limits. We recommend to make their list and definitions clearer to applicants. | 12.1. MoLSA will evaluate the wording and definitions of technical and financial limits and submit the results of this evaluation to IOP MA 12.2. MoLSA will include the outputs from evaluation to the revisions of calls for IA 3.1 | ad 1) 31.5.2012 ad 2) see measure No 8 | MoLSA | 12.1. MoLSA sent to the IOP MA the results of evaluation of limits related to the calls for IA 3.1 12.2. see the Revision of calls and recommendation No 8.1 Activity 3.1a) – the limits have already been modified by Guideline No 1, additional revisions are included in Chapter 3.4.1 of HAB, activity 3.1b) – in the revision which is currently under preparation the limits are modified in problem areas and specified in HAB in Chapter 3.4.1 and in Annex No 1 to HAB, activity 3.1 c) - following the evaluation the limits were modified in HAB in Chapter 3.4.1. |  |
| 13. IOP MA shall have the design of technical and financial limits examined by an expert | 13.1. MA will commission external experts to elaborate an opinion 3.2. The results will be discussed with MoLSA | ad 1) 1.7.2012 ad 2) 31.8.2012 | IOP MA | MoLSA sent to the IOP MA the evaluation of limits under the calls for IA 3.1.; Nonetheless, the IOP MA was dissatisfied with the evaluation, which is why it commissioned an external expert to evaluate the financial and technical limits by the given deadline, based on which the IOP MA conducted an administrative check, the conclusions of which are being finalised. As of 30 Sep 2012, the discussion with MoLSA has not been held; a meeting with MoLSA will be convened with the view to propose corrective measures. |  |
| Setting the conditions |  |
| 15. MoLSA shall distinguish between the completion of project implementation and financial completion of the project and shall set the date for the payment of the last due commitment prior to the deadline for the submission of payment claim. | 15.1. MoLSA will incorporate this deadline in the guidance documentation of calls and in the model conditions, see point No 8. | See measure No 8 | MoLSA | 15.1. The deadline of completion of project implementation was added to all the revisions of calls for IA 3.1 and IA 3.3 both to the text of HAB and model conditions for the Decision on providing a grant. |  |
| 16. To accelerate the administration: a) CRD shall propose measures to accelerate the control of completed tenders b) MoLSA shall propose measures to accelerate the issuance of Decision/Statement of expenditure in the existing system. | Point a) CRD 16.1. CRD provided for an on-going monitoring of controls of tender documentations and documentations of carried out public procurement procedures, monitoring of deadlines and their regular evaluation within the entire organisation 16.2. In the near future, a unit will be established which will handle only the contracts and manage their control and administration 16.3. CRD submitted to MoLSA the recommendation concerning the selection of an expert in the field of administration of tenders. The conduct of the tender would be outsourced. The expert would assist the applicants in regions to prepare the project application 16.4. CRD submitted to MoLSA the recommendation concerning the introduction of a single contracting authority profile 16.5. CRD submitted to MoLSA the recommendation concerning the simplification of requirements as well as the processes of control and contracts of the Ist category This recommendation was sent to MoLSA on 4 Jun 2012 16.6. CRD will recommend to beneficiaries and applicants to consult the tenders at CRD branches and to exploit the possibility to have the tenders controlled prior to signing the contracts on work done Point b) MoLSA 16.7. Issuance of a single (merged) document – with respect a part of projects the Registration of the projects will not be issued in ARS/ASOA, but the merged document Registration and the Decision on providing a grant/Statement of expenditure will be issued. 16.8. Revision of MoLSA IB HWP = the issuance of the Decision/Statement of expenditure shall be preceded by by the conduct of an administrative check of the project, namely in line with the HWP procedure. Examples of relevant modifications of HWP: - definition of supporting documents which MoLSA is entitled to request for the issuance of the Decision/Statement of expenditure. - removal of the possibility to issue the Decision/Statement of expenditure for a stage only. - introduction of the record keeping of the handing over of the supporting documents between MoLSA and CRD units. - to speed up signing guidance documents (handing over of the guidance documents to be signed in person - secretariat to MA 68) - to make clearer (shorter description) the relevant chapters of HWP for the issuance of guidance documentation. | ad a) CRD 1) implement-ted since 4/2012 2) 31.8.2012 3,4,5) sent to grant provider on 4.6.2012, 31.8.2012 6) continuous-ly, 31.7.2012 point b) MoLSA 30.6.2012 | CRD MoLSA | a) CRD 16.1. Accomplished + Being fulfilled continuously. Monitoring and evaluation of controls of tender documentation and tenders have been under way since 4/2012. The evaluation is also presented to CRD HQ senior officials – at least once a month 16.2. Accomplished. A autonomous unit was established on 13 Aug 2012 16.3. Accomplished. The recommendation was sent to MoLSA on 4 Jun 2012 and 31 Aug 2012 16.4. Accomplished. The recommendation was sent to MoLSA on 4 Jun 2012 and 31 Aug 2012 16.5. Accomplished. The recommendation was sent to MoLSA on 4 Jun 2012, 31 Aug 2012 and 13 Sep 2012 16.6. Accomplished + Being fulfilled continuously. This recommendation is communicated to beneficiaries during the consultations at CRD branches and during training courses for applicants and beneficiaries b) MoLSA 16.7. Issuance of a merged Decision on providing a grant/Statement of expenditure was stipulated in the approved HWP in Chapter 10.12 16.8. Administrative check of projects was incorporated in Chapter 10.10.2 and checklists in Annex P3 – Model documents for the check. The documents which MoLSA can request, as agreed with IOP MA, will be listed in the updated HABs for individual calls. (The update was delayed due to the protracted comment procedure of IOP MA for the intended model call for 3.1c). The possibility to issue a Decision on providing a grant/Statement of expenditure for a stage was deleted in the approved HWP. See annexes to the AP attached under the title Revision of MoLSA IB HWP, version 1.4. |  |
| 17. CRD shall observe the deadlines for the control of tender documentation prior to the announcement of the tender | 17.1. Control of the observance of deadlines for the control of tender documentation prior to the announcement of the tender is ensured by CRD HQ, which regularly monitors and evaluates the progress of controls of tender documentation at CRD branches - deadline: implemented since 4/2012 | 30.4.2012 | CRD | Done already |  |
| 18. MoLSA shall remove the excessive requirements for applicants a) MoLSA shall ask the MoF whether the ARS form as an obligatory annex to the application elaborated by applicants before the issuance of the Decision can be replaced by an automatically generated ARS form from Benefit (just as in other IA.) b) MoLSA shall remove the annual requirement for the beneficiary to submit the financial settlement and for the purpose of financial settlement of relations with the state budget the information available in ARS/ASOA system shall be used | 18.1. MoLSA does not intend to act upon the recommendation of evaluators, the MA will continue to discuss this topic with MoLSA. | 31.8.2012 | MoLSA | a) In September 2012 a series of meetings between IOP MA, MoF CR and MoLSA CR was held, in the course of October 2012 the IOP MA in collaboration with MoLSA and CRD discuss which documents will be entered by CRD in IS Monit7+IOP and which will be supplied by beneficiaries. b) In keeping with the referred to opinion, the requirement for the submission of annual settlement remained in the HWP. b) In keeping with the referred to opinion, the requirement for the submission of annual settlement remained in the HWP. |  |
| 19. MoLSA and CRD shall continue to recommend the applicants and beneficiaries to divide the projects into more stages/stages into sub-stages. a) In the framework of consultations of new projects and seminars for applicants b) To continue to directly address project beneficiaries via e.g. the already sent letter of the director of department No 82 with a request to divide the projects into smaller stages, where it is possible. | MoLSA a) 19.1. Forwarding the information through an e-mail to all the FM and PM implementing the calls for IA 3.1 and IA 3.3 with a request to include the required information in all the consultations and seminars 19.2. Sending the letter of the director of department 82 to applicants who plan to submit the projects from September 2012 until the end of the calls (it applies to 3.3 b, c) and 3.1 a)) b) 19.3.Beneficiaries who have not been addressed so far and in whose projects unsuitable divison to stages is identified, will be sent a letter of the director of department 82 with the recommendation of more appropriate division into stages CRD a) 19.4. The CRD representatives are ready to take part in the consultations or seminars for applicants and beneficiaries | MoLSA ad a) No later than 5 working days following the approval of the Action Plan, 31.7.2012 ad b) No later than 1 month following the approval of the Action Plan, 31.8.2012 CRD ad a) continuously according to the grant provider | MoLSA CRD | 19.1. On 26 Jul 2012, the senior officers of IB were notified of the necessity to divide the projects into stages; the information was also disseminated at meetings of individual units; an e-mail was sent by the director on 3 Aug 2012 19.2. and 19.3. Activity 3.1b) – letters to beneficiaries with identified long stages, in which the shortening of stages was required, were sent on 4 Sep 2012. In 3.1 c) it is irrelevant. In projects under IA 3.3 letters to applicants who plant to submit their projects (3.3 a) were sent on 28 Aug 2012; letters to beneficiaries (3.3 a),b),c)) with identified long stages requiring a shortening of these long stages were sent before 31 Aug 2012. 19.4. Being fulfilled continuously |  |
| Evaluation of eligibility and formal requisites |  |
| 20. MoLSA shall specify the working checklists for the control of eligibility and formal requisites for CRD (incl. sub-criteria) | 20.1. MoLSA together with CRD will specify the wording of the checklist 20.2. The modified version of the checklist was reflected in the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 20.1. and 20.2. Accomplished in the framework of revision of MoLSA IB HWP, version 1.4 |  |
| 21. MoLSA shall hold a seminar for CRD staff focused on the evaluation of eligibility and formal requisites | 21.1. A seminar (or seminars) will be held as a follow-up to the revision of calls for IA 3.1 | No later than 14 days following the approval of revision of the given call | MoLSA | 21.1. As of 1 Oct 2012 no revision of the MoLSA call was approved. The deadline was postponed. |  |
| 22. MoLSA shall adopt measures to improve the quality of projects: a) to specify the descriptions in HAB with respect to the supporting documents and annexes most frequently exhibiting errors b) to specify the description of inclusion of individual categories in the limits of eligible expenditure and definitions of parameters of the action c) more intensive holding of seminars for applicants d) practical targeting of seminars (use of best practice) | a) and b) 22.1. It will be included in the revision of individual calls, see measure No 8 c) 22.2. MoLSA will increase the number of seminars held, especially for activity c) IA 3.1. It will present a plan of seminars for the upcoming half-year d) 22.3. The implementation is also described in measures No 2 and 7 | ad a) and b) as a follow-up to measure No 8, ad c) 30.9.2012, ad d) 31.8.2012 | MoLSA | 22.1. Examples of modifications: Activity 3.1a) – modifications a) in the revision sent to IOP MA, modifications were made in Chapter 4.2. Form and way of submission of application - HAB, in which parts regarding the specific indicators and parts concerning the investment plan were specified. The modification to Annex No 1b Specific indicator; modifications b) in revision sent to IOP MA Chapter No 3.4.1 in HAB was modified, the wording was specified. Activity 3.1b) - modifications a) in the revision which is being prepared modifications were made in Chapter 3.5.Monitoring indicators, in which the description of specific indicators was made more precise, 4.2. Annexes to the application – parts of the text concerning the investment plan were specified; modifications b) the revision which is being prepared specifies the chapter focusing on eligible expenditure in Chapter 3.4.1. of HAB, modifications to Annex No 1 to HAB Chapter 1, in HAB specifications were made in the chapter concerning the parameter of indicators Chapter 3.5. In activity 3.1 c) modifications a) as well as modifications b) were added to the revision of the call in HAB. 22.2. 8.11.2012 a planned seminar for applicants under 3.1c), 12.9.2012 a speech of a PM under 3.1c) given at the Tessea international conference on social entrepreneurship (information on the focus of the call, extension of duration of the call, possibility of consultations). 22.3. Due to the recent series of seminars for applicants which brought hardly any results, the targeted consultations and presentations shall rather be held directly at potential applicants under 3.1b (at the turn of the year seminars were held in Prague, Olomouc, Liberec, Karlovy Vary, České Budějovicce and Hradec Králové). The invitation to the seminar held in Prague was sent to roughly 100 municipalities, the invitations to regional events were distributed by regional Roma coordinators, the seminars were however regularly attended also by the representatives of organisations and municipalities from other regions. Moreover, in Ostrava an event organised by the Municipal Authority of Ostrava was held in March in order to attract persons interested in the call (all the organisations operating in the city were invited). For reasons above more intensive organisation of seminars is not foreseen. Ad d) The prepared seminars will cover the examples of best practice. |  |
| 23. Observance of the procedures for entering data in IS MONIT7+ by staff of CRD branches, or their additional training (held also on a continuous basis in case of high turnover of staff) and random checks by HQ | 23.1. Training of staff of CRD branches shall take place where necessary with respect to the issuance of the new MG 18 for MoLSA (checks of activities of CRD branches are under way, including the checks focused on the observance of deadlines.) | 31.8.2012, then continuous-ly | CRD | 23.1. Being fulfilled continuously. The staff of CRD branches are trained on a continuous basis - through consultations with CRD HQ, at regular meetings between the heads of CRD branches and CRD HQ or through CRD HQ guidelines. It is also verified by checks conducted by CRD HQ. |  |
| 24. IOP MA shall conduct a check of delegated activities focused on the observance of procedures of entering the data in IS Monit7+ | 24.1. MA will conduct an administrative check | by 30.11.2012 |  |  |  |
| 25. MoLSA shall set the procedure and clear conditions, incl. the selection and size of the sample for control mechanisms to assure the grant provider of the regularity of operations performed within the delegated activities at CRD. | 25.1. It will be addressed within the revision of MoLSA IB HWP, the measure cannot be applied, the check of CRD cannot be delegated by IOP MA to MoLSA. The possibility to file a motion with the IOP MA to initiate a check was added to HWP. | 31.7.2012 | MoLSA | 25.1. In the framework of revision of MoLSA IB HWP, version 1.4., in the comment procedure a part called CRD checks was added to the introductory chapter of MoLSA IB HWP focusing on controls, which was removed during the comment procedure. The motions to conduct CRD checks were subsequently added to the newly created Chapter 8 Observance of deadlines, record keeping of deadlines and regular reporting "If any of the IB staff discover a non-observance of the deadline in project administration, not caused by MoLSA, he shall first notify his superior thereof and subsequently the IOP MA will be notified by the respective monthly report on MoLSA IB activities". |  |
| Evaluation of quality |  |  |  |  |  |
| 27. Suspension of administration in case of the necessity to conduct the 3rd evaluation was addressed through the issuance of the Methodological Guideline No 26, which has to be incorporated in the revision of HWP, version 1.4. | 27.1. Incorporation in the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 27.1. In the framework of HWP revision it will be added to Chapter 10.6.1 Evaluation of project quality. |  |
| 28. MoLSA shall set in HWP the deadline for the 3rd evaluation and in 3.1 the possibility to suspend it. | 28.1. Incorporation in the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 28.1. In the framework of HWP revision it will be added to Chapter 10.6.1 Evaluation of project quality. |  |
| 29. MoLSA shall set the deadline for evaluation of quality as of the delivery of the file to MoLSA | 29.1. Incorporation in the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 29.1. In the framework of HWP revision it will be added to Chapter 10.6.1 Evaluation of project quality. |  |
| 30. CRD shall see to it that the project file is handed over from CRD to MoLSA by the set out deadline | 30.1. CRD will see to it continuously. The training of all CRD staff with respect to the issuance of new MG 18 for MoLSA | Immediate-ly after the issuance of MG 18, 31.7.2012 | CRD | 30.1. The training will be held by the end of 2012. |  |
| 31. Differences between the evaluation of individual evaluators leading to the necessity to use the 3rd evaluator (arbiter), or between the quality of work of evaluators, were not assessed, they can be subject to another analysis. | 31.1. More intensive and thorough training of evaluators (see measure to 9b.). 31.2. More stringent requirement concerning the harmony between scoring and verbal comments. 31.3. Analysis of the evaluation by evaluators (see measure to 32) | 30.9.2012 | MoLSA | 31.1. See point 9b. 31.2. In the framework of training of evaluators, major stress is put on the harmony between the scoring and verbal comments, modifications in HWP were made, see 32.1 31.3. 3.1a) In the framework of evaluation of 24 projects, it was necessary to use the institute of an arbiter only once 3.1b) During the evaluation of 21 projects, in two cases only the need arose to use the institute of an arbiter, even though the differences in evaluation were negligible (e.g. in project %8240 the scoring of 3 evaluators ranged from 61 to 66 points) 3.1c) the need to use an arbiter is also rare In order to achieve the effectiveness of measures in the revised HWP version 1.4, an analysis of evaluations done by evaluators is carried out on a representative sample. The outputs of this analysis will be included in the Monthly report on IB activities. |  |
| 32. MoLSA shall clearly set the rules for the control of outputs of external evaluators by the PM following their receipt and the procedure to be taken in case the PM has objections to the elaborated evaluation. | 32.1. Incorporation in the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 32.1. In the framework of HWP revision it will be added to Chapter 10.6.1 Evaluation of project quality. |  |
| Ex-ante risk analysis |  |
| 33. MoLSA shall make sure that the deadlines set in HWP are observed. | 33.1. In regular reporting, one part of the document will be dedicated by MoLSA to the monitoring of deadlines in ex-ante checks 33.2. MoLSA will monitor (IOP coordination meetings) and regularly report to IOP MA the observance of deadlines in ex-ante checks 33.3. An e-mail will be sent to all the staff, pointing at the observance of deadlines, the senior officers will introduce regular check of the deadlines. | ad 1) 30.6.2012, ad 2) 30.7.2012 ad 3) 31.7.2012 | MoLSA | 33.1. Regular reporting of MoLSA has been sent to IOP MA continuously since 2011, it is stored on the internal shared disc K: where it is available to all MoLSA IB IOP staff, it was modified in the part dedicated to ex-ante check. 33.2. MoLSA monitors the observance of deadlines at regular meetings of IOP and reports on the results to IOP MA at the meeting of directors with IOP MA. 33.3. On 3 Aug 2012 an e-mail with the required information was sent by the director of the department |  |
| 34. Observance of procedures for entering the data in IS Monit7+ by MoLSA staff, or their additional training (also continuously in case of high turnover of staff) | 34.1. E-mail from the director of the department pointing at the necessity to observe the procedures for entering fate data in IS Monit7 addressed to MoLSA staff responsible for this IOP agenda, and discussion thereof at the coordination meeting | 31.7.2012 | MoLSA | 34.1. On 3 Aug 2012 an e-mail with the required information was sent by the director of the department. |  |
| 36. MoLSA shall observe the procedures for risk analysis set in IOP OM. | 36.1. MoLSA introduced the system of monitoring of procedures and deadlines in risk analysis (see recommendation No 33). On the shared disc of all the IBs detailed information on the carried out risk analyses is stored. Potential problems will be addressed at regular meetings of IB senior officers of departments 82 and 68. The prohibition of inadmissible request of supporting documents, telephone conversations with applicants and other unacceptable behaviour will be notified to the staff conducting the risk analysis by an e-mail from IB directors | 30.6.2012, then continuous-ly | MoLSA | 36.1. See measure 33, on 3 Aug 2012 an e-mail with the required information was sent by the director of the department. |  |
| 37. IOP MA shall place a requirement to incorporate the function in IS Monit7+ | 37.1. See the wording of recommendation. | 1.10.2012 | IOP MA | 37.1. Modified. In IS Monit7+IOP the data concerning new projects is entered into 1 checklist. In older projects 2 checklists of risk analysis are completed ex-ante. |  |
| Ex-ante check |  |
| 38. MoLSA shall set the deadline for the completion of ex-ante check in HWP revision in dependence on the selected form of check. | 38.1. Incorporation in MoLSA IB HWP revision, version 1.4 | 30.6.2012 | MoLSA | 38.1. In the framework of MoLSA IB HWP revision the deadline was incorporated in Chapter 10.6.3 Ex-ante risk analysis and ex-ante check. |  |
| 39. MoLSA shall insist on cutting down the duration of ex-ante check. | 39.1. See measure No 33 | 31.7.2012 | MoLSA | 39.1. On 3 Aug 2012 an e-mail with the required information was sent by the director of the department. |  |
| 42. MoLSA shall observe the procedures for the conduct of checks, as defined in Chapter C of IOP OM, use the possibility of on-the-spot checks or monitoring visits for the sake of verification of the status given in project application. | 42.1. The information will be added to the e-mail of IB directors. | By 14 days after the approval of the Action Plan | MoLSA | 42.1. On 3 Aug 2012 an e-mail with the required information was sent by the director of the department. |  |
| 43. MA shall focus the checks of delegated activities on the stage of ex-ante checks | 43.1. See the wording of the recommendation. | 1.10.2012 | IOP MA | 43.1. The check is under way |  |
| 44. We recommend to MoLSA to prevent the high share of rejected projects through the provision of quality service prior to the submission of the application (thematic seminars, consultations). | 44.1. See measures No 2, 19 and 73. | See the deadlines of respective measures | MoLSA |  |  |
| 45. MoLSA shall check the wording and definitions of technical and financial limits. We recommend to make the list and definitions clearer to applicants. | 45.1. See measure No 12 | See measure No 12 | MoLSA |  |  |
| 46. IOP MA shall have the setting of technical and financial limits examined by an expert | 46.1. IOP MA will seek an external expert and commission him with the elaboration of an opinion. 46.2. Based on the results of the opinion the MA will launch discussions with MoLSA concerning potential revision of HAB | 31.9.2012 | IOP MA | 46.1. and 46.2. The check based on the expert′s opinions is under way |  |
| 47. MoLSA shall reduce the high number of projects covered by ex-ante checks: a) by observing the set procedures for risk analysis so that the ex-ante check is carried out only in applications which shall be subject to ex-ante checks in line with the rules b) by examining the setting of scoring of risk analysis, it shall identify the most frequent reasons for checks and propose changes in the design of risk analysis | 47.1. In the framework of MoLSA IB HWP revision the scoring of risk analysis in IA 3.1 will be modified, a new procedure will be described for the control of technical and financial limits, which are often the subject matter of ex-ante checks. | 30.6.2012 | MoLSA | 47.1. It was incorporated in the framework of revision of MoLSA IB HWP, Chapter 10.6.3 Ex-ante risk analysis and ex-ante check. |  |
| 48. On the basis of exchange of experience with the ministries with a similar type of projects (MoC, MoI – 3.4), MoLSA shall develop a detailed procedure for ex-ante checks in order to avoid duplicate checks and running into excessive details. | 48.1. Incorporation in the revision of MoLSA IB HWP, version 1.4 – it shall be consulted with IOP MA 48.2. MoLSA will organise a working meeting with the relevant ministries concerning the comparison of procedures | ad 1) 31.7.2012, ad 2) 15. 9. 2012 | MoLSA | 48.1. It was consulted with IOP MA. 48.2. In order to exchange experience with the conduct of ex-ante checks with the ministries, the MoI, MoC, MoH and IOP MA have been addressed. Because of the extreme workload of invited persons, the meeting took place on 26 Sep 2012. The MoC and MoH representatives promised to come to the meeting. The MoH representatives, however, excused themselves from the meeting due to other work engagements (26.9.2012). During the meeting the representatives of MoC, MoLSA and IOP MA exchanged their experience. The outputs from the meeting are being analysed and subsequently will be acted upon. |  |
| Selection Committee |  |
| 49. MoLSA shall provide for (standardize) the supervision over the observance of set procedures and rules of the Selection Committee | 49.1. MoLSA will continue to introduce the SC members to their competencies and the necessity to stick to them and shall ensure that they do not re-evaluate projects to which the score was given by evaluators. 49.2. MoLSA will always invite MA to the meeting with SC. | ad 1) 31.7.2012, ad 2) 31.7.2012 | MoLSA | 49.1. and 49.2. MoLSA always introduces the new SC members to their competencies and ensures the transparency and correctness of procedures taken by the SC during its meetings. IOP MA is always invited to the SC meetings. |  |
| 50. MoLSA shall set the powers and competencies of the Selection Committee in such way so as to prevent undesired interventions in the process of evaluation compromising its unbiased and independent nature, and thus prevent the questioning of the management and control system in the field of assessing the efficiency and economy of project expenditure. | 50.1. Incorporation in the revision of MoLSA IB HWP, version 1.4, modification of competencies of the SC 50.2. Updating the Order of the Minister on the Statute and the Rules of Procedure of the SC for IA 3.1 of IOP | ad 1) 30.6.2012, ad 2) 31.8.2012 | MoLSA | 50.1. Modifications to Chapter 10.6.4 Considerations of the projects by the Selection Committee in MoLSA IB HWP and Annex P2_2 containing the Statute and the Rules of Procedure of the SC for IA 3.1. 50.2. On 27 Aug 2012, a proposal of Addendum No 3 to the Order of the Minister No 27 of 2009, comprising the Statute and the Rules of Procedure of the SC for IA 3.1, was submitted to internal comment procedure of MoLSA. The comment procedure will take place until 31 Aug 2012, the document will subsequently be presented at the meeting of MoLSA senior officials and to the Minister for Labour and Social Affairs of the CR for approval. The foreseen date of submission to the meeting of senior officials: 6 Sep 2012, the foreseen date of approval of the Addendum No 3 to the Order of the Minister No 27_2009: 7 Sep 2012. |  |
| Registration of the action |  |
| 51. MoLSA shall add the missing deadlines to HWP: (1) prior to the issuance of Registration of the action the deadline for the handing over of the file from department 82 to department 68 of MoLSA, (2) after sending the checked RA by the beneficiary back to MoLSA the deadline for the approval of RA by the senior officer of MoLSA, following which the project file and 1 copy of the approved RA is handed over to CRD. | 51.1. Incorporation in the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 51.1. As of 1 Oct 2012 no revision was approved for any of the calls. |  |
| 52. MoLSA shall align the handbooks (with respect to the issuance of RA) – to align the HAB with HWP. | 52.1. See measure No 8 – it will be included in the revisions of calls for 3.1 and 3.3 | See measure No 8 | MoLSA |  |  |
| Decision/Statement of expenditure |  |
| 55. MoLSA and CRD shall accelerate the administration of projects: a) CRD shall propose measures to accelerate the control of tenders b) MoLSA shall propose measures to accelerate the issuance of the Decision/Statement of expenditure in the existing system. c) MoLSA shall describe in HWP the procedure for ex-ante management control, for the purpose of control it shall use the outputs from CRD activities and it shall inform the beneficiaries on the control in HAB. d) MoLSA shall push for the amendment to the Order of the Minister with the view to accelerate the issuance of guidance documentation (e.g. by reducing the number of signatures necessary for the issuance of the Decision/Statement of expenditure). | CRD a) 55.1. See point No 16 MoLSA b) and c) 55.2. included in the revision of MoLSA IB HWP, for more details see recommendation No 16. d) 55.3. IB will officially request the amendment to the order of the minister in line with IOP conditions | CRD: see point No 16 MoLSA: 30.6.2012 | MoLSA CRD | CRD 55.1. Accomplished. See point No 16 MoLSA 55.2. b) see the accomplishment of recommendation No 16 55.2. c) ex-ante management control is described in Chapter 10.9 of HWP/the use of outputs from CRD activities is described in chapters of Part 10 of HWP 55.3. d) IOP management control cannot be removed from the system of MoLSA management control. |  |
| 56. IOP MA shall examine the risk of duplicate control with respect to the ex-ante management control of MoLSA and the check of supporting documents for the issuance of the Decision/ Statement of expenditure performed at CRD | 56.1. It will be included in the plan of controls for the 2nd half of 2012 | By the end of 2012 | IOP MA | Included in the plan of controls for the 2nd half of 2012 |  |
| 57. MoLSA shall propose the scope of parameters which will be listed in the Decision. | 57.1. MoLSA proposed the parameters, which will be listed in the Decision/Statement of expenditure and sent to the MA the proposed scenario (the document called Parameters) – statement with regard to the tasks from the minutes of the meeting held on 10 May 2012. 57.2. Where necessary, it will also be addressed through the revision of HWP or revision of calls | ad 1) 31.8.2012 ad 2) 30.6.2012, revision of calls see measure No 8 | MoLSA | 57.1. and 57.2. The proposal was handed over by department 82 to IOP MA at MRD on 25 May 2012, based on the current experience the minutes were taken of 30 Jul 2012, the content of which was included in the revision of the call No 8 for activity 3.1c,) and subsequently the steps will be taken in line with the accomplishment of recommendation No 8. |  |
| 58. MoLSA shall draft an instruction for applicants of how to set the parameters correctly and shall include it in FAQ | 58.1. It will be addressed within the update of FAQ | 31.7.2012 | MoLSA | 58.1. The update of FAQ will be done in connection to the revision of calls for IA 3.1 and IA 3.3, in which the modifications of parameters were incorporated, the revisions shall be approved before their publication. |  |
| 59. MoLSA shall introduce measures to prevent the postponement of project completion: a) Use of a warning system (alerts) for beneficiaries, e.g. through Benefit b) To place the information (reminder) concerning an appropriate setting of deadlines for project completion in FAQ. c) To specify and highlight the information concerning this stage in HAB – to add to HAB the information that at the turn of the year no change Decision concerning the funds and the so called limit can be issued, and the related recommendation for beneficiaries that it is recommended to complete projects in this period in case the Decision/Statement of expenditure has to be issued for the last tender of the project d) A change in the condition for the submission of payment claims and Stage Monitoring Report for the first stage – no later than 20 working days following the approval of the Decision/Statement of expenditure if it is done after the completion of the 1st stage. | a) 59.1. After a consultation with IOP MA a manner will be proposed in which to use Benefit/Monit to inform on individual deadlines b) 59.2. It will be addressed in the framework of update of FAQ c) and d) 59.3. It will be addressed in the framework of revisions of calls and related measures, including measure No 8. | ad 1) 30.7.2012 ad 2) 31.8.2012 ad 3) see measure No 8 | MoLSA | 59.1. IOP MA was sent a proposal for the information (reminder) in Benefit 59.2. It will be added to FAQ based on the revisions of IA 3.1. 59.3. It is a component part of the revisions, see measure No 8 |  |
| 60. MoLSA shall again consider the number of supporting documents which are really necessary for the issuance of the Decision | 60.1. It will be reconsidered during the works on revisions of calls by the deadlines given in point No 8. | See the deadlines in point No 8 | MoLSA |  |  |
| Evaluation of the construction part of the project |  |
| 61. MoLSA shall specify and describe the procedures with the view to accelerate the approval process: a) to describe procedures concerning the provision of opinions on construction documentation in HWP b) to sufficiently describe the obligation of applicants concerning the issuance of the Decision on providing a grant on MoLSA website for calls No 1 – 3 | a) 61.1. It is addressed in the revision of MoLSA IB HWP b) 61.2. Drafting the text and its publishing on MoLSA website | ad a) 30.6.2012, ad b) 31.8.2012 | MoLSA | 61.1. Within the revision of HWP the Chapter 10.11 was modified 61.2. The text was drafted and posted on MoLSA website by 5 Sep 2012 http://www.mpsv.cz/files/clanky/11712/faq_3-1a_040912.pdf |  |
| 62. MoLSA shall observe the set out procedures (in opinions of the Institute of Rationalisation in the Construction Industry) | 62.1. The respective part of HWP with the commentary of MA department 68 will be sent electronically to all the PM 68 (and for information to FM 82 who execute the reimbursement of invoices). | 30.6.2012 and then continuous-ly | MoLSA | 62.1. Accomplished on 11 Jun 2012 (see the annex Tasks 62-64 and 75). |  |
| 63. MoLSA shall check the format of the received opinions | 63.1. The respective part of HWP with the commentary of MA department 68 will be sent electronically to all the PM 68 (and for information to FM 82 who execute the reimbursement of invoices). | 30.6.2012 and then continuous-ly | MoLSA | 63.1. Check of the format of the received opinions and communication on them was transferred to Department 68 which avails of competent staff, see HWP in Chapter 10.11. |  |
| 64. MoLSA shall increase the limit for the value of the construction part of the projects which necessitates the evaluation by IRCI so that not all the projects are subject to evaluation of project documentation | 64.1. After the meeting with IRCI on 28 May 2012 the deadlines were cut and the limit increased to CZK 3 million net of VAT (incorporated in MoLSA IB HWP, version 1.4). | 30.6.2012 | MoLSA | 64.1. The limit was increased within the revision of MoLSA IB HWP in Chapter 10.11. |  |
| 65. MoLSA shall explain in HAB which expenditure on the elaboration of project documentation is eligible (in case of redrafting the PD based on the result of evaluation) | 65.1. See measure No 8 | 31.8.2012 | MoLSA | 65.1. It was sent within the revision of HAB 3.1a) see recommendation No 8 (Redrafting of erroneous PD or completion of incomplete PD is always ineligible expenditure). |  |
| Administration of changes |  |
| 66. MoLSA shall introduce measures to reduce the number of changes in projects: a) by speeding up the administration, see recommendations No 16, 39 b) by clarifying and simplifying the requirements for applicants and beneficiaries. | a) 66.1. See recommendations No 16 and 19 b) 66.2. It will be addressed within the revision of calls and continuous update of FAQ | See measure No 8 and measure No 5. | MoLSA |  |  |
| 67. MoLSA and CRD shall explain the design of the system/processes: a) responsibilities for individual processes when assessing a change, b) consistency of MoLSA and CRD handbooks at the stage of administration of changes, c) description of an exact procedure to assess the change, including the requirement for handover of the file. | MoLSA 67.1. Point a) will be addressed in the framework of MoLSA IB HWP revision 67.2. Points b) and c) will be addressed in cooperation with IOP MA (see measure No 81) CRD 67.3. Aligning of processes and making the manuals consistent, i.e. MG 18 of MoLSA and MoLSA HWP, it will be provided for by the approval and alignment of these documents by IOP MA, and their subsequent issuance | 30.6.2012 | MoLSA CRD | MoLSA: 67.1. In the framework of MoLSA IB HWP revision those chapters were modified that relate to changes in 11.1 Administration of changes in project, 11.1.1 Changes requiring the approval by MoLSA, 11.1.2 Changes requiring the issuance of a new Decision on providing a grant/Statement of expenditure for financing a GA action and 11.1.3 Changes in project arising from Amendment to Act No 235/2004 Coll., on value added tax, as amended. CRD: 67.3. Accomplished. Alignment of processes and consistency of manuals were arranged for by IOP MA |  |
| Low number of projects under implementation |  |
| 68. MoLSA shall continue to cooperate with the National Centre for Support of the Transformation of Social Services on the preparation of projects under activity 3.1a) | 68.1. Carrying on the implementation of OP HRE individual project, under which the NCT is financed 68.2. MoLSA will submit to OP HRE MA a follow-up individual project focused on the support of the process of transformation of residential social service facilities. | 31.8.2012 | MoLSA | 68.1. The project continues to be implemented as planned, including the support of IOP applicants during the preparation of projects 68.2. A follow-up individual project was submitted by OP HRE MA, the project was registered on 11 June; now the project is under evaluation. |  |
| 69. MoLSA shall ensure that that applicants under activity 3.1b) are offered intensive consultation support from grant providers | 69.1. MoLSA intensifies consultation activities in projects under 3.1 b) by increasing the number of consultations. The consultations are provided to all the applicants who are interested in them. The increase in the number of consultations is illustrated by the data given e.g. in the monthly report on activities. | Continuous-ly | MoLSA | 69.1. The task is being fulfilled, the number of consultations is reported to IOP MA in the monthly report on activities. |  |
| 70. MoLSA shall align its procedures, requirements and their interpretation for applicants see recommendation No 11 | 70.1. MoLSA will modify the calls for IA 3.1 to align as much as possible the procedures, requirements and their interpretation for applicants and beneficiaries. The recommendation is included in measures 8, 10 and 11. | 31.8.2012 | MoLSA | 70.1. Accomplished, see measures 8, 10 and 11. |  |
| 71. MoLSA shall continue to support the discussion on social economy among the professional as well as general public | 71.1. Participation in seminars, conference and events focused on the support of social economy. MoLSA shall consider the possibility to take part in conferences and seminars in the 2nd half of 2012. | 31.8.2012 | MoLSA | 71.1. MoLSA conducted an analysis of conferences and events focused on the support of social economy and concluded that social entrepreneurship is on the agenda of only a single conference held on 12 Sep 2012 in the framework of TESSEA project. A project manager under activity 3.1c took part in the discussions at the conference on behalf of MoLSA. The conference provided a forum for participants to ask questions, obtain explanations of issues, etc. |  |
| 73. In IA 3.3 to continue to strongly support the development and implementation of projects by MoLSA (cooperation in addressing problems caused by external factors) | 73.1. MoLSA will continue to strongly support the projects, consultations with beneficiaries under IA 3.3 will be reported in monthly reports on activities | Continuous-ly | MoLSA | 73.1. It is being fulfilled continuously. |  |
| 74. MoLSA in cooperation with MA shall solve the use of the remaining allocation for 3.3c), and consider the announcement of a new call with simplified conditions | 74.1. It will be addressed in cooperation with MA | 31.8.2012 | MoLSA | 74.1. A new call 3.3 c) was submitted to MA by 31 Aug 2012; comment procedure/approval of this call will follow after the approval of revision of the 8th call. |  |
| Funding |  |
| 75. To observe the procedures and deadlines for the issuance of the so called limit by MoLSA | 75.1. The respective part of HWP with comments by MA 68 will be sent by e-mail to all the staff of department 68. | 30.6.2012, continuous observed | MoLSA | 75.1. It was modified in Chapters 13.4.1 and 13.4.2 within the HWP revision, the possibility to issue the so called limit for only a stage was cancelled (see recommendation No 76) |  |
| 76. MoLSA can change the mechanism of gradual release of funds based on the approved tender (Decision + the so called limit), to issue the so called limit for a stage (or a year), to cancel gradual corrections of the Decision in line with the tendered prices and linking the so called limit to the tendered amount only. The beneficiaries would return the unabsorbed funds to MoLSA in the framework of the annual settlement of accounts. | 76.1. In HWP, version 1.4 this recommendation was partly reflected. The possibility to issue the so called limit for a stage only was abolished, they are now issued throughout the year. Following the meeting with IOP MA on 5 Jun 2012, the incorporation of recommendation No 16b (identical to 55b) was preferred against the remaining parts of this recommendation. | 30.6.2012 | MoLSA | 76.1. Accomplished, see the text of corrective measure. |  |
| 77. For final evaluation of action only a simplified form shall be requested by MoLSA from beneficiaries, the remaining information will be requested from CRD. | 77.1. MoLSA does not intend to act upon the evaluators' recommendation, the MA will continue to discuss this issue with MoLSA. | 31.7.2012 | MoLSA | 77.1. MoLSA will act upon this recommendation as requested by IOP MA. |  |
| Sustainability |  |
| 78. MoLSA shall strongly support the provision of state guarantee for state funding of social services | 78.1. EU Funds Implementation Department (82) shall request the Social Services and Social Work Department (22) to express its opinion on the declaration of state guarantee for state funding of social services | 30.9.2012 | MoLSA | 78.1. EU Funds Implementation Department requested the Social Services and Social Work Department to express its opinion on the declaration of state guarantee for state funding of social services, with this guarantee being a highly valuable means of reducing barriers to the absorption of funds in IOP intervention areas. The reply of the Social Services and Social Work Department has not been sent as yet. |  |
| 80. MoLSA shall elaborate an interpretation of the indicator, where necessary the target value in projects can be changed and an explanation of why the MI will not be fulfilled can be included in the annual reports. | 80.1. It was addressed by providing the interpretation of the indicator in the course of May 2012. | 30.6.2012 | MoLSA | 80.1. IOP MA approved the methodology of reporting the indicators at the level of projects and IA 3.3 in April 2012. |  |
| Implementation system |  |
| 81. MoLSA shall complement the handbooks and in cooperation with CRD ensure the consistency between HWP and MG-18 in the field of communication procedures, competencies and responsibilities. | 81.1.IOP MA includes the CRD comments in its own comments, by which the consistency of both the documents is guaranteed. | 31.7.2012 | MoLSA CRD | 81.1. See the text of corrective measure |  |
| 83. MoLSA shall hand over the motions to conduct a check of delegated activities to IOP MA, which can conduct the checks of activities delegated to CRD | 83.1. MoLSA shall use monthly reports on implementation for handing over the motions. See measure No 25. | 5.7.2012 and then continuous-ly | MoLSA | 83.1. It is being fulfilled continuously in the framework of monthly reports on activities. |  |
| 84. MoLSA shall align as much as possible the procedures for 3.1 and 3.3, identical procedures shall be stated only once | 84.1. It is under way within the revision of MoLSA IB HWP, version 1.4 | 30.6.2012 | MoLSA | 84.1. Done within the revision of HWP. |  |
| 86. MoLSA and CRD shall decrease the number of handovers of the whole project files. | 86.1. In MoLSA IB HWP, version 1.4 those parts are modified where MoLSA could request the delivery of the whole project file in case of the notification of a change. | 30.6.2012 |  | 86.1. Done within the revision of HWP. |  |
| 89. IOP MA in cooperation with MoLSA have been working on the alignment and higher reporting value of individual reports. | 89.2. Monthly reporting has been carried out since December 2011. Simplification was prepared in the 1st quarter of 2012, minor changes in reporting are addressed between the persons responsible. | Continuous-ly | MoLSA |  |  |
| 90. Higher consistency of methodology with respect to the division of staff into individual MoLSA units. | 90.1. Improved collaboration of departments 82 and 68 when drafting the methodological documents was ensured. Holding of regular “Interdepartmental” coordination meetings, at which methodological procedures and materials, etc. are discussed. Fulfilment of tasks from coordination meetings is monitored by the directors of departments. | Continuous-ly | MoLSA |  |  |

## Annex No 3 – System of monitoring of sleeping and risky projects

| No | Parameter | Problems | Tools, measures |
| --- | --- | --- | --- |
| 1 | The legal act is not issued 3 months following the project's approval by the Selection Committee | ■ Delay in the issuance of the legal act (LA) on the part of the IB ■ Delay in the issuance of the LA on the part of the aid beneficiary ■ Failure to meet the project timetable and postponement of activities to next project stages ■ Excessively long stages in project application (e.g. 12 and more months) ■ A link to other projects which have so far not been completed ■ Investigation by OPC, TO in progress ■ Tenders have to be repeated due to the submission of one or no bid ■ Selection of the general contractor of Česká pošta for IRS NIS project and links to regional standardised IRS projects ■ Unnecessary requirements for grant provider ■ Changes in staffing at the ministry and changes in project design | 1) Bilateral meetings between IOP MA and IB on the issuance of LA 2) Trilateral meetings between the beneficiary, IB and IOP MA 3) Monthly reporting by the beneficiary to the IB and subsequently from the IB to IOP MA 4) Adoption of a crisis timetable of project implementation and absorption of funds approved by the beneficiary, IB and IOP MA 5) Division of project into stages (recommended period of 6 months) 6) A document on sleeping projects to be submitted to the Government 7) IOP MA and IB call upon the OPC/TO to speed up the investigation 8) A project will not be extended again by the IB and IOP MA 9) Extension of the project will be approved by IOP MA only if the project is divided into more stages |
| 2 | No funds or eligible funds amounting to less than 5 % of the budget are absorbed 12 months following the issuance of the legal act |  |  |
| 3 | All the tenders are not completed 6 months before to the completion of project implementation |  |  |
| 4 | All the tenders are not commenced 6 month before to the completion of project implementation |  |  |
| 5 | Tenders that take more than 1 year |  |  |
| 6 | Less than 50 % of funds is reimbursed 6 months before the project completion |  |  |
| 7 | Extension of the project by more than 1 year |  |  |
| 8 | No tender was commenced 6 month following the issuance of the legal act |  |  |

System of monitoring the sleeping and risky projects was introduced by IOP MA in July 2012 for the following reasons:

( long-term failure to fulfil the forecast absorption caused primarily by the failure of beneficiaries to meet the timetables and implement the activities, which results in a major risk of non-fulfilment of N+3 rule

( conclusions of the 9th IOP MC meeting held on 31 May 2012 (point C/7) stating that the IOP MA shall present to the 10th meeting of IOP MC a list of sleeping projects across all the intervention areas and propose an appropriate solution thereto, including the possibility of their cancellation

( a document of MRD – National Coordination Authority concerning the risky operational programmes to be submitted to the Government, where the IOP MA and MoI CR IB shall set up stable teams (project task force) for Intervention area 1.1 and allocate the funds from sleeping projects to a new call under Intervention area 1.1 and to topping up the current allocation for the 3rd call for Intervention area 5.1

( conclusions from the meeting with the EC held on 30 Mar 2012 regarding the situation of SA and IOP (point 4), where the MoI CR IB presented a list of sleeping projects under Intervention area 1.1 to the EC and to the GCIS, together with the proposal for a withdrawal from project implementation

( a document of MRD submitted to the Government on 29 Feb 2012 – Information on risks in IOP implementation which informed the Government on the on-going trend of a failure to fulfil the forecast absorption, which is caused especially by the failure of beneficiaries to meet the timetables and activities, and on the high risk of non-fulfilment of N+3 rule in case this trend continues

Procedure taken by IOP MA during the introduction of the sleeping projects management system

- The first draft of individual reports with sleeping/risky projects was compiled by IOP MA in the course of July

- When the first version of the report was drafted, the Intermediate Bodies updated the data in IS Monit by 31 Jul 2012 and examined the causes and reasons behind the inclusion of the project in the group of risky projects

- IOP MA elaborated the final report with sleeping projects as of 1 Aug 2012

- IB shall assign the problem and a suitable tool/measure to solve it to the individual project, together with a deadline by which it is to be tackled, thus the project will be removed from the group of sleeping/risky projects (selection from the proposed measures, or a proposal of a new measure)

- Adequacy of the selected solution is examined by IOP MA and the level of risk is assigned to the respective project based on the legend below

- IB shall primarily focus on projects designated as sleeping or high-risk projects and projects with a submitted application for payment

- IB shall, in the framework of the annex to the Monthly Monitoring Report, monthly reports to IOP MA on the progress made in the implementation of sleeping and high-risk projects, the progress made since the previous month will be highlighted

Procedures to be taken in the months to come

- Generation of reports from IS Monit 7+ at a three-month interval

- Assignment of the problem and a suitable tool/measure together with the deadline by which it shall be tackled by IOP IB (selection from the proposed measures or a new measure); by CRD in projects above CZK 5 million

- Verification of adequacy of the opted for solution and assignment of the level of risk based on the legend by IOP MA

- Implementation of specific tools/measures for the respective problems and elimination of risks primarily in identified as sleeping and high-risk projects

- Monthly reporting, within the annex to the Monthly Monitoring Report, on the progress achieved in the implementation of sleeping and high-risk projects

Legend for the purpose of assigning the level of risk to projects

sleeping project

high-risk project

risky project

no-risk project

Timetable of activities and individual stages

## Annex No 4 – List of Sleeping Projects

| Registration number of the project | Name of the project | Name of the applicant | IA | SF decision | Number of parameter based on the table in Annex No 3 |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | Number of incidence in the group of risky projects |
| CZ.1.06/1.1.00/03.05995 | Central Service Point project – Communication infrastructure of Public Administration Information Systems | MINISTRY OF INTERIOR | 1.1 | 518 500 000,00 | no | no | yes | yes | no | yes | yes | no | 4 |
| CZ.1.06/1.1.00/07.06387 | Building Access Points – access points of the CR to the European architecture of social security | MINISTRY OF LABOUR AND SOCIAL AFFAIRS | 1.1 | 56 165 000,00 | no | yes | no | no | no | no | yes | no | 2 |
| CZ.1.06/1.1.00/07.06393 | 159 – Development of information and communication interface of the CSSA for the purpose of provision of information to clients | CZECH SOCIAL SECURITY ADMINISTRATION (CSSA) | 1.1 | 198 050 000,00 | no | yes | no | no | yes | no | no | no | 2 |
| CZ.1.06/1.1.00/07.06410 | Creation of the network of geoportals and a data repository linked to the Public administration portal | CENIA, Czech Environmental Information Agency | 1.1 | 29 291 543,61 | no | no | yes | yes | no | yes | no | no | 3 |
| CZ.1.06/1.1.00/07.06414 | Provision of infrastructure for operation centres of IRS basic units | MINISTRY OF INTERIOR | 1.1 | 255 000 000,00 | no | yes | no | no | no | no | yes | yes | 3 |
| CZ.1.06/2.1.00/08.07329 | Part V. Calls – Data warehouses, management IS and Business Intelligence tools | PARDUBICKÝ REGION | 2.1 | 10 618 710,00 | no | yes | yes | yes | no | yes | no | no | 4 |
| CZ.1.06/2.1.00/08.07378 | II. Digital map of public administration – special-purpose cadastral map and planning analytical materials of Královéhradecký region | Královéhradecký region | 2.1 | 14 392 710,00 | no | yes | yes | yes | no | yes | no | no | 4 |
| CZ.1.06/2.1.00/08.07380 | IV. Internal integration of the authority and integration with the Public Administration IS | Královéhradecký region | 2.1 | 18 419 500,00 | no | yes | yes | yes | no | yes | no | no | 4 |
| CZ.1.06/2.1.00/08.07381 | V. Data warehouse and BI tools of Královéhradecký region | Královéhradecký region | 2.1 | 10 200 000,00 | no | yes | yes | yes | no | yes | no | no | 4 |
| CZ.1.06/3.2.01/02.06100 | Strategic noise maps - stage II | National Institute of Public Health, semi-budgetary organisation | 3.2 | 39 463 671,65 | no | yes | yes | no | no | yes | no | no | 3 |
| CZ.1.06/3.2.01/02.06104 | System tools for the protection and promotion of public health and prevention of health risks of population | National Institute of Public Health, semi-budgetary organisation | 3.2 | 48 935 714,28 | no | yes | yes | yes | no | yes | no | no | 4 |
| CZ.1.06/3.2.01/02.06119 | Modernisation of equipment of NIPH for surveillance of selected infectious diseases and ATB resistance | National Institute of Public Health, semi-budgetary organisation | 3.2 | 19 732 143,45 | no | no | yes | yes | no | yes | yes | no | 4 |
| CZ.1.06/3.2.01/02.06121 | Modernisation of the Information System of Infectious Diseases (NEW EPIDAT) | National Institute of Public Health, semi-budgetary organisation | 3.2 | 22 351 782,80 | no | yes | yes | yes | no | yes | no | no | 4 |
| CZ.1.06/3.2.01/03.06019 | Expert NIS integrating the process management in the University Hospital Brno | University Hospital Brno | 3.2 | 25 476 000,00 | no | yes | yes | no | yes | yes | yes | no | 5 |
| CZ.1.06/3.3.00/04.07958 | Labour Office CR - Písek – reconstruction of the education and training centre | Labour Office of the Czech Republic | 3.3 |  | yes | no | no | no | no | no | no | no | 1 |
| CZ.1.06/3.4.00/05.06275 | Contact and coordination centres II – Regional Police Directorate of Central Bohemia | Regional Police Directorate of Central Bohemia | 3.4 | 50 677 000,00 | no | yes | yes | yes | no | yes | yes | no | 5 |
| CZ.1.06/5.1.00/01.06128 | Schola naturalis – project on revitalisation of Veltrusy chateau and the Centre for the European Landscape Convention | National Heritage Institute | 5.1 | 196 903 434,15 | no | no | no | no | no | no | yes | no | 1 |
| TOTAL |  |  |  | 1 514 177 209,94 | 1 | 12 | 12 | 10 | 2 | 12 | 7 | 1 |  |

## Annex No 5 – Action Plan of NCA for IOP

| ID | Area | Description of the risk | Impact of the risk | Proposed measure | Description of the measure | Deadline | Actual date of accomplish-ment | Person respon-sible | Accom-plished (Y/N) | Description of accomplishment in case it does not correspond with the proposed measure |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1a | Fulfilment of n+3/n+2 rule | Failure to fulfil N+3 rule means the decommit-ment of unabsorbed allocation |  | To make necessary steps in order to achieve the set forecast level of funds paid to beneficiaries and funds included in aggregate payment claims accounted for by the PCA | 1.It is necessary to update the data in Monit7+ in order to specify the forecast absorption, especially at IBs. 2.The accomplishment of this measure will be monitored by MRD-NCA at the given dates set during the IOP crisis management meetings. | 30 June 2012 30 September 2012 31 March 2013 30 June 2013 | 30.6.2012; 31.7.2012 | MA, IB | Y |  |
| 1b |  |  |  | To fulfil the forecast absorption for 2012 by individual Intermediate Bodies | Individual grant providers will administer sufficient volume of applications for payment by the end of 2012 in order to achieve the following amount of total certified expenditure: MoI CR - CZK 3 925 mil. MoLSA - CZK 148 mil. MoH- CZK 3 086 mil. MoC CR - CZK 1 375 mil. MRD - CZK 3 132 mil. | 31.12.2012 control calculation as at 7 Sep 2012 (based on the data of August 2012) | 18.9. (control calculation) | MA, IB |  | Control calculation based on the data as of 4 Sep |
| 1c |  |  | Due to incorrect forecast of absorption the IOP MA or IOP IBs cannot adopt appropriate measures to fulfil N+3 rule and to set measures at project level. | To present realistic forecast absorption for the current year and project timetables. | To submit to the IOP MA the realistic forecast absorption for the current year and project timetables, based on the data from Monit7+. | 15.7.2012 | 16.7.2012 | MA, MoI, MoH, MoLSA and MoC | Y |  |
| 1d |  |  |  | To submit to the IOP MC members the forecast absorption of funds until the end of the programming period | To submit to the IOP MC members the forecast absorption of funds until the end of the programming period | 15.7.2012 | 16.7.2012 | IOP MA | Y |  |
| 1e |  |  |  | To develop measures to improve the reporting value of the forecast absorption. | To develop measures to improve the reporting value of forecast absorption, to inform IOP MC members | 30.7.2012 | 31.7.2012 | IOP MA | Y |  |
| 2a | Absorption capacity and project manage-ment | Slow rate of implementa-tion of Intervention areas 3.1 and 3.3, especially due to: 1) extension of timetables of preparation and implementa-tion of projects by applicants and aid beneficiaries, 2) lengthy and complicated administra-tion of submitted applications and approval of projects by Intermediate Bodies. | Fulfilment of n+3/n+2 rule, length of administrative process, high % of rejected applications | Conduct of evaluation of barriers to the absorption in Intervention areas 3.1 and 3.3 with specific measures. | Measure was accomplished. Accomplishment of this measure/other individual steps arising therefrom will be monitored by MRD-NCA by the deadline set during the IOP crisis management meetings. | By the end of May 2012 | 18.5.2012 | MA | Y | The report is available on: http://www.strukturalni-fondy.cz/Files/67/67e1803b-5bf4-46f4-a7da-50320b19c203.pdf. |
| 2b |  |  |  | To make the financial and technical limits clearer and during the control to focus on important items. | 1. MoLSA will evaluate the wording and definition of technical and financial limits and it shall submit the results of the evaluation to IOP MA 2. MoLSA will propose the scope of parameters to be included in the Decision (with respect to the reduction of their number and details). 3. MoLSA will elaborate an instruction for applicants how to correctly set the parameters, and include it in FAQ. During the control of limits to focus only on important items with the view to accelerate the administrative process at MoLSA. | By the end of August 2012 | 31.5.2012 | MoLSA |  | ad 1) MoLSA sent the evaluation of limits for IA 3.1 to IOP MA.; but IOP MA was dissatisfied with the evaluation results which is why it commissioned en external expert to evaluate the financial and technical limits by the given deadline, based on which the IOP MA conducted an administrative check, the conclusions of which are currently being finalised; ad 2) MoLSA proposals are subject to revisions of calls which are currently under way. In connection with the modification of call No 8 for IA 3.1, the other MoLSA calls will be probably modified (The approval of revision of call No 8 is anticipated in September 2012); ad 3) Elaboration of the instruction is a part of the revision of call No 8 for IA 3.1, which has not been approved as yet. For this reason the instruction could not be published. |
| 2c |  |  |  | To cut the deadlines for the conduct of ex-ante checks. | 1.MoLSA will propose the cutting of deadlines for the conduct of ex-ante checks. 2. Following the approval by MA, the deadlines shall be incorporated in the operational manual. 3. Cutting the actual time necessary for the conduct of ex-ante checks by 60%. | By the end of May 2012 By the end of September 2012 | ad 1) a 2) 2.7.2012 | MoLSA |  | ad 1) and ad 2) has already been incorporated in MoLSA HWP (revision 1.4 - 2.7.2012) – IOP MA monitors the actual duration of the current ex-ante checks (projects in which the duration of ex-ante checks exceeded 60 working days); MoLSA has undertaken to cut the deadlines for ex-ante checks; ad 3) since 2 July no ex-ante checks have been completed, for this reason it cannot be ascertained; MoLSA sends info on the progress of ex-ante risk analysis within monthly reporting to the MA. Call No 8 is anticipated to be approved in the course of September. |
| 2d |  |  |  | To reduce and simplify the requirements for beneficiaries. | To adopt measures proposed based on the conducted evaluation of barriers to the absorption in Intervention areas 3.1 and 3.3: 1. MoLSA will reconsider the volume of supporting documents which is really necessary for the issuance of the Decision. 2. MoLSA will introduce a measure to increase the number of changes in projects: a. by accelerating the administration of changes b. by clarifying and simplifying the requirements for applicants and beneficiaries 3. For final evaluation, the MoLSA will request only a simplified form from beneficiaries, and if there is any information missing it will be requested from the CRD. 4. MoLSA and CRD will continue to recommend the applicants and beneficiaries to divide the projects into more stages. | By the end of August 2012 |  | MoLSA |  | ad 1) The measure is implemented within the revision of calls and HAB; once the MoLSA gives its opinion on IOP MA comments concerning call No 8, other calls will be revised (IOP MA expects that to happen in the course of September 2012); ad 2) Cutting down the requirements for applicants is addressed within the current revisions of calls; ad 3) Discussions are currently held with the involvement of the Ministry of Finance concerning the interpretation of statutory obligations of IB (grant provider) in projects financed from the Structural Funds; the result is anticipated by the end of September 2012 ad 4) All the project and financial managers of IBs have been informed during meetings about the necessity to divide the projects into more stages; since then no seminar for applicants has been held – for this reason it could not be checked; MoLSA has already contacted the regions applying under call No 7 for IA 3.1 (activity a) and asked them to set shorter stages in projects and to reconsider the long stages set in the already submitted projects; in the same spirit the CRD will approve any potential changes and recommend them to applicants and beneficiaries (extending or merging the stages will not be allowed). |
| 2e |  |  |  | To observe the deadlines for evaluation and approval of tender documentation and tenders. | 1. To observe the deadlines set in the Operational Manual and to check the observance of these deadlines at monthly meetings of IOP MA and CRD. 2. Introduction of summary reporting of the status of individual tender dossiers and documentation for tenders at CRD. 3. In case of non-observance of deadlines to justify the non-observance or to introduce the penalty/ sanction. | By the end of May 2012 | 31.5.2012 | CRD | Y | The deadlines set by IOP OM are usually observed in dependence on priorities and work load of CRD. Since May 2012 regular monthly reporting of the status of individual tender dossiers and documentation for tenders at CRD has been introduced, in the framework of which the CRD gives reasons for the potential non-observance of set deadlines. |
| 2f |  |  |  | To update the forecast timetable within regular reporting of projects in line with actual status of their implementation. | To update the forecast timetable within regular reporting of projects in line with the actual status of their implementation. | 4.7.2012 | 4.7.2012, 4.8.2012,4.9.2012 | MoLSA |  | In the framework of regular monthly monitoring the MoLSA gives updated timetables of submitted projects and forecast absorption. |
| 2g |  |  |  | To consider the reallocation at MoLSA in Intervention areas 3.1 and 3.3. | To consider the reallocation in case MoLSA fails by the end of October 2012 to issue the Decisions on providing a grant/Statement of expenditure on financing GA actions in the amount of 50 % of allocation for Intervention areas 3.1 and 3.3. | 16.11.2012 |  | IOP MA |  | It will be elaborated based on the results of MoLSA concerning the issuance of guidance documentation. |
| 2h |  |  |  | To evaluate the effectiveness of implementation of proposed measures. | To draw a clear table with adopted measures and to evaluate their effectiveness with respect to the contracted funds (the limit of 50% by the end of October 2012) and to the reimbursed funds (limit see ID 1b), including the impact of the measure on the implementation of respective intervention areas. | By the end of 2012 |  | MA |  | It will be elaborated based on the results of MoLSA concerning the issuance of guidance documentation. |
| 3a |  | Delays in the implementa-tion and administra-tion of projects under the responsibility of MoI CR. Unclear coordination and management of Smart Administra-tion strategy. | Fulfilment of n+3/n+2 rule, delays in project implementa-tion, duration of administrative process | To elaborate a document to be submitted to the Council Government for Information Society (CGIS), including a list of projects in which the implementation of Intervention area 1.1 is delayed. To adopt a decision concerning the cancellation of their implementation. Subsequently, to announce a call for funds from cancelled projects for strategic projects with implementation period of up to 1 year. | The proposal for the measure is clearly defined. | By the end of May 2012 |  | MoI, CGIS |  | The elaboration of MoI CR document on sleeping projects for the Government is under way. 2 projects were withdrawn from implementation, the remaining projects have crisis timetables of implementation in and absorption of funds in place which have to be observed. A new call for IA 1.1 for AIS was announced in August. |
| 3b |  |  |  | For each project implemented in Intervention area 1.1 to create a stable team (“task force of the project“) composed of the representatives of the Intermediate Body, contracting entity and project holder, which shall monitor the progress made in the project at micromanagerial level, and will operatively step in if any problems emerge. | MoI will set up a working team composed of the representatives of: MA/IB (financial and project manager, or others), beneficiary or also key suppliers (in case of project implementation through public contracts). In the framework of system of management of sleeping projects, the set up team shall monitor the progress in the project (especially the fulfilment of timetable and the level of absorption, fulfilment of the timetable of the award of public contracts) and based on monthly meetings with beneficiaries will identify problems and risks, propose a solution thereto and monitor and evaluate their implementation and impacts. Where specific problems/needs occur, the team should be adequately extended. The MA shall report the results of activities performed in individual projects to MRD-NCA. | By the end of June 2012 | Starting with August 2012 | MA, MoI | Y | Since August 2012 regular monthly bilateral meetings with all the beneficiaries under IA 1.1 have been held, where the fulfilment of timetables and the level of absorption of funds, fulfilment of timetables for the award of public contracts are monitored based on completed status reports and the relevant measures to eliminate the problems and risks are proposed. |
| 3c |  |  |  | To submit once a month to the Managing Authority and MRD-NCA a summary of implementation of individual projects in Intervention area 1.1, including the description of the current status and identified risks. | To continue to proceed as in case of the supporting document for the IOP Monitoring Committee meeting in the first half of 2012. | Starting with April 2012 | Starting with July 2012 | MoI | Y |  |
| 3d |  |  |  | To engage CRD and MRD in the administration of Intervention area 2.1. | To proceed in line with activities set by the MA. | By the end of May 2012 | 29.6.2012 | MA, CRD, MoI | Y |  |
| 3e |  |  |  | To engage CRD and MRD in the administration of Intervention area 3.4. | To proceed in line with activities set by the MA. | By the end of May 2012 | 29.6.2012 | MA, CRD, MoI | Y |  |
| 3f |  |  |  | To submit the information on the way of implementation and monitoring of Smart Administration Strategy. | To submit at the next meeting of IOP MC the information on the way of implementation and monitoring of Smart Administration Strategy, to describe the individual levels of structures, their powers and responsibilities. | 10th IOP MC 21.11.2012 |  | MoI, RCIS |  | IOP MA compiles the supporting documents for the 10th meeting of MC which shall be disseminated to all the MC members, including NCA representatives. |
| 3g |  |  |  | Completion of a summary of all projects fulfilling the Smart Administration Strategy as defined by the EC. | To ensure the completion of a summary of all the projects fulfilling the Smart Administration Strategy as defined by the EC, financed from all sources, not only from the EU Structural Funds. The projects will be linked to the individual objectives of Smart Administration Strategy and the MoI CR shall evaluate the fulfilment of these objectives. The summary and evaluation shall be sent by the MoI CR through IOP MA to the IOP Monitoring Committee members by 31 Jul 2012. | 31.7.2012 | 13.9.2012 | MoI | Y |  |
| 3h |  |  |  | To update the Smart Administration website and to post all the relevant documents on it. | To update the Smart Administration website and to post all the relevant documents on it. | 31.7.2012 | 31.7.2012 | MoI | Y |  |
| 3i |  |  |  | To evaluate the impacts of the above mentioned measures on the implementation of Intervention areas 1.1, 2.1 and 3.4. Based on these results to adopt a decision on potential revision of the programme. | Based on the final status of absorption at the end of 2012 (see ID 1b) and evaluation of the changed rate of absorption since the adoption of the measures to evaluate their impact on the implementation of Intervention areas 1.1, 2.1 and 3.4. | By the end of 2012 |  | MA |  |  |
| 4a |  | Delays in the implementa-tion of projects in Intervention area 5.1 have an impact on the overall delays in programme implementa-tion and fulfilment of n+3/n+2 rule |  | To carry out a screening of the status of implementation of all projects in Intervention area 5.1. To focus on projects in which the implementation is delayed, compliance with the timetable, tendered contracts and prerequisites of timely completion of project implementation. To use the funds from “sleeping” projects to top up the allocation for the 3rd call for Intervention area 5.1 | 1. In selected projects the Intermediate Body will conduct an analysis of the fulfilment of timetables (particularly the financial plan, timetable of individual project activities, timetable of the award of public contracts) and forecast absorption. 2. In projects exhibiting delays in implementation or other identified problems the Intermediate Body shall adopt appropriate corrective measures (such as the task force of the project), where necessary it shall modify the timetables or withdraw from the Decision /Contract on providing a grant and use the funds to top up the allocation for the 3rd call for Intervention area 5.1. 3. The result of the screening and adopted measures shall be reported by the Managing Authority to the MRD-NCA. | By the end of May 2012 |  | MoC | Y | ad. 1 The projects exhibiting delays or other sort of risk are included in the list of “sleeping and risky projects“. In these projects the timetables are closely monitored and measures are applied to minimise the delays. If some of the projects are withdrawn from implementation, the saved funds shall be provided to a substitute project (enlisted in the pipeline of projects under the 3rd call). ad. 2 Measures: Intensified and continuous supervision over the fulfilment of the timetable of project implementation with the view to minimise the delays between individual steps. It is done continuously and regularly through the monitoring reports, controls of tenders, notifications of a change of beneficiary, and the like. Discussion with beneficiaries on progress in project implementation are continuously held. In Veltrusy project, a professional tender administrator, Otidea company, has been involved in the preparation of a tender since July 2012. This resulted in substantial improvement of quality of tender documentation and overall acceleration. A tender will be announced for a supplier of project management services, the involvement of whom shall considerably improve the quality of project management. |
| 4b |  |  |  | In risky projects to propose radical measures focused on implementation and absorption. | In the so called sleeping projects to commence the process of withdrawal from the legal act. In projects with major delays in implementation to cut the eligible expenditure on salaries of project team members. | By the end of June 2012 |  | MoC | N | Reasoning: The process of withdrawal from project implementation has so far not been launched in any of the “sleeping” projects. Intensive activities are being done to implement all the projects. Low absorption of funds by “sleeping” projects is caused by setting the conditions for the call, in which the applicants were obliged to produce a building permit for a substantial part of the project no later than 1 year following the issuance of the Decision. This is directly linked to the fact that in majority of the so called “sleeping” risky projects the construction works contractor has not been selected as yet and the absorption of funds is therefore low. As soon as the contracts on work done are signed, the absorption shall greatly increase. The MoC has not cut the eligible expenditure on salaries of project team members in these projects as yet. By letter of the director of 27 Aug 2012, Ref. No 30235/2012-26, the MA requested the MoC to apply this measure in projects which repeatedly ask for the extension of implementation and fail to observe the timetable of activities. |
| 4c |  |  |  | To issue legal acts (Decision on providing a grant, Statement of expenditure) for all the projects selected under the 3rd call. | To adopt such a timetable of activities for the issuance of legal acts (Decision on providing a grant and Statement of expenditure), including the approval at MoF CR, for all the projects selected under the 3rd call so that they can be issued by the end of August. | By the end of August 2012 |  | MoC | N | As of August 2012 the Decision on providing a grant was signed for the project called “Stone and light project – revitalisation of the interior of the church of Saint Barbara in Kutná Hora“, and for the project called “Centre of Education and Training in Broumov – revitalisation of the monastery the Decision on providing a grant was issued on 4 September. In the remaining Kladruby project the registration was handed over to the MoF for approval. |
| 5a |  | Fulfilment of n+3/n+2 rule in annual commitments of municipalities with IUDP. | Change of allocation for individual municipalities | To carry out the evaluation of IUDP implementation based on the annual monitoring reports. To identify risky IUDPs. In risky municipalities to continuously monitor the status of absorption and the fulfilment of objectives. In IUDPs which in 2012 fail to meet the 40 % absorption threshold, to cut the volume of funds earmarked for IUDP and to use the saved funds in other IUDPs. | To apply the same procedure as during the evaluation of the observance of the 25 % threshold in 2011. | Second half of 2012 |  | MA |  | The IOP MA carries out the evaluation of IUDP implementation, the results will be available in supporting documents for the 10th MC meeting which will be sent to all the MC members, including the NCA representatives. The anticipated date of fulfilment is 21 Nov 2012. |
| 5b |  |  |  | To inform the members of the Monitoring Committee of the Integrated Operational Programme on the results of evaluation and proposed measures. | To apply the same procedure and form as at the MC in the first half of 2012. | Second half of 2012 |  | MA |  | The IOP MA carries out the evaluation of IUDP implementation, the results will be available in supporting documents for the 10th MC meeting which will be sent to all the MC members, including the NCA representatives. The anticipated date of fulfilment is 21 Nov 2012. |
| 6 |  | Protraction of the process of UDF selection on the grounds of the amendment to legislation | Failure to absorb the Jessica FI loans by the end of the programming period | To ensure the implementation of Jessica Financial Instrument | To ensure the implementation of Jessica Financial Instrument which shall be as effective as possible with respect to the operational costs and maximum amount earmarked for loans. The costs of the Holding Fund should be the lowest possible. | 10th IOP MC 21 Nov 2012 |  | IOP MA |  | The IOP MA implements the Jessica Financial Instrument and compiles the supporting documents for the 10th MC meeting which will be sent to all the MC members, including the NCA representatives. The anticipated date of fulfilment is 21 Nov 2012. |
| 7 |  | Projects requiring a large volume of funds constitute a considerable part of the programme allocation (more than 60 %). Delays in implementa-tion of these projects consist particularly in the reimburse-ment or implementa-tion of projects. | Fulfilment of n+3/n+2 rule | To regularly (weekly) monitor, evaluate and manage the risks associated with the implementation of projects requiring a large volume of funds, with stress put on the implementation of public contracts. | The Managing Authority has these procedures already in place. The Managing Authority shall harmonise the existing monthly frequency with the proposed measure for the management of sleeping projects and monitoring of the issuance of legal acts in projects with individually assessed expenditure. | Continuously |  | MA, IB | Y | IOP MA updates the list of sleeping projects 4 times a year. |
| 8a | Administra-tive capacity | High turnover rate at the level of programme (in 2011, it accounted for 33.2 %). The highest turnover rate: MoI IB 78.6 %, MoLSA IB 32.5 %. | Fulfilment of n+2/n+3 rules, impact on the duration of administrative process, loss of institutional memory (institutional amnesia) | To continue to apply the Resolution of the Government of the CR No 818/2007, or 1332/2009, which enable to motivate the employees implementing the Integrated Operational Programme through financial and non-financial incentives (area of education and training). | To proceed in line with the set procedures. To apply the Resolution No 1332/2009 when dealing with Intermediate Bodies, i.e. to use not only as a positive motivation, but also as a potential source of sanctions in case of non-fulfilment of the forecast absorption. Where the sanctions are imposed, the Managing Authority defines the conditions of violation. | Continuously |  | MA, IB | N | For more details see measure 8c below. |
| 8b |  |  |  | To inform on results of the analysis of administrative capacity and outsourced activities in IOP implementation structure. | At the next meeting of IOP MC to inform on results of the analysis of administrative capacity and outsourced activities in the IOP implementation structure. | 10th IOP MC on 21 Nov 2012 |  | IOP MA |  | Foreseen date of accomplishment 21 Nov 2012. |
| 8c |  |  |  | To prepare the possible cutting down of the bonuses of IOP IB pursuant to the Government Resolution No 1332/2009 as a consequence of non-fulfilment of forecast absorption | To prepare the possible cutting down of the bonuses of IOP IB pursuant to the Government Resolution No 1332/2009 as a consequence of non-fulfilment of forecast absorption | 31.8.2012 | 31.8.2012 | IOP MA | Y | The methodological guideline of IOP MA was drafted by the deadline, its content and impact are analysed in cooperation with the CRD based on the data from August. The information about the guidelines was forwarded to IOP IBs on 11 Sep 2012 at the meeting of MA with IB directors. |
| 9a | Manage-ment and control systems | High foreseen error rate (13.78 %) in the Annual Control Report 2011 | Potential suspension pursuant to Article 91 of the General Regulation | To implement corrective measures as a consequence of findings identified by the Delegated Audit Body (Annual Control Report for 2011). | To continue to implement the measures adopted based on the audits. To monitor the submission of the draft response of the CR to the preliminary report from the EC audit on IOP (to send to the Commission by 10 Jun 2012). To continue to cooperate with the PCA, AA, NCA and EC. To continue the discussions with the TO and OPC concerning the acceleration of investigation of irregularities or tenders in EU projects. | Continuously, no later than by July 2012 | Accompli-shed continuously | MA, IB | Y |  |
| 9b |  |  |  | To inform about the relaunch the certification of expenditure in the programme. | To inform the IOP MA members about the relaunch of certification of expenditure in the programme, or requirements set by the EC as a prerequisite for the relaunch of certification. | 30.7.2012 |  | MA | N | The foreseen date of accomplishment 21 Nov 2012. |
| 10a |  | Existence of sleeping projects in the programme | Non-fulfilment of the timetable of absorption of the programme as a consequence of the extension of the timetable of projects and the risk of decommitment of allocation in projects which will not be fully or partly implement by the end of the programme implementation | To present a list of sleeping projects for all the intervention areas. | To submit at the next IOP MC meeting a list of sleeping projects for all the intervention areas, in which adequate progress will not be achieved in the three months starting with 31 May 2012 with respect to the conclusion of contracts with suppliers, and a proposal of relevant solutions of individual projects, including the possibility of their cancellation. | 10th IOP MC on 21 Nov 2012 |  | MA, IB |  | The foreseen date of accomplishment 21 Nov 2012. |
| 10b |  |  |  | To prepare the methodology governing the work with sleeping projects and identification of sleeping projects in individual intervention areas. | In cooperation with IOP IB to prepare and approve the procedures for individual categories which identify the sleeping projects. To complete the verification of correctness of the data entered in IS Monit and selection of sleeping projects in individual intervention areas. | 15.8.2012 | 15.8.2012 | MA, IB | Y |  |

## Annex No 6 – Summary of Measures Taken in Response to the Conclusions of the Previous Meeting of IOP MC

| Task assigned to | Number of the conclusion / task | Deadline | Accomplishment of the task |
| --- | --- | --- | --- |
| IOP MA | C/1 To incorporate the comments raised during the discussion and sent by the IOP Monitoring Committee members in the text of the Report on Implementation of IOP as of 31 Mar 2012 | 29.6.2012 | Comments were incorporated in the Report on Implementation of IOP as of 31 Mar 2012 in June 2012; |
| IOP MA | C/2 To inform the members of IOP Monitoring Committee on the relaunch of certification of expenditure in the programme, or on the requirements set by the EC as a prerequisite for the relaunch of certification | 30.7.2012 | MA shall inform the IOP MC members at the 10th meeting of IOP MC; |
| IOP MA | C/3 To inform on results of the analysis of administrative capacity and outsourced activities in IOP implementation structure at the next meeting of IOP Monitoring Committee | 10th meeting of IOP MC | MA shall include the information in the dossier for the 10th meeting of IOP MC; |
| IOP MA, MoI CR and CRD CR | C/4 To transfer the administration of projects, including adequate administrative capacity, in Intervention area 2.1 before 29 Jun 2012; | 29.6.2012 | Addendum No 2 to the Agreement on delegating the tasks was signed on 29 Jun 2012. Information on the change in delegated activities in Intervention areas 2.1 and 3.4 of IOP was sent to the EC on 3 Jul 2012; |
|  | C/4 To make a decision concerning the transfer of activities and work positions in Intervention area 3.4 before 1 Jul 2012 | 22.6.2012 | Sent to the EC on 3 Jul 2012; |
| IOP MA in cooperation with MoI CR | C/5 Through IOP MA to send to the EC a thorough analysis of impacts of Česká pošta s.p. involvement in the implementation of projects in Intervention areas 1.1 and 3.4 (changes in project timetables, tenders and their control) before 29 Jun 2012 | 29.6.2012 | Sent to the EC on 29 Jun 2012 |
| IOP MA in cooperation with MoI CR | C/6 Through IOP MA to inform the members of the IOP Monitoring Committee on solving the situation of sleeping projects and on the use of saved funds before 29 Jun 2012 | 29.6.2012 | MoI CR draws up a document on sleeping projects that is intended to be submitted to the Government in October 2012. Two projects in Intervention area 1.1 have been withdrawn from implementation, for the remaining projects, crisis timetables of implementation and absorption of funds have been adopted, which have to be observed at all costs, any other changes in implementation and timetable will not be allowed by the IOP MA. In August, a new call for Intervention area 1.1 was announced, namely for Agenda Information Systems. |
| IOP MA | C/7 To submit at the next IOP MC meeting a list of sleeping projects for all the intervention areas, in which adequate progress will not be achieved in the three months starting with 31 May 2012 with respect to the conclusion of contracts with suppliers, and a proposal of relevant solutions of individual projects, including the possibility of their cancellation. | 10th IOP MC | MA shall include this information in the dossier for the 10th meeting of IOP MC; |
| MoI CR, MoLSA, MoH and MoC | C/8 To submit to IOP MA realistic forecast absorption for the current year and project timetables, based on the data in Monit7+. IOP MA shall hand it over to the members of the IOP Monitoring Committee by 15 July 2012 and at every future meeting of the IOP Monitoring Committee | 16.7.2012 | Sent to IOP MC members on 16 Jul 2012; |
| IOP MA | C/9 To submit to the members of IOP Monitoring Committee a forecast absorption of funds until the end of the programming period before 15 July 2012 | 16.7.2012 | Sent to IOP MC members on 16 Jul 2012; |
| IOP MA in cooperation with IOP IB | C/10 In cooperation with IOP IB to prepare measures to improve the reporting value of forecast absorption and to inform the members of the IOP Monitoring Committee before 30 Jul 2012 | 30.7.2012 | Sent to IOP MC members on 31 Jul 2012; |
| MoI CR | C/11 In cooperation with the Government Council on Information Society to present at the next meeting of IOP Monitoring Committee the information on the way of implementation and monitoring of Smart Administration Strategy, to describe individual levels of structures, their powers and responsibilities | 10th meeting of IOP MC | MA shall include this information in the dossier for the 10th meeting of IOP MC; |
| MoI CR | C/12 To ensure the completion of a summary of all the projects fulfilling the Smart Administration Strategy as defined by the EC, financed from all sources, not only from the EU Structural Funds. The projects will be linked to the individual objectives of Smart Administration Strategy and the MoI CR shall evaluate the fulfilment of these objectives. The summary and evaluation shall be sent by the MoI CR through IOP MA to the IOP Monitoring Committee members by 31 Jul 2012. | 31.7.2012 | Sent to IOP MC members on 13 Sep 2012; |
| MoI CR | C/13 To update the Smart Administration website and to post on it all the relevant documents | 31.7.2012 | Updated as of 31 Jul 2012 |
| IOP MA | C/14 To send the Action Plan of IOP MA, CRD CR and MoLSA from the evaluation of barriers in Intervention areas 3.1. and 3.3 to the members of the IOP Monitoring Committee for comments | 29.6.2012 | Sent to IOP MC members on 11 Jul 2012; |
| IOP MA | C/15 To ensure the implementation of Jessica Financial Instrument which shall be as effective as possible with respect to the operational costs and maximum amount earmarked for loans. The costs of the Holding Fund should be the lowest possible. | June 2012 | Accomplished on 18 Jun 2012; |
| IOP MA | C/16 To inform on the application of 3E principles in IOP implementation at the next meeting of IOP Monitoring Committee | 10th meeting of IOP MC | MA will include the information in the dossier for the 10th meeting of IOP MC; |
| IOP MA | C/17 To prepare the possible cutting down of the bonuses of IOP IB pursuant to the Government Resolution No 1332/2009 as a consequence of non-fulfilment of forecast absorption |  | IOP MA has drafted a proposal and will discuss it with IB; |
| MoLSA | C/18 To update the forecast timetable within regular reporting of projects in line with the actual status of their implementation. | 4.7.2012 | Accomplished on 4 Jul 2012; |
| IOP MA | C/19 To consider the reallocation in case MoLSA fails by the end of October 2012 to issue the Decisions on providing a grant/Statements of expenditure on financing GA actions in the amount of 50 % of allocation for Intervention areas 3.1 and 3.3. | 16.11.2012 | Decision concerning the potential reallocation will be made by IOP MA on 16 Nov 2012. |
| MRD CR | C/20 To engage the representatives of non-governmental non-profit organisations in the discussion on the State Tourism Development Policy 2014+ | Provision of information to IOP MC at the 10th meeting of IOP MC | Accomplished on 1 Aug 2012 and on the occasion of other meetings on elaborating the State Tourism Development Policy (2014-2020). A representative of non-governmental non-profit organisations – Association of Tourist Regions of the CR – was involved in activities of the Working Group for drafting the policy. The Working Group was established to develop a new policy with the view to discuss the procedure of its drafting in terms of content and process with the representatives of self-governing bodies, professional public and academia; WG met on 5.3.2012, 20.4.2012, 6.6.2012, 1.8.2012 and 4.9.2012; The policy has been developed, right now the Strategic Environmental Assessment (SEA) and comments procedures are under way ; The policy is expected to be submitted to the Government of the CR for approval in November 2012. |

# Footnotes

Number of submitted applications and number of Projects with issued Decision/signed Contract in multi-objective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero (except for Priority axis 4).

In Intervention area 3.1 the total amount of funds paid to beneficiaries (column d) is lower than the amount of funds included in aggregate applications for payment (column e), it is due to the technical aspects of the output report in MSC2007, which serves as a source of data for this table. It is caused by projects financed in ex-ante financing regime with the use of the so called limit (funding from an account for a limited amount), in which a part of the expenditure of the stage is financed through an order, i.e. in ex-post financing regime. The expenditure financed by an order is not included in column d in the table, but in column e.

Number of submitted applications and number of Projects with issued Decision/signed Contract in multi-objective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero (except for Priority axis 4).

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology. The reason for negative amount in this column may be withdrawal of the project or issue of the change Decision to Grant. Explanation of the specific reason for reduction of the amount is stated in the text of chapter 3 at the appropriate areas of intervention.

The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

For the purpose of monitoring the statistical data on rejected projects it is essential to distinguish between the rejected and denied projects. Rejected projects = all projects in negative statuses. Denied projects = all projects in negative statuses with the exception of status N5 Project application withdrawn by the applicant and status N7 Project not completed/withdrawn. There is a difference between the case of a project rejected by the administrator or withdrawn by the applicant/beneficiary himself.

Number of submitted applications and number of Projects with issued Decision/signed Contract is due to the multiobjective nature of these priority axes given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology.

The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology.

The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology.

In Intervention area 3.1 the total amount of funds paid to beneficiaries (column d) is lower than the amount of funds included in aggregate applications for payment (column e), it is due to the technical aspects of the output report in MSC2007, which serves as a source of data for this table. It is caused by projects financed in ex-ante financing regime with the use of the so called limit (funding from an account for a limited amount), in which a part of the expenditure of the stage is financed through an order, i.e. in ex-post financing regime. The expenditure financed by an order is not included in column d in the table, but in column e.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology.

The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data, the data as of 31 Mar 2012 was recalculated in line with the new methodology.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data,  the data as of 31 Mar 2012 was recalculated in line with the new methodology.

The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data,  the data as of 31 Mar 2012 was recalculated in line with the new methodology.

Number of submitted applications and number of Projects with issued Decision/signed Contract in multiobjective priority axes are given only in intervention areas related to the Convergence objective (a). In intervention areas falling under the Regional competitiveness and employment objective (b) the number is zero.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data,  the data as of 31 Mar 2012 was recalculated in line with the new methodology.

The amount of certified expenditure dropped for the reason of exclusion of applications for payment with a suspected irregularity under investigation.

In column (c) Projects with issued Decision/signed contract only projects at positive stages are included. For the sake of comparability of data,  the data as of 31 Mar 2012 was recalculated in line with the new methodology.

The Ministry of Finance of the CR has started to use the term “Delegated Audit Body“ (DAB) instead of the originally used “Authorised Audit Entity“  (AAE)